## Sheet1
Area | Geomarket | Country | Welltrak_Project_Guid | Avance_ID | PPM_Project_ID | ProjectName | ProjectType | Drilling_TIC | Commercial Model | WellName | Latitude | Longitude | Field | Shape | WellType | SpudDate | Type | RigName | Summary | Forecast | Project_Guid | Comments | PLAN_Days | BCC_PLAN_Days | Rig_Release | Plan_Ft_Day | Plan_Par_Ft_Day | RIR | ROPO_Adherence | PAR_Revenue | PAR_Time | PYmaxEndDT | PYminStartDT | PYminTopDepthFT | PYmaxBottomDepthFT | PYTDorCDreachedDT | PYNPTDays | PYFlatDays | PYdaysToTDorCD | PYOpsDays | PYNPTPercent | PYFeetPerDay
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR40 | 24.7901 | 53.2112 | Sarb | Horizontal | Single Oil Producer targeting Arab D Reservoir | 2018-01-03 00:00:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | CIRCULATED HOLE CLEAN, FR= 255 GPM, SPP= 2600 PSI | 69.35 |  | 2018-03-12 08:22:11.000 | [6 empty] | 2018-03-04 15:00:00.000 | 2018-01-02 00:00:00.000 | 72 | 19900.0006 | 2018-02-18 09:00:00.000 | 11.4167 | 32 | 46.375 | 60.625 | 18.8316 | 429.1105
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR43 | 24.7905 | 53.2107 | Sarb | Horizontal | Oil Producer | 2018-03-08 08:00:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | CONT'D RIH 6" RSS ASSY F/9,168'' FT T/ 9,548' FT * F/U EVERY STRING EVERY 15 STDS | 73.22 |  | 2018-05-17 05:21:00.000 | [6 empty] | 2018-05-25 11:00:00.000 | 2018-03-08 00:00:00.000 | 0 | 21520.0007 | 2018-05-11 22:00:00.000 | 15.8125 | 45.6771 | 64.5833 | 78.125 | 20.24 | 333.2129
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR46 | 24.7903 | 53.211 | Sarb | Horizontal | Oil Producer | 2018-05-29 03:00:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | PJSM WITH ALL CREW , DISCUSSED RIG MOVE PLAN, RISK INVOLVED AND CONTROL MEASURE. | 77.23 |  | 2018-08-11 05:34:12.000 | [6 empty] | 2018-07-25 12:00:00.000 | 2018-05-26 00:00:00.000 | 0 | 23082.0007 | 2018-07-13 19:00:00.000 | 5.0208 | 32.0625 | 45.6667 | 57.375 | 8.7509 | 505.4453
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR48 | 24.7897 | 53.2116 | Sarb | Horizontal | Single oil producer | 2018-08-01 06:00:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | PJSM FOR M/U AND RIH 6" MOTORISED RSS BHA. | 74.8 |  | 2018-10-08 19:16:12.000 | 400.48 | [5 empty] | 2018-11-16 11:00:00.000 | 2018-07-26 00:00:00.000 | 0 | 22117.0007 | 2018-11-06 00:00:00.000 | 51.3542 | 77.7708 | 96.75 | 107.2083 | 47.9013 | 228.5995
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR54 | 24.7899 | 53.2114 | Sarb | Deviated | Gas injector | 2018-11-19 13:30:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | PJSM | 54.19 |  | 2019-01-09 04:39:00.000 | 469.35 | [5 empty] | 2019-01-11 15:00:00.000 | 2018-11-16 11:00:00.000 | 0 | 13850.0004 | 2018-12-17 17:30:00.000 | 3.1458 | 18.9375 | 28.1667 | 53.0625 | 5.9285 | 491.716
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR55 | 24.792 | 53.2113 | Sarb | Horizontal | Single Oil Producer | 2019-01-13 16:00:00.000 | Primary Drilling | ND-78 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | M/U AND RIH 6" SCHL RSS ASSY T/ 151 FT. * 6" NEW PDC BIT + PD ORBIT475+(5 7/8" STABILIZED CC)+FILTER SUB+VORTEX MOTOR+UPPER CLINK+ MICROSCOPE475+IMPULSE+5 3/4" STRINNG STAB+PERISCOPE+ADN | 68.62 |  | 2019-03-22 00:54:00.000 | 402 | [5 empty] | 2019-03-18 18:00:00.000 | 2019-01-12 00:00:00.000 | 0 | 21358.0007 | 2019-03-05 21:30:00.000 | 8.1458 | 32.5208 | 51.2292 | 64.0833 | 12.7113 | 416.911
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR57 (P111) | 24.7905 | 53.2115 | Sarb | Horizontal | Oil Producer | 2019-03-25 19:30:00.000 | Primary Drilling | ND-78 | POOH 12-1/4" RSS ASSY WHILE L/D DC'S & JAR. P/U, M/U & RIH WITH NEW 12-1/4" BIT, RSS ASSY, JAR & DC'S TO 5,816' | CONTINUE RIH 12-1/4" RSS ASSY TO BTM. RESUME DRILLING 12-1/4" HOLE AS PER PLAN TO SECTION TD | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | HPJSM | 70.82 |  | 2019-06-03 19:42:00.000 | 378 | [5 empty] | 2019-07-08 19:30:00.000 | 2019-03-25 00:00:00.000 | 0 | 27128.0009 | 2019-07-05 07:00:00.000 | 36.5625 | 72.5417 | 101.4792 | 105 | 34.8214 | 267.3258
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR11 ST | 24.7912 | 53.2128 | Sarb | Deviated |  | 2015-04-30 00:00:00.000 | Primary Drilling | ND-79 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | ATTEMPTED TO RETRIEVED H1 VALVE WITHOUT SUCCESS. | 42 |  | 2018-01-03 23:57:17.000 | [6 empty] | 2018-01-07 18:00:00.000 | 2017-11-23 05:00:00.000 | 9750.0003 | 15280.0005 | 2017-12-13 09:00:00.000 | 0.95833 | 14.5833 | 958.375 | 983.75 | 0.097416 | 15.9437
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR41 | 24.792 | 53.2127 | Sarb | Horizontal | Single Oil Producer targeting Arab D Reservoir | 2018-01-11 08:00:00.000 | Primary Drilling | ND-79 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | CONT. RIH 6" SLB DIR. ASSY. FROM 569' TO 1496' ON 4" DP STANDS | 68.35 |  | 2018-03-20 08:25:54.000 | [6 empty] | 2018-03-15 00:00:00.000 | 2018-01-11 03:00:00.000 | 0 | 18236.0006 | 2018-02-27 08:00:00.000 | 11.0208 | 34.4583 | 47 | 62.6667 | 17.5864 | 388
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR44 | 24.791 | 53.213 | Sarb | Horizontal | Oil Producer | 2018-03-19 16:00:00.000 | Primary Drilling | ND-79 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | PERFORMED SHALLOW TEST 230 GPM, 2010 PSI. TEST OK | 71 |  | 2018-05-24 23:55:48.000 | [6 empty] | 2018-06-22 16:00:00.000 | 2018-03-19 16:00:00.000 | 0 | 22475.0007 | 2018-06-11 14:00:00.000 | 34.9375 | 60.8542 | 83.9167 | 95 | 36.7763 | 267.8252
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR50 | 24.7913 | 53.2135 | Sarb | Horizontal | Water Injector | 2018-09-05 07:00:00.000 | Primary Drilling | ND-79 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | CHANGE OUT HANDLING EQUIPMENT TO 5" SIZE | 41.29 |  | 2018-10-14 06:53:24.000 | 571.89 | [5 empty] | 2018-10-18 00:00:00.000 | 2018-09-03 05:00:00.000 | 0 | 14765.0005 | 2018-09-28 20:30:00.000 | 2.9792 | 13.6875 | 23.5625 | 42.7083 | 6.9756 | 626.6313
EH | EME | United Arab Emirates | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | 576 | 21534 | ADMA SARB Island UAE | IDS | Gulf | AFE Assurance | SR52 | 24.7912 | 53.2136 | Sarb | Horizontal | Water injector | 2018-10-20 01:30:00.000 | Primary Drilling | ND-79 |  |  | 8A9BE9CEA0CC4F4FA39298D5EF2EF0F7 | CONT. RIH WITH 12 1/4" RSS ASSY ON 5 7/8" DP FROM 4523' TO 5000' * FILL UP STRING EVERY 20 STANDS. | 30.98 |  | 2018-11-27 12:15:00.000 | 569 | [5 empty] | 2018-11-29 06:00:00.000 | 2018-10-18 00:00:00.000 | 0 | 14893.0005 | 2018-11-14 01:30:00.000 | 2.9583 | 16.8542 | 25 | 40.1875 | 7.3613 | 595.72
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH 1086 |  |  | Haradh (HRDH) |  |  | 2019-04-23 11:00:00.000 | Primary Drilling | CTD-1 | N2 Pressure Test. Perform Accumulator drill, mass flow meter calibration, ESD & HPS pump function test . Finalize acceptance docs. | Finalize Rig acceptance. Start HRDH-1086 Operations. | FA73583975BB4932864F2B2073535247 | RIH W/ CLEAN OUT ASSEMBLY TO 8,430 FT (TAG OBSTRUCTION W/ 5K SET DOWN), PULL BACK 90 FT AND OPEN WELL. ~ PACK COIL EVERY 1,000 FT. ~ PREFORMED SHALLOW TEST AT 1,000 FT AND 5,000 FT (GOOD). ~ WT. CHECK EVERY 3,000 FT. ~ PUMPED COIL TREATMENTS. | 31.98 |  | 2019-05-24 23:31:12.000 | [6 empty] | 2019-05-22 00:15:00.000 | 2019-04-23 10:45:00.000 | 11804.0004 | 14874.0005 | 2019-05-19 17:00:00.000 | 4.0208 | 11.5938 | 26.25 | 28.5521 | 14.0825 | 566.6286
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1196 |  |  | Haradh (HRDH) |  |  | 2018-07-28 15:00:00.000 | Primary Drilling | CTD-1 |  |  | FA73583975BB4932864F2B2073535247 | RIH W/ BHA #1, OPEN WELL AT SURFACE (AS PER BFW), DEPTH CORRELATION W/ GR F/ 11,200 FT - 11,660 FT (+10 FT), SWITCH OVER TO CCL CONTINUE RIH BELOW SETTING COLLAR @ 12,169 FT. ~ D&M TESTED TOOLS EVERY 3,000 FT & PREFORMED WT CHECKS. ~ PUMP COIL TREATMENT. | 27 |  | 2018-08-24 00:00:00.000 | [6 empty] | 2018-08-23 12:00:00.000 | 2018-07-28 05:00:00.000 | 11580.0004 | 15429.0005 | 2018-08-14 11:30:00.000 | 3.375 | 7.0104 | 16.8542 | 25.875 | 13.0435 | 915.4413
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1197 |  |  | Haradh (HRDH) |  |  | 2019-03-21 03:00:00.000 | Primary Drilling | CTD-1 | UBD Hydro/ N2 PT on production line. Perform ESD & Engine Kills. Fix electrical plugs. Function test HPS pumps. (OK). PJSM. PU BHA#1, RIH. | RIH to TOC. POH, PU Whipstock BHA and Set the same APP. POH to mill window at HRDH-1197 APP. | FA73583975BB4932864F2B2073535247 | Start RIH BHA#2 (21.6 ft) Drilling Fluid (Caustic / pH= 11) . Continued RIH , Weight check every 3,000 ft. Slow for restrictions. 17:30 hrs: H2S Muster drill At 10,000 ft MD- Run GR correlation to 10,140 ft MD at 10 ft/min - corrected depth by +5 ft to 10,145 ft MD. Continue RIH at 40 ft/min as per D&M to 12,140 ft MD with CCL. | 30.78 |  | 2019-04-20 18:43:12.000 | [6 empty] | 2019-04-17 05:00:00.000 | 2019-03-21 02:45:00.000 | 12033.0004 | 15000.0005 | 2019-04-11 03:00:00.000 | 3.9271 | 9.6042 | 21 | 27.0833 | 14.5 | 714.2857
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1257 |  |  | Haradh (HRDH) |  |  | 2018-11-01 15:30:00.000 | Primary Drilling | CTD-1 | RIH with BHA#2 / POOH for Tool failure / RIH w/BHA#3 and set Whipstock at 11,313 ft MD / POOH / Undeploy BHA#03 - days since spud 1.6 days | RIH and Mill window | FA73583975BB4932864F2B2073535247 | At 7,500 ft MD - GR sensor failure. Troublehsoot with no success. Started POOH to surface. Isolated and bleed off 5k choke, well on 10k Choke, SiWHP = 2,198 psi. UBD flush surface equipment. | 50.9 |  | 2018-12-21 21:36:00.000 | [6 empty] | 2018-12-26 00:15:00.000 | 2018-11-01 15:30:00.000 | 11277.0004 | 14324.0005 | 2018-12-05 09:30:00.000 | 9 | 22.3542 | 33.75 | 54.3646 | 16.5549 | 424.4148
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1258 |  |  | Haradh (HRDH) |  |  | 2018-08-31 04:00:00.000 | Primary Drilling | CTD-1 | Complete N2 Pressure tests on UBD equipment’s. Performed forward slack management / ESD functions tests / close out action items. Rig got accepted – PU and deployed BHA#01 (Whipstock assembly) @ 05:00 hrs – in progress. | Deploy BHA#01 / RIH to set Whipstock APP. | FA73583975BB4932864F2B2073535247 | PU and Deployed BHA#01 (Whipstock#106397914, Weep Sub, Gyro Collar, Drilling orientor, Drilling Head, TFO= 222 deg. Test Tools Communication in lubricator (Good). Checked data communication between coil cab & D&M - Good. SiWHP= 2,930 psi. | 31 |  | 2018-10-01 00:00:00.000 | [6 empty] | 2018-09-25 07:30:00.000 | 2018-08-31 04:00:00.000 | 12047.0004 | 14795.0005 | 2018-09-23 14:00:00.000 | 1.2708 | 8.5417 | 23.4167 | 25.1458 | 5.0539 | 631.815
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1267 |  |  | Haradh (HRDH) |  |  | 2018-10-03 16:00:00.000 | Primary Drilling | CTD-1 | POOH to surface / Inspected BHA / RIH with Milling Assy / Ream and mill Obstructions / POOH / M/U and RIH with Whip#2 | RIH and Set Whipstock in place - POOH for milling Assy. | FA73583975BB4932864F2B2073535247 | D&M start Make Up Milling Assembly (Diamond Speed Mill, Diamond string Mill, Extreme Motor, XO, DCD 30K, Fusion NOV, DO, DBV, DH, HUK). Checked data communication between coil cab and D&M - OK | 29.44 |  | 2018-11-01 10:33:36.000 | [6 empty] | 2018-10-27 07:30:00.000 | 2018-10-03 16:00:00.000 | 12178.0004 | 15287.0005 | 2018-10-21 11:00:00.000 | 0.083333 | 7.1354 | 17.7917 | 23.6458 | 0.35242 | 859.2225
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1310 |  |  | Haradh (HRDH) |  |  | 2019-01-02 11:00:00.000 | Primary Drilling | CTD-1 | POOH w/ Whop setting tool / MU BHA#3 / RIH / Start Milling Window f/ 11,869 ft to 11,877 ft MD / Drill 10 ft Rat hole / Ream window area. | Cont Mill Window& Rat hole APP / POOH to change BHA | FA73583975BB4932864F2B2073535247 | Started POOH to surface pumping 1.8 bpm to circulate Hi Vis Out. At 9,000 ft MD - Reduced pump rate to min 0.25 bpm. Pumped internal corrosion inhibitor. At 2,500 ft MD - Shut-in the well, SiWHP= 0 psi. Continued POOH normal speed pumping minimum to fill coil / UBD isolated 5K and flush UBD Package. At 2,000 ft MD - PJSM for BHA change. | 31.6 |  | 2019-02-02 14:24:00.000 | [6 empty] | 2019-01-26 00:15:00.000 | 2019-01-02 10:45:00.000 | 11882.0004 | 15323.0005 | 2019-01-17 22:30:00.000 | 2.0208 | 5.8333 | 15.4792 | 23.5521 | 8.5803 | 989.9112
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HWYH-1103 |  |  | Hawiyah (HWYH) |  |  | 2019-02-04 05:00:00.000 | Primary Drilling | CTD-1 |  |  | FA73583975BB4932864F2B2073535247 | PJSM, DEPLOY BHA #1 W/ 4 1/2" BAKER MONOBORE WHIPSTOCK #106397443-01 ASSEMBLY (2 PIECES). ~ SURFACE TEST TOOL COMMUNICATION (GOOD TEST). ~ SIWHP @ 2,600 PSI. | 30.44 |  | 2019-03-06 10:33:36.000 | [6 empty] | 2019-03-12 20:00:00.000 | 2019-02-04 05:00:00.000 | 13200.0004 | 16170.0005 | 2019-02-22 13:00:00.000 | 1.9375 | 9.625 | 18.3333 | 36.625 | 5.2901 | 882
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HWYH-1116 |  |  | Hawiyah (HWYH) |  |  | 2019-06-15 18:30:00.000 | Primary Drilling | CTD-1 | N2 TEST,CALI METERS, CLOSE OUT ITEMS, LOW,ACCEPT RIG , RIH /POH | UNDEPLOY, RIH WITH W/STOCK, SET W/STOCK, POH, RIH, MILL WINDOW | FA73583975BB4932864F2B2073535247 | PULL BACK TO 11,205 FT AND ORIENTATE GYRO TOOL FACE TO 272.69 DEG. (15 DEG LEFT OF HS). ~ STAGE PUMP RATE UP TO 1.5 BPM, SET 4-1/2" WHIPSTOCK (106419152.01) @ 11,205 FT WITH 1,050 PSI AND WHP @ 1,800 PSI. ~ CONFIRM SET WITH 5K SET DOWN WEIGHT. ~ PULL BACK AND FLAG COIL @ 11,155 FT | 28.57 |  | 2019-07-13 13:40:48.000 | [6 empty] | 2019-07-11 00:15:00.000 | 2019-06-15 18:30:00.000 | 11200.0004 | 14286.0005 | 2019-06-27 01:30:00.000 | 1.4792 | 4.8542 | 11.2917 | 25.2396 | 5.8605 | 1265.1809
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HWYH-1118 |  |  | Hawiyah (HWYH) |  |  | 2018-06-27 09:30:00.000 | Primary Drilling | CTD-1 |  |  | FA73583975BB4932864F2B2073535247 | STAGE P/R TO 42 GPM, ACTIVATE SETTING TOOL. - STAGE P/R TO 53 GPM, SET BOTTOM WHIPSTOCK @ 11,751 FT. - SETTING PRESSURES: CP @ 1,420 PSI, IP @ 5,680 PSI, ANNULAR PRESS @ V3,130 PSI, DIFF PRESS @ 2,549 PSI. - SET DOWN 3K TO CONFIRM SET - GOOD. | 25 |  | 2018-07-22 00:00:00.000 | [6 empty] | 2018-07-21 00:00:00.000 | 2018-06-27 09:30:00.000 | 11751.0004 | 14400.0005 | 2018-07-19 03:30:00.000 | 2 | 8.6667 | 21.75 | 23.6042 | 8.4731 | 662.069
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | JFYN-7 |  |  | Haradh (HRDH) |  |  | 2019-05-29 07:00:00.000 | Primary Drilling | CTD-1 | Completed Pre start up N2 pressure tests to both CTD / UBD equipment. Performed accumulator drill / ESD function tests and emergency kills. Started to work on rig acceptance / close out action items Rig acceptance for operations at 07:00 hrs on May 19, 2019. Deploy BHA#1, running correlation | Tag Cement plug, drill the same and 6 ft Rat Hole & POH for change BHA. Undeploy BHA#1, Deploy BHA#2 | FA73583975BB4932864F2B2073535247 | PJSM - PU & deploy BHA#1, Clean out Cemment BHA (Security 3 5/8" RR PDC 13168995, PDM Motor ABH= Zero°, DCD 30K, Max Overpull= 19K). Check data communication between coil cab & D&M (OK). Line Up to 10K CM. Open T6, SiWHP = 0 psi. Line up to 5K choke and open well | 51.21 |  | 2019-07-19 05:02:24.000 | [6 empty] | 2019-06-05 09:30:00.000 | 2019-05-29 07:00:00.000 | 15680.0005 | 15741.0005 | 2019-06-03 01:30:00.000 | 1.2292 | 4.4792 | 4.7708 | 7.1042 | 17.3021 | 3299.4237
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1028 |  |  | Shadgam-SDGM |  |  | 2019-07-18 12:00:00.000 | Primary Drilling | CTD-1 | Rig Accepted for Operations. Deploy BHA#1. Start RIH | RIH to TOC. Drill cement, shoe track, rat hole, ream the same. Drill BUS for SDGM-1028 L-1 APP | FA73583975BB4932864F2B2073535247 | PJSM - Deploy BHA#1 (PDC 3-5/8" BH5302529, XP Turbine 1.5 ABH, DCD 30K, FS, ENP, DO, DBV, DH, HUK, Max Over pull= 14.5 K). Check data communication between coil cab & D&M (Good). Line Up & Equalize 200 psi to 10K CM. Open T6, SiWHP= 0 psi. Line up well to 5K CM. | 22.8 |  | 2019-08-09 19:12:00.000 | [6 empty] | 2019-08-04 11:00:00.000 | 2019-07-18 00:00:00.000 | 14761.0005 | 15624.0005 | 2019-08-01 07:00:00.000 | 1.4792 | 8.0625 | 13.7917 | 16.9583 | 8.7224 | 1132.858
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1109 |  |  | Shadgam-SDGM |  |  | 2019-10-04 21:30:00.000 | Primary Drilling | CTD-1 | Performed forward slack management. Conducted N2 Pressure tests to both CTD and UBD equipment APP. Performed gas line meter factor calibration and function test equipment. Finalize Documents / Close out items @ 05:00 hrs – in progress. | Finalize Rig acceptance documentation. Start SDGM-1109 drilling operations. | FA73583975BB4932864F2B2073535247 | WORKING ON CLOSE OUT ACTION ITEMS. ~ REVIEW RIG ACCEPTANCE DOCUMENTATION. ~ CLOSE OUT ACTION ITEMS. ~ GENERAL HOUSE KEEPING. ~ PERFORM FINAL SAFETY WALK AROUND. ~ PERFORM H2S MAN DOWN DRILL AT RIGSITE & MAIN CAMP. ~ DISCUSS DRILLING PROGRAM AND FORWARD PLAN. | 18.27 |  | 2019-10-22 06:28:48.000 | [6 empty] | 2019-10-19 00:15:00.000 | 2019-10-04 00:00:00.000 | 14320.0005 | 15283.0005 | 2019-10-15 23:00:00.000 | 1.2917 | 7.6667 | 11.0625 | 14.1146 | 9.1513 | 1381.5142
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1111 |  |  | Shadgam-SDGM |  |  | 2019-09-14 09:00:00.000 | Primary Drilling | CTD-1 | Continue general RU / maintenance. Perform Emergency engine kills. N2 Line P/T. Function test equipment. Finalize Documents / Close out items | Start SDGM-1111 drilling operations | FA73583975BB4932864F2B2073535247 | CONTINUE RECEIVING RIG ACCEPTANCE PAPERWORK. ~ 06:15 HELD H2S MUSTER/MAN DOWN DRILL WITH AM CREW. ~ PERFORM PHYSICAL INVENTORY OF CTD/UBD CRITICAL SPARES. ~ UBD FIX LEAKS ON FRAC TANK TRANSFER HOSES. | 22.53 |  | 2019-10-06 12:43:12.000 | [6 empty] | 2019-09-28 05:00:00.000 | 2019-09-14 00:00:00.000 | 12970.0004 | 14600.0005 | 2019-09-22 14:00:00.000 | 1.0208 | 4.7917 | 8.2083 | 13.8333 | 7.3795 | 1778.6803
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | UTMN 2041 |  |  | Uthmaniya (UTMN) |  |  | 2019-08-12 17:00:00.000 | Primary Drilling | CTD-1 | Continued to work on closing actions items’ GD&WD In-House Assessment Audit. Waiting for Critical Spare Parts @ 05:00 hrs – in progress. | Close out action items. Finalize Rig Acceptance and start UTMN-2041 drilling operations | FA73583975BB4932864F2B2073535247 | General H2S Drill. PJSM with All Crew - Discussed Forward Operations plan. | 35.75 |  | 2019-09-16 18:00:00.000 | [6 empty] | 2019-09-07 15:00:00.000 | 2019-08-12 00:00:00.000 | 14992.0005 | 16639.0005 | 2019-09-05 14:00:00.000 | 2.6667 | 12.4167 | 23.875 | 25.9167 | 10.2894 | 696.9215
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-57 |  |  | Ghazal (GHZL) |  |  | 2019-05-03 18:00:00.000 | Primary Drilling | XTD-2 | Complete N2 tests, Accept the rig @ 3rd Mai, RIH BHA#1 Clean out assembly, Drill cement from 13,798 ft to 13,845 ft. | Complete drill cement and rat hole \ POOH BHA#1 Cleanout \ RIH BHA#2 Build. | FA73583975BB4932864F2B2073535247 | PJSM, UNDEPLOY MOTOR DRILLING BHA#1 ~ TAG STRIPPER; WHP @ 0 PSI. ~ INSPECT COIL & UTT ~ MINIMUM COIL THICKNESS ON UTT READING: "0.170". BIT GRADING: 1-1-WT-A-X-0-NO-BHA | 29.45 |  | 2019-06-01 10:48:00.000 | [6 empty] | 2019-06-06 05:00:00.000 | 2019-05-03 18:00:00.000 | 13894.0004 | 15593.0005 | 2019-05-28 18:00:00.000 | 6.0625 | 13.7188 | 25 | 33.4583 | 18.1196 | 623.72
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-66 |  |  | Ghazal (GHZL) |  |  | 2019-03-23 06:00:00.000 | Primary Drilling | XTD-2 | Continue rigging up and performing N2 Pressure test & Slack management | Finish rig up and rig acceptance , spud well | FA73583975BB4932864F2B2073535247 | DRILL OUT CEMENT TO CASING SHOE ~ PR @ 92 GPM, CP @ 2780 PSI. RPM @ 178, G/R @ 0.0 MMSCF. ~ AVG WHP @ 0 PSI, TCA @ 370 PSI, BHP @ 5950 PSI, BHT @ 253 DEGF. ~ RG @ 0.0%, HVP & WEIGHT CHECKS AS REQU'D. | 32.32 |  | 2019-04-24 07:40:48.000 | [6 empty] | 2019-04-27 18:00:00.000 | 2019-03-23 06:00:00.000 | 13889.0004 | 15534.0005 | 2019-04-04 02:30:00.000 | 1.8125 | 4.9167 | 11.8542 | 35.5 | 5.1056 | 1310.4253
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-75 |  |  | Ghazal (GHZL) |  |  | 2018-12-28 12:00:00.000 | Primary Drilling | XTD-2 | Complete pressure testing / Accept the Rig / Deploy BHA#1 / RIH / drill cement and rat hole / Ream cement and shoe track. Daily drilling footage = 5 ft. | POOH / Undeploy BHA#1 / Deploy and RIH BHA#2 Build Assembly / Drill build | FA73583975BB4932864F2B2073535247 | Undeploy of BHA#1. Close T6. Last recorded siWHP = 0 psi. Lay down lubricator with BHA#1. | 31.25 |  | 2019-01-28 06:00:00.000 | [6 empty] | 2019-01-25 05:00:00.000 | 2018-12-28 12:00:00.000 | 13652.0004 | 15650.0005 | 2019-01-17 08:30:00.000 | 1.6667 | 8.375 | 19.8542 | 27.7083 | 6.015 | 788.2477
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-77 |  |  | Ghazal (GHZL) |  |  | 2019-06-09 12:15:00.000 | Primary Drilling | XTD-2 |  |  | FA73583975BB4932864F2B2073535247 | REAM SHOE TRACK WITH DIFFERENT TF ~ PUMP SWEEPS. ~ REAM ACROSS SHOE TILL LOW DIFF OBSERVED. ~ MAKE 2 DRY PASSES @ 5 FPM & 10 FPM; FREE. | 31.03 |  | 2019-07-13 00:43:12.000 | [6 empty] | 2019-07-02 07:00:00.000 | 2019-06-12 14:30:00.000 | 13821.0004 | 15575.0005 | 2019-06-30 19:00:00.000 | 1.8542 | 7.9479 | 21.2812 | 22.7812 | 8.139 | 731.8649
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-80 |  |  | Ghazal (GHZL) |  |  | 2019-03-02 12:30:00.000 | Primary Drilling | XTD-2 | Complete N2 testing \ Accept the Rig \ RIH BHA#1 cleanout assembly \ drill cement and rat hole \ Daily drilling footage = 2 ft. | Complete the rat hole \ ream cement section \ POOH BHA#1 \ RIH BHA#2 Build Assembly \ Drill build | FA73583975BB4932864F2B2073535247 | REAM SHOE TRACK WITH DIFFERENT TF ~ PUMP SWEEPS. ~ CONT REAMING TILL NO MOTOR WORK. ~ MAKE DRY PASS; FREE. | 29.3 |  | 2019-03-31 07:12:00.000 | [6 empty] | 2019-03-16 08:00:00.000 | 2019-03-02 12:30:00.000 | 13795.0004 | 14017.0004 | 2019-03-05 06:00:00.000 | 0.0625 | 1.4375 | 2.7292 | 13.8125 | 0.45249 | 5136.0002
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-84 |  |  | Ghazal (GHZL) |  |  | 2018-11-27 08:30:00.000 | Primary Drilling | XTD-2 | Complete N2 pressure test / Accept the rig / Deploy & RIH with BHA#1 Cleanout assembly / Cleanout cement & Rat hole / Ream cement section / Daily drilling footage = 5 ft. | POOH / Undeploy BHA#1 / Deploy & RIH with BHA#2 build assembly / Drill build section. | FA73583975BB4932864F2B2073535247 | PJSM, UDEPLOY BHA#1 APP. WHP = 0 PSI. ~ BIT GRADING: 1-0-WT-X-A-0-NO-BHA ~ UTT LAST 18' OF COIL; 0.170". ~ CHANGE TWO BEARING ON INJECTOR CHAINS | 30 |  | 2018-12-27 00:00:00.000 | [6 empty] | 2018-12-22 10:00:00.000 | 2018-11-27 08:00:00.000 | 13518.0004 | 15178.0005 | 2018-12-09 14:00:00.000 | 0 | 4.9792 | 12.2292 | 25.0625 | 0 | 1241.1312
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | GHZL-85 |  |  | Ghazal (GHZL) |  |  | 2019-01-30 17:00:00.000 | Primary Drilling | XTD-2 |  |  | FA73583975BB4932864F2B2073535247 | AT 9,565 FT MD, ATTEMPT TO PASS THROUGH AT DIFFERENT RUNNING SPEED & TF WITHOUT PUMPS - NO SUCCESS (SEVERAL STALLS, NO OP). ~ INCREASE PR TO 93 GPM, ATTEMPT TO PASS THROUGH W/ DIFFERENT SPEED & TF - NO SUCCESS (SEVERAL STALLS, NO OP). MULTIPLE MOTOR STALLS & DIFF PRESSURE SPIKES F/ 150 PSI TO 700 PSI. ** INFORM ARAMCO OFFICE, DECISION TO POH & INSPECT BHA. | 30.2 |  | 2019-03-01 04:48:00.000 | [6 empty] | 2019-02-24 10:30:00.000 | 2019-01-30 17:00:00.000 | 14240.0005 | 15998.0005 | 2019-02-10 04:00:00.000 | 0.52083 | 6.2917 | 10.4583 | 24.7292 | 2.1061 | 1529.6893
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH 1274 |  |  | Haradh (HRDH) |  |  | 2019-07-13 06:00:00.000 | Primary Drilling | XTD-2 | Complete N2 tests \ Open well for initial flow \ Accept the rig \ RIH BHA#1 drift BHA \ POOH BHA#1 \ RIH BHA#2 Whipstock. | Set whipstock \ POOH BHA#2 \ RIH BHA#3 milling assembly | FA73583975BB4932864F2B2073535247 | Set depths RIH with BHA#1 clean out assembly. Pumped inhibitor 1 Drum of (Corton RN-477) with 5 drums of diesel down the coil. Pumped inhibitor 1 Drum of (Corton 0-3670-R) back side. Pump 10 gpm down coil. Perform weight checks every 3,000 ft. MD. 6000 ft. MD Open up well to UBD package | 32.28 |  | 2019-08-15 06:43:12.000 | [6 empty] | 2019-08-13 00:15:00.000 | 2019-07-14 06:00:00.000 | 12030.0004 | 14828.0005 | 2019-08-10 14:00:00.000 | 2.6042 | 11.0625 | 28.3333 | 30.7604 | 8.466 | 523.3412
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-1256 |  |  | Haradh (HRDH) |  |  | 2019-08-18 05:00:00.000 | Primary Drilling | XTD-2 | Complete all pressure tests. | Accept the rig \ RIH BHA#1 drift BHA | FA73583975BB4932864F2B2073535247 | PJSM; POH W/COC BHA#1 TO SURFACE. ~ TAKE CCL LOG @ 17 FPM FROM 13,500' TO 13,200'; NO CORRECTION COMAPRED WITH TALLY. | 25.89 |  | 2019-09-12 21:21:36.000 | [6 empty] | 2019-09-14 05:00:00.000 | 2019-08-18 05:00:00.000 | 12822.0004 | 16450.0005 | 2019-09-05 03:30:00.000 | 6.9375 | 10.4375 | 17.9375 | 27 | 25.6944 | 917.0732
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | HRDH-2124 |  |  | Haradh (HRDH) |  |  | 2019-09-22 05:00:00.000 | Primary Drilling | XTD-2 | Complete pressure testing / Flow well. | Flow well / Accept rig / Deploy BHA#1 / RIH. | FA73583975BB4932864F2B2073535247 | HPJSM, UNDEPLOY BHA#1 ~ WHP @ 120 PSI ~ INSPECT LAST 18 FT OF COIL; MIN UTT @ 0.175" | 34.94 |  | 2019-10-26 22:33:36.000 | [6 empty] | 2019-10-22 05:00:00.000 | 2019-09-22 05:00:00.000 | 11163.0004 | 13792.0004 | 2019-10-19 12:30:00.000 | 0.16667 | 17.0417 | 27.3125 | 30 | 0.55556 | 504.9703
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1034 |  |  | Shadgam-SDGM |  |  | 2018-09-20 00:00:00.000 | Primary Drilling | XTD-2 | M/U BHA # 1, RIH and set whipstcok @ depth 13,629 ft, POOH and M/U BHA # 2 - milling assembly, RIH and mill window | Continue milling the casing window and drill rat hole, then POOH | FA73583975BB4932864F2B2073535247 | Milling window. Pump Rate = 105 GPM, N2 Rate = 0 scfm, ELV = 105 gpm, CT Pressure = 2943 psi, Motor Diff Pressure = 619 psi, fBHP= 5935 psi, fWHP= 7 psi, Choke Size= 126/64th,Gas Rate = 0 MMscfd, Liquid Return Rate = 112 GPM, Gas Export Rate = 0.0 MMscfd, TCA = 794 psi, CT SO = 49 Klbs, WOB = 6.0 Klbs, ROP = 1 ft/hr, RG = 0.15%, H2S= 0 ppm, CO2= 0%, Caustic (out) = 0 pail /hr, PH (In) = 10.5, PH (out) = 10. BHT = N/A DegF. Chlorides = 3500 ppm. BSW= 100%. 3 bbls gel/hr (70 Vis). | 53.5 |  | 2018-11-12 12:00:00.000 | [6 empty] | 2018-10-30 00:00:00.000 | 2018-09-20 00:00:00.000 | 13620.0004 | 14886.0005 | 2018-10-14 10:30:00.000 | 3.5625 | 13.5 | 24.4375 | 40 | 8.9063 | 609.1458
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1036 |  |  | Shadgam-SDGM |  |  | 2018-08-09 03:00:00.000 | Primary Drilling | XTD-2 |  |  | FA73583975BB4932864F2B2073535247 | 13,026 ft MD. POOH to pick up build BHA. Shut in well at 5K. Line up to 10K choke. siWHP = 0 psi. Pump 10 gpm down the coil. 22:30 hrs: Hold H2S muster drill. Good response. Hold TBT with crew for Pressure undeployment/deployment. Engage X-Tag @ 150 ft. MD - reduce the pulling speed to 3 ft/min. Tag Stripper, WHP = 0 psi. | 24.2 |  | 2018-09-02 04:48:00.000 | [6 empty] | 2018-08-27 09:00:00.000 | 2018-08-09 02:45:00.000 | 12990.0004 | 15578.0005 | 2018-08-17 06:00:00.000 | 2.9792 | 2.6979 | 8.125 | 18.25 | 16.3242 | 1917.2924
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-1051 |  |  | Shadgam-SDGM |  |  | 2018-07-15 10:30:00.000 | Primary Drilling | XTD-2 | Finish N2 and accept the rig (7.1 days), spud well SDGM-1051, P/U BHA # 1, RIH and clean out cement, POOH | P/U BHA # 2 - RIH and drill BUS of lateral # 1 | FA73583975BB4932864F2B2073535247 | PATTERN THE BIT & CONTINUE TURBINE DRLG BUS FOR L0-1 AS PER GOC. - PR @ 101 GPM, CP @ 2975 PSI. G/R @ 0.0 MMSCF. - AVG WHP @ 0 PSI, TCA @ 698 PSI, BHP @ 5445 PSI, BHT @ 282 DEGF. - HVP & WEIGHT CHECKS AS REQU'D. - H2S @ 0 PPM & CO2 @ 0 % | 25 |  | 2018-08-09 00:00:00.000 | [6 empty] | 2018-08-02 08:00:00.000 | 2018-07-15 10:30:00.000 | 12420.0004 | 15531.0005 | 2018-07-28 20:30:00.000 | 0 | 4.0312 | 13.4167 | 17.8958 | 0 | 1157.5901
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | SDGM-211 |  |  | Shadgam-SDGM |  |  | 2018-09-02 13:00:00.000 | Primary Drilling | XTD-2 |  |  | FA73583975BB4932864F2B2073535247 | RIH W/BHA#1 TO TOP OF CEMENT ~ LOG & CORRELATE GAMMA FROM 12,500'. CORRECTION (+30'). ~ TAG TOC @ 12,830' | 23.2 |  | 2018-09-25 04:48:00.000 | [6 empty] | 2018-09-12 11:00:00.000 | 2018-09-02 13:00:00.000 | 12830.0004 | 15363.0005 | 2018-09-07 12:30:00.000 | 0.47917 | 1.7396 | 4.9792 | 9.9167 | 4.8319 | 3085.4562
EH | KSA | Saudi Arabia | FA73583975BB4932864F2B2073535247 | 600 | 200000000000000000432017 | CTD UBD Saudi Aramco | IDS | KSA | Other | UTMN-2041 |  |  | Uthmaniya (UTMN) |  |  | 2018-11-05 11:00:00.000 | Primary Drilling | XTD-2 | Complete N2 pressure tests. days since rig release 6.2 | Flow the well / Accept the rig / Deploy & RIH with BHA#1 (Drift run) to 14,300 ft. MD / POOH. | FA73583975BB4932864F2B2073535247 | RIH W/BHA#1 TO WS SET DEPTH ~ LOG & CORRELATE CCL FROM 11,900'. CORRECT DEPTH @ 12,180' (+40'). ~ CONT RIH FREELY TO 14,300' (100' BELOW WS SET DEPTH). ~ MAKE DRY PASSES THRU WHIPSTOCK SET DEPTH; OK. | 45 |  | 2018-12-20 00:00:00.000 | [6 empty] | 2018-11-14 00:15:00.000 | 2018-11-05 11:00:00.000 | 14200.0005 | 14809.0005 | 2018-11-11 10:00:00.000 | 0 | 3.9375 | 5.9583 | 8.5521 | 0 | 2485.4267
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-312 (AK-21 V) | 30.5339 | 47.5899 | Zubair | Vertical | Zubair Vertical | 2018-02-28 13:00:00.000 | Primary Drilling | RMG 101 | DRILLED AHEAD 8 1/2" SECTION FROM 3322 M TO 3497 M, WELL TD, CONFIRM BY ZFOD GEOLOGIST, SWEEP HOLE BY 15 M3 HI.VIS AND CIRCULATE HOLE CLEAN, POOH TO 3950 M, IN PROGRESS. | POOH TO SURFACE, RUN, CEMENT AND SET 7" LINER HANGER, POOH LINER HANGER RUNNING TO SURFACE, RIH CLEAN OUT ASSY., DISPLACE HOLE BY BRINE, POOH AND L/D DRILL STING SINGLE BY SINGLE , | ACCD407A530443079C6987C8E474FE37 | SWEEP HOLE BY 15 M3 HI.VIS PILL AND CIRCULATE HOLE CLEAN. - FR: 1900 LPM, SPP: 2385 PSI. - RECIPROCATED A SINGLE WHILE CIRCULATING HOLE CLEAN - OBSERVED 40-30% SPLINTERY CAVING, 2-4 CM AFTER ONE BOTTOM UP. | 28.82 |  | 2018-03-28 19:43:43.000 | 387 | [5 empty] | 2018-04-02 12:00:00.000 | 2018-02-28 13:00:00.000 | 170.6037 | 11473.0975 | 2018-03-24 20:45:00.000 | 2.1458 | 15.1667 | 24.3229 | 32.9583 | 6.5107 | 471.6991
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-335 (AP-30 DIR) | 30.4574 | 47.625 | Zubair | Deviated | Mishrif Deviated | 2018-01-20 22:00:00.000 | Primary Drilling | RMG 101 | RIH CSG 9 5/8" TO 2307 M, CEMENTED AS PER PLAN. INSTALLED 9 5/8" PACK OFF AND PT SAME, INSTALLED WEAR BUSHING, P/U & M/U 8 1/2" BHA AND RIH TO 1015 M. | DRILL 8 1/2" SECTION. | ACCD407A530443079C6987C8E474FE37 | CONTINUED P/U & M/U 8 1/2" BHA AND RIH TO 98 M. | 42.04 | 42.04 | 2018-03-04 00:50:49.000 | 387 | [5 empty] | 2018-02-20 14:00:00.000 | 2018-01-21 00:00:00.000 | 185.6955 | 8385.827 | 2018-02-15 10:00:00.000 | 6.8854 | 17.375 | 25.5 | 30.6667 | 22.4524 | 328.856
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-338 (AO-33 DIR) | 30.4436 | 47.6167 | Zubair | Deviated | Mishrif Deviated | 2017-12-16 11:00:00.000 | Primary Drilling | RMG 101 | CONTINUE CIRCULATION. SPOT BRIDGING PILL ACROSS MISHRIF. POOH TO SURFACE L/D DIRECTIONAL TOOL. PERFORMED WL OPEN HOLE LOG.R/U WTF LINER RUNNING EQUIPMENT.7" TSH BLUE LINER SHOE TRACK AND RUN TO 42 M. | CONTINUE RUNNING 7" LINER TO SETTING DEPTH, PERFORM, CEMENT 7" LINER, POOH 7" LINER HANGER RUNNING TOOLS, RIH TANDUM SCRAPER BHA AND DISPLACE WELL BY BRINE. | ACCD407A530443079C6987C8E474FE37 | CONTINUED CIRCULATED HOLE CLEAN. 3 BOTTOMS UP. - FR: 1865 LPM, SPP: 2125- 2180 PSI, RPM: 80-120, TQ: 7.75-8.5 K.LBS*FT. - RECIPROCATE STRING UP/DOWN WITH ROTATION - CONFIRM SHAKERS CLEAN | 42.73 | 42.73 | 2018-01-27 17:31:01.000 | 387 | [5 empty] | 2018-01-13 07:00:00.000 | 2017-12-16 11:00:00.000 | 0 | 8651.5751 | 2018-01-08 23:30:00.000 | 5.0104 | 15.8542 | 23.5208 | 27.8333 | 18.0015 | 367.826
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-350 | 30.5517 | 47.5732 | Zubair | Deviated | Mishrif | 2018-05-14 00:00:00.000 | Primary Drilling | RMG 101 | P/U & M/U 8 1/2" BHA TO 102 M. RIH TO 2269 M (TOC), DRILLED SHOE TRACK. CONTINUED DRILLING 8 1/2 SECTION TO 2447 M. | DRILL 8 1/2" SECTION TO +/- 2627 M. | ACCD407A530443079C6987C8E474FE37 | DRILLED 8 1/2" SECTION FROM 2363 M TO 2398 M. - WOB: 5-16 TONS; FR:1900 LPM; SPP: 1325 PSI; RPM: 120, TORQUE 7-14 KFT-LBS. - MW IN/OUT: 1.07 SG. - AVG. ROP: 11.7 M/HR, ON BOTTOM ROP: 12 M/HR. - PUMP 4 M3 OF HI.VIS PILL TWO TIMES EACH STAND DRILLED. - REAM UP AND REAMED DOWN EACH STAND DRILLED. - LITHOLOGY @ 2320 M: 100% LIMESTONE. - FORMATION: MISHRIF - MAX. TGAS: 6 %. - NO DOWN HOLE LOSSES. | 44.59 |  | 2018-06-27 14:15:36.000 | 387 | [5 empty] | 2018-06-10 15:00:00.000 | 2018-05-14 00:00:00.000 | 170.6037 | 8503.9373 | 2018-06-03 16:00:00.000 | 4.4167 | 11.6042 | 20.6667 | 27.625 | 15.9879 | 411.4808
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-351 | 30.5578 | 47.5764 | Zubair | Deviated | Mishrif | 2018-04-13 11:30:00.000 | Primary Drilling | RMG 101 | CONTINUED DRILLING TO 1822 M. | DRILLING 17 1/2" SECTION, CIRCULATE, POOH FOR 9 5/8" CASING | ACCD407A530443079C6987C8E474FE37 | DRILLING 17 1/2" HOLE FROM 1752 M TO 1808 M (TOP OF HARTHA). - WOB: 15 - 20 MT; FR: 3300 LPM; SPP: 1880 PSI; RPM: 120 - 130, TQ: 17 KFT.LB. - MW IN/OUT 1.14 SG; - AVG ROP: 8 M/HR, ON BOTTOM ROP: 10 M/HR. - LITHOLOGY @ 1800 M: 100% ARGILLACEOUS LIMESTONE - FORMATION: SHIRANISH - NO DOWN HOLE LOSSES. | 36.57 |  | 2018-05-19 13:35:19.000 | 387 | [5 empty] | 2018-05-06 06:00:00.000 | 2018-04-13 11:30:00.000 | 187.0079 | 8031.4963 | 2018-04-29 23:15:00.000 | 2.3958 | 8.2708 | 16.4896 | 22.7708 | 10.5215 | 487.0648
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-371 Dir ( AM-27 ) | 30.4913 | 47.6059 | Zubair | Deviated | Mishrif | 2018-09-20 00:00:00.000 | Primary Drilling | RMG 101 | DRILLED 23" HOLE SECTION TO SECTION TD, CIRCULATE HOLE CLEAN, POOH TO 100 M. | LAY DOWN 23" BHA, RIH 18 5/8" CASING, CIRCULATE, RIH STINGER, CEMENT JOB, RUN GYRO, POOH STINGER, WOC, ROUGH CUT. | ACCD407A530443079C6987C8E474FE37 | SPUD THE WELL @00:00 ON 20 SEP 2018. - TAGGED BOTTOM AT 51 M. - CLEARED RAT HOLE DOWN TO 57 M | 17.01 |  | 2018-10-07 00:12:35.000 | 387 | [5 empty] | 2018-10-10 06:00:00.000 | 2018-09-20 00:00:00.000 | 167.3228 | 8366.142 | 2018-10-04 05:00:00.000 | 1.2083 | 8.1771 | 14.2083 | 20.25 | 5.9671 | 588.8194
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-375 Dir | 30.478 | 47.6204 | Zubair | Deviated | Mishrif | 2018-06-19 00:00:00.000 | Primary Drilling | RMG 101 | DRILLED 17 1/2" SECTION TO 1870 M. | DRILL AHEAD TO SECTION TD, CIRCULATE HOLE CLEAN, POOH FOR 13 3/8" CASING. | ACCD407A530443079C6987C8E474FE37 | DRILLING 17 1/2"" HOLE FROM 1763 M TO 1831 M. ( TOP OF HARTHA) - WOB: 9-10 MT; FR: 2235 LPM; SPP: 2400 PSI; RPM: 90-100, TQ: 12-15 KFT.LB. - MW IN/OUT 1.14 SG; - AVG ROP: 10.88 M/HR, ON BOTTOM ROP: 13.0 M/HR. - PUMP HI VIS IN THE MIDDLE OF EACH STAND - BACK REAM AND REAMED DOWN ONE SINGLE OF EACH STAND DRILLED. - LITHOLOGY @ 1830 M: 100% ARGILLACEOUS LIMESTONE - FORMATION: SHIRANISH - LIMESTONE 100%. - NO DOWN HOLE LOSSES. | 21.25 |  | 2018-07-10 06:05:21.000 | 387 | [5 empty] | 2018-07-16 17:00:00.000 | 2018-06-19 00:00:00.000 | 167.3228 | 8868.1105 | 2018-07-12 00:00:00.000 | 4.4479 | 15.0417 | 23 | 27.7083 | 16.0526 | 385.57
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-376 | 30.371 | 47.6 | Zubair | Vertical | Mishrif Vertical | 2018-07-26 00:00:00.000 | Primary Drilling | RMG 101 | POOH AND LAID DOWN 23" BHA, RIG UP WFD, RIH 18 5/8" CASING, CIRCULATE, RIH STINGER, CEMENT JOB, POOH STINGER, WOC, ROUGH CUT. | LIFT DIVERTER, INSTALL WELL HEAD, N/U 20 3/4" BOP, MAKE UP 17 1/2" BHA. | ACCD407A530443079C6987C8E474FE37 | CIRCULATE ONE BOTTOM UP. - FLOW RATE: 1500 LPM, PRESSURE: 70 PSI. * NO DOWN HOLE LOSSES. | 36.56 |  | 2018-08-31 13:23:31.000 | 387 | [5 empty] | 2018-08-14 09:00:00.000 | 2018-07-26 00:00:00.000 | 177.1654 | 8021.6538 | 2018-08-04 23:30:00.000 | 1.0313 | 5.375 | 9.9792 | 19.375 | 5.3226 | 803.84
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-381 | 30.5167 | 47.6353 | Zubair | Vertical | vertical | 2018-08-22 00:00:00.000 | Primary Drilling | RMG 101 | POOH 17 1/2" BHA FROM 1969 M TO SURFACE, LAID DOWN BHA, RETRIEVED WEAR BUSHING, PERFORM DUMMY RUN, R/U 13 3/8" WF HANDLING EQU., P/U, M/U AND RIH 13 3/8" SHOE TRACK, RIH 13 3/8" CSG TO 1286 M. | RUN AND CEMENT 13 3/8" CASING, WORKING ON WELL HEAD, P/U 12 1/4" PD VORTEX BHA. | ACCD407A530443079C6987C8E474FE37 | PERFORMED FLOW CHECK. - STATIC LOSSES: 2 M3/HR | 20.64 |  | 2018-09-11 15:22:12.000 | 387 | [5 empty] | 2018-09-12 05:00:00.000 | 2018-08-22 00:00:00.000 | 167.3228 | 10377.2969 | 2018-09-06 18:00:00.000 | 0.98958 | 8.3646 | 15.75 | 21.2083 | 4.666 | 658.876
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-384 | 30.5085 | 47.6362 | Mishrif | Vertical | Mishrif Vertical Injection | 2018-12-11 00:00:00.000 | Primary Drilling | RMG 101 | DRILL 12 1/4" HOLE TO 2442 M. | DRILL 12 1/4" HOLE SEC. TD, CIRCULATE HOLE CLEAN, POOH FOR WL OPERATION.. | ACCD407A530443079C6987C8E474FE37 | P/U AND M/U 12 1/4" PD BHA TO 292 M. | 15.35 |  | 2018-12-28 08:25:00.000 | 387 | [5 empty] | 2018-12-30 09:00:00.000 | 2018-12-13 18:00:00.000 | 160.7612 | 8123.3598 | 2018-12-23 07:00:00.000 | 0.0625 | 5.0104 | 12.2917 | 19.375 | 0.32258 | 660.8835
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-393 Dir | 30.57 | 47.5664 | Mishrif | Deviated | Mishrif Deviated | 2018-11-14 00:00:00.000 | Primary Drilling | RMG 101 | POOH AND L/D TANDEM SCRAPPER BHA AND ALL TUBULAR SINGLE BY SINGLE, PERFORM CASED HOLE LOGGING. R/D LOGGING TOOLS. PRESSURE TESTED CASING TO 2500 PSI, OK. R/U TBG HANDLING EQUIPMENT, RAN 4 1/2" TBG AS KILL STRING. LANDED TBG HANGER AND P/T SAME, INSTALLED BPV, N/D 13 5/8" BOP STACK, N/U X-MASS TREE AND P/T SAME, RETRIEVED BPV, SECURED THE WELL AND HANDOVER TO ZFOD. RIG RELEASED @ 24:00 HR ON 4TH DECEMBER 2018. | RIG DOWN. | ACCD407A530443079C6987C8E474FE37 | - RU SLB WL LOGGING TOOLS FOR RUN #1: - RUN #1 [ USIT FOR 9 5/8" CASING] | 18.25 |  | 2018-12-03 06:04:02.000 | 387 | [5 empty] | 2018-12-05 00:00:00.000 | 2018-11-15 00:00:00.000 | 170.6037 | 8303.806 | 2018-11-30 05:00:00.000 | 0.42708 | 8.7604 | 16.2083 | 21 | 2.0337 | 512.3171
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-334 (AM-17 DIR) | 30.4795 | 47.6174 | Zubair | Deviated | Deviated | 2018-02-03 00:00:00.000 | Primary Drilling | RMG 102 | RIH CASING 13-3/8 UP TO 1921 M. CIRCULATED HOLE CLEAN. R/U CEMENT HEAD & LINES, PERFORMED 1ST STAGE CEMENT JOB, ACTIVATE & INFLATE PACKER, OPEN DV TOOL, CIRCULATE, R/D CRT WTHFD. CEMENTING 2nd STAGE IN PROGRES | PERFORM 2ND STAGE CEMENT JOB 13-3/8" CSG @ 1921 M. , ND 21 3/4" BOP, NU 13 5/8" 5K , PU & MU BHA 12.25" RIH, | ACCD407A530443079C6987C8E474FE37 | INSTALL CEMENT HEAD. - MIXING 208 BBL (33.07 M3) OF 1.90 SG BATCH TAIL SLURRY, IN PROGRESS | 42.73 |  | 2018-03-17 17:31:01.000 | [6 empty] | 2018-03-26 08:30:00.000 | 2018-02-03 01:00:00.000 | 187.0079 | 8746.7194 | 2018-03-10 16:00:00.000 | 10.0312 | 23.5938 | 35.6667 | 51.3542 | 19.5335 | 245.2351
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-336 (AM-26 DIR) | 30.496 | 47.6055 | Zubair | Deviated | Mishrif Deviated | 2017-12-21 19:30:00.000 | Primary Drilling | RMG 102 | DRILLED 8 1/2" SECTION FROM 2518 M TO 2660 M (TD), CIRCULATED HOLE CLEAN, SPOTTED 10 M3 LCM BRIDGING PILL, POOH TO 2006 M. | CONTINUE TO POOH TO SURFACE, L/D D&M TOOLS AND RUN WL OH LOGS. | ACCD407A530443079C6987C8E474FE37 | DRILLED 8 1/2" SECTION FROM 2539 M TO 2548 M. - WOB: 3-9 TONS; FR:1965-1970 LPM; SPP: 1780-1820 PSI; RPM: 100-130, TORQUE: 9-12 KFT-LBS. - MW IN/OUT: 1.11 SG. - AVG. ROP: 7.2 M/HR, ON BOTTOM ROP: 12 M/HR. - PUMP 4 M3 OF LCM-BRIDGING PILL EACH STAND DRILLED. - REAM UP AND REAMED DOWN EACH STAND DRILLED. - APPLIED DRILL AND SEAL PROCEDURE. - MAKE CONNECTION ONE JOINT OFF BOTTOM. - FORMATION: MISHRIF - DOWN HOLE LOSSES: 5 M3/HR LAST SURVEY: MD 2515.07 M, INC: 47.37 DEG, AZIM: 123.51 DEG. CT-CT: 10.4 M, 10.26 LEFT, 1.27 ABOVE. | 42.73 |  | 2018-02-01 17:31:01.000 | 387 | [5 empty] | 2018-01-26 06:00:00.000 | 2017-12-21 19:30:00.000 | 183.727 | 8727.0344 | 2018-01-16 17:30:00.000 | 4.1458 | 13.4688 | 25.9167 | 35.4375 | 11.699 | 336.7344
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-343Dir | 30.5295 | 47.605 | Zubair | Deviated | Deviated | 2018-04-03 00:00:00.000 | Primary Drilling | RMG 102 | RIH 9-5/8" CSG AT 2310 M. CIRCULATED PRIOR TO CEMENT. PERFORMED CEMENTED JOB, PRESSURE TEST CASING, INSTALL PACK OFF, PRESSURE TEST IT, PRESSURE TEST BOP, PU/ MU 8.5" DIR. BHA, RIH AT 389 M | CEMENT 9-5/8" CSG AT 2310 M. INSTALL AND TEST PACK OFF. TEST BOP. INSTALL WEAR BUSHING. M/U & RIH 8-1/2" DIR BHA. | ACCD407A530443079C6987C8E474FE37 | PRESSURE TEST 13-5/8" BOP. 300 PSI FOR 5 MINS, 3000 PSI FOR 10 MINS PER TEST. ALL OK. - TEST #1: ANNULAR, NRV, HCR - TEST #2: INNER KILL LINE, MANUAL CHOKE, UPPER PIPE RAMS - TEST #3: OUTER KILL LINE, LOWER IBOP, UPPER PIPE RAMS, COFLEX HOSE, CHOKE MANIFOLD VALVES 2 4 6 7 - TEST #4: LOWER PIPE RAMS, STAND PIPE, ROTARY HOSE | 42.26 |  | 2018-05-15 06:15:07.000 | 387 | [5 empty] | 2018-05-14 18:00:00.000 | 2018-04-03 00:00:00.000 | 177.1654 | 8464.5672 | 2018-05-08 22:00:00.000 | 15.375 | 18.3542 | 35.9167 | 41.75 | 36.8263 | 235.6724
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-352 Dir | 30.5585 | 47.5862 | Mishrif | Deviated | Production | 2018-07-01 08:00:00.000 | Primary Drilling | RMG 102 | ACCEPTED RIG AT 08:00 AN AND SPUD THE WELL AT 08:15 HR. DRILLED 23" HOLE TO 502 M. | DRILL 23" HOLE TO +/- 747 M (SECTION TD), CIRCULATE HOLE CLEAN, POOH TO SURFACE, RIH 18 5/8" CSG. | ACCD407A530443079C6987C8E474FE37 | "PJSM PRIOR TO SPUD THE WELL WITH ALL PERSONNEL INVOLVE IN OPERATIONS. - RIH WITH 23" ROTARY BHA AND TAGGED AT 54 M. - DRILLED OUT CEMENT AND FS TO 58 M WITH CONTROLLED PARAMETERS. WOB: 1 - 5 T; RPM: 40 - 50; FR: 1000 LPM. ** RIG ACCEPTED AND SPUD THE WELL AT 8:15 HRS, 01ST JULY 2018 | 19.47 |  | 2018-07-20 11:16:12.000 | 387 | [5 empty] | 2018-07-24 14:00:00.000 | 2018-07-01 08:00:00.000 | 177.1654 | 8444.8822 | 2018-07-20 15:30:00.000 | 2.0417 | 11.3438 | 19.3125 | 23.25 | 8.7814 | 437.2755
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-353 | 30.371 | 47.6018 | Zubair | Vertical | Zubair Vertical | 2018-08-02 11:45:00.000 | Primary Drilling | RMG 102 | PERFORMED 9 5/8" CEMENT JOB, R/D CEMENT AND WTHF EQUIPMENT, R/D HANGER RT, INSTALLED AND PT 9 5/8" PACK OFF, INSTALLED WEAR BUSHING, RIH WITH 8 1/2" BHA TO 3131 M, DRILLED OUT SHOE TRACK FROM 3131 M TO 3166 M, DRILLED 8 1/2" HOLE FROM 3166 M TO 3171 M. | DRILL AHEAD 8 1/2" HOLE AS PER PROGRAM. | ACCD407A530443079C6987C8E474FE37 | DRILLED OUT PLUGS, SHOE TRACK AND RAT HOLE FROM 3131 M TO 3166 M. - WOB: 2-11 TON, FR: 1500 LPM, SPP: 1390-1820 PSI, RPM: 48-70, TRQ: 3-8 KFT-LBS. - WASH UP AND REAM DOWN TWICE ENSURE FREE PASS SHOE TRACK. - PUMP 5 M3 OF HI.VIS PIL AFTER DRILL OUT SHOE TRACK AND RAT HOLE. - NO DOWN HOLE LOSSES | 50.78 |  | 2018-09-21 18:37:03.000 | 387 | [5 empty] | 2018-08-31 17:30:00.000 | 2018-08-02 10:15:00.000 | 0 | 11607.6119 | 2018-08-24 14:45:00.000 | 3.0938 | 14.0625 | 22.125 | 29.2396 | 10.5807 | 524.6378
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-354 Dir | 30.4475 | 47.6314 | Mishrif | Deviated | J Type | 2018-05-22 11:00:00.000 | Primary Drilling | RMG 102 | P/U, M/U AND RIH WITH 8 1/2" BHA FROM SURFACE TO 1776 M, STOPPED RIH OPERATION DUE TO HIGH WIND SPEED, RESUMED RIH AND TAGGED TOP PLUG @ 2314 M, DRILLED OUT SHOE TRACK TO 2346 M. | DRILL OUT SHOE TRACK, DRILL AHEAD 8 1/2" HOLE SECTION. | ACCD407A530443079C6987C8E474FE37 | DRILLED OUT PLUGS, SHOE TRACK AND RAT HOLE FROM 2314 m TO 2346 m. - WOB: 0-5 TON, FR: 1900 lpm, SPP: 1200-1400 psi, RPM: 40-60, TRQ: 5-12 KFT-LBS. - RECIPROCATED THROUGH FLOAT COLLAR & FLOAT SHOE. - PUMPED 5 m3 OF HI. VIS PILL, OBSERVED RUBBERS OF PLUGS AND MEDIUM CEMENT ON SHAKERS. - NO DOWN HOLE LOSSES. | 16.56 |  | 2018-06-07 13:30:35.000 | 387 | [5 empty] | 2018-06-23 12:30:00.000 | 2018-05-22 11:00:00.000 | 0 | 8464.5672 | 2018-06-18 19:45:00.000 | 7.625 | 17.875 | 27.3646 | 32.0625 | 23.7817 | 309.3256
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-368 | 30.399 | 47.6286 | Zubair | Deviated | Mishrif | 2018-10-10 02:00:00.000 | Primary Drilling | RMG 102 | PERFORMED 9 5/8" CSG CEMENT JOB, INSTALLED PACK OFF AND P/T SAME, INSTALLED WEAR BUSHING, RIH WITH 8 1/2" BHA AND TAGGED CEMENT @ 2296 M, DRILLED OUT SHOE TRACK AND P/T 9 5/8" CSG. DRILLED AHEAD 8 1/2" SECTION TO 2348 M. | DRILL AHEAD 8 1/2" SECTION TO WELL TD @ +/- 2575 M, CIRCULATE HOLE CLEAN, POOH TO SURFACE. | ACCD407A530443079C6987C8E474FE37 | RIH 8 1/2" BHA FROM 97 M TO 2296 M. - TAG TOP OF CEMENT BY 5 TONS AT 2296 M. - PERFORMED SHALLOW TEST WITH FR: 1600 LPM, SPP: 250 PSI. - FILL UP STRING EVERY 15 STANDS. - METAL DISP: 7.5 M3, ACTUAL DISP.: 7.5 M3. | 18.61 |  | 2018-10-28 14:37:10.000 | 387 | [5 empty] | 2018-11-01 22:00:00.000 | 2018-10-10 02:00:00.000 | 177.1654 | 8300.5252 | 2018-10-28 09:00:00.000 | 1.5625 | 10.5938 | 18.2917 | 22.8333 | 6.8431 | 453.7873
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-372 Dir | 30.513 | 47.5951 | Mishrif | Deviated | Mishrif Deviated | 2018-11-07 22:00:00.000 | Primary Drilling | RMG 102 | DRILLED 8 1/2" HOLE TO 2530 M [WELL TD], CIRCULATED HOLE CLEAN, POOH TO 92 M. | POOH TO SURFACE, PERFORM WL LOGGING JOB, RIH 7" LINER AS PER TALLY. | ACCD407A530443079C6987C8E474FE37 | RIH 8 1/2" DIRECTIONAL BHA FROM 991 M TO 2296 M ( TOP OF FC). - FILLED UP EACH 15 STANDS. - WASHED DOWN LAST STAND, FR: 1500 LPM. - TAGGED WITH 5 TON. - NO DOWN HOLE LOSSES. NOTE: PERFORMED KICK DRILL WITH GOOD RESPONSE FROM RIG CREW (WELL SECURED IN 30 SEC). | 17.53 |  | 2018-12-24 12:38:52.000 | 387 | [5 empty] | 2018-12-27 20:00:00.000 | 2018-12-08 00:00:00.000 | 314.9606 | 8300.5252 | 2018-12-23 16:30:00.000 | 0.66667 | 8.5833 | 45.7708 | 49.9167 | 1.3356 | 181.3497
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-383 | 30.4803 | 47.6185 | Zubair | Vertical | Nahr Umr Vertical | 2018-09-10 13:30:00.000 | Primary Drilling | RMG 102 | RAN 13 3/8" CSG TO 1844 M, CIRCULATED HOLE CLEAN, PERFORMED 1ST CEMENT STAGE. | PERFORM 2ND CEMENT STAGE, WOWH, RIH WITH 12 1/4" BHA. | ACCD407A530443079C6987C8E474FE37 | RIH 12 1/4" BHA FROM 303 M TO 503 M. - PERFORMED MWD SHALLOW TEST AT 503 M, FR: 2000 LPM, SPP: 780-800 PSI., IN PROGRESS - NO DOWN HOLE LOSSES. | 17.63 |  | 2018-09-27 15:09:11.000 | 387 | [5 empty] | 2018-10-01 23:30:00.000 | 2018-09-10 13:30:00.000 | 173.8845 | 10078.7405 | 2018-09-27 01:30:00.000 | 2.3854 | 9.7292 | 16.5 | 21.4167 | 11.1381 | 610.8328
EH | EME | Iraq | ACCD407A530443079C6987C8E474FE37 | 711 | 77314 | ENI Iraq Zubair Drilling 2 x 1500 | IDS | Gulf | LSTK | ZB-392 Dir | 30.5593 | 47.5758 | Mishrif | Deviated | Mishrif Deviated | 2018-11-09 15:00:00.000 | Primary Drilling | RMG 102 | M/U 8.5" DIRECTIONAL BHA. RIH TO 500 M, SHALLOW TEST DM TOOLS. RIH AND TAGGED FC AT 2336 M. DRILLING 8 1/2" AT 2560 M | DRILL 8.5" HOLE TO TD. | ACCD407A530443079C6987C8E474FE37 | P/U. M/U 8 1/2" PD BHA AND RIH TO 101 M WITH PU ALL COMPONENTS FROM PIPE RACKS. - 8 1/2" USED PDC BIT MSi716LWPX(JN3503) + PD + GVR-6.2 + ARC-6 + TELESCOPE_8-3/8" S/STAB + SONIC VISION 675 + 8 1/4" STB + 6 3/4" PBL SUB + 3 JOINTS 5" HWDP + 6-1/2" D.JAR + 3 JOINTS 5" HWDP. | 18.15 |  | 2018-11-27 03:30:12.000 | 387 | [5 empty] | 2018-11-28 00:00:00.000 | 2018-11-09 15:00:00.000 | 0 | 8513.7798 | 2018-11-25 07:15:00.000 | 0 | 7.6667 | 15.6771 | 18.375 | 0 | 543.0717
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HWYH-1155 |  |  | Hawiyah (HWYH) | Deviated | K-2 | 2017-11-27 21:00:00.000 | Primary Drilling | AD-41 | DRILL AHEAD 5 7/8" DIRECTIONAL HOLE TO 15210 FT | DRILL AHEAD 5 7/8" DIRECTIONAL HOLE | 3B0D04B4CA504F1D85399BD86E4B8A1F | DIRECTIONAL DRILL 5 7/8" HOLE FROM 10498 FT TO 14808 FT (10' INTO NEW FORMATION) - 10-15 WOB , 200 GPM , 2000 -2300 PSI , 40 RPM , TRQ 4-5 KLB.FT | 69.74 | 62.25 | 2018-02-16 09:07:30.000 | 309.79 | 309.79 |  |  |  |  | 2018-02-16 09:00:00.000 | 2017-11-27 21:00:00.000 | 49 | 16417.0005 | 2018-01-31 23:00:00.000 | 2.4375 | 34.8125 | 65.0833 | 80.5 | 3.028 | 252.2458
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HWYH-1175 |  |  | Uthmaniya (UTMN) | Vertical | MK-1 | 2018-11-24 18:00:00.000 | Primary Drilling | AD-41 | CONTINUE DRILLING 5 7/8" SECTION TO TD +/- 15688 ft (125 ft INTO THE TAWIL FORMATION) CONFIRMED BY GOC. FROM 13555 FT TO 14250 FT. NO INDICATIONS OF STICKING OBSERVER IN KHUFF C. | CONTINUE DRILLING 5 7/8" SECTION TO TD +/- 15688 ft (125 ft INTO THE TAWIL FORMATION) CONFIRMED BY GOC. | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TDS. | 65.97 | 53.49 | 2019-01-29 04:24:00.000 | 317 | 291.75 |  |  |  |  | 2019-01-21 08:00:00.000 | 2018-11-24 17:00:00.000 | 49 | 15507.0005 | 2019-01-02 21:30:00.000 | 1.1042 | 21.4375 | 39.1458 | 57.5833 | 1.9175 | 396.1341
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HWYH-1176 | 24.8284 | 49.2507 | Hawiyah (HWYH) | S-Shape | K-2 | 2019-05-10 10:00:00.000 | Primary Drilling | AD-41 | CONTINUE RIH 5 7/8" PERFORMANCE BHA. WASHED DOWN AND TAGGED CEMENT AT 13905 FT, DRILLED OUT SHOE TRACK WHILE RELOGGING FOR GOC TO 14020 FT. PERFORMED POSITIVE CASING TEST - OK. DRILLED OUT THE SHOE TRACK CLEARED RATHOLE AND DRILLED 10 FT NEW FORMATION. PERFORMED FIT - OK. DRILLED AHEAD 5 7/8" SECTION TO 14365 FT. | CONTINUE DRILLING 5 7/8" SECTION TD +/- 15055 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CONTD PERFORMANCE DRILLING 5 7/8" HOLE SECTION FROM 14140 FT TO 14365 FT. - WOB: 15-20 KLBS, RPM: 60-90, Q: 200 GPM, P: 1700-1800 PSI, DIFF. PRESS.: 150-250 PSI, TQ: 10-11 KLBS.FT. - MW IN/OUT: 96 PCF. NO LOSS/GAIN. - FOLLOWED MUD BRIDGING PLAN AV ROP 21 FT/HR BIT/BHA HRS:-12.5 HWDP HRS:- 27.75 CCA ZERO PSI | 86.86 | 65.71 | 2019-08-05 01:41:28.000 | 213 | 216.47 |  |  |  |  | 2019-08-13 00:30:00.000 | 2019-05-10 10:00:00.000 | 49 | 15019.0005 | 2019-07-25 07:15:00.000 | 2.2083 | 46.0521 | 75.8854 | 94.6042 | 2.3343 | 197.9168
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HWYH-1180 |  |  | Hawiyah (HWYH) | S Shaped | K-2 | 2019-01-26 11:00:00.000 | Primary Drilling | AD-41 | CONTINUE DRILLING 5 7/8" SECTION FROM 14725 FT TO 14990 FT. MUD WT IN/OUT 92 PCF ADDING BRIDGING MATERIAL AS PER PROGRAM. | CONTINUE DRILLING 5 7/8" SECTION TD AT +/- 15271 FT (200 FT INTO TWIL) | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TDS | 76.02 | 52.26 | 2019-04-30 15:44:24.000 | 213 | 205.8 |  |  |  |  | 2019-04-30 13:00:00.000 | 2019-01-26 10:30:00.000 | 49 | 15335.0005 | 2019-04-13 11:30:00.000 | 5.6979 | 41.3854 | 77.0208 | 94.0833 | 6.0562 | 199.102
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2260 |  |  | Uthmaniya (UTMN) | Vertical | MK-1 | 2018-02-24 16:00:00.000 | Primary Drilling | AD-41 | CONTINUED DRILLING AHEAD 5 7/8" SECTION WITH ROTARY BHA. ENCOUNTERED SOME STICK SLIP AND HARD FORMATIONS, ADJUSTED PARAMETERS TO MAXIMIZE ROP. ROP DECREASED GRADUALLY UNTIL ALMOST NO PROGRESS AT 13874 FT, DISCUSS W/ TOWN, DECISION TO POOH, FLOW CHECK, POOH | CONTINUE POOH, CHANGE HWDP, MWD AND BIT, RUN BACK TO BOTTOM, CONTINUE DRILLING 5 7/8" HOLE. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL 5 7/8" HOLE WITH ROTARY BHA FROM 13723 FT TO 13805 FT WITH 105 PCF KCL MUD- NO LOSSES / GAINS - CONTINUE ADDING BRIDGING MATERIALS IN THE MUD - WOB- 22 KLBS, RPM- 120-130, TRQ- 4.5-6 KFTLBS, GPM- 200 PRESSURE- 1600-1700 PSI, B/O TQ 4-6 KFTLB. - ROP =13.7FT/HR - TOP KHUFF D1 @ 13288 FT MD - TOP KHUFF D2 @ 13386 FT MD - TOP KHUFF D3 @ 13486 FT MD - TOP KHUFF D4 @ 13565 FT MD - TOP KHUFF D5 @ 13677 FT MD - TOP KHUFF D6 @ 13737 FT MD | 60.44 | 48.54 | 2018-04-18 19:19:12.000 | 292.1 | 292.1 |  |  |  |  | 2018-04-18 21:00:00.000 | 2018-02-24 16:00:00.000 | 49 | 14464.0005 | 2018-03-31 03:45:00.000 | 6.9688 | 20.5833 | 34.4896 | 53.2083 | 13.0971 | 419.373
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2275 |  |  | Uthmaniya (UTMN) | S-Shape | K-2 | 2018-04-24 09:30:00.000 | Primary Drilling | AD-41 | CONT. DRILLING 5 7/8" HOLE SECTION FROM 14169 FT TO 14279 FT. LOST MWD SIGNAL AND NOT ABLE TO RECOVER (DECIDED TO POOH). PERFORMED FLOW CHECK. POOH 5 7/8" BHA TO SURFACE. REPLACED MWD AND BIT. RIH 5 7/8" DRILLING BHA #2 TO 100 FT. | CONT. RIH TO BOTTOM. CONT. DRILLING 5 7/8" HOLE SECTION TO WELL TD @ 14997 FT MD (-/+ 125 FT INTO TAWIL FORMATION). | 3B0D04B4CA504F1D85399BD86E4B8A1F | DNM NPT P/U OFF BOTTOM 60 FT. TROUBLESHOOTED LOST MWD SIGNAL BY ANTI-JAMMING PROCEDURE BY INCREASING FLOW RATE IN STAGES 50-100-150-200-250-280 GPM. NO SUCCESS. DECIDED TO POOH FOR MWD CHANGE. | 73.74 | 55.44 | 2018-07-25 06:43:12.000 | 236.13 | 236.13 | 20180622084100 |  |  |  | 2018-07-25 09:00:00.000 | 2018-04-24 09:30:00.000 | 49 | 14960.0005 | 2018-06-23 08:15:00.000 | 21.0312 | 35.1771 | 59.9479 | 91.9792 | 22.8652 | 249.55
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3038 |  |  | Uthmaniya (UTMN) | Horizontal | K-2 | 2018-08-02 22:30:00.000 | Primary Drilling | AD-41 | WASHED DOWN & TAGGED TOC @ 12635 FT. CONT. D/O SHOE TRACK UP TO 12779 FT (-/+ 25 FT ABOVE SHOE) WHILE DISPLACING WELL TO NEW 73 PCF OBM. PERFORMED CASING PRESSURE TEST WITH 3100 PSI SURFACE PRESSURE. OK. CONT. D/O SHOE TRACK AND 10 FT FRESH FORMATION TO 12810 FT. CIRCULATED & PERFORMED FIT TO 110 PCF EMW WITH 3074 PSI SURFACE PRESSURE. DRILLED 5 7/8" HOLE SECTION FROM 12810 FT TO 13225 FT. | DRILL 5 7/8" HOLE SECTION TO WELL TD @ 17140 FT MD / 12147 FT TVD. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5 7/8" HOLE SECTION FROM 12800 FT TO 12810 FT FOR FIT. - WOB: 10 KLBS, SURFACE / MOTOR RPM: 30/97, Q: 210 GPM, P: 2150 PSI, DIFF. PRESS.: 250 PSI, TQ: 4.0-5.0 KLBS.FT. | 79.91 | 60.84 | 2018-10-21 02:43:26.000 | 260.65 | 260.65 |  |  |  |  | 2018-11-14 20:00:00.000 | 2018-08-02 22:30:00.000 | 49 | 17255.0006 | 2018-10-25 00:00:00.000 | 22.5833 | 50.2292 | 83.0625 | 103.8958 | 21.7365 | 207.7351
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3090 | 25.0802 | 49.4173 | Uthmaniya (UTMN) | Vertical | K-2 | 2019-08-24 12:30:00.000 | Primary Drilling | AD-41 | CONTINUE TO RIH WITH 8 3/8" BHA, DRILL OUT AND PRESSURE TEST DV. CONTINUE RIH AND DRILL OUT SHOE TRACK TO 30 FT INSIDE THE SHOE, PRESSURE TEST CASING - OK. DRILLOUT SHOE; DISPLACE TO 100 PCF MUD, THEN DRILL 10 FT NEW FORMATION TO 12811 FT, PERFORM FIT. DRILL AHEAD 8 3/8" SECTION FROM 12811 FT TO 13020 FT WITH 100 PCF MUD TREATED WITH BRIDGING MATERIAL | CONTINUE PERFORMANCE DRILLING 8 3/8" SECTION TO SECTION TD =/- 14061 FT ( 450 FT INSIDE THE KFDA) CONTINUE TO ADD BRIDGING MATERIAL AS PER PLAN | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL 10 FT NEW 8 3/8" HOLE FROM 12801 FT TO 12811 FT WITH 100 PCF KCL MUD WOB- 10-15 KLBS, RPM- 40 TRQ- 10-12 KLBS, GPM- 500 PR- 3050 PSI DIFF PR- 150 - 200 PSI | 67.51 | 48.89 | 2019-11-08 05:26:24.000 | 228.5829 | [5 empty] | 2019-10-21 17:30:00.000 | 2019-08-24 12:30:00.000 | 49 | 14201.0005 | 2019-10-18 04:30:00.000 | 0.083333 | 26.6354 | 54.6667 | 58.2083 | 0.14316 | 259.7744
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | SDGM-1094 | 25.61 | 49.4 | Shedgum | Vertical | MK-2 | 2018-03-16 22:00:00.000 | Primary Drilling | AD-42 | MOTOR DRILLED 5-7/8" SECTION FROM 13,600' TO 14,320'. | MOTOR PERFORMANCE DRILL 5-7/8" SECTION TO +/-14,964' (+/-200' INTO TAWIL FM). | 3B0D04B4CA504F1D85399BD86E4B8A1F | TDS RIG SERVICE | 73.91 | 59.81 | 2018-05-25 03:58:48.000 | 262.94 | 262.94 |  |  |  |  | 2018-05-25 00:15:00.000 | 2018-03-16 22:00:00.000 | 49 | 14843.0005 | 2018-05-11 02:45:00.000 | 4.1667 | 37.0625 | 55.1979 | 69.0938 | 6.0305 | 268.9051
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | SDGM-1112 | 25.644 | 49.345 | Shedgum | Vertical | MK-2 | 2018-06-02 07:00:00.000 | Primary Drilling | AD-42 | DISPLACE HOLE TO 82 PCF OBM. PERFORMANCE DRILL 5-7/8" VERTICAL SECTION FROM 12,505' TO 13,450'. | PERFORMANCE DRILL 5-7/8" VERTICAL SECTION TO +/-14,144' (WELL TD, +/-200' INTO TAWIL FM). | 3B0D04B4CA504F1D85399BD86E4B8A1F | MOTOR DRILLED 5-7/8" SECTION FROM 12,505' TO 12,535' W/ CONTROLLED PARAMETERS. - WOB: 10-15 KLBS, FR: 248 GPM, SRPM: 58, BIT RPM: 259, TQ: 5-7 KLB.FT, SPP: 2,000-3,500 PSI, DIFF: 150-200 PSI. - AVG. ROP: 8.5 FT/HR * DISPLACED HOLE TO 82 PCF VERSADRIL OBM (20 BBL WATER, 30 BBL DIESEL FOLLOWED BY OBM) WHILE DRILLING W/ REDUCED PARAMETERS. | 59.26 | 85.87 | 2018-07-28 21:25:34.000 | 262.94 | 262.94 |  |  |  |  | 2018-07-28 23:00:00.000 | 2018-06-02 07:00:00.000 | 49 | 14146.0005 | 2018-07-17 09:15:00.000 | 1.1458 | 23.8542 | 45.0938 | 56.6667 | 2.0221 | 313.702
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2072 | 25.1735 | 49.3714 | Uthmaniya (UTMN) | S-Shape | K-2 | 2018-01-01 11:15:00.000 | Primary Drilling | AD-42 | CONT. RIH W/ 5-7/8" ROTARY BHA. D/O SHOE TRACK UP TO 30 FT ABOVE FS. PERFORM CSG P/T, OK. D/O REMAINING SHOE TRACK & 10 FT NEW FORMATION. PERFORM FIT (110 PCF EMW), OK. DRILL 5-7/8" SECTION F/ 14,255 TO 14,610 FT. | CONT. DRILL 5-7/8" SECTION TO TD (+/- 15,178 FT). CHC. POOH TO SURFACE. RUN WL LOGGING. | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMED FIT TO 110 PCF EMW BY APPLYING 1,170 PSI ON SURFACE FOR 15 MIN, OK. - MW IN/OUT: 97 PCF. - FLUSHED KILL LINE, BOP, CHOKE MANIFOLD & POOR BOY W/ WATER. - COMPLETED IDS-WC-CL-001 BEFORE FIT. | 65.63 | 53.04 | 2018-03-07 07:09:36.000 | 236.13 | 236.13 |  |  |  |  | 2018-03-07 08:00:00.000 | 2018-01-01 11:15:00.000 | 49 | 15085.0005 | 2018-02-24 06:15:00.000 | 1.9167 | 31.625 | 53.7917 | 64.8646 | 2.9549 | 280.4338
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2090 | 25.5318 | 49.3957 | Uthmaniya (UTMN) | Horizontal | K-2 | 2019-01-28 08:00:00.000 | Primary Drilling | AD-42 | RIH 5-7/8" VORTEX BHA FROM 7,900' TO 13,560'. D/O SHOE TRACK & 10' FM TO 13,706' WHILE DISPLACED TO 78 PCF OBM. PERFORM FIT. DIRECTIONAL DRILLED 5-7/8" SECTION W/ VORTEX BHA TO 14,200' | DIRECTIONAL DRILL 5-7/8" HOLE TO +/- 18,146' (WELL TD) | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED W/ 5-7/8" RSS+MOTOR BHA FROM 13,694' TO 13,706' W/ CONTROLLED PARAMETERS. - WOB: 18 KLB, FR: 250 GPM, SP: 2800 PSI, RPM: 40, TQ: 4 KLB.FT - AVERAGE ROP: 12 FT/HR. | 74.4 | 60.43 | 2019-04-11 01:23:12.000 | 213 | 237.53 |  |  |  |  | 2019-04-12 00:00:00.000 | 2019-01-28 07:00:00.000 | 50 | 18089.0006 | 2019-03-28 22:45:00.000 | 6.7396 | 35.3125 | 59.6146 | 73.6667 | 9.1488 | 303.4325
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2094 | 25.001 | 49.35 | Uthmaniya (UTMN) | Horizontal | K2K-SL | 2019-10-17 21:00:00.000 | Primary Drilling | AD-42 | PERFORMANCE DRILLED 28" SECTION FROM 660' TO 1,885' | PERFORMANCE DRILL 28" SECTION TO +/-2,699' (+/-50' INTO AHMADI FM) | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMANCE DRILLED 28" HOLE SECTION FROM 588' TO 660'. (100% CIRC) - WOB: 20-40 KLB, SRPM 20-40, BRPM: 108-128, TORQUE: 5.-11.0 KLB-FT, FR: 800 GPM, SPP: 1050-1350 PSI. DIFF: 200- 400 PSI - OBSERVED LOW TO MEDIUM SHOCKS & VIBRATIONS. - AVG. ROP= 96 FT/HR. JAR, 3 STRR & BIT: 0.45 HRS. KRevs: 4.5 DC's, / MOTOR / SHOCK SUB: 24.25 HRS | 74.37 | 61.56 | 2019-12-30 13:51:39.000 | [6 empty] | 2019-10-22 06:00:00.000 | 2019-10-17 21:00:00.000 | 50 | 2550.0001 | 2019-10-22 05:00:00.000 | 0 | 1.7708 | 4.3333 | 4.375 | 0 | 588.4616
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3010 | 25.041 | 49.344 | Uthmaniya (UTMN) | Vertical | K-2 | 2019-04-23 21:00:00.000 | Primary Drilling | AD-42 | CONT. DRILLING 5-7/8" WITH PERFORMANCE BHA F/ 13,444 FT TO 13,755 FT, WELL TD. CHC, FLOW CHECK. WIPER TRIP TO 7" CSG SHOE & RUN BACK TO BTM, CHC. | FLOW CHECK. POOH 5-7/8" PERFORMANCE BHA TO SURFACE, L/D BHA. R/U & RIH LOGGING TOOLS. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CONT. DRILLING 5-7/8" SECTION WITH PERFORMANCE BHA FROM 13727 FT TO 13755 FT (WELL TD). - FR: 250 GPM, SPP: 2350-2550 PSI, DIFF PR: 50-200 PSI, RPM: 60-100, WOB: 15-22 KLB, TRQ: 2.5-4 KLB-FT. - AVG ROP: 7 FT/HR. - TOP OF TWLF CONFIRMED BY GOC @ 13,638 FT (TVD)/13,639 FT (MD) & DECIDED TO DRILL 115 FT INSIDE TWLF. | 66.42 | 46.84 | 2019-06-30 17:30:00.000 | 213 | 192 |  |  |  |  | 2019-06-28 20:00:00.000 | 2019-04-23 21:00:00.000 | 0 | 13795.0004 | 2019-06-21 22:45:00.000 | 2.2188 | 37.6354 | 59.0729 | 65.9583 | 3.3639 | 233.525
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3013 | 25.256 | 49.353 | Uthmaniya (UTMN) | Vertical | K-2 | 2018-10-20 22:00:00.000 | Primary Drilling | AD-42 | CONT'D POOH WITH C/O BHA, L/D SAME. P/U, M/U & RIH WITH 5-7/8" PERFORMANCE BHA. RE-LOG AS PER ARAMCO GOC. DRILL 5-7/8" SECTION TO 13000 FT. | DRILL WITH 5-7/8" PERFORMANCE BHA TO SECTION TO TD +/- 13649 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | RIH WITH 5-7/8" PERFORMANCE BHA ON 4" DP FROM 2000' TO 2876' - MONITOR WELL USING TRIP TANK & TRIP SHEET. * COMPLETED IDS-E&T-CL-001 * COMPLETED IDS-DRL-CL-002 * COMPLETED IDS-HCT-CL-002 | 73.44 | 53.13 | 2019-01-13 20:18:00.000 | 213 | 230.82 |  |  |  |  | 2019-01-14 01:15:00.000 | 2018-10-20 20:30:00.000 | 49 | 13715.0004 | 2018-12-30 10:00:00.000 | 23.4271 | 50.9688 | 70.5 | 85.1354 | 27.5174 | 194.539
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3036 | 25.4 | 49.25 | Uthmaniya (UTMN) | Horizontal | MK-1 | 2018-08-06 23:00:00.000 | Primary Drilling | AD-42 | DIRECTIONAL DRILLED 5-7/8" SECTION FROM 13,040' TO 13,538' MD (12,239' TVD). BHA NOT ABLE TO FOLLOW DIRECTIONAL PLAN.. CHC. POOH 5-7/8" VORTEX BHA TO 13,388'. STRING STUCK. WORK ON STRING STUCK TILL GOT FREE. CLEAR TIGHT SPOT & POOH 5-7/8" BHA W/ HARD BACKREAMING F/ 13,400' TO 13,345' | POOH & L/D 5-7/8" VORTEX BHA TO SURFACE. P/U, M/U & RIH 5-7/8" DIRECTIONAL BHA TO 13,538' W/ STAGING PROCEDURE. DIRECTIONAL DRILL 5-7/8" SECTION TO +/- 17,305' (AS PER DIRECTIONAL PLAN). | 3B0D04B4CA504F1D85399BD86E4B8A1F | CIRCULATE HOLE CLEAN. FR: 220 GPM, SPP: 2,300 PSI. | 61.41 | 53.45 | 2018-10-12 11:09:00.000 | 327.4 | 327.4 |  |  |  |  | 2018-10-12 12:00:00.000 | 2018-08-06 23:00:00.000 | 49 | 17234.0006 | 2018-09-24 06:45:00.000 | 7.8958 | 29.6667 | 48.3229 | 66.5417 | 11.866 | 356.6424
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3042 | 25.041 | 49.35 | Uthmaniya (UTMN) | Horizontal | K-2 | 2019-07-06 10:30:00.000 | Primary Drilling | AD-42 | DRILL 10 FT NEW FORMATION WITH 5-7/8" VORTEX BHA, CHC & PERFORM FIT. DIRECTIONAL DRILL 5-7/8" HOLE FROM 13,408' TO 13,649'. LOST MWD SIGNAL, TROUBLE SHOOT MWD WITH NO SUCCESS. POOH TO CHANGE MWD TOOL TO 3200'. | CONT. POOH TO SURFACE, L/D DIRECTIONAL BHA, P/U NEW NHA. RIH WITH 5-7/8" DIRECTIONAL BHA, DRILL 5-7/8" DIRECTIONAL HOLE TO TD (+/- 18,152') | 3B0D04B4CA504F1D85399BD86E4B8A1F | FLOW CHECK, @ 7" CSG SHOE, WELL STATIC. | 74.37 | 59.4 | 2019-10-11 17:00:00.000 | [6 empty] | 2019-10-11 21:00:00.000 | 2019-07-06 10:30:00.000 | 50 | 18025.0006 | 2019-09-06 23:30:00.000 | 9.8438 | 32.6771 | 62.5417 | 97.4375 | 10.1026 | 288.2079
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1270 | 24.05 | 49.07 | Haradh (HRDH) | Horizontal | K-2 | 2018-05-27 11:30:00.000 | Primary Drilling | AD-43 | RIH 5 7/8" DIRECTIONAL BHA (M/U 4" DP) FROM 4,550' TO 12,377' (TOC). D/O SHOETRACK TO 12,531' (30' ABOVE 7" SHOE). P/T 7" LINER (EMW 110 PCF). D/O SHOE + 10' NEW FORMATION TO 12,576' (DISPLACING TO 95 PCF OBM). CIRCULATED. PERFORMED FIT (EMW 110 PCF). DRILL WITH 5 7/8" DIRECTIONAL BHA TO 12,700'. | DRILL WITH 5 7/8" DIRECTIONAL BHA TO +/- 17,371 MD / 12,139 TVD (KC10). | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMED FIT WITH 95 PCF MUD + 1237 PSI (EMW= 110 PCF), OK. VOL PUMPED AND RETURNED= 4.0 BBL. | 80.35 | 56 | 2018-08-15 13:27:36.000 | 248.81 | 248.81 |  |  |  |  | 2018-08-06 15:00:00.000 | 2018-05-27 11:30:00.000 | 49 | 17521.0006 | 2018-07-17 18:30:00.000 | 2.3125 | 27.6875 | 51.2917 | 71.1458 | 3.2504 | 341.5955
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1292 | 24.9268 | 49.0392 | Haradh (HRDH) | S-Shape | K-2 | 2017-10-20 13:30:00.000 | Primary Drilling | AD-43 | D/O CMT FROM 13,257' TO 13,273' (20' ABOVE 7" SHOE). P/T 7" LINER. D/O CMT + 7" SHOE (13,293') + RATHOLE TO 13,296'. DRILLED 10' NEW FORMATION TO 13,306'. CIRCULATED. PERFORMED FIT. DRILLED 5 7/8" SECTION WITH ROTARY BHA TO 13,517'. | DRILL 5 7/8" SECTION WITH ROTARY BHA TO +/- 13,763' (150' INTO BASE UNAYZAH FORMATION). CIRCULATE. POOH TO 13,293' (7" SHOE). RIH TO BOTTOM. CIRCULATE. POOH TO SURFACE. R/U WL UNIT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CIRCULATED (CONFIRMED MW IN/OUT= 105 PCF). POOH BIT ABOVE 7" SHOE. * FR= 200 GPM, SPP= 1850 PSI, TDS= 40 RPM, TQ= 11.5 KLB-FT. * COMPLETED CHECKLIST: IDS-WC-CL-001 Before the FIT or LOT. | 63.01 | 48.47 | 2018-01-04 19:14:24.000 | 245.25 | 245.25 |  |  |  |  | 2018-01-05 00:30:00.000 | 2017-10-20 13:30:00.000 | 49 | 13797.0004 | 2017-12-20 20:30:00.000 | 5.8542 | 37.0312 | 61.2917 | 76.4583 | 7.6567 | 225.104
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1366 | 24.4709 | 49.0719 | Haradh (HRDH) | Horizontal | MK1K-SL | 2019-09-24 16:00:00.000 | Primary Drilling | AD-43 | WIPER TRIP, POOH & L/D 8 3/8" DIRECTIONAL BHA. R/U WIRELINE AND PERFORMED WIRELINE LOGGING TOOL #1 ON OH (ON GOING ON RPT). | CONT. PERFORM WIRELINE LOGGING TOOL #1 ON OH AND CH. POOH. P/T ANNULAR WITH 7" JT, R/U CSG RUNNING TOOLS. RIH 7" LINER. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CIRCULATED 1.5 x ANNULAR VOLUME AND HOLE CLEAN.- * FR= 540 GPM, SPP= 3600 PSI, TDS= 80 (DOWN) / 40 (UP) RPM, TQ= 3.5 KLB-FT, MW IN/OUT= 110 PCF. * NO GAIN / LOSS. * MEANWHILE: - RECORDED SCR. - TOOK SURVEY AND DOWNLINK D&M TOOL TO SET ON TRIP MODE. | 69.56 | 47.56 | 2019-11-26 11:01:48.000 | [6 empty] | 2019-10-22 01:30:00.000 | 2019-09-24 16:00:00.000 | 49 | 12215.0004 | 2019-10-21 00:30:00.000 | 0.54167 | 17.9167 | 26.3542 | 27.3958 | 1.9772 | 463.4941
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1367 |  |  | Haradh (HRDH) | Horizontal | K-2 | 2019-03-18 08:00:00.000 | Primary Drilling | AD-43 | CONT. DISPLACING HOLE TO 78 PCF OBM, P/T 7" LINER (EMW 110 PCF). CONT. D/O SHOE + 10' NEW FORMATION TO 13,550' . CIRCULATE. PERFORM FIT (EMW 110 PCF). DRILL WITH 5 7/8" DIRECTIONAL BHA TO 14,035 FT (ON GOING AT RPT) | DRILL WITH 5 7/8" DIRECTIONAL BHA TO +/- 20,840 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CIRCULATED AND CONFIRMED MW IN/OUT= 78 PCF. * COMPLETED CL: FORMATION PRESSURE TEST READINESS. | 97.8 | 68.31 | 2019-06-14 07:19:12.000 | 317 | 203.46 |  |  |  |  | 2019-06-14 04:15:00.000 | 2019-03-18 08:00:00.000 | 49 | 20646.0007 | 2019-05-24 20:45:00.000 | 4.25 | 33.9167 | 67.5312 | 87.8438 | 4.8381 | 305.7251
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1371 |  |  | Haradh (HRDH) | Horizontal | MK-1 | 2019-06-21 12:00:00.000 | Primary Drilling | AD-43 | DRILL WITH 5 7/8" DIRECTIONAL BHA TO 13,665 FT. | DRILL WITH 5 7/8" DIRECTIONAL BHA TO +/- 18,395 FT.(KHUFF-C LAYER 9). CIRCULATE POOH TO SURFACE. WIRELINE LOGS. | 3B0D04B4CA504F1D85399BD86E4B8A1F | REAMED FULL STD. REPEATED SURVEY. PERFORMED IDS CONNECTION PRACTICE. | 72.53 | 57.59 | 2019-09-18 09:12:36.000 | 317 | 283.31 |  |  |  |  | 2019-09-19 09:00:00.000 | 2019-06-21 12:00:00.000 | 49 | 17667.0006 | 2019-08-30 03:15:00.000 | 13.4479 | 43.9688 | 69.6354 | 89.875 | 14.9629 | 253.7071
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1830 |  |  | Haradh (HRDH) | Horizontal | MK-1 | 2018-08-14 15:30:00.000 | Primary Drilling | AD-43 | P/T 7" LINER (EMW 110 PCF). D/O SHOE + 10' NEW FORMATION TO 13033' . CIRCULATE. PERFORM FIT (EMW 110 PCF). DRILL 5 7/8" SECTION TO 13220 FT. GOT STUCK ON AT 13184 FT, WORK ON STUCK TILL RELEASE. POOH TO CHECK BHA (8500 FT AT RPT) | CONT. POOH WITH 5 7/8" BHA, L/D SAME AND INSPECT, RIH WITH NEW BHA, DRILL WITH 5 7/8" DIRECTIONAL BHA TO +/- 18023 MD. | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMED FIT WITH 72 PCF MUD + 3256 PSI (EMW= 110 PCF), TEST OK. * VOL PUMPED AND RETURNED= 15 BBL. | 65.55 | 52.79 | 2018-10-07 00:14:35.000 | 325.02 | 325.02 |  |  |  |  | 2018-10-07 22:00:00.000 | 2018-08-14 15:30:00.000 | 49 | 17175.0005 | 2018-09-21 13:45:00.000 | 3.9688 | 23.4062 | 37.9271 | 54.2708 | 7.3129 | 452.8426
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1846 |  |  | Haradh (HRDH) | Vertical | MK-1 | 2018-01-13 17:00:00.000 | Primary Drilling | AD-43 | CIRC. CONDUCTED FIT (120 PCF EMW). DISPLACED HOLE TO 97 PCF K FORMAT MUD. DRILLED AHEAD 5 7/8" SECTION F/14103 FT TO 14460 FT. | DRILL AHEAD 5 7/8" SECTION TO SECTION TD. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DISPLACED HOLE TO 97 PCF K-FORMAT MUD. - PUMPED HIVIS & WATER AS SPACER. | 50.27 | 42.95 | 2018-03-11 19:45:00.000 | 326.13 | 326.13 |  |  |  |  | 2018-03-12 07:00:00.000 | 2018-01-13 17:00:00.000 | 49 | 14940.0005 | 2018-02-27 23:00:00.000 | 0.85417 | 26.7708 | 45.25 | 57.5833 | 1.4834 | 330.1658
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1870 |  |  | Haradh (HRDH) | Vertical | K-2 | 2018-03-21 01:30:00.000 | Primary Drilling | AD-43 | CIRCULATED TO CONFIRM MW IN/OUT= 96 PCF. PERFORMED FIT (EMW 120 PCF, OK). DRILLED WITH 5 7/8” DIRECTIONAL BHA FROM 13,610’ TO 13,830’ (SLIDED 13,735-13,755’). | DRILL WITH 5 7/8" DIRECTIONAL BHA TO +/- 14,014' MD (+/- 150' INTO PUZU/QUSAIBA MEMBER). CIRCULATE. POOH TO SURFACE (WIPER TRIP ONLY IF NECESSARY). RETRIEVE WEARBUSHING. P/T BOP + THS. INSTALL WEARBUSHING. R/U WL UNIT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED FROM 13,600 FT TO 13,610 FT (10 FT OF NEW FORMATION).- * FR= 192 GPM, WOB= 10 KLB, SRPM= 40, DHM= 113 RPM, TQ= 3.5-4.5 KLB-FT. | 71.09 | 52.58 | 2018-05-21 06:43:36.000 | 260.34 | 260.34 |  |  |  |  | 2018-05-21 00:15:00.000 | 2018-03-21 01:30:00.000 | 49 | 13927.0004 | 2018-05-09 13:00:00.000 | 6.6458 | 30.5417 | 49.4792 | 60.9479 | 10.9041 | 281.472
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2106 |  |  | Haradh (HRDH) | Vertical | MK-1 | 2018-10-12 12:00:00.000 | Primary Drilling | AD-43 | DRILLED TO 14,159' (10' NEW FORMATION). PERFORM FIT (EMW= 120 PCF): FIT OK. DRILL WITH 5 7/8" PERFORMANCE BHA TO 14,462'. | DRILL WITH 5 7/8" PERFORMANCE BHA TO +/- 14,941' (+/- 150' INTO QUSAIBA MEMBER). | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED FROM 14,149 FT TO 14,159 FT (10 FT OF NEW FORMATION). * WOB= 8 KLB, FR= 200 GPM, SPP= 2050 PSI, DHM= 130 RPM, TDS= 40 RPM, TQ= 7 - 8 KLB-FT | 140.05 | 101.82 | 2019-03-09 15:30:00.000 | 317 | 245.68 |  |  |  |  | 2019-03-09 17:00:00.000 | 2018-10-12 12:00:00.000 | 49 | 14926.0005 | 2019-02-24 12:00:00.000 | 79.3854 | 104.2396 | 135 | 148.2083 | 53.5634 | 110.563
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1369 | 24.4021 | 49.1187 | Haradh (HRDH) | Horizontal | MK-1 | 2019-10-12 22:30:00.000 | Primary Drilling | AD-46 | DRILLED 5-7/8" HOLE F/ 12277 FT TO 12960 FT. | DRILL 5-7/8" HOLE AS PER DIRECTIONAL PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5-7/8" HOLE F/ 12277 FT TO 12320 FT. - WOB: 5-20 KLBS, FR: 200 - 250 GPM, SPP: 2200 - 2850 PSI, DIFF: 200-250 PSI, SURF RPM: 30 - 50, TRQ: 3 - 4 KFTLBS. - AVG ROP: 15.6 FT/HR. - BEFORE CONNECTION, BACK REAM & REAM COMPLETE STAND. - TOOK SURVEY BEFORE CONNECTION 30 FT OFF BOTTOM. - DOWN LINKED AS PER D & M PROCEDURE. - ADDED BRIDGING MATERIAL IN ACTIVE SYSTEM AS PER PLAN. | 64.46 | 50.59 | 2019-10-06 02:58:48.000 | [6 empty] | 2019-10-06 00:30:00.000 | 2019-08-03 14:00:00.000 | 48 | 16930.0005 | 2019-09-20 12:00:00.000 | 8.9583 | 28.9688 | -22.4375 | -6.9167 | -129.5181 | -754.5404
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1383 | 24.402 |  | Haradh (HRDH) | Horizontal | MK1K-SL | 2019-10-12 22:30:00.000 | Primary Drilling | AD-46 | DRILL 16" HOLE F/ 2670 FT TO 3718 FT. | DRILL 16" HOLE TO 4899 FT (+/- 50 INTO MID THAMAMA LIMESTONE) AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 16" HOLE F/ 2670 FT TO 2710 FT. - WOB: 20 - 45, SURF RPM: 100 - 120, TRQ: 4 - 8 KFTLBS, FR: 1000 - 1100 GPM, SPP: 1400 - 1750 PSI. - AVG ROP: 12.3 FT/HR. - ADDED 10 SKS/HR MICA MED, 10 SKS/HR NUT PLUG TO PREVENT LOSSES - FOLLOWED IDS CONNECTION PRACTICE. | 68.61 | 53.73 | 2019-12-21 11:00:00.000 | 300 | 300 |  |  |  |  | 2019-10-22 05:00:00.000 | 2019-10-12 22:30:00.000 | 49 | 3788.0001 | 2019-10-22 05:00:00.000 | 0.09375 | 4.6563 | 9.2708 | 9.2708 | 1.0112 | 408.5933
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2062 | 25.0545 | 49.1738 | Uthmaniya (UTMN) | Horizontal | MK-1 | 2018-02-20 20:00:00.000 | Primary Drilling | AD-46 | RE LOGGED F/ 12070 FT TO 12099 FT. DRILLED OUT CEMENT & SHOE TRACK TO 12226 FT. DRILLED OUT RAT HOLE & 10 FT TO NEW FORMATION TO 12253 FT. CIRC. PERFORMED FIT TO 120 EMW - OK. DRILLED 5-7/8" DIR. HOLE F/ 12253 FT TO 12745 FT. | DRILL 5-7/8” DIR. HOLE AS PER DIRECTIONAL PLAN TO +/- 13452 /12592 FT MD/TVD. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED RAT HOLE + 10 FT OF NEW FORMATION F/ 12226 FT TO 12253 FT. - WOB: 5-8, FR: 229 - 250 GPM, SPP: 2200 - 2600 PSI, SURF. RPM: 40, TRQ: 3.5-4 KLB.FT, DIFF PRESS: 100-200 PSI. | 51.59 | 37.1 | 2018-05-29 17:50:24.000 | 309.28 | 309.28 |  |  |  |  | 2018-05-29 08:30:00.000 | 2018-02-20 20:00:00.000 | 48 | 13535.0004 | 2018-04-30 05:00:00.000 | 51.6667 | 53.4375 | 68.375 | 97.5208 | 52.9801 | 197.9525
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2267 | 24.97 | 49.25 | Uthmaniya (UTMN) | Vertical | K-2 | 2018-01-02 20:00:00.000 | Primary Drilling | AD-46 | PERFORMED 30" CSG CMT JOB, POOH W/ STINGER, WOC, CUT 30" CSG, P/U, M/U & RIH W/ 28" PERFORMANCE DRLG BHA TO TOC @ 508 FT, DRLD OUT CMT, F.S @ 612 FT & CMT TO 614 FT, OBSERVED COMPLETE LOSS, WASH DOWN TO 681 FT, PERFORMANCE DRLG 28" HOLE SECTION TO 1095 FT. | CONT PERFORMANCE DRLG 28" HOLE SECTION TO 24" CSG PT @ +/- 2383 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | BLIND PERFORMANCE DRLG 28" HOLE SECTION F/ 681 FT TO 777 FT WITH MUD MIX ON FLY. - DRLG PARAMETERS: WOB: 5-40 KLB, FR: 750-1000 GPM, SPP: 750-1350 PSI, RPM: 25-50, TRQ: 5-10 KLB.FT, DIFF PRESS: 100-250 PSI. - WASH UP & REAM DOWN EVERY STD BEFORE CONNECTION. - PUMP HVP EVERY 30 FT DRLD & SPOT HVP BEFORE CONNECTION. - FILLED ANNULUS WITH MUD @60 BPH - AVG ROP: 48 FT/HR. | 56.28 | 45.01 | 2018-03-31 21:54:36.000 | [6 empty] | 2018-02-13 09:00:00.000 | 2018-01-02 20:00:00.000 | 49 | 2348.0001 | 2018-01-27 14:00:00.000 | 41.5417 | 22.6042 | 24.75 | 41.5417 | 100 | 94.8687
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2274 | 24.9577 | 49.3389 | Uthmaniya (UTMN) | S-Shape | K-2 | 2019-04-01 09:30:00.000 | Primary Drilling | AD-46 | DRILLED COMPLETE RAT HOLE & NEW FORMATION TO 14335 FT. CIRC. PERFORMED FIT WITH 100 PCF MUD TO 110 PCF EMW. DRILLED 5-7/8" HOLE F/ 14335 FT TO 14826 FT. | DRILL 5-7/8" HOLE TO ± 14,999 FT TVD / 15262 FT MD (200 FT INTO TAWIL) AS PER PLAN. CIRC. POOH 5-7/8" PERF. BHA TO SURFACE. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5 7/8 HOLE SECTION FROM 14325 FT TO 14335 FT WITH BELOW PARAMETER - WOB - 10 -15 K LB, FLOW RATE - 240 GPM, SPP - 2300 PSI, DIFF PRESSURE - 200 PSI, RPM - 50, TORQUE - 8 - 9 K LB-FT. | 71.37 | 48.23 | 2019-07-25 22:43:48.000 | 213 | 216.4 |  |  |  |  | 2019-07-25 14:00:00.000 | 2019-04-01 09:30:00.000 | 49 | 15157.0005 | 2019-07-04 03:45:00.000 | 37.6667 | 63.5729 | 93.7604 | 115.1875 | 32.7003 | 161.6567
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2285 | 24.97 | 49.25 | Uthmaniya (UTMN) | Vertical | K-2 | 2018-06-05 13:15:00.000 | Primary Drilling | AD-46 | - PERFORMANCE DRILLED 5 7/8" VERTICAL HOLE TO TD 13922', SECTION TD, CHC, FLOW CHECK, OK, POH, HAD 3 TIGHT SPOT DEPTHS, BACK REAMED OK, POH TO 7" LINER CSG SHOE, FLOW CHECK, POH TO SURFACE, L/D BHA. | - FLOW CHECK AT TOP OF BHA, CONT. POH, L/D BHA, R/UP SLB WL LOGGING TOOLS AND RIH. | 3B0D04B4CA504F1D85399BD86E4B8A1F | PJSM PRIOR TO PULL OUT OF HOLE. | 64.24 | 47.78 | 2018-08-08 15:42:20.000 | 252.45 | 252.45 |  |  |  |  | 2018-08-08 15:30:00.000 | 2018-06-05 13:15:00.000 | 49 | 13922.0004 | 2018-07-24 16:30:00.000 | 5.6875 | 28.2083 | 49.1354 | 64.0938 | 8.8737 | 283.3394
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3014 | 25.0534 | 49.2213 | Uthmaniya (UTMN) | Vertical | K-2 | 2018-10-07 20:00:00.000 | Primary Drilling | AD-46 | DRILL COMPLETE SHOE TRACK & 10 FT NEW FORMATION TO 13090 FT. CIRC. PERFORM FIT TO 110 EMW. DISPLACE WELL TO 94 PCF MUD. DRILL 5-7/8" HOLE F/ 13090 FT TO 13540 FT. | DRILL 5-7/8" HOLE TO +/- 14738 FT (200 FT INTO TAWIL FORMATION). | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5-7/8" VERTICAL HOLE FROM 13,080 FT TO 13,090 FT. - FR: 230 GPM, SPP: 2,000-2,250 PSI, RPM: 40-50, TQ: 5-6 KLB.FT. | 72.63 | 47.98 | 2019-01-29 14:18:07.000 | 213 | 247 |  |  |  |  | 2019-01-29 23:00:00.000 | 2018-10-07 20:00:00.000 | 49 | 14687.0005 | 2019-01-01 17:30:00.000 | 35.1771 | 62.2812 | 85.8958 | 114.125 | 30.8233 | 170.9862
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3083 | 25.1046 | 49.2238 | Uthmaniya (UTMN) | Deviated | MK-1 PS | 2018-08-15 17:00:00.000 | Primary Drilling | AD-46 | CONTINUE TO RIH 5-7/8" VORTEX BHA TO 12,562 FT. DRILL CEMENT TO 12,635 FT. DISPLACED HOLE TO 76 PCF KCL POLYMER MUD. CONT. TO DRILL SHOE TRACK TO 12,735 FT (30 FT ABOVE SHOE). CIRCULATED. PRESSURE TESTED CASING. DRILL 10 FT OF NEW FORMATION TO 12,780 FT. PERFORMED FIT. DRILLED 5-7/8" DIRECTIONAL SECTION TO 13,166 FT. | CONTINUE DRILLING 5-7/8" TO ±13,865 FT. CIRCULATE HOLE CLEAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5-7/8" DIRECTIONAL HOLE FROM 12,770 FT TO 12,780 FT. - FR: 230 GPM, SPP: 1,450-1,550 PSI, RPM: 40-50, TQ: 5-6 KLB.FT. | 51.6 | 41.21 | 2018-10-02 13:39:50.000 | 309.28 | 309.28 |  |  |  |  | 2018-10-02 00:30:00.000 | 2018-08-15 17:00:00.000 | 48 | 13825.0004 | 2018-09-20 20:45:00.000 | 1.8125 | 21.4583 | 36.1562 | 47.3125 | 3.8309 | 382.3682
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3084 | 25.2307 | 49.2589 | Uthmaniya (UTMN) | S-Shape | MK-1 PS | 2019-02-05 09:00:00.000 | Primary Drilling | AD-46 | DRILLED 5-7/8" DIRECTIONAL SECTION TO 12675 FT (TD). CIRCULATE. WIPER TRIP TO 7" CSG + RIH BACK TO BOTTOM + CIRCULATE + POOH RSS BHA #9 TO SURFACE + L/D RSS BHA #9 + PERFORM OPEN HOLE LOGGING. | PERFORM OPEN HOLE LOGGING. P/U & RIH 4.5" LINER. | 3B0D04B4CA504F1D85399BD86E4B8A1F | FLOW CHECK, WELL STATIC. - PUMPED 25 BBLS OF SLUG - DROPPED 3 1/2" DRIFT INSIDE 5 1/2" D/PS. | 51.61 | 39.58 | 2019-03-27 11:55:48.000 | 317 | 278 |  |  |  |  | 2019-03-27 10:00:00.000 | 2019-02-05 09:00:00.000 | 49 | 12675.0004 | 2019-03-16 05:15:00.000 | 5.0312 | 23.2604 | 38.8438 | 50.0417 | 10.0541 | 326.3073
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HWYH-1170 |  |  | Hawiyah (HWYH) | S-Shape | K-2 | 2018-12-27 05:00:00.000 | Primary Drilling | AD-55 | DRLD 5-7/8" HOLE SECTION FROM 14,330 FT TO 14,575 FT. | DRILL 5-7/8" HOLE SECTION TO ±14,780 FT, CHC, POOH 5-7/8" ROTARY BHA TO SURFACE & L/D SAME | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TDS | 108.47 | 55.72 | 2019-05-11 16:06:36.000 | 213 | 202.52 |  |  |  |  | 2019-05-13 16:00:00.000 | 2018-12-27 02:00:00.000 | 50 | 14671.0005 | 2019-04-25 21:30:00.000 | 42.3646 | 79.8021 | 119.6875 | 137.4583 | 30.8199 | 122.5775
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2110 |  |  | Uthmaniya (UTMN) | S-Shape | K-2 | 2019-05-18 21:30:00.000 | Primary Drilling | AD-55 | CONT DRILLED 22" HOLE F/ 3630 FT TO 4,000 FT- OBSERVED TOTAL LOSSES AT 4,000 FT- CONT DRILLED BLIND 22" HOLE F/ 4,000 FT TO 4460 FT. | CONT DRILL 22" HOLE TO +/- 6376 FT (+/- 50 INTO HITH FORMATION). | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 22" VERTICAL HOLE F/ 3630 FT TO 4,000 FT. - WOB: 10-20 KLB, RPM: 90, GPM: 900- 950, SPP: 1300-1500 PSI - TRQ: 6-9 K.FT.LB, DIFF PRESS: 150-250 PSI. - ON BTM ROP: 80 FT/HR, AVG ROP: 55 FT/HR. - INCREASED GPM TO 950, OBSERVED SHAKERS & POSSUM BELLY OVERFLOWING. - WASH UP & REAM DOWN FULL STAND AFTER DRILLED. - PUMPED 80 BBLS HI-VIS EVERY STAND DRILLED. - LOADING MUD SYSTEM WITH LCM. - OBSERVED TOTAL LOSSES AT 4,000 FT. | 117.94 | 66.66 | 2019-10-24 12:47:12.000 | [6 empty] | 2019-08-17 15:00:00.000 | 2019-05-19 00:15:00.000 | 50 | 6355.0002 | 2019-06-14 08:00:00.000 | 90.6146 | 14.2188 | 26.4375 | 90.7292 | 99.8737 | 240.3783
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2322 |  |  | Uthmaniya (UTMN) | S-Shape | K-2 PK S | 2019-08-23 19:00:00.000 | Primary Drilling | AD-55 | OBSERVED DISCREPANCY ON DISPLACEMENT VOLUME. FLOW CHECK, WELL STATIC. CONT. RIH OBSERVED DISCREPANCY AGAIN. SUSPECT FLOAT LEAK, CIRC. IN ORDER TO CLEAN PROBABLE DEBRIS, NO SUCCESS. DECISION MADE TO POOH. OBSERVED STRING TWISTED OFF AT BELOW 8-1/4" NMSS. L/D D&M TOOLS. P/U, M/U & RIH W/ 13-3/4" OVERSHOT FISHING BHA. PERFORM FISHING OPERATION, OBSERVED GOOD INDICATION. POOH W/ FISHING ASSY. ON GOING. | CONT. POOH W/ FISHING ASSY. L/D FISH. P/U, M/U & RIH W/ 16" VORTEX BHA. DRILL 16" HOLE TO SECTION TD (+/- 10447 FT). | 3B0D04B4CA504F1D85399BD86E4B8A1F | FILL UP THE STRING AND PERFORMED SHALLOW TEST. | 98.44 | 67.94 | 2019-12-09 08:30:36.000 | [6 empty] | 2019-10-22 01:30:00.000 | 2019-08-23 18:30:00.000 | 49 | 10591.0003 | 2019-10-15 15:00:00.000 | 10.7604 | 28.0417 | 52.8333 | 59.2708 | 18.1547 | 200.4606
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3035 | 25.5164 | 49.3516 | Uthmaniya (UTMN) | Horizontal | K-2 | 2018-08-31 19:30:00.000 | Primary Drilling | AD-55 | DRILL 5 7/8" HORIZONTAL HOLE FROM 13635 FT TO 14064 FT. | CONT DRILL 5 7/8" HORIZONTAL HOLE TO SECTION TD +- 18338 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5 7/8" HORIZONTAL HOLE WITH 85 PCF OBM FROM 13,874 FT TO 14064 FT. - FOLLOWED IDS CONNECTION PROCEDURE. - REAM UP / DOWN ONE SINGLE. - TAKE SURVEY ONE JOINT OFF BOTTOM. - WOB: 12-15K LB; FR: 240 GPM, SPP: 3,100 PSI, DIFF. PRESSURE: 250-350 PSI; SRPM: 70-90 RPM / MOTOR RPM: 111 RPM, TQ: 4-5K FT-LB. - OBSERVED INTERMITTENT SHOCK LEVEL 2 & HIGN STICKSLIP ADJUSTED DRILLING PARAMETERS TO MITIGATE. - MW IN & OUT: 85 PCF. - ON-BOTTOM ROP:22 FT/HR; AVG., ROP: 16FT/HR. - NO GAIN/NO LOSSES. - LAST SURVEY @ 13872FT; INCL: 86.42°; AZIM: 87.25°; TVD: 12574.14 FT. - WELL PATH: 3FT RIGHT , 3FT ABOVE THE PLAN. CENTER TO CENTER 4.6 FT. - All CCA : 0 PSI. - BHA & BIT TIME: 32 HRS. | 75.68 | 65.94 | 2018-12-15 16:48:50.000 | 260.65 | 260.65 |  |  |  |  | 2018-12-16 00:00:00.000 | 2018-08-31 19:30:00.000 | 49 | 18339.0006 | 2018-11-27 13:00:00.000 | 6.7604 | 54.0729 | 87.7292 | 106.1875 | 6.3665 | 209.0411
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1341 |  |  | Haradh (HRDH) | Horizontal | MK1 | 2019-09-07 05:00:00.000 | Primary Drilling | AD-56 | RIH 5 7/8" VORTEX DRLG BHA, D/O CEMENT F/ 12,740' & F.SHOE . DRILL 10 FT OF NEW FORMATION FROM 12780' TO 12790'. PERFROMED FIT TO EMW 110 PCF, DIRECTIONAL DRLG 5-7/8" HOLE TO 12,938' MD, LOST COMMUNICATION BETWEEN MWD, PD & ADN, TROUBLESHOOTING IN PROGRESS. | , CONT. TROUBLESHOOTING MWD COMMUNICATIONS, CONTINUE DRILL AHEAD 5-7/8" HOLE DIRECTIONAL DRILLING. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 10 FT OF NEW FORMATION FROM 12780' TO 12790'. - WOB: 5-10, FR: 220 GPM, SPP: 2170 PSI, RPM: 40, TRQ: 2.5-3.5 KLB.FT, DIFF PRESS: 150-200 PSI. | 75.37 | 53.99 | 2019-11-18 17:51:36.000 | [6 empty] | 2019-10-22 00:15:00.000 | 2019-09-07 05:00:00.000 | 49 | 12938.0004 | 2019-10-21 03:30:00.000 | 2.2187 | 29.5312 | 43.9375 | 44.8021 | 4.9523 | 294.4637
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1844 | 24.0884 | 49.1779 | Haradh (HRDH) | Vertical | MK-1 | 2018-09-27 23:30:00.000 | Primary Drilling | AD-56 | CONT. DISPLACE WELL TO 98 PCF K-FORMATE MUD. D/O CMT, SHOE AND CLEAN POCKET. MTR DRLG 5 7/8" VERTICAL HOLE TO 14096', CHC, PERFORM FIT W/ 115 PCF EMW. MTR DRLG 5 7/8" HOLE TO 14225'. | MTR DRLG 5 7/8" HOLE TO TD @ +/- 15007'. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CIRCULATED HOLE CLEAN FOR 1.2 BTM'S UP, CONFIRMED FORMATION SAMPLES AT THE SURFACE. - MW IN/OUT 98 PCF. - FR 200 GPM, 1900 PSI. - PULL BACK INSIDE THE SHOW. | 54.96 | 39.04 | 2018-12-29 14:55:58.000 | 326.77 | 326.77 |  |  |  |  | 2018-12-29 21:00:00.000 | 2018-09-27 23:30:00.000 | 49 | 14963.0005 | 2018-12-13 16:45:00.000 | 11.8542 | 54.0938 | 76.7188 | 92.8958 | 12.7607 | 195.0371
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1893 |  |  | Haradh (HRDH) | Vertical | K-2 | 2019-01-15 05:00:00.000 | Primary Drilling | AD-56 | CIRCULATED HOLE CLEAN & PERFORMED FIT. ROTARY DRILLING 5-7/8" VERTICAL HOLE FROM 13180 FT TO 13590 FT. | CONT. ROTARY DRILLING 5-7/8" VERTICAL HOLE TO WELL TD @ ± 14,082’ (150’ INTO PUZU/QUSB). | 3B0D04B4CA504F1D85399BD86E4B8A1F | SWEPT HOLE W/ 30 BBLS HI-VIS PILL & CIRCULATED HOLE CLEAN. - MW IN/OUT 103 PCF. - FR 240 GPM, 1900 PSI. - PULL BACK INSIDE THE SHOE. | 67.07 | 51.29 | 2019-05-02 10:00:36.000 | 213 | 208.57 |  |  |  |  | 2019-05-02 08:00:00.000 | 2019-01-15 05:00:00.000 | 49 | 14020.0004 | 2019-04-14 01:30:00.000 | 25.0938 | 58.8021 | 88.8542 | 107.125 | 23.4247 | 157.7866
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2177 |  |  | Haradh (HRDH) | Vertical | K-2 | 2019-05-11 06:30:00.000 | Primary Drilling | AD-56 | ROTARY DRLG 5 7/8" VERTICAL HOLE F/ 14,917' TO 15,173'. | CONT. DRLG 5 7/8" VERTICAL HOLE TO SECTION TD (150' INTO TAWIL FORMATION). WIPER TRIP. CHC, FLOW CHECK. POOH 5-7/8" ROTARY BHA TO SURFACE. | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TOP DRIVE. | 80.87 | 65.17 | 2019-07-31 01:51:00.000 | 213 | 209.15 |  |  |  |  | 2019-08-27 11:00:00.000 | 2019-05-11 06:30:00.000 | 49 | 15481.0005 | 2019-08-02 05:00:00.000 | 8.2708 | 48.6979 | 82.9375 | 108.1875 | 7.6449 | 186.6586
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1379 | 24.5559 | 49.0627 | Haradh (HRDH) | Horizontal | K-2 +P | 2019-06-26 23:00:00.000 | Primary Drilling | AD-59 | RIH 12'' PERFORMANCE BHA TO BOTTOM, RE- LOG GR AND DRILLING 12'' HOLE SECTION FROM 9,792 FT TO 10,210 FT. | CONT. DRILLING 12'' HOLE SECTION TO +/- 11,059 FT MD (5’ INTO BASE SUDAIR DOLOMITE) | 3B0D04B4CA504F1D85399BD86E4B8A1F | PROFILE BIT AND PERFORMANCE DRLG 12" HOLE FROM 9,792 FT TO 10,100 FT. - WOB: 35-40, FR: 800 GPM; 800 SPP: 3700- 4200 PSI, RPM: 60 -100, TRQ: 12-15 K.FT-LB. - O.B ROP: 20-45 FPH; AVG ROP: 24.2 FPH. - LAST SURVEY AT 9983 FT, INC: 1.3 DEG, AZM: 115.16. | 85.26 | 76.26 | 2019-12-08 18:00:36.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-06-26 23:00:00.000 | 49 | 11058.0004 | 2019-10-20 01:00:00.000 | 69.8438 | 82.0521 | 115.0833 | 117.0417 | 59.6743 | 96.0869
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2125 |  |  | Haradh (HRDH) | Vertical | K-2 | 2019-03-11 14:30:00.000 | Primary Drilling | AD-59 | DISPLACE TO 98 K-FORMATE MUD, DRILL 10 FT OF NEW FORMATION. CONTINUE DRILLING 5-7/8" TO 14550'. | DRILL 5-7/8" TO SECTION TD 15244'. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL OUT SHOE & 10 FT OF NEW FORMATION HOLE TO 14,193'. - WOB: 5-10 KLB, FR: 240 GPM, SPP: 2,250 PSI, RPM: 30, TQ: 3.5-4.8 KLBFT. | 68.45 | 53.99 | 2019-06-07 20:28:39.000 | 213 | 225 |  |  |  |  | 2019-06-07 23:00:00.000 | 2019-03-11 14:30:00.000 | 49 | 15617.0005 | 2019-05-23 19:15:00.000 | 2.4792 | 43.5833 | 73.1979 | 88.3542 | 2.8059 | 213.3531
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2126 | 24.0793 | 49.1822 | Haradh (HRDH) | Vertical | MK-1 | 2018-12-02 15:00:00.000 | Primary Drilling | AD-59 | CONT. TO POOH TO SURFACE. M/U & RIH 5-7/8" ROTARY MWD BHA AND RIH TO 14,440 FT. RE-LOGGED TO 14,520 FT. | CONT. RE-LOG TO 14,533 FT (BOTTOM). DRILL AHEAD 5-7/8" SECTION TO ±15,078 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CHECK MWD TEMPERATURE - FR: 200 GPM, SPP: 1,800 PSI. - PUMPED SLUG. | 55.97 | 41.22 | 2019-02-22 06:07:48.000 | 317 | 273.21 |  |  |  |  | 2019-02-22 14:30:00.000 | 2018-12-05 04:30:00.000 | 560 | 15249.0005 | 2019-01-31 20:00:00.000 | 3.6771 | 22.0833 | 60.2083 | 81.9792 | 4.4854 | 253.2706
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-1995 |  |  | Uthmaniya (UTMN) | Horizontal | K-2 | 2019-01-17 05:00:00.000 | Primary Drilling | AD-64 | DRILL 10' OF NEW FORMATION TO 13,682'. CHC. PERFORM FIT TO 110 PCF EMW. DRILL 5 7/8" HORIZONTAL SECTION F/ 13,682' TO 14,080'. | CONTINUE TO DRILL 5 7/8" HORIZONTAL SECTION. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL 5-7/8" HOLE F/ 13,736' TO 13,745' WITH CONTROLLED PARAMETERS. - FR: 250 GPM, SPP: 2,600 PSI, RPM: 60, TRQ: 3-6 KLB.FT, WOB: 15-19 KLBS. - AV ROP : 9 FPH. | 80.6 | 66.45 | 2019-06-11 16:06:36.000 | 213 | 213.6 |  |  |  |  | 2019-06-12 13:00:00.000 | 2019-01-17 05:00:00.000 | 48 | 18449.0006 | 2019-05-13 17:30:00.000 | 41.1979 | 81.2708 | 116.5208 | 146.3333 | 28.1535 | 158.3322
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2057 | 25.1135 | 49.2219 | Uthmaniya (UTMN) | Horizontal | K-2 | 2018-06-13 07:00:00.000 | Primary Drilling | AD-64 | CONT DRILL OUT SHOE TRACK WHILE DISPLACING TO 75 PCF OBM, DRILL 10 FT NEW FORMATION & PERFORM FIT, DRILL 5 7/8" HORIZONTAL SECTION TO 13990 FT MD/ 13069 FT TVD. | CONT DRILL 5 7/8" HORIZONTAL SECTION TO +/- 18132 FT MD/ 13304 FT TVD. | 3B0D04B4CA504F1D85399BD86E4B8A1F | CONTINUE TO DISPLACE HOLE WITH 75 PCF OBM - FR: 250 GPM, SPP: 2200-3400 psi. - MW IN= MW OUT = 75 PCF | 92.13 | 72.08 | 2018-11-02 10:24:00.000 | 260.65 | 260.65 |  |  |  |  | 2018-10-24 09:00:00.000 | 2018-06-13 05:00:00.000 | 0 | 18132.0006 | 2018-10-05 16:30:00.000 | 34.0208 | 84.0521 | 114.3958 | 133.0833 | 25.5636 | 158.5023
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2283 | 24.986 | 49.3268 | Uthmaniya (UTMN) | S-Shape | K-2 | 2019-06-22 01:30:00.000 | Primary Drilling | AD-64 | CONTINUE RIH WITH 5-7/8'' ROTARY BHA TO TOC 13,871 FT. DRILL OUT SHOE TRACK TO 13970 FT ( 30 FT ABOVE SHOE). CHC. P/T CASING. CONT. D/O REMAINING SHOE TRACK & 10' NEW FORMATION. PERFORM FIT TO 110 PCF EMW. DRILL 5 7/8" SECTION F/ 14,015 FT TO 14,160 FT. | DRILL AHEAD 5-7/8" SECTION TO ±14,704 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMED FIT TO EMW 110 PCF, APPLIED 560 PSI SURFACE PRESSURE WITH 104 PCF MUD FOR 15 MIN. | 78.12 | 56.87 | 2019-09-07 07:57:00.000 | 213 | 204.87 |  |  |  |  | 2019-09-30 00:30:00.000 | 2019-06-22 01:30:00.000 | 49 | 14726.0005 | 2019-09-13 08:00:00.000 | 10.9271 | 50.8333 | 83.2708 | 99.9583 | 10.9316 | 176.8446
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3017 | 25.0412 | 49.2039 | Uthmaniya (UTMN) | Vertical | MK-2 | 2018-11-01 20:00:00.000 | Primary Drilling | AD-64 | DRILLED 5-7/8" SECTION F/12, 830 FT TO 13,470 FT. | DRILL AHEAD 5-7/8" SECTION TO ±13,807 FT. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5-7/8" SECTION FROM 12,830 FT TO 12,983 FT - FR: 240 GPM; SPP: 2900-3400 PSI, DIFF PRESS: 400-480; WOB: 10-20 KLB, RPM: 60-70, TQ: 2.5-5 KLB*FT. - AVG ROP: 29 FT/HR. - MAKE CONNECTION AS PER IDS CONNECTION PRACTICES. | 66.16 | 44.91 | 2019-01-01 01:19:49.000 | 286 | 240.08 |  |  |  |  | 2019-01-01 02:30:00.000 | 2018-11-01 20:00:00.000 | 48 | 13878.0004 | 2018-12-18 10:30:00.000 | 0.88542 | 26.7917 | 46.6042 | 60.2708 | 1.4691 | 297.7845
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3034 | 25.3724 | 49.2469 | Uthmaniya (UTMN) | Horizontal | K2KSL | 2019-10-12 01:30:00.000 | Primary Drilling | AD-64 | CONTINUE M/U BHA, TOC @ 632 FT, CHANGE OEVR TO WATER, HYDRO TEST OK, DRILL OUT CEMENT AND SHOE, CONTINUE DRILL 28" WITH 64 PCF MUD from 635 FT to 1915 FT. | CONTINUE DRILLING 28" HOLE SECTION TO SECTION TD +/- 2709 FT. SWEEP HOLE WITH 200 BBL AND CIRCULATE CLEAN, SPOT 500 BBL HI-VIS, POOH, L/D 28" BHA. R/U FOR 24" CASING. | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICED TOP DRIVE. | 74.38 | 64.63 | 2019-12-21 07:04:12.000 | 233 | 233 |  |  |  |  | 2019-10-22 05:00:00.000 | 2019-10-12 01:30:00.000 | 49 | 2719.0001 | 2019-10-20 06:00:00.000 | 0 | 5.6979 | 8.1875 | 10.1458 | 0 | 332.0916
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1376 |  |  | Haradh (HRDH) | Horizontal | MK-1 | 2018-12-15 01:00:00.000 | Primary Drilling | AD-65 | CONT. RIH WITH DIRECTIONAL BHA, TAGGED TOC @ 12,585 FT, DRILL OUT CEMENT AND SHOE TRACK TO 12,780 FT WHILE DISPLACE TO 72 PCF OBM, PT 7" LINER, CLEAN OUT SHOE TRACK AND DRILL 10 FT OF NEW FORMATION, PERFORMED FIT, DRILL 5 7/8" SECTION TO 13,100 FT. | CONT. DRILL 5 7/8" SECTION AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TDS. | 72.5 | 60.34 | 2019-02-24 17:01:12.000 | 317 | 256 |  |  |  |  | 2019-04-11 08:00:00.000 | 2018-12-15 01:00:00.000 | 0 | 18439.0006 | 2019-03-15 21:30:00.000 | 45.0625 | 68.4271 | 90.8542 | 117.2917 | 38.4192 | 202.9516
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1882 | 24.01 | 49.04 | Haradh (HRDH) | Horizontal | MK-1 | 2018-09-27 05:00:00.000 | Primary Drilling | AD-65 | CONT. WASH DOWN, TAGGED CMT, DRILL OUT CMT, L.COLLAR, HARD CMT, F.COLLAR, HARD CMT TO 13,305 FT WHILE DISPLACING TO 95 PCF OBM, PRESSURE TEST 7" LINER, DIRILL OUT F.SHOE, 5 FT RATE HOLE AND 10 FT NEW FORMATION, FLOW CHECK, PERFORMED FIT, DRILL 5 7/8" HOLE SECTION FROM 13,540 FT TO 14,060 FT. | DRILL 5 7/8" HOLE SECTION. | 3B0D04B4CA504F1D85399BD86E4B8A1F | HELD PJSM, PERFORMED FIT TO 110 PCF EMW - TEST OK. | 58.56 | 53.47 | 2018-12-05 01:00:00.000 | 325.02 | 325.02 |  |  |  |  | 2018-12-05 01:00:00.000 | 2018-09-27 05:00:00.000 | 0 | 17758.0006 | 2018-11-24 01:30:00.000 | 1.7604 | 39.5 | 57.8542 | 68.8333 | 2.5575 | 306.9442
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1885 | 23.9994 | 49.0797 | Haradh (HRDH) | Horizontal | K2K-SL | 2019-08-18 05:00:00.000 | Primary Drilling | AD-65 | POOH 8 3/8" DIRECTIONAL BHA, L/D DIRECTIONAL TOOLS AND R/B BHA, R/U WIRE LINE EQ, TEST WL TOOLS IN SURFACE, RIH WL TOOLS ON TLC TO 7,000 FT. | PERFORM WIRE LINE LOGS AS PER PROGRAM, POOH STRING, R/D WIRE LINE EQ, P/U CSG RUNNING EQ. AND RIH 7" LINER AS PER PLAN, CEMENT 7" LINER. | 3B0D04B4CA504F1D85399BD86E4B8A1F | POOH 8 3/8" DIRECTIONAL BHA 1,616 FT TO 78 FT. ON ELEVATORS. - R/B 8 3/8" BHA. - MONITORED WELL WITH TRIP TANK AND SHEET. - NO GAIN / NO LOSSES. | 87.45 | 64.22 | 2019-11-16 19:17:19.000 | [6 empty] | 2019-10-22 05:00:00.000 | 2019-08-18 05:00:00.000 | 45 | 12922.0004 | 2019-10-22 05:00:00.000 | 0.97917 | 42.8854 | 65 | 65 | 1.5064 | 198.8
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1890 | 24.1555 | 48.9934 | Haradh (HRDH) | Horizontal | K-2 | 2019-04-26 05:00:00.000 | Primary Drilling | AD-65 | CONTINUED POOH 5 7/8" DIRECTIONAL BHA FROM 322 FT TO SURFACE AND L/D SAME. M/U 5 7/8" TRICONE BIT & RIH ON ROTARY BHA. CLEAN OUT SHOE TRACK FROM 12412 FT TO 12533 FT. P/T LINER & CASING AT 110 PCF EMW - OK. DRILL OUT REAMING SHOE TRACK TO 12563 FT. DRILLED 5 7/8" HOLE TO 12573 FT. PERFORMED FIT AT 110 PCF EMW - OK. POOH 5 7/8" ROTARY BHA TO SURFACE & L/D SAME. BOP P/T IS IN PROGRESS. | CONTINUE BOP PRESSURE TEST AS PER ARAMCO PROCEDURE. M/U & RIH WITH 5 7/8" DIRECTIONAL BHA TO DRILL AHEAD AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | PULL STRING INSIDE SHOE, PERFORMED FIT TO 110 PCF EMW - TEST OK. | 79.91 | 54.59 | 2019-07-15 02:55:48.000 | 213 | 226.89 |  |  |  |  | 2019-07-29 02:00:00.000 | 2019-04-26 05:00:00.000 | 45 | 16134.0005 | 2019-07-11 16:00:00.000 | 8.8021 | 48.7188 | 76.4583 | 93.875 | 9.3764 | 211.0169
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2119 | 23.853 | 49.1383 | Haradh (HRDH) | Vertical | MK-1 | 2018-07-03 20:00:00.000 | Primary Drilling | AD-65 | CONTINUED POOH 5 7/8" PERFORMANCE BHA FROM 3900 FT TO SURFACE. PERFORMED WIRELINE RUN # 1 LOGGING OPERATIONS. RIH WITH 5 7/8" ROTARY BHA TO 6500 FT FOR CONDITION TRIP. | CONTINUE RIH WITH 5 7/8" ROTARY BHA TO PERFORM CONDITION TRIP. RUN WIRELINE & RECORD LOGS AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | L/D WIRELINE LOGGING TOOLS & R/D SHEAVES. | 61 | 47.45 | 2018-09-16 09:12:36.000 | 326.77 | 326.77 |  |  |  |  | 2018-09-18 12:00:00.000 | 2018-07-03 20:00:00.000 | 0 | 15252.0005 | 2018-08-31 08:00:00.000 | 5.3125 | 39.3333 | 58.5 | 76.6667 | 6.9293 | 260.718
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1269 |  |  | Haradh (HRDH) | Horizontal | K-2 | 2019-02-17 04:30:00.000 | Primary Drilling | AD-66 | CONT. RIH W/ RRS DIRECTIONAL BHA TO LADING COLLAR , D/OUT LAND COLLAR , CMT & FLOAT COLLAR & CMT , DISPLACE WELL TO 85 PCF ,PERFORMED CSG TEST EMT 110 PCF , CONT DRILL OUT REST OF CMT & SHOE , DRILL 10 FT FORMATION & PERFORM FIT( EMW 110 PCF ) , DRILL 5 7/8" HOLE FROM 13700 FT TO 13820 FT | CONT. DRILL 5 7/8" HOLE FROM 13820 FT TO +/- 19015 FT ( 5 7/8" SECTION TD) | 3B0D04B4CA504F1D85399BD86E4B8A1F | PERFORMED FIT WITH 85 PCF MUD W/ 2100 PSI SURFACE PRESSURE (EMW= 110 PCF), OK. VOL PUMPED AND RETURNED= 7.6 BBL | 105.19 | 67.97 | 2019-07-03 00:37:48.000 | 213 | 212 |  |  |  |  | 2019-07-03 00:00:00.000 | 2019-02-17 04:30:00.000 | 49 | 19016.0006 | 2019-06-08 03:30:00.000 | 28.1667 | 78.75 | 110.9583 | 135.8125 | 20.7394 | 171.3797
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1315 | 24.2634 | 48.9598 | Haradh (HRDH) | Horizontal | MK-1 | 2018-05-11 22:30:00.000 | Primary Drilling | AD-66 | DRILL 5-7/8" HOLE AS PER DIRECTIONAL PLAN F/ 13,258 ft to 13,922 FT. | CONTINUE DRILLING 5-7/8" HOLE AS PER DIRECTIONAL PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL AHEAD 5-7/8" HOLE F/ 13,207 FT T 13,213 FT. - FR: 230 GPM, SURFACE RPM: 40-50, PRESS: 2,500 PSI, WOB: 10-15 K LBS. | 68.21 | 56.83 | 2018-08-02 05:37:12.000 | 264.6 | [5 empty] | 2018-08-02 01:30:00.000 | 2018-05-11 22:30:00.000 | 49 | 18043.0006 | 2018-07-13 11:00:00.000 | 7.6146 | 39.9271 | 62.5208 | 82.125 | 9.2719 | 288.5918
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1837 |  |  | Haradh (HRDH) | Horizontal | MK-1 | 2018-11-28 00:00:00.000 | Primary Drilling | AD-66 | CONT. P/UP & RIH WITH NEW 5-7/8" DIRECTIONAL BHA & RELOG LAST 100 FT , AND DRILL 10 FT CMT & SHOE AT 13215 FT , DRILL 10 FT NEW FORMATION , PERFORM FIT EQ 110 PCF& DRILL 5 7/8" HOLE TO 13400 ft | CONT DRILL DIRECTIONAL 5 7/8" HOLE FROM 13400 TO WELL TD AT +/- 17832 FT | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED WITH 5 7/8" DIRECTIONAL BHA FROM 13,225 FT TO 13400 FT. - WOB= 15-16 KLB, RPM= 70-110 RPM, FR= 230 GPM, SPP= 2000- 2050 PSI, TQ= 4-6 KLB-FT, MW= 80 PCF. - FOLLOW CONNECTION PRACTICES. - AV ROP 21 FT/HR - BIT & BHA HOURS FOR TODAY 9.25 HRS - TOTAL BIT & BHA HOURS FOR TODAY 9.25 HRS ACCORDING TO LAST SURVEY COMPARE TO PLAN :- 0.75 FT BELOW 0.19 FT RIGHT , CT-CT 0.8 ft | 66.56 | 54.13 | 2019-02-08 17:52:12.000 | 317 | 261.25 |  |  |  |  | 2019-02-08 21:00:00.000 | 2018-11-28 00:00:00.000 | 50 | 17832.0006 | 2019-01-20 08:00:00.000 | 8.3542 | 32.3958 | 53.3333 | 72.875 | 11.4637 | 334.35
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-1892 |  |  | Haradh (HRDH) | Horizontal | MK-1 | 2019-07-11 05:00:00.000 | Primary Drilling | AD-66 | CONT. DRILL 5 7/8" HOLE SECTION DIRECTION ALLY FROM 13110 FT TO 13675 FT | DRILL 5 7/8" HOLE SECTION DIRECTION ALLY FROM 13675 FT TO +/- 20400 FT | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED WITH 5 7/8" PD VORTEX DIRECTIONAL BHA FROM 12970 FT TO 13010 FT - WOB= 8-12 KLB, FR= 230 GPM, SPP= 3600- 3800 PSI, DHM= 105 RPM, TDS= 50 RPM, TQ= 3-6.0 KLB-FT, DIFF PRESS= 200-300 PSI, MW= 92 PCF. - AVG ROP= 30 FT/HR. - NO LOSSES / GAINS. - CONTROLLING PARAMETERS TILL BHA GET OUT OF CSG | 97.51 | 60.95 | 2019-10-27 22:07:48.000 | [6 empty] | 2019-10-23 04:00:00.000 | 2019-07-11 05:00:00.000 | 49 | 20580.0007 | 2019-09-12 10:00:00.000 | 39.6354 | 40.3646 | 63.2083 | 103.9583 | 38.1263 | 325.59
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | HRDH-2104 |  |  | Haradh (HRDH) | Vertical | K-2 | 2018-08-17 02:30:00.000 | Primary Drilling | AD-66 | DRILL 5-7/8' SECTION FROM 14,585 FT TO 14,910 FT . | CONTINUE DRILL 5-7/8" SECTION AS PER THE VERTICAL PLAN TO SECTION TD . CHC. POOH 5-7/8" BHA TO SURFACE. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED FROM 14,585 FT TO 14,711 FT. - WOB= 15-20 KLB, FR=230 GPM, SPP= 2600 PSI, TDS= 60-70 RPM, TQ= 4.0-6.0 KLB-FT, DIFF PRESS= 200- 250 PSI, MW= 98 PCF. - AVG ROP = 13 FT/HR - NO LOSSES / GAINS | 75.62 | 58.39 | 2018-11-19 21:09:52.000 | 260.34 | 261 |  |  |  |  | 2018-11-19 20:30:00.000 | 2018-08-17 02:30:00.000 | 50 | 14934.0005 | 2018-10-26 10:30:00.000 | 14.3438 | 46.5938 | 70.3333 | 94.75 | 15.1385 | 212.3318
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2277 | 24.9507 | 49.3231 | Uthmaniya (UTMN) | S-Shape | K-2 | 2018-06-26 07:00:00.000 | Primary Drilling | AD-67 | CONT RIH. DRILL OUT CMT AND SHOE TRACK FROM 13754 FT TO 13875 FT. CIRCULATE. P/T 7" LINER - OK. DRILL OUT REMAINING SHOE TRACK. CLEAN RAT HOLE TILL 13915 FT AND DRILL 5-7/8" HOLE TO 13925 FT. CIRCULATE. PERFORMED FIT. DRILL AHEAD 5-7/8" HOLE SECTION FROM 13925 FT TO 14065 FT WITH 16 AVG ROP. | DRILL AHEAD 5-7/8" SECTION TO WELL TD AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILLED 5-7/8" SECTION FROM 13917 FT TO 13925 FT. - FR: 230 GPM, SPP: 2060 PSI, RPM: 40-50, WOB: 5 -10 KLBS, TRQ: 5.3- 6.6 KLB.FT. | 101.24 | 51.15 | 2018-11-06 16:44:24.000 | 236.13 | 236.13 |  |  |  |  | 2018-11-06 19:00:00.000 | 2018-06-26 05:00:00.000 | 50 | 14927.0005 | 2018-10-13 21:15:00.000 | 33.3958 | 79.2917 | 109.5938 | 133.5 | 25.0156 | 136.203
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-2295 | 24.993 | 49.367 | Uthmaniya (UTMN) | Horizontal | MK-1 | 2019-06-27 21:30:00.000 | Primary Drilling | AD-67 | DRILL 5 7/8" DIR HOLE WITH VORTEX BHA FROM 13810 FT TO 14,245 FT | CONT DRILL 5 7/8" HOLE TO( ±16,320’ MD / 13,546’ TVD) TOP OF KHUFF- C CARBONATE AS PER PLAN # 16 | 3B0D04B4CA504F1D85399BD86E4B8A1F | SERVICE TOP DRIVE | 117.99 | 63.71 | 2019-11-08 03:30:31.000 | [6 empty] | 2019-10-22 12:30:00.000 | 2019-06-27 21:30:00.000 | 49 | 16113.0005 | 2019-10-21 13:45:00.000 | 60.0833 | 85.4896 | 115.6771 | 116.625 | 51.5184 | 139.2929
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3005 | 25.0407 | 49.3501 | Uthmaniya (UTMN) | Vertical | MK-2 | 2018-11-16 21:00:00.000 | Primary Drilling | AD-67 | DRILL 5-7/8" HOLE FROM 12,425 FT TO 12,952 FT WITH 41 FT/HR AVG ROP. OBSERVE DROP IN DIFFERENTIAL PRESSURE AND TORQUE WITH NO FURTHER DRILLING PROGRESS. CIRCULATE. POOH FROM 12952 FT TO 437 FT WITH REGULAR FLOW CHECKS. | POOH TO SURFACE. REPLACE MUD MOTOR AND RIH PERFORMANCE BHA TO BOTTOM. DRILL AHEAD 5-7/8" HOLE AS PER PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL 5-7/8" HOLE FROM 12,470 FT TO 12,940 FT. - WOB: 18 KLBS, SRPM/BRPM: 100-115 / 215-230, TQ: 4~5 FT-KLBS, - FR: 250 GPM, SPP: 3720-3850 PSI, DIFF PRESS: 250~280 PSI - MAKE CONN AS PER IDS PROCEDURE. - NO GAIN/LOSSESS. - AVG ROP: 41.8 FT/HR. | 70.54 | 45.18 | 2019-02-01 16:56:41.000 | 286 | 241.79 |  |  |  |  | 2019-02-01 14:00:00.000 | 2018-11-16 21:00:00.000 | 50 | 13977.0004 | 2019-01-12 23:15:00.000 | 5.7396 | 36.0208 | 57.0938 | 76.7083 | 7.4823 | 244.8079
EH | KSA | Saudi Arabia | 3B0D04B4CA504F1D85399BD86E4B8A1F | 440 | 134352 | Ghawar Gas LSTK1 | IDS | KSA | LSTK | UTMN-3071 | 25.1997 | 49.3819 | Uthmaniya (UTMN) | Horizontal | MK-1 | 2019-02-14 00:30:00.000 | Primary Drilling | AD-67 | DRILL/OUT CMT F/ 13,240 FT TO 13,270 FT. DISPLACE 137 PCF WBM W/ 88 PCF OBM. DRILL SHOE TRACK F/ 13,270 FT TO 13,370 FT. P/T CSG. DRILL REMAINING SHOE TRACK CMT & RAT HOLE. DRILL 10 FT OF NEW FORMATION. PERFORM FIT. DRILL AHEAD 5-7/8" HOLE TO 13,535 FT. | DRILL AHEAD 5-7/8" HOLE AS PER DIR. PLAN. | 3B0D04B4CA504F1D85399BD86E4B8A1F | DRILL 5-7/8" HOLE F/ 13,421 FT TO 13,535 FT W/ CONTROLLED PARAMETERS. - WOB: 10 KLBS, FR: 230 GPM, SPP: 2,970 PSI - 50/210 S/DH RPM, TQ: 5 KFT-LBS, DIFF. PRESS: 300 PSI - AVG ROP : 13 FPH. - RECORD T&D & PERFORM STICKING TEST AT CONN. B/FREE TQ - 3.5 KFT-LBS. - DOWNLINK RSS | 74.01 | 60.94 | 2019-06-15 09:00:00.000 | 317 | 247.4 |  |  |  |  | 2019-06-15 11:00:00.000 | 2019-02-14 00:30:00.000 | 50 | 18080.0006 | 2019-05-24 00:30:00.000 | 35.2188 | 63.5 | 99 | 121.4375 | 29.0015 | 182.6263
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah E-2 | 20.4039 | 55.2844 | Sahmah | Vertical | Development & Exxploration for Deep Horizons | 2019-01-18 19:00:00.000 | Primary Drilling | SLR-279 | DRILL 6" HOLE SECTION FROM 3836 M TO 3928 M. | DRILL 6" HOLE SECTION TO 3930 M MD. FLOW CHECK. POOH TO 7" LINER SHOE. FLOW CHECK. POOH TO SURFACE & L/D MOTOR BHA. P/U, M/U & RIH 6" RSS BHA. | B3FE819BFB934EFD95256A4CB356F507 | DRILL FROM 3913 M TO 3922 M. (IN ROTATING DRILLING MODE). - FR: 290-300 GPM, SPP: 2360 - 2480 PSI, WOB: 13-15 KLBS , DIFF PRESSURE: 70-100 PSI. - ON BOTTOM ROP: 3-8 M/HR, AVG ROP: 03 M/HR. - LAST SURVEY AT 3899 M MD, 95.99 DEG INC, 14.13 DEG AZ, 3776.07 M TVD. - DEVIATION FROM PLAN CT-CT 3.3 M, 3.05 M LEFT & 1.27 M BELOW. - PROJECTION AT BIT 3916 M MD, 97 DEG INC, 13.5 DEG AZ, 3774.19 M TVD. | 108.14 |  | 2019-05-06 03:25:55.000 | 183 | [5 empty] | 2019-05-14 10:00:00.000 | 2019-01-18 19:00:00.000 | 45.9318 | 17647.6384 | 2019-03-10 03:30:00.000 | 20.9167 | 21.0938 | 50.3542 | 115.625 | 18.0901 | 350.4703
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah-25H1 | 20.42 | 55.25 | Sahmah | Horizontal | Development Well | 2018-05-05 06:15:00.000 | Primary Drilling | SLR-279 | W&R AND RIH 8-3/8"ROTARY BHA FROM 3599 TO 4280 M.DRILLED 8-3/8"PILOT HOLE FROM 4280 TO 4412 M. | CONTINUE TO DRILL 8-3/8"PILOT HOME. | B3FE819BFB934EFD95256A4CB356F507 | RIG SERVICE PUMP #2 AND #3 - MOVE UP/ DOWN STRING | 111.4 |  | 2018-08-24 09:36:00.000 | 200 | [5 empty] | 2018-08-03 11:15:00.000 | 2018-05-05 06:15:00.000 | 0 | 15872.7039 | 2018-06-23 05:00:00.000 | 13.1875 | 22.7812 | 48.9479 | 90.2083 | 14.6189 | 324.2774
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah-26H1 | 20.42 | 55.25 | Sahmah | Horizontal | Development Well | 2018-08-23 02:00:00.000 | Primary Drilling | SLR-279 | RIH 8-1/2" BHA TO TOC AT 3700 M. DRILL OUT CEMENT & SHOE TRACK. DRILL 8-1/2" HOLE SECTION TO 3491 M. | DRILL 8-1/2" HOLE SECTION TO SECTION TD. | B3FE819BFB934EFD95256A4CB356F507 | DRILLED 8-1/2” HOLE FROM 3432 M TO 3491 M. - WOB: 20-24 KLB, RPM 100, TRQ: 8-12 KLB.FT, - FR: 580 GPM, SPP: 3040-3100 PSI. - ON BOTTOM ROP: 3-18 MPH. AVG ROP: 7 MPH. - MW IN = MW OUT = 10.5 PPG. - WASHED UP AND REAMED DOWN EVERY STAND DRILLED. | 43.46 |  | 2018-10-05 11:03:41.000 | 177 | [5 empty] | 2018-10-06 11:00:00.000 | 2018-08-23 02:00:00.000 | 0 | 12660.7616 | 2018-09-25 13:15:00.000 | 7.1563 | 15.2083 | 33.4688 | 44.375 | 16.1268 | 378.2861
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah-26H2 | 20.42 | 55.25 | Sahmah | Horizontal | Re-Entry | 2019-05-29 08:00:00.000 | Re-Entry | SLR-279 | DRILLED 6"HORIZONTAL HOLE FROM 4648 M TO 4796 M(WELL TD). CIRCULATED, BTM'S UP. DISPLACED OPEN HOLE WITH COMPLETION FLUID. POOH TO 4737 M. | POOH TO SURFACE & L/D DPs & DIRECTIONAL BHA. | B3FE819BFB934EFD95256A4CB356F507 | CIRCULATED TANDEM PILL & CLEAN HOLE - FR: 250 GPM, SPP: 2200 PSI - MEANWHILE KEPT STRING RECIPROCATED | 31.25 |  | 2019-06-29 06:00:36.000 | 122 | [5 empty] | 2019-07-07 00:00:00.000 | 2019-06-01 13:30:00.000 | 10875.9846 | 15734.9086 | 2019-07-04 18:30:00.000 | 7.3958 | 20.0417 | 36.4375 | 38.6667 | 19.1272 | 431.8328
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah-27H1 | 20.41 | 55.25 | Sahmah | S Shaped | Development Well | 2018-11-29 16:00:00.000 | Primary Drilling | SLR-279 | DRILL & WASH DOWN CEMENT TO 936 M - CLEAR RAT HOLE TO 939 M - DRILL 12 1/4" HOLE TO 1515 | DRILL 12 1/4 TO +/- 1750 M | B3FE819BFB934EFD95256A4CB356F507 | DRILLED 12-1/4” HOLE WITH CONTROL PARAMETERS FROM 939 M TO 952 M. - WOB: 15-20 KLB, RPM 60 - 70 , TRQ: 5-8 KLB.FT, FR: 500- 800 GPM, SPP: 600 -1800 PSI, - ON BTM ROP: 04-10 M/HR, AVE. ROP: 5 M/HR. - WASHED UP AND REAMED DOWN EVERY STAND DRILLED. - PUMPED HI-VIS PILL EACH STAND DRILLED. | 87.64 |  | 2019-02-24 15:25:14.000 | 198 | [5 empty] | 2019-01-07 22:45:00.000 | 2018-11-29 15:45:00.000 | 45.9318 | 11561.6802 | 2018-12-29 03:15:00.000 | 4.1042 | 12 | 29.4688 | 39.2812 | 10.4482 | 392.337
EH | EME | Oman | B3FE819BFB934EFD95256A4CB356F507 |  | 261370 | HCF Project | IDS | Gulf | Day Rate | Sahmah-27H2 | 20.41 | 55.25 | Sahmah | Horizontal | Re-Entry | 2019-07-24 10:00:00.000 | Re-Entry | SLR-279 | RIH 8-1/2" CLEAN OUT BHA BY P/U PIPES FROM THE RACK TO TOC. PRESSURE TEST CASING INTEGRITY, OBSERVED PRESSURE DROPPED. RIH & TAG TOC. MILL OUT CEMEN TO 3470 M. POOH TO 3420 M. SPOT LCM PILL. POOH TO 3370 M & CIRCULATE STRING TO FLUSH BIT FREE OF LCM. | SQUEEZE LCM PILL INTO EXPECTED LOSS PERFORATION INTERVAL. PRESSURE TEST CASING. POOH 8-1/2" CLEAN OUT BHA TO SURFACE. P/U & M/U 8-1/2" MILLING BHA & RIH TO 3471 M. MILL SL FISH & 9-5/8" BRIDGE PLUG. DISPLACE WELL TO 10.5 PPG HPWBM. | B3FE819BFB934EFD95256A4CB356F507 | RIH 8-1/2” CLEAN OUT BHA FROM 3260 M TO 3285 M - HAS HELD UP AT 3285 M WITH 15 KLBS. - CONNECT TDS & RECORDED PARAMETERS - PU: 385 KLBS, SO: 285 KLBS, RT WT: 326 KLBS, FR: 550 GPM, SPP: 1700 PSI, TQ: 10 KLBS-FT - AVG TRIPPING SPEED 17 JNTS/HR | 24.46 |  | 2019-08-17 11:01:22.000 | 127 | [5 empty] | 2019-08-30 00:00:00.000 | 2019-07-24 10:00:00.000 | 11561.6802 | 15784.1212 | 2019-08-29 03:00:00.000 | 4.4688 | 24.4688 | 35.7083 | 36.5833 | 12.2153 | 442.0291
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-1530D | 26.008 | 50.5475 | Awali | S Shaped | Oil Producer | 2019-08-22 03:30:00.000 | Primary Drilling | HP-339 | DRILL 8½" PRODUCTION HOLE, POH AND L/D BHA, R/U SLB W/LINE | SLB WIRELINE OPERATIONS, WIPER TRIP | 58B1110929EF43D7B5BDC3168966AFC5 | POOH RUN1: PEX-HRLA-HNGS TOOLSTRING TO SURFACE UP LOG GR-CNL FROM 9 5/8" CASING SHOE TO 100' | 8.56 |  | 2019-08-29 13:27:24.000 | 239 | [5 empty] | 2019-08-31 11:00:00.000 | 2019-08-22 00:00:00.000 | 22 | 2025.0001 | 2019-08-26 03:30:00.000 | 0.1875 | 2.4375 | 4 | 9.3125 | 2.0134 | 506.25
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-1785D | 26.0073 | 50.5474 | Awali |  |  | 2019-07-14 08:30:00.000 | Primary Drilling | HP-339 | CONTINUE RUN 13 3/8" CASING, R/D CRT, RUN 12¼" CLEAN OUT TRIP, PICK UP 12¼" DRILLING BHA, RIH AND DRILL 12¼" SECTION. EXPERIENCE PACKOFF. POOH TO SURFACE. | CHANGE MUD SYSTEM TO 9.9PPG. DRILL 30FT WITH ROTARY BHA. SIMULATE CONNECTION SCENARIO. POOH TO SURFACE. RIH & DRILL 12-1/4" SECTION WITH DIRECTIONAL BHA. | 58B1110929EF43D7B5BDC3168966AFC5 | PICK UP SLB 12¼" DRILLING BHA. 12¼" SMITH TCI BIT, S/N# RL0071, GFSi06UBVEC, IADC 427X, TFA = 0.994, USED. RIH TO 440' MD, SCRIBE PIPE FOR MOTOR HIGH SIDE. | 6.44 |  | 2019-07-24 17:00:00.000 | 218 | [5 empty] | 2019-07-19 10:45:00.000 | 2019-07-14 00:00:00.000 | 22 | 560 | 2019-07-19 00:00:00.000 | 0 | 4.0625 | 4.6458 | 5.0938 | 0 | 120.5381
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-2073D | 26.0109 | 50.5458 | Awali | Deviated | Oil Producer | 2019-08-14 05:30:00.000 | Primary Drilling | HP-339 | DRILL OUT CEMENT, FIT, DRILL 8.5" PRODUCTION HOLE, WIPER TRIP, POOH 8.5" BHA, E-LOG | WIRELINE, RUN/CMT 7" CASING, INSTALL TUBING HEAD, SECURE WELL, RELEASE | 58B1110929EF43D7B5BDC3168966AFC5 | DRILL 8½" PRODUCTION HOLE FROM 1470' TO 1630' TOTAL LOSSES AT 1488' MD. INCONSISTENCE RETURNS TO SURFACE AS DRILLING AHEAD. DYNAMIC LOSSES VARIES, 100-300 BPH. DRILLING PARAMETERS: WOB 4-12 KLBS, SRPM 40, 2-5K TQ 450 GPM, 1200 PSI ON BOTTOM, 1050 PSI OFF BOTTOM MW IN / OUT 9.8 PPG, PU WT 69K / SO WT 64K / ROT WT 64K PUMP 10 BBL HI-VIS EVERY JOINT | 5.05 |  | 2019-08-19 01:12:00.000 | 368 | [5 empty] | 2019-08-17 20:00:00.000 | 2019-08-14 00:00:00.000 | 0 | 1920.0001 | 2019-08-16 06:45:00.000 | 0 | 1.125 | 2.0521 | 3.6042 | 0 | 935.6345
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-2075D | 26.0323 | 50.5406 | Awali | S Shaped | Oil Producer | 2019-08-18 08:00:00.000 | Primary Drilling | HP-339 | WL, RUN/CMT 7" CASING, N/D BOP, SET CSG SLIPS, INSTALL & TEST TUBING HEAD, SECURE WELL, RIG RELEASE | RIG MOVE AND OPERATION ON WELL A-1530D | 58B1110929EF43D7B5BDC3168966AFC5 | LAY DOWN RUN2: SONIC SCANNER TOOLSTRING RIG DOWN WIRELINE SHEAVES AND EQUIPMENT | 4.72 |  | 2019-08-21 18:27:36.000 | 419 | [5 empty] | 2019-08-21 15:00:00.000 | 2019-08-18 00:00:00.000 | 0 | 2010.0001 | 2019-08-20 11:00:00.000 | 0.16667 | 1.1667 | 2.125 | 3.2917 | 5.0633 | 945.8824
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-2077D | 26.043 | 50.5435 | Awali | S Shaped | S | 2019-06-26 07:30:00.000 | Primary Drilling | HP-339 | WIRELINE LOGS RUN #1 PEX-HRLA, RUN #2 FMI (3 PASSES), RUN #3 - XPT | CONTINUE TAKING XPT LOGS AS PER PROGRAM. POOH XPT TOOL. RIG DOWN WIRELINE UNIT. PERFORM WIPER TRIP. RIG UP WIRELINE UNIT. RIG UP MDT TOOL. RUN #4 MDT TOOL | 58B1110929EF43D7B5BDC3168966AFC5 | MAKE UP LOGGING RUN #2 FMI-SONIC SCANNER. RIH AND LOG WITH 3 PASSES AS PER PROGRAM. PULL OUT OF HOLE AND RIG DOWN RUN #2 MONITOR WELL ON TRIP TANK. STATIC. | 5.56 |  | 2019-07-03 07:00:00.000 | 385 | [5 empty] | 2019-07-03 09:00:00.000 | 2019-06-26 07:30:00.000 | 0 | 2163.0001 | 2019-06-28 20:30:00.000 | 0.29167 | 1.2292 | 2.5417 | 7.0625 | 4.1298 | 851.0164
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-2078D | 25.9969 | 25.9969 | Awali | Build & Hold | Productor | 2019-07-06 17:00:00.000 | Primary Drilling | HP-339 | RIH/DRILL 8½" PRODUCTION HOLE, WIPER TRIP, POOH AND LAY DOWN BHA, RUN WIRELINE. | CONTINUE OPEN HOLE WIRELINE LOGGING OPERATIONS | 58B1110929EF43D7B5BDC3168966AFC5 | PULL INSIDE CASING SHOE AND CIRCULATE UNTIL 9.8 PPG IN/OUT PERFORM F.I.T. WITH APPLIED SURFACE PRESSURE OF ~175 PSI, EMW 12.0 PPG – SUCCESSFUL | 6.55 |  | 2019-07-21 17:00:00.000 | 318 | [5 empty] | 2019-07-13 19:00:00.000 | 2019-07-06 17:00:00.000 | 0 | 2070.0001 | 2019-07-09 11:00:00.000 | 0.041667 | 1.5208 | 2.75 | 7.0833 | 0.58824 | 752.7273
WH | KSA | Bahrain | 58B1110929EF43D7B5BDC3168966AFC5 |  | 608227 | IDS - BAH Tatweer Petroleum drilling in | IDS | KSA | Day Rate | A-2079D | 26.0231 | 50.5439 | Awali | S Shaped | Oil Producer | 2019-09-01 00:00:00.000 | Primary Drilling | HP-339 | POOH & L/D 12 1/4" DIRECTIONAL BHA. RUN AND CEMENT 9 5/8" CASING. N/U AND TEST BOPE. P/U 8 1/2" BHA, RIH AND DROUT, DRILL 8 1/2" SECTION | DRILL 8 1/2" HOLE, WIPER TRIP, POH AND L/D BHA, R/UP AND RUN SLB W/LINE LOGS | 58B1110929EF43D7B5BDC3168966AFC5 | PICK UP AND MAKE UP 8 1/2'' DIRECTIONAL ASSEMBLY. SMITH 8 1/2" MS516 PDC BIT S/N# JP4225, TFA 0.648 IN², USED. SCRIBE MOTOR HIGH SIDE TO MWD SENSOR FOR TOOLFACE CORRECTION. | 7.66 |  | 2019-09-06 20:51:36.000 | 282 | [5 empty] | 2019-09-06 15:00:00.000 | 2019-08-31 18:00:00.000 | 22 | 2135.0001 | 2019-09-03 04:00:00.000 | 0 | 1.125 | 2.1667 | 5.625 | 0 | 985.3846
WH | LAN | Ecuador | BA4E4D2D0C964CBA819875F7FF425D0F |  | 519683 | IDS - ECU ENAP SIPEC Drill 2018-2019 LS | IDS | MCA | AFE Assurance | INCHI B-10 | -0.33326 | -76.9498 | MDC | Deviated | J Modificado | 2018-09-10 14:30:00.000 | Primary Drilling | HP-138 | Perforó con BHA #5 direccional desde 8672' hasta 9143' repasando una vez cada parada perforada. Bombeó 30 Bls de píldora dispersa en 8858', 8948', 9038', 9133'. Perforó deslizando con BHA #5 direccional desde 9143' hasta 9163'. Continuó perforando con BHA #5 direccional desde 9163' hasta 9463' repasando una vez cada parada perforada y bombeando píldora dispersa a la mitad de cada parada. Bombeó 30 Bls. de píldora dispersa en 9230', 9320'. Perforó deslizando con BHA #5 direccional desde 9463' hasta 9474'. Continuó perforando con BHA #5 direccional desde 9474' hasta 9576'. | Continuar perforando sección de 12-1/4” hasta +/- 9740’ (30’ arriba del tope de Basal Tena) de acuerdo a programa. Cambiar de fluido de perforación + realizar prueba FIT. Sacar BHA #5 direccional | BA4E4D2D0C964CBA819875F7FF425D0F | Perfora con BHA #5 direccional con parámetros normales desde 8600' hasta 8672' repasando 1 vez cada parada perforada. Parámetros de perforación: 1050 GPM, 1850 - 2200 Psi, 40 RPM, TQ: 16-23 Klbs/ft, WOB: 18-20 Klbs. * Pesos de la sarta: Subiendo: 320 Klbs Bajando: 200 Klbs Rotando: 250 Klbs * Registra datos Survey | 6.74 |  | 2018-09-17 23:45:36.000 | [6 empty] | 2018-10-09 02:15:00.000 | 2018-09-11 06:00:00.000 | 44 | 11259.0004 | 2018-10-03 11:00:00.000 | 0.083333 | 10.4167 | 22.8542 | 28.4896 | 0.2925 | 492.6454
WH | LAN | Ecuador | BA4E4D2D0C964CBA819875F7FF425D0F |  | 519683 | IDS - ECU ENAP SIPEC Drill 2018-2019 LS | IDS | MCA | AFE Assurance | MDC-40 | -0.40969 | -76.842 | MDC | Vertical | Vertical | 2019-09-09 19:30:00.000 | Primary Drilling | Tuscany-117 | Perforó sección 8-1/2" con BHA # 3 direccional (PD 675 X6 + MWD/GR) y broca PDC 8-1/2” Tipo: GT65DO desde 7323' hasta 7435' + Continuó perforando sección 8-1/2" con parámetros controlados en Conglomerado Inferior con BHA # 3 direccional (PD 675 X6 + MWD/GR) y broca PDC 8-1/2” Tipo: GT65DO desde 7435' hasta 8035' + Continuó perforando sección 8-1/2" con parámetros normales con BHA # 3 direccional (PD 675 X6 + MWD/GR) y broca PDC 8-1/2” Tipo: GT65DO desde 8035' hasta 8080'. | Continuar perforando sección de 8-1/2” con BHA # 3 direccional (PD 675 X6 + MWD/GR) y broca PDC 8-1/2” Tipo: GT65DO de acuerdo a programa hasta +/- 8740' + Bombear píldoras de limpieza hasta retornos limpios + sacar BHA # 3 a superficie. | BA4E4D2D0C964CBA819875F7FF425D0F | Perforó sección 8-1/2" con BHA # 3 direccional (PD 675 X6 + MWD/GR) y broca PDC 8-1/2” Tipo: GT65DO desde 7265' hasta 7323'. Parámetros rotando: 540 GPM / 1500 psi / 110 RPM / WOB: 20 - 25 Klbs / TQ: 15 - 16 Klbs-ft * Repasó dos veces cada parada perforada con 60 RPM hacia arriba y abajo con los mismos parámetros de perforación + toma survey cada 2 paradas. * Peso del lodo: 9.9 ppg - 42 sec/qt. | 23.01 |  | 2019-10-02 06:08:38.000 | 523 | [5 empty] | 2019-09-24 08:30:00.000 | 2019-09-09 19:30:00.000 | 43 | 10130.0003 | 2019-09-21 06:30:00.000 | 0.041667 | 4.8333 | 11.4583 | 14.5417 | 0.28653 | 884.0728
WH | LAN | Ecuador | BA4E4D2D0C964CBA819875F7FF425D0F |  | 519683 | IDS - ECU ENAP SIPEC Drill 2018-2019 LS | IDS | MCA | AFE Assurance | MDC-41 | 0.4113 | 76.8405 | MDC | Deviated | Desarrollo | 2019-10-02 14:30:00.000 | Primary Drilling | Tuscany-117 | Bajó BHA #3 direccional desde 5590' hasta 7940. Bajó lavando desde 7940 hasta 8112' (TOC). Realizó drill out perforando tapones de desplazamiento + Collar Flotador (8114') + Shoe track + Zapato Rimador (8155') y 20' de formación nueva desde 8155' hasta 8175' con BHA # 3 Direccional, Ok. Realizó desplazamiento de fluido de perforación Polimérico de 10.4 ppg por fluido de perforación Klashield de 9.9 ppg, Ok. Con la sarta @ 8145', cerró pipe rams y realizó prueba FIT, Ok. Continuó perforando sección de 8 1/2"con BHA # 3 Direccional con parámetros normales desde 8175' hasta 8330'. Continuó perforando sección de 8 1/2"con BHA # 3 Direccional (PD X6 + MWD + GR) y broca PDC 8 1/2” Tipo: GT65DO en paradas de 5 1/2" HT-55 DP con parámetros controlados en el Conglomerado Inferior desde 8330' hasta 8775'. TOPE CONGLOMERADO INFERIOR: @ 8423' MD, 7520' TVD, 46' ABAJO DE PROGNOSIS. | Continuar perforando sección de 8 1/2"con BHA # 3 Direccional (PD X6 + MWD + GR) y broca PDC 8 1/2” Tipo: GT65DO en paradas de 5 1/2" HT-55 DP de acuerdo a programa. | BA4E4D2D0C964CBA819875F7FF425D0F | Continuó armando y bajando BHA # 3 direccional (PD + MWD + GR) con broca PDC 8 1/2" Tipo: GT65DO en hueco entubado en paradas de 5" HWDP, como sigue: - 30 x 5" HWDP (30 joints) - Hydraulic Jar (SN: 517984) - Se mantiene el mismo martillo de la sección anterior. - 9 x 5" HWDP (9 joints) - X-Over 4 1/2" IF Pin x 5 1/2" HT-55 Box * Long. total del BHA: 1327.51' * Peso bajo el martillo: 46 Klbs. * Peso de BHA: 60 Klbs. * Peso sobre el martillo: 14 Klbs. | 21 |  | 2019-10-23 05:54:14.000 | 581.3 | [5 empty] | 2019-10-21 02:00:00.000 | 2019-10-03 03:00:00.000 | 45 | 11219.0004 | 2019-10-21 02:00:00.000 | 0.91667 | 5.4583 | 18.4792 | 18.4792 | 4.9605 | 607.1161
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | MIRA-10 | 0.020413 | 76.4757 | Mira | Build & Hold | Directional Well | 2019-08-25 06:00:00.000 | Primary Drilling | Hilong-15 | 'Drill from 12005 to 12670 ft | 'Drill to TD. Wiper Trip. POOH BHA 7 to surface to run Liner | B99D61AAB2924F0DB25C7378EA61086F | "Drill Rotating and Sliding from 11980 to 12005 ft. Rotating 5 ft w/ 360 gpm, 1800 psi, 45 rpm, 20/25 kpd.ft, 10/15 kpd. Observe good rop roptating the first 15 ft (fast rop 65 ft/h +) Aligne Motor, test tools Sliding w/ 380 gpm, 1620 psi, 10/15 kpd, ongoing Last Lithology @ 11980 - 70% shale + 30% limestone" | 25.5 |  | 2019-09-19 18:01:01.000 | 472 | 472 |  |  |  |  | 2019-09-22 19:00:00.000 | 2019-08-25 10:00:00.000 | 44 | 12940.0004 | 2019-09-20 13:30:00.000 | 0.45833 | 14.2917 | 26.3125 | 28.5417 | 1.6058 | 491.7815
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | Mira-4 | 0.20417 | -76.4757 | Mira | Deviated | J | 2019-07-17 02:00:00.000 | Primary Drilling | Hilong-15 | Drill Rotating from 10820 to 10755 ft. Circulate. Perform Wiper Trip. | POOH BHA 6 to surface to Run Liner | B99D61AAB2924F0DB25C7378EA61086F | Condition Hole to drill testing parameters. Drill Rotating from 10810 to 10820 ft w/ 380 gpm, 60 rpm, ongoing. | 22.1 |  | 2019-08-08 08:22:00.000 | 521.6 | 521.6 |  |  |  |  | 2019-08-11 03:00:00.000 | 2019-07-17 22:00:00.000 | 44 | 11755.0004 | 2019-08-09 02:00:00.000 | 0.52083 | 10.8958 | 23 | 25.0417 | 2.0799 | 511.087
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | ENO-10 | -0.10858 | -76.8599 | Eno | Build & Hold |  | 2018-05-05 06:30:00.000 | Primary Drilling | Tuscany-117 | Continued RIH BHA # 5, drilled out plugs and cement + 9 ft of new formation. Performed FIT. Continued drilling to 11845'. | Continue drilling 8 1/2" section as progra | B99D61AAB2924F0DB25C7378EA61086F | 'Driling out cement plugs + float collar + cement + shoe to 11770'. Drilling 9 ft new formation to 11789'. Q: 420 gpm, 2000 psi, ROT: 40 rpm, WOB: 8-10 klb, TQ: 14-19 klb-ft. Observe plugs on surface. | 10.63 |  | 2018-05-15 21:07:12.000 | 521.45 | 521.45 |  |  |  |  | 2018-06-02 13:00:00.000 | 2018-05-05 06:30:00.000 | 0 | 13627.0004 | 2018-05-29 22:30:00.000 | 2.0833 | 13.3333 | 24.6667 | 28.2708 | 7.3692 | 552.446
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | ENO-9 | -0.10858 | -76.8599 | Eno | Build & Hold |  | 2018-04-06 14:00:00.000 | Primary Drilling | Tuscany-117 | RIH BHA #4 from 1237' to 9464', drill out shoe track + collar + shoe. Change 10.7 ppg Hydraglide to 10.5 ppg Hydraglide. Drill out 15' of new formation, performed FIT, drill 8.5" section to 9927' | Drill 8 1/2" Section as program. | B99D61AAB2924F0DB25C7378EA61086F | Rig service: grease travelling block, drawworks, crown block and TDS. * Calibrate sensor block position. | 23.38 |  | 2018-04-29 15:07:12.000 | 525.68 | 525.68 |  |  |  |  | 2018-04-23 14:00:00.000 | 2018-04-06 14:00:00.000 | 0 | 11006.0004 | 2018-04-20 15:30:00.000 | 0.10417 | 6 | 14.0625 | 17 | 0.61275 | 782.6489
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | Mira-3 | 0.20409 | -76.4757 | Peña Blanca | Build & Hold |  | 2018-07-13 00:00:00.000 | Primary Drilling | Tuscany-117 |  |  | B99D61AAB2924F0DB25C7378EA61086F | RIH BHA #10 from 1232 to 3200'. | 16.29 |  | 2018-07-29 12:57:36.000 | 508.93 | 508.93 |  |  |  |  | 2018-08-14 04:00:00.000 | 2018-07-13 06:30:00.000 | 40 | 12190.0004 | 2018-08-11 17:00:00.000 | 2.7292 | 19.7708 | 29.7083 | 32.1667 | 8.4845 | 410.3226
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | Ron-5 | -0.10629 | -76.7867 | Ron | Build & Hold |  | 2018-02-15 22:00:00.000 | Primary Drilling | Tuscany-117 | RIH BHA # 6 from 1424' to 10030', drill out shoe track + collar + shoe. Change Hydraglide of 10.9 ppg by Hydrglide of 10.5 ppg. Drill 15' of new formation, performed FIT, drill 8.5" | Drill 8 1/2" Section as program. | B99D61AAB2924F0DB25C7378EA61086F | Prejob safety meeting prior to M/U BHA # 6 to 8 1/2" section | 18.5 |  | 2018-03-05 18:00:00.000 | 531.97 | 531.97 |  |  |  |  | 2018-03-13 08:00:00.000 | 2018-02-15 22:00:00.000 | 0 | 11515.0004 | 2018-03-09 07:00:00.000 | 1.125 | 10.1875 | 21.375 | 25.4167 | 4.4262 | 538.7135
WH | LAN | Ecuador | B99D61AAB2924F0DB25C7378EA61086F |  | 447042 | IDS - ECU Orion Drilling Campaing 4th LS | IDS | MCA | Other | Ron-6 | -0.1063 | -76.7867 | Ron | Build & Hold |  | 2019-01-24 12:00:00.000 | Primary Drilling | Tuscany-119 | RIH 9 5/8" CSG to 10313'. Perform Cementing Job. Wash Wellhead. Install and Tes Pack Off. Install Wear Bushing. M/U and RIH BHA 4. | Drill Out Shoe Track. Condition Mud (Perform Displacement). FIT. Drill 8 1/2" Section. | B99D61AAB2924F0DB25C7378EA61086F | 'Calibrate Tuscany, D&M and GSS Depth Sensors | 23.37 |  | 2019-02-16 14:54:59.000 | 566.13 | 566.13 |  |  |  |  | 2019-02-18 09:30:00.000 | 2019-01-24 12:00:00.000 | 0 | 11760.0004 | 2019-02-12 09:30:00.000 | 2.9375 | 10.1458 | 18.8958 | 24.8958 | 11.7992 | 622.3594
EH | EUR | United Kingdom | BBCD6529F719401D9D53F8B08D5B05AB |  | 212660 | IDS - GBR Ithaca Cookfield Dev ALN | IDS | Europe | Day Rate | Cook 21/20a-P2 | 57.36 | 0.83447 | Cook | Deviated | Water Injector | 2019-03-20 00:00:00.000 | Primary Drilling | Deepsea Bergen | Completed slip and cut drilling line. Cont RIH with 8-1/2" BHA and tagged TOC @ 12451 ft. Performed well control and choke drills. Drilled out cement plugs and shoetrack from 12451 ft to 12533 ft. | Drilling 8 1/2" section to TD | BBCD6529F719401D9D53F8B08D5B05AB | Continued RIH on another 5 1/2" DP from 9140 ft to 11158 ft. Performed well control kick drill. | 60.04 |  | 2019-06-20 14:50:02.000 | [6 empty] | 2019-05-05 20:45:00.000 | 2019-03-27 05:30:00.000 | 379 | 13045.0004 | 2019-05-02 19:30:00.000 | 2.5521 | 23.6042 | 43.8125 | 46.8646 | 5.4457 | 297.7461
EH | SEA | India | A6E4E3115B764B9BAD2FC706DCBA9FFC |  | 542920 | IDS - IND V&V Integrated Appraisal LS | IDS | Asia | LSTK | Vandana-4 | 25.483 | 71.42 | VnV | Build & Hold | J | 2019-10-11 21:00:00.000 | Primary Drilling | JE-14 | RIH WITH BIT, MOTOR & 11 3/4'' STRING STAB ON HWDP TO 210 M. POOH BY BACK REAMING. B/OFF BIT L/D MOTOR. M/U & R/B 1 STD OF 4 1/2'' DP WITH 9 5/8'' VAM-21 WATER BUSHING. R/U HYD CATWALK & TESTED. PERFORMED DUMMY RUN FOR CSG HANGER. R/U TO RIH CSG. RIH 9 5/8'' 47 PPF VAM-21 CSG, GOT HELD UP AT 240 M. L/D JT #17 & P/U DP STD WITH WATER BUSHING. TRIED TO CLEAR HELD UP BY WASH DN & REAM DN. NO SUCCESS. POOH & L/D CSG. RIH CLEAN OUT BHA T/66 M. FURTHER RIH IN PROGRESS. | RIH CLEAN OUT BHA TO 997 M. CIRC TILL SHAKERS CLEAN. POOH CLEAN OUT BHA. B/OFF BIT & L/D MOTOR, STAB. R/U TO RIH CSG. RIH 9 5/8'' 47 PPF VAM-21 CSG TO 992.8 M (SHOE). CIRC PRIOR TO CMT JOB. | A6E4E3115B764B9BAD2FC706DCBA9FFC | M/U R-RUN BIT, MOTOR, FLOAT SUB, 11 3/4'' STAB. | 35.75 |  | 2019-11-15 18:02:08.000 |  |  | 20191016170044 |  |  |  | 2019-10-21 00:00:00.000 | 2019-10-11 21:00:00.000 | 100.3937 | 4370.0789 | 2019-10-20 14:30:00.000 | 2.3125 | 6.2292 | 8.7292 | 9.125 | 25.3425 | 500.6296
EH | SEA | India | A6E4E3115B764B9BAD2FC706DCBA9FFC |  | 542920 | IDS - IND V&V Integrated Appraisal LS | IDS | Asia | LSTK | Vandana 3 | 25.823 | 71.7007 | VnV | Build & Hold | Appraisal | 2019-09-21 13:30:00.000 | Primary Drilling | JE-28 | PRESSURE TEST BOP. P/U AND M/U 13 4" DP STDS AND RACK BACK. M/U 6" BHA. RIH TO 531M. | RIH 6" BHA TO 2400M. DRILL OUT SHOE TRACK. PERFORM LOT. DRILL 6" SECTION. | A6E4E3115B764B9BAD2FC706DCBA9FFC | P/U, M/U AND R/B 4" DP - P/U, M/U and R/B 13 stands of 4" DP | 37.14 |  | 2019-10-28 03:20:20.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-09-21 13:30:00.000 | 96.7848 | 10600.394 | 2019-10-22 00:00:00.000 | 8.8125 | 20.5208 | 30.4375 | 30.4375 | 28.9528 | 348.2676
EH | FEA | China | 8140224BB0724C09BD1490C81CC5E101 |  | 442923 | IDS : PZOC Shale Gas PAD drilling | IDS | Asia | LSTK | YS112H11-4 | 28 | 105 | Zi Jin Ba | Horizontal | Develop Well | 2018-04-04 00:00:00.000 | Primary Drilling | SL70112 | Drilling 8 1/2" section as per directional plan | Cont 8 1/2" section as per directional plan | 8140224BB0724C09BD1490C81CC5E101 | Chang out TDS washpipe - POOH to casing shoe working on TDS. | 61.8 |  | 2018-06-04 19:12:00.000 | [6 empty] | 2018-06-13 00:00:00.000 | 2018-04-04 00:00:00.000 | 93.5039 | 13366.1422 | 2018-05-25 02:00:00.000 | 20.7708 | 25.5938 | 51.0833 | 70 | 29.6726 | 261.6537
EH | EUR | Turkey | E9D16292D5A643EC94C14C4D91EB0E37 |  | 460973 | IDS EUR TR BOTAS - Kuzey Marmara 18 offs | IDS | Europe | AFE Assurance | KM-31 |  |  | Kuzey Marmara | Vertical | Appraisal | 2019-02-04 12:00:00.000 | Primary Drilling | Saturn | - RIH 8 1/2" Clean Out BHA. - Drill out cement and drill 3 m. of new formation. - Displace the well with PROFLO mud. - Perform FIT. - POOH 8 1/2" Clean Out BHA. | - RIH 8 1/2" X 4" Coring BHA. - Cut core. - POOH 8 1/2" X 4" Coring BHA to surface. - M/U 8 1/2" Drilling BHA. | E9D16292D5A643EC94C14C4D91EB0E37 | Drill 3m of new formation from 1213m to 1216m - Parameters: 350gpm, 820psi, WOB 3-5 Tons, 70 RPM, Torque 4-5 lbs-ft - Total metal recovery: 0.3 kg - Cutting Sample at 1216m: 40% Clay, 60% Marl | 42.65 |  | 2019-03-18 15:39:55.000 | [6 empty] | 2019-04-13 16:00:00.000 | 2019-02-04 12:00:00.000 | 137.7953 | 4606.2994 | 2019-03-09 12:00:00.000 | 9.7292 | 22.9583 | 33 | 68.1667 | 14.2726 | 139.5848
EH | RCA | Russian Federation | 2119AB2220B5422392450097672F2CA3 | 881 |  | IDS RUL RU Lukoil WS | IDS | RCA | AFE Assurance | 1095h | 61.98 | 74.85 | Vostochno-Pridorozhnoye | Horizontal | Horizontal (3ML) | 2018-01-12 23:00:00.000 | Primary Drilling | BU-3000 EUK_924 | RIH liner to TD, Circulate the well. Packer activation (+), pressure test (+), unlatching service tool (+) | Circulate the well, POOH running string, meanwhile L/D DP on racks | 2119AB2220B5422392450097672F2CA3 | Packer activation QUANTUM: P=110atm, for 10min; 9t (to 79t) и 9t (to 29t)-hanger - ok, P=0atm. Packer PT 60atm for 10- (+). pressure test (+), unlatching service tool (+). Hanger at 3235,57m. | 40.18 |  | 2018-02-21 04:19:12.000 | [6 empty] | 2018-02-28 19:00:00.000 | 2018-01-13 00:00:00.000 | 0 | 12572.1789 | 2018-02-21 23:00:00.000 | 4.4375 | 23.9062 | 40 | 46.8333 | 9.4751 | 314.3045
EH | RCA | Russian Federation | 2119AB2220B5422392450097672F2CA3 | 881 |  | IDS RUL RU Lukoil WS | IDS | RCA | AFE Assurance | 6160h | 61.5 | 74.6833 | Nivagalskoye | Horizontal | Horizontal (3ML) | 2018-01-13 18:00:00.000 | Primary Drilling | BU-3000 EUK_924 | M/U BHA. Drilling in int. 0-54. POOH & L/D BHA | WOC. M/U & RIH BHA. Drilling to 300m | 2119AB2220B5422392450097672F2CA3 |  | 32.23 |  | 2018-02-14 05:31:12.000 | [6 empty] | 2018-02-17 05:00:00.000 | 2018-01-13 18:00:00.000 | 0 | 9461.9426 | 2018-02-14 04:30:00.000 | 3.8021 | 18.5104 | 31.4375 | 34.4583 | 11.0339 | 300.9763
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D79P | 31.76 | 46.08 | Gharraf | S Shaped | Deviated Well Producer | 2019-03-26 21:00:00.000 | Primary Drilling | IDC-54 | Continued pressure test BOP. 'P/U & M/U 12 1/4" directional assy. RIH to 616m. | RIH 12-1/4" directional BHA.tag TOC , DOC & 3 m form new formation ,CHC dicplace with new KCL mud 10.2.Perform FIT .Resume drilling 12-1/4". | EAA44A98568E41DC92820C9C858FE3E0 | PJSM. P/U & M/U 12-1/4"" directional BHA: (12-1/4"" new PDC bit + 9 5/8"" Motor w/ 1.15 deg BH, 12-1/8"" Sleeve Stab.+ 11 3/4"" St. Stab.) Shallow test Motor with FR: 521 GPM, SPP: 275 psi - OK. P/U and M/U ARC-8, telescope528,8"" NMDC & Cross over. | 76 |  | 2019-07-02 03:00:00.000 | 160 | [5 empty] | 2019-07-02 03:00:00.000 | 2019-03-26 15:00:00.000 | 98.4252 | 12125.9846 | 2019-06-03 15:00:00.000 | 16.1979 | 31.4271 | 68.75 | 97.25 | 16.656 | 176.378
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D80P | 31.7593 | 46.0822 | Gharraf | S Shaped | Deviated Well producer | 2018-12-04 12:00:00.000 | Primary Drilling | IDC-54 | Cont Pressure test .13-5/8" BOP.P/U &M/U 12 1/4 RSS BHA RIH to 237M | RIH 12 1/4'' RSS , P/U & M/U 5'' DP & 5 1/2'' DP . | EAA44A98568E41DC92820C9C858FE3E0 | Cont P/U & M/U 12 1/4'' RSS BHA (8 1/4'' ARC-8+ 8 1/4'' Telescope 825 +8" NMDC+ 61/2'' X/O+9 X 5" HWDP+ 61/2'' Hydra-Jar AP +12 X 5" HWDP ) RIH to 237m | 86.25 |  | 2019-03-06 10:59:59.000 | 158.1 | [5 empty] | 2019-03-06 16:00:00.000 | 2018-12-11 01:00:00.000 | 98.4252 | 13608.9243 | 2019-02-08 04:30:00.000 | 6.0208 | 30.8854 | 65.6875 | 92.1667 | 6.5325 | 207.1768
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D84P | 31.7592 | 46.0821 | Gharraf | S Shaped | Deviated Well producer | 2018-08-02 08:30:00.000 | Primary Drilling | IDC-54 | CONTINUED RIH 12-1/4" BIT W/DIR, ASSY FROM 515M TO 1798M (TAGGED TOC). DRILLED OUT SHOE TRACK TO 1822M. POOH 2 STANDS, SUSPENDED THE OPERATION TILL MANIFOLD P/T FINISHED. CONTINUED DRILL 12 1/4" DIRECTIONAL HOLE FROM 1833M TO 1834M. | DRILL 12-1/4" HOLE SECTION TO 3541.36 M-MD / 2454.93 M-TVD. | EAA44A98568E41DC92820C9C858FE3E0 | SHALLOW TESTED MWD TOOLS - 615 GPM, 950 PSI-OK. | 64.2 |  | 2018-10-29 19:23:56.000 | 175.2 | [5 empty] | 2018-11-20 12:00:00.000 | 2018-08-02 08:30:00.000 | 98.4252 | 11571.5227 | 2018-10-17 11:30:00.000 | 25.9375 | 41.7292 | 76.125 | 110.1458 | 23.5483 | 152.0069
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-J92P | 31.737 | 46.062 | Gharraf | S Shaped | Deviated Well Producer | 2019-09-29 19:30:00.000 | Primary Drilling | IDC-54 | RIH 17-1/2" Directional BHA to bottom . Pressure Test 18-5/8" Casing @ 500 psi . Drill Float equipment and 3m new formation. Performed FIT to 11.0ppg EMW . Drill 17 1/2'' Hole to 386 m. | Drill ahead 17 1/2" Hole . | EAA44A98568E41DC92820C9C858FE3E0 | Cont. P/U and M/U 17 1/2 Rock bit + 9 5/8 Motor ( Sleeve Stab 17 1/4") W/ 1.5 BH + Float sub + 14 1/4'' string stabilaizar + XOS +5'' PUP joint and performed motor shallow test with 200 GPM , 100 Psi (OK) | 83.2 |  | 2019-12-21 04:04:48.000 | 145.2 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-09-29 19:30:00.000 | 104.9869 | 5547.9004 | 2019-10-22 00:00:00.000 | 1.7917 | 9.25 | 22.1875 | 22.1875 | 8.0751 | 250.0462
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D77P | 31.7582 | 46.0821 | Gharraf | S Shaped | Deviated Well Producer | 2018-08-23 21:00:00.000 | Primary Drilling | IDC-58 | CONTINUED RIH 12-1/4” DIRECTIONAL BHA TO TOC. DRILLED OUT CEMENT AND 3M NEW FORMATION. DISPLACED HOLE WITH NEW MUD. PERFORMED FIT. DRILLED 12-1/4" HOLE TO 1864 MMD. | DRILL AHEAD 12-1/4" HOLE TO 3468.84 MMD / 2456.24 MTVD. | EAA44A98568E41DC92820C9C858FE3E0 | RIG OPERATIONS SUSPENDED DUE TO MISSING CERTIFICATION FOR 3-1/8" 5K MANUAL VALVE ON KILL LINE ON 13-5/8" BOP STACK. - RECEIVED REQUIRED CERTIFICATE AND SUSPENSION STATUS ENDED AT 13:00 HRS. - IDC - 58 WILL RESUME OPERATIONS AS PER PLAN. | 54.12 |  | 2018-10-16 07:59:03.000 | 174.3 | [5 empty] | 2018-12-04 20:30:00.000 | 2018-08-23 21:00:00.000 | 98.4252 | 11305.7746 | 2018-11-03 11:30:00.000 | 25.7708 | 44.2396 | 71.6042 | 102.9792 | 25.0253 | 157.8927
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D78P | 31.7581 | 46.082 | Gharraf | Build & Hold | Deviated Well Producer | 2019-07-19 13:00:00.000 | Primary Drilling | IDC-58 | P/U, M/U 12-1/4" directional BHA. & RIH to 299m. Slip & cut drilling line , Troubleshooting with Drawwork calibration anti-collision system sensor.Ok ,Perform function test drawwork three times (Crown O-matic, Floor saver, Anti-collision system),Ok. | RIH 12-1/4" Dir. BHA to 1677.3m (float collar), P/T 13-3/8" CSG , drill out shoe and 3m in new formation, circulate & displace hole with new KCL mud 10.2ppg, perform FIT, directional drill 12 1/4''hole as per plan. | EAA44A98568E41DC92820C9C858FE3E0 | Troubleshooting with Drawwork calibration anti-collision system sensor.Ok. | 62 |  | 2019-11-01 21:00:00.000 | 157.43 | 157.43 |  |  |  |  | 2019-10-22 00:00:00.000 | 2019-07-19 22:00:00.000 | 104.9869 | 9534.121 | 2019-10-15 14:45:00.000 | 51.7083 | 67.875 | 88.0729 | 94.4583 | 54.7419 | 108.2526
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D83P | 31.7584 | 46.0823 | Gharraf | S Shaped | Production | 2019-04-11 10:00:00.000 | Primary Drilling | IDC-58 | POOH & L/D Test Assembly with plug.Install Wear bushing.P/U and M/U 12-1/4" Directional BHA .Slip & cut drilling line. RIH with 12-1/4" Directional BHA T/ 818 m. | Cont ,RIH with 12-1/4" Directional BHA to bottom @ 2206 m (Tag Float Collar).Drill out floats, cement and 3m new formation.Circulate hole clean and perform FIT to 12ppg EMW (455 psi).Drill ahead 12-1/4" directional hole. | EAA44A98568E41DC92820C9C858FE3E0 | PJSM. P/U & M/U 12-1/4" directional BHA: (12 ¼” PDC Bit+ A962M564.0XP with 12 1/8" Sleeve Stab (With 1.15 BH) / With float valve+ 11 ¾” String Stabilizer + ARC-8 + Telescope 825 HF + 8" NMDC + CrossOver + 9 X 5" HWDP + Jar + 12 X 5"HWDP & RIH 5" DP from 243 m to 358 m. - Shallow test Motor with FR: 260 GPM, SPP: 110 psi - OK. | 82.04 |  | 2019-07-11 11:30:00.000 | 155.3 | [5 empty] | 2019-07-11 11:30:00.000 | 2019-04-11 10:00:00.000 | 104.9869 | 12736.2209 | 2019-06-13 17:15:00.000 | 7.6771 | 26.0521 | 63.3021 | 91.0625 | 8.4306 | 201.1975
EH | EME | Iraq | EAA44A98568E41DC92820C9C858FE3E0 |  | 546344 | IDS UCD Petronas PCIHBV/2014/DRL/381/Pac | IDS | Gulf | Day Rate | Ga-D85P | 31.7585 | 46.0824 | Gharraf | S Shaped | Deviated Well Producer | 2018-12-08 12:00:00.000 | Primary Drilling | IDC-58 | P/U & M/U & rack back on derrick 5.5"x 39 joints DP (13 stands). (Drift all pipes), RIH 12 ¼” directional BHA on 5" DP to 1363m, Perform slip & cut drilling line. | Cont. slip & cut drilling line, Resume RIH 12-1/4" directional BHA, Tag bottom & Drill-Out Floats, Cement & 3m of New Formation, Circulate Hole Clean, Perform FIT, Drill ahead 12-1/4" directional hole. | EAA44A98568E41DC92820C9C858FE3E0 | P/U & M/U & rack back on derrick 5 1/2" DP 13 stand 69 joints (Drift all pipes, B/O and re-M/U every connection). | 80.83 |  | 2019-03-23 00:00:00.000 | 163.3 | [5 empty] | 2019-03-23 10:30:00.000 | 2018-12-25 03:00:00.000 | 104.9869 | 12247.3757 | 2019-02-21 03:00:00.000 | 11.9375 | 27.1979 | 74.625 | 104.9375 | 11.3758 | 164.1189
EH | EUR | United Kingdom | 8E757E6BE810451D9B41AF6D511A4FB4 |  | 612077 | IDS – GBR – BP Vorlich Integrated Drilli | IDS | Europe | Other | Vorlich North | 56.8678 | 2.0722 | Vorlich | Horizontal | Development | 2019-06-20 00:00:00.000 | Primary Drilling | PBLJ | Picked up 5-1/2" drillpipe and racked back same. Performed sucesful function test of DMAS system. Made up and RIH with 8-1/2" BHA. Recovered BHA to suface due to error in tool programming. Reprogrammed tools and RIH with BHA. | RIH with 8-1/2" BHA. Wash down and tag TOC. Perform WC drills. Displace well to RDF. Drill out cement and shoe track and 3m new formation. Update at 06:00: Performing D4 well control drill. | 8E757E6BE810451D9B41AF6D511A4FB4 | Picked up and made up BHA as instructed by directional driller | 30.05 | 21.43 | 2019-07-22 01:09:00.000 | [6 empty] | 2019-08-09 10:00:00.000 | 2019-06-22 23:30:00.000 | 0 | 13149.6067 | 2019-08-04 04:45:00.000 | 4.8333 | 23.5 | 45.1979 | 50.4167 | 9.5868 | 290.9339
EH | EUR | United Kingdom | 8E757E6BE810451D9B41AF6D511A4FB4 |  | 612077 | IDS – GBR – BP Vorlich Integrated Drilli | IDS | Europe | Other | Vorlich South | 56.86 | 2.0725 | Vorlich | Horizontal | Development | 2019-06-25 05:15:00.000 | Primary Drilling | PBLJ | Singled in 8-1/2" BHA with 33joints 5-1/2" drillpipe. Performed D4 drill with night shift. RIH with 8-1/2" BHA on 5-1/2" drillpipe. Performed D4 drill with day shift drill crew. Offloaded 1.30sg OBM RDIF from the vessel.. Displaced well to 1.30sg OBM. Drilled out shoetrack and shoe and reamed across rathole and shoe. | Drill 3m new formation and perfrom FIT. Flowcheck well. Drill ahead in 8-1/2" hole. Update at 06:00: Perfromed FIT to 1.62sg EMW. Flow checked well - static. | 8E757E6BE810451D9B41AF6D511A4FB4 | RIH with 8-1/2" BHA from 499m to 1473mMDBRT. Filling the string every twenty stands | 25.64 | 20.01 | 2019-07-20 15:15:00.000 | [6 empty] | 2019-09-29 21:15:00.000 | 2019-06-25 08:30:00.000 | 368.4383 | 14025.591 | 2019-09-23 17:00:00.000 | 5.8646 | 24.7917 | 90.4896 | 96.6667 | 6.0668 | 154.9967
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H63-2 |  |  | Wei Yuan | Horizontal | Horizontal Well | 2018-09-04 10:15:00.000 | Primary Drilling | GWDC-50058 | PD Archer D/A 8.5" hole section | PD Archer D/A 8.5" hole section | DA72DE685EC242C4AA8FBD618D1D06EF | D/A 8.5" hole F/2854m T/2938m. - WOB 8-10T, TDS RPM 100, ON-BTM torque 9-20Kn.m, FR 30L/s, SPP 28MPa. - Cuttings return observed on shale shaker, OK. | 20 |  | 2019-01-12 00:00:00.000 | [6 empty] | 2019-08-25 06:00:00.000 | 2018-12-23 00:00:00.000 | 8356.2995 | 15003.2813 | 2019-08-09 02:00:00.000 | 183.9792 | 198 | 338.6562 | 354.8229 | 51.851 | 44.3024
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H41-2 |  |  | Wei Yuan | Horizontal | Horizontal Well | 2018-10-26 20:00:00.000 | Primary Drilling | GWDC-50613 | Drill ahead from 3387m to 3499m | Drill ahead to 3650m | DA72DE685EC242C4AA8FBD618D1D06EF | repair pump | 20 |  | 2018-11-15 00:00:00.000 | [6 empty] | 2018-11-19 06:00:00.000 | 2018-10-26 20:00:00.000 | 11076.1158 | 17988.8457 | 2018-11-17 15:15:00.000 | 3.7604 | 6.0729 | 21.8021 | 23.4167 | 16.0587 | 825.0976
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H41-4 |  |  | Wei Yuan | Horizontal | Development Well | 2019-05-31 21:15:00.000 | Primary Drilling | GWDC-50613 | Drilled 8 1/2" hole from 4575m to 4658m. | Drill 8 1/2" hole as per plan. | DA72DE685EC242C4AA8FBD618D1D06EF | Drilled 8 1/2" hole fro 4591m to 4658m. Note: Entered Wufeng formation from 4538m to 4632m, TVD 0.8m | 24.79 |  | 2019-06-24 18:57:36.000 | 330 | [5 empty] | 2019-07-05 03:00:00.000 | 2019-05-31 00:00:00.000 | 10990.814 | 18175.8536 | 2019-07-02 20:00:00.000 | 4.8229 | 15.0312 | 31.9479 | 34.2396 | 14.0858 | 568.9214
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H41-6 |  |  | Wei Yuan | Horizontal | Development Well | 2019-04-06 14:15:00.000 | Primary Drilling | GWDC-50613 | Drill shoe track and POOH. | RIH & Drilling. | DA72DE685EC242C4AA8FBD618D1D06EF | L/D BHA. | 14 |  | 2019-04-19 00:00:00.000 | 330 | [5 empty] | 2019-05-20 21:30:00.000 | 2019-04-05 00:00:00.000 | 11282.8088 | 18585.9586 | 2019-05-18 10:00:00.000 | 3.6875 | 22.9479 | 41.8229 | 44.3021 | 8.3235 | 444.3965
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H39-4 |  |  | Wei Yuan | Horizontal | Horizontal Well | 2018-08-17 15:00:00.000 | Primary Drilling | GWDC-70110 | 0:00-4:30 Drill ahead to MD 3205.80m 4:30-7:30 repair wash pipe 7:30-0:00 Drill ahead to MD 3314m | Drill ahead to MD 3450m, suspend drilling and adjust mud property to reduce over-high GR value of OBM. | DA72DE685EC242C4AA8FBD618D1D06EF | Drill ahead from 3205.8 to 3314m | 20 |  | 2018-09-23 18:00:00.000 | [6 empty] | 2018-09-28 08:30:00.000 | 2018-08-17 04:00:00.000 | 9970.4728 | 16207.3496 | 2018-09-26 00:00:00.000 | 7.0729 | 24.6875 | 39.375 | 41.7292 | 16.9496 | 411.6152
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H62-1 | 29.5 | 104.5 | Wei Yuan | Horizontal | Horizontal Well | 2018-08-03 20:30:00.000 | Primary Drilling | GWDC-70180 | R/U D&M surface unit, M/U Archer+SP, RIH, D/A | D/A | DA72DE685EC242C4AA8FBD618D1D06EF | M/U BHA: X516+Archer+Slimpulse; M/U & test Slimpulse at surface, OK. | 20 |  | 2018-08-23 00:00:00.000 | [6 empty] | 2018-09-03 00:00:00.000 | 2018-08-03 00:00:00.000 | 8353.0186 | 14993.4388 | 2018-08-22 00:30:00.000 | 16.7188 | 5.7917 | 18.1667 | 30.1458 | 55.4596 | 825.3269
CHA | FEA | China | DA72DE685EC242C4AA8FBD618D1D06EF |  | 555355 | IDS-CHG-GWDC Drilling performance optimi | IDS | Asia | AFE Assurance | Wei202H75-4 | 29.26 | 104.31 | Wei Yuan | Horizontal | Development well | 2018-12-14 19:15:00.000 | Primary Drilling | GWDC-70180 | 0:00-9:15 Do drill pipe washing run; 9:15-19:15 M/U and RIH new BHA with PD archer and DTX motor.19:15-0:00 drill ahead from 2831m to 2857m | drill 8-1/2" hole section | DA72DE685EC242C4AA8FBD618D1D06EF | wash drill pipe with flow rate 2400LPM. | 20 |  | 2019-01-01 00:00:00.000 | 330 | 330 |  |  |  |  | 2019-01-26 15:00:00.000 | 2018-12-13 00:00:00.000 | 9288.058 | 15984.2525 | 2019-01-26 15:00:00.000 | 10.8438 | 19.6875 | 42.8229 | 42.8229 | 25.3223 | 373.264
EH | EUR | United Kingdom | BED87C9A208A4D98B4D8C116FC0FF922 |  | 599344 | IDS_GB_Ithaca_Stella Well | IDS | Europe | Day Rate | Stella Well 30/06a-B3 | 56.8211 | -2.0723 | Stella | Horizontal | Horizontal Producer | 2019-04-15 17:15:00.000 | Primary Drilling | Maersk Resilient | Completed BOP and manifold testing. Laid out excess 12 1/4" BHA. Laid out 3 1/2" cement stinger. Commenced picking up 8 1/2" BHA and RIH. | RIH with 8 1/2" BHA. Drill out shoetrack and displace well to 14.2ppg mud. Drill ahead in 8 1/2" hole. | BED87C9A208A4D98B4D8C116FC0FF922 | Cleaned and cleared rig floor. Serviced DDM and prepared handling equipment for picking up 8 1/2" BHA. Held TBT and picked up 8 1/2" BHA from surface to 152ft. WCE step no 1.1; 1.7.68; 14.1; 14.5; 14.6; 14.8.1 - M/up 8 1/2" BHA. POOH to 110ft and installed radioactive sources into Geosphere tool. RIH to 152ft. Continued to pick up 8 1/2" BHA and RIH from 152ft to 196ft. | 71.26 |  | 2019-06-25 06:12:18.000 | [6 empty] | 2019-06-27 07:00:00.000 | 2019-04-15 17:15:00.000 | 449 | 14157.0005 | 2019-06-06 12:00:00.000 | 23.3646 | 35.9062 | 51.7812 | 72.5729 | 32.1946 | 273.4001
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-475 | 30.8775 | 47.3178 | West Qurna | Horizontal | ERD | 2018-10-28 10:30:00.000 | Primary Drilling | GW-145 | POOH with wire line cable, L/D SES and WL sheaves. POOH to surface, L/D WL assembly, P/T BOP, P/T CSG, M/U 6-1/8" directional BHA, started RIH P/U 4" DP to 203m | RIH with 6 1/8" Directional BHA, P/U 4-1/2" DPs | D9124EEB42B742BA86643AEBA81E8C66 | M/U 1 st of 4" DP from rack back, changed power tong dies. | 45.36 |  | 2018-12-12 08:38:24.000 | 327 | 327.3 |  |  |  |  | 2018-12-13 16:00:00.000 | 2018-10-28 10:30:00.000 | 226.378 | 15834.4821 | 2018-12-09 08:30:00.000 | 9.4167 | 29.1771 | 41.9167 | 46.2292 | 20.3695 | 377.761
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-477 | 30.8775 | 47.3179 | West Qurna | Horizontal | Mishrif | 2018-12-14 22:00:00.000 | Primary Drilling | GW-145 | Continued POOH with 8-1/2" Directional BHA to surface, L/D same. R/U TRS 7" CSG running tools. Performed a PJSM. M/U & RIH with 97 joints of 7" casing (26#, L-80, VAM TOP HC). P/U & M/U L.H BHA. Circulated with max 700 psi. RIH liner hanger BHA with 5" HWDP to 1534 M. | Continue RIH with 7" liner hanger BHA to bottom. Circulate hole till shakers clean. Set liner hanger. Perform cement job as per plan. POOH with liner hanger BHA to surface. | D9124EEB42B742BA86643AEBA81E8C66 | R/U TRS 7" CSG RUNNING TOOLS. | 41.66 |  | 2019-01-24 15:50:24.000 | 367 | 327.3 |  |  |  |  | 2019-01-28 05:00:00.000 | 2018-12-14 22:00:00.000 | 213.2546 | 16227.0346 | 2019-01-24 12:30:00.000 | 7.1875 | 28.4688 | 40.6042 | 44.2917 | 16.2277 | 399.6396
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-479 | 30.8768 | 47.3179 | West Qurna | Horizontal | Sadi | 2019-02-07 01:30:00.000 | Primary Drilling | GW-145 | CONTINUED PERFORMING CEMENT EVALUATION LOG FOR 7" LINER. 13-5/8" BOP PRESSURE TEST. M/U AND RIH 6 1/8" DIRECTIONAL BHA, TAGGED CEMENT AT 2694 M, DRILLED OUT CEMENT AND SHOE, CLEAR RAT HOLE, DRILL 3 M OF NEW FORMATION, CIRCULATED HOLE CLEAN, PERFORMED FIT TEST AT 1.45 SG EMW -OK-. DRILLED 6 1/8" HOLE SECTION THROUGH SADI AT 2746 M. | CONTINUE DRILLING 6 1/8" HOLE SECTION | D9124EEB42B742BA86643AEBA81E8C66 | RIH 6 1/8" DIRECTIONAL BHA ON 4" DP FROM 90 M TO 545 M. - Tripping speed 21.3 stands/hr - No down hole losses | 28.67 |  | 2019-03-07 16:05:03.000 | 433 | 326.9 |  |  |  |  | 2019-03-15 17:00:00.000 | 2019-02-07 01:30:00.000 | 213.2546 | 11548.5568 | 2019-03-09 23:15:00.000 | 13.5938 | 23.6458 | 30.9062 | 36.6458 | 37.0949 | 373.6641
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-481 | 30.877 | 47.3189 | West Qurna | Horizontal | Mishrif | 2019-03-17 00:00:00.000 | Primary Drilling | GW-145 | CONTINUED POOH 6 1/8" CLEAN OUT BHA TO SURFACE AND L/D THE SAME, PERFORMED WIRELINE LOGGING FOR CEMENTING EVALUATION OF 7" LINER, PRESSURE TESTED CASING & 7" PACKER, M/U & RIH 6 1/8" DIRECTIONAL BHA TO 522 M. | RIH 6 1/8" DIRECTIONAL BHA TO BOTTOM, DRILL OUT SHOE TRACK AND 3 M NEW FORMATION, PERFORM FIT AND DRILL 6 1/8" HORIZONTAL HOLE SECTION AS PER PROGRAM. | D9124EEB42B742BA86643AEBA81E8C66 | TDS SERVICE. | 43.84 |  | 2019-04-29 20:09:37.000 | 364 | 327.3 |  |  |  |  | 2019-04-23 11:00:00.000 | 2019-03-17 00:00:00.000 | 228.0184 | 15374.0162 | 2019-04-19 18:30:00.000 | 11.7083 | 25.0521 | 33.7708 | 37.4583 | 31.257 | 455.2454
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-483 | 30.897 | 47.324 | West Qurna | Horizontal | Mishrif | 2019-05-05 00:00:00.000 | Primary Drilling | GW-145 | SPUD WELL WQ1-483 AND DRILLED 17-1/2" HOLE SECTION FROM 70 M TO 830 M | DRILL 17-1/2" SECTION TO TD .CIRCULATE HOLE CLEAN AND PERFORM WIPER TRIP BEFORE POOH. RIH 13-3/8" CSG. | D9124EEB42B742BA86643AEBA81E8C66 | DRILLED 17-1/2" HOLE SECTION FROM 206 M TO 363 M. - FR: 1950-2555 l/min; SPP: 820-1500 psi - WOB: 0-14 MT; RPM: 55-60, Torque: 3-21 kft/lb. - Avg. overall ROP: 52 m/hr, Avg. on bottom ROP: 96 m/hr. - MW in= 1.05 SG; MW out= 1.05 SG. - Wash up & ream down 1 joint every stand drilled. - Pumped Hi Vis every middle of stand. - Survey @ 337.50 m : INC.1.06°; AZM: 221.45°; TVD: 337.48 m. - Formation: DIBDIBBA - No Downhole Losses. | 44.28 |  | 2019-06-18 06:44:05.000 | 364 | 327.3 |  |  |  |  | 2019-05-31 08:00:00.000 | 2019-05-05 00:00:00.000 | 229.6588 | 15675.8535 | 2019-05-28 19:30:00.000 | 4.2708 | 16.5 | 23.8125 | 26.3333 | 16.2184 | 658.3036
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-486 | 30.897 | 47.324 | West Qurna | Horizontal | Mishrif | 2019-06-01 14:30:00.000 | Primary Drilling | GW-145 | P/U & M/U 6-1/8" BHA & RIH TO 1000 M, SLIP & CUT DRILLING LINE. CONT RIH TO 2757 M, DRILLED OUT CEMENT & SHOETRACK TO 2767 M, DRILLED 3 M NEW FORMATION TO 2773 M, PERFORMED FIT AT 1.20 S.G EMW, DRILLED 6-1/8" HORIZONTAL SECTION FROM 2773 M TO 3044 M. | CONTINUE DRILLING 6-1/8" HORIZONTAL SECTION AS PER PLAN | D9124EEB42B742BA86643AEBA81E8C66 | RIH WITH 6 1/8" DIRECTIONAL BHA FROM 1000 M TO 2757 M. - Fill up every 1000 m. - Passed free from 7" TOL @ 1672 m. - No down hole losses. - Washed down last stand | 44.48 |  | 2019-07-15 11:31:27.000 | 364 | 327.3 |  |  |  |  | 2019-06-28 00:00:00.000 | 2019-06-01 14:30:00.000 | 229.6588 | 15649.6068 | 2019-06-24 08:30:00.000 | 2.75 | 14.9896 | 22.75 | 26.3958 | 10.4183 | 687.8948
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-488 | 30.8975 | 47.3248 | West Qurna | Horizontal | Mishrif Horizontal | 2019-07-08 00:00:00.000 | Primary Drilling | GW-145 | RIH USIT -CBL- TRACTOR FOR 7" LINER CEMENT EVALUATION, P/U & M/U 6-1/8" DIRECTIONAL BHA , RIH WITH 6-1/8" DIRECTIONAL BHA , DRILL OUT CEMENT AND FORMATION FROM 3104 M TO 3120 M. | DISPLACE WELL BY FLOPRO 1.05 SG, PERFORM FIT, DRILL 6 1/8" HORIZONTAL SEC. TO 500 M, CIRCULATE HOLE CLEAN FOR WIPER TRIP. | D9124EEB42B742BA86643AEBA81E8C66 | P/U & M/U 6-1/8" DIRECTIONAL BHA AS FOLLOW: - 6-1/8" Used PDC Bit, Type: MDi613, Nozzles= 3*13, S/n: 8208. - PD 75 w/ 6" sleeve stab. - Microscope 475. - Impulse. - ADN with 5-7/8" Stab. | 0 |  | 2019-08-24 15:21:36.000 | 364 | 327.3 |  |  |  |  | 2019-08-03 15:30:00.000 | 2019-07-08 00:00:00.000 | 224.0814 | 16778.2158 | 2019-07-31 22:00:00.000 | 1.3438 | 13.9792 | 23.9167 | 26.6458 | 5.043 | 701.5282
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-490 | 30.897 | 47.325 | West Qurna | Horizontal | Mishrif Horizontal | 2019-08-04 16:00:00.000 | Primary Drilling | GW-145 | ** SPUD WELL WQ1-490 @ 04th August 2019 at 16:00, DRILLED 17.5" HOLE SECTION TO 414M. | CONTINUE DRILLING 17.5" SECTION TO SECTION TD AT 863M. | D9124EEB42B742BA86643AEBA81E8C66 | RIG SERVICE. | 35.02 |  | 2019-09-08 00:29:35.000 | 364 | 327.3 |  |  |  |  | 2019-08-26 00:00:00.000 | 2019-08-04 16:00:00.000 | 229.6588 | 12234.2524 | 2019-08-23 10:00:00.000 | 0.1875 | 11.75 | 18.75 | 21.3333 | 0.87891 | 652.4935
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-492 | 30.897 | 47.325 | West Qurna | Horizontal | Mishrif Horizontal | 2019-09-04 11:00:00.000 | Primary Drilling | GW-145 | CONTINUED RIH WL TOOLS FROM 3360 M TO BOTTOM AT 3427 M, LOGGED UP FROM 3427 M TO 3000 M, POOH WL TOOLS TO SURFACE, R/D WL TOOLS & EQUIPMENT. PERFORMED FULL BOP PRESSTURE TEST. M/U 6 1/8" DIRECTIONAL BHA, RIH TO 2477 M, SLIP & CUT, CONTINUED RIH TO 3427 M, DRILLED OUT SHOE TRACK & RAT AND DRILLED 3 M NEW FORMATION, PERFORMED FIT TO 1.20 SG EMW (OK) AND SERVICED ON TDS IBOP. | CONTINUE DRILLING 6 1/8" HORIZONTAL SECTION TO SECTION TD AT 4176 M | D9124EEB42B742BA86643AEBA81E8C66 | P/U & M/U 6 1/8" DIRECTIONAL BHA FROM SURFACE TO 90 M - 6 1/8" RR PDC Bit (MDi613, S/N: JN 9617) + PD 475 X6 AA, with 6" sleeve CC and ported float valve + PD 475 Receiver (Slick) + IMPulse + ADN4 w/5 7/8" Stabilizer + 1 std 3 1/2" HWDP + 4 3/4" Jar + 1 std 3 1/2" HWDP + XO | 39.24 |  | 2019-10-13 05:48:28.000 | [6 empty] | 2019-10-15 15:30:00.000 | 2019-09-04 11:00:00.000 | 229.6588 | 13700.7878 | 2019-10-13 05:45:00.000 | 15.3542 | 30 | 38.7812 | 41.1875 | 37.2787 | 353.2838
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-493 | 30.897 | 47.325 | West Qurna | Horizontal | Sadi Horizontal | 2019-10-16 13:30:00.000 | Primary Drilling | GW-145 | SPUD THE WELL AT 13:30, DRILLED 17 1/2" SECTION FROM 70 M TO 132 M. | CONTINUE DRILLING 17 1/2" SECTION TO SECTION TD AROUND 881 M, CIRCULATE HOLE CLEAN, POOH 17 1/2" DIR BHA TO SURFACE AND L/D, N/D FLOWLINE & RISER, ROUGH CUT CONDUCTOR, R/U TRS EQUIPMENT & RIH 13 3/8" CASING. | D9124EEB42B742BA86643AEBA81E8C66 | REPAIRED MUD PUMP #2 | 39.04 |  | 2019-11-24 00:57:59.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-10-16 13:30:00.000 | 229.6588 | 3818.8978 | 2019-10-22 00:00:00.000 | 1.7917 | 3.6667 | 5.4375 | 5.4375 | 32.9502 | 702.326
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-472 | 30.8934 | 47.3214 | West Qurna | Horizontal | Development | 2018-07-02 08:00:00.000 | Primary Drilling | SLR-203 | RIH 6-1/8'' Dir BHA, drill out remaining shoe track cement and 3 m of new formation, circulate hole clean, Perform FIT test to 1.2 SG, resume drilling 6-1/8" section to 3072m. | Continue drilling 6 1/8" horizontal section to 3332 m, wiper trip. | D9124EEB42B742BA86643AEBA81E8C66 | Continue RIH 6-1/8'' Dir BHA by 4'' DP to 619 m. - Fill string every 15 stand. - RIH speed 18 stand/hr -Meanwhile pressure test choke manifold offline by 300/3000 PSI for 5/10 min. | 65.96 |  | 2018-09-05 23:02:24.000 | 327.3 | 327.3 |  |  |  |  | 2018-09-15 13:30:00.000 | 2018-07-02 08:00:00.000 | 213.2546 | 16453.4126 | 2018-09-10 16:15:00.000 | 27.6979 | 52.7604 | 70.3438 | 75.2292 | 36.8181 | 233.9001
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-474 | 30.8933 | 47.321 | West Qurna | Horizontal | ERD | 2018-09-15 12:00:00.000 | Primary Drilling | SLR-203 | L/D 5" HWDP. M/U and RIH 6-1/8" Dir BHA up to 3146m. Perform 7" Liner integrity test to 2500 psi. Wash down till tag cement at 3182m. Drill out shoe track cement & shoe to 3193m. Drill out rathole and 3m new formation while displacing hole to 1.05 SG FloPro mud system. | Displace hole to 1.05 SG FloPro mud. FIT to 1.2 SG. Drill 6-1/8" hole (horizontal section). | D9124EEB42B742BA86643AEBA81E8C66 | Change elevator to 3-1/2", prepare tongs to handle 4-3/4" BHA. | 47.54 |  | 2018-11-03 12:57:36.000 | 327 | 327.3 |  |  |  |  | 2018-10-31 18:00:00.000 | 2018-09-17 04:30:00.000 | 246.063 | 17053.8063 | 2018-10-26 12:00:00.000 | 4.8646 | 23.3646 | 41 | 46.25 | 10.518 | 415.9465
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-476 | 30.8933 | 47.321 | West Qurna | Horizontal | ERD | 2018-11-06 15:00:00.000 | Primary Drilling | SLR-203 | S&C drilling line, D/O cement + 3 m new formation, circulate, Performed FIT, Drilled 6-1/8'' Section in Saadi formation from 2627 m to 2685 m. | Drill 6 1/8" horizontal section. | D9124EEB42B742BA86643AEBA81E8C66 | Calibrated depth and hookload weight sensors for DD. | 38.21 |  | 2018-12-14 05:02:24.000 | 327 | 326.9 |  |  |  |  | 2018-12-14 09:30:00.000 | 2018-11-06 15:00:00.000 | 213.2546 | 11190.9452 | 2018-12-01 22:45:00.000 | 4.2083 | 15.7917 | 25.3229 | 37.7708 | 11.1418 | 441.9296
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-478 | 30.893 | 47.321 | West Qurna | Horizontal | Mishrif | 2018-12-15 07:30:00.000 | Primary Drilling | SLR-203 | PERFORM CEMENT EVALUATION LOGGING RUN#2. R/D WIRELINE. RETRIEVED WEAR BUSHING, P/T BOP, INSTALLED WEAR BUSHING. M/U 6 1/8" DIR. BHA TO 840M. | RIH 6-1/8" DIRECTIONAL BHA. P/T LINER TOP PACKER, D/O SHOE TRACK + 3 M NEW FORMATION, FIT, DRILL DIRECTIONAL 6 1/8" SECTION. | D9124EEB42B742BA86643AEBA81E8C66 | PU AND MU 6-1/8 DIRECTIONAL BHA AND RIH TO 99 M: - 3 JTS X 3-1/2" HWDP. - 4-3/4" JAR. - 3 JTS X 3-1/2" HWDP. - XO 3-1/2" IF PIN X XT 39 BOX. | 39.65 |  | 2019-01-23 15:31:39.000 | 367 | 327.3 |  |  |  |  | 2019-01-29 04:15:00.000 | 2018-12-15 07:30:00.000 | 242.7822 | 15387.1396 | 2019-01-25 05:30:00.000 | 9.2708 | 30.4479 | 40.9167 | 44.8646 | 20.664 | 376.0604
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-480 | 30.842 | 47.3186 | West Qurna | Horizontal | Oil Producer | 2019-02-18 15:00:00.000 | Primary Drilling | SLR-203 | RIH 6-1/8'' DIR BHA TO 2599 M, PERFORMED SLIP AND CUT, PRESSURE TEST TBR PACKER WITH 2500 PSI, DRILLED RAT HOLE AND 3 M IN NEW FORMATION, PERFORMED FIT EMW=1.22 SG, DRILL AHEAD 6-1/8'' SECTION TO 3113M. | CONTINUE DRILL SECTION TO TD, PERFORM WIPER TRIP FOR 500 M. | D9124EEB42B742BA86643AEBA81E8C66 | RIH 6-1/8'' DIR BHA WASH DOWN FROM 2650 M TO 2676 m. | 35.56 |  | 2019-03-25 13:28:31.000 | 364 | 327.3 |  |  |  |  | 2019-03-13 13:00:00.000 | 2019-02-18 15:00:00.000 | 223.0971 | 12358.9243 | 2019-03-10 21:15:00.000 | 0 | 12.9681 | 20.2604 | 22.9167 | 0 | 610.0035
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-482 | 30.842 | 47.319 | West Qurna | Horizontal | Oil Producer | 2019-03-14 08:00:00.000 | Primary Drilling | SLR-203 | RIG ACCEPTED AND SPUD WELL WQ1-482 ON DRILLING 17 1/2" SECTION FROM 70 M TO 205 M, POOH and MAKE-UP REST BHA, CONTINUE DRILLING TO 340 M. | CONTINUE DRILLING 17-1/2'' SECTION TO TD, POOH 17-1/2'' DIR BHA, AND RIH 13-3/8'' CASING. | D9124EEB42B742BA86643AEBA81E8C66 | RIG ACCEPTED AND SPUD-IN WQ1-482 ON 14TH MARCH 2019 AT 08:00 HRS. - TAG AT DEPTH 65M, CLEAN OUT TO 73M - DRILLING 17 1/2" SECTION WITH RR PDC Z616 BIT (S.N: JM7733, NOZZLES: 9X12) FROM DEPTH 73M TO 205M WOB 1-4 T, FR 1800-2500 lpm, SPP 300-800psi, 40-60 RPM, Torque 1-5 Kft-lbs, diff press on motor 200-300psi. - KOP at 180m - Mark Top of Dibdiba at 186m MD - Average ROP 22 m/hr, On bottom ROP 31.76 m/hr. - Wash up ream down 1 single each stand. - sweep the hole with 3 rapid sweep each connection. | 45.1 |  | 2019-04-28 02:23:51.000 | 364 | 327.3 |  |  |  |  | 2019-04-07 18:00:00.000 | 2019-03-14 08:00:00.000 | 239.5013 | 15928.4782 | 2019-04-04 22:15:00.000 | 0.66667 | 12.6667 | 21.5938 | 24.4167 | 2.7304 | 737.643
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-484 | 30.842 | 47.319 | West Qurna | Horizontal | Injector | 2019-04-08 09:00:00.000 | Primary Drilling | SLR-203 | RAN THE COMPLETION STRING, R/U SILCK LINE, RAN 3.75'' GAUGE CUTTER ASSEMBLY, RIH WITH 3.813" N-TEST TOOL AND SET SAME ON BAKER XN NIPPLE AND SET THE PACKER AND TEST, N/D BOP AND N/U X-TREE. | INSTALLED TWCV AND TEST THE UPPER MASTER VALVE CONNECTION. | D9124EEB42B742BA86643AEBA81E8C66 | RIH WITH 3.813" N-TEST TOOL AND SET ON BAKER XN NIPPLE. - Kept the running tool latch with NTT. | 45.35 |  | 2019-05-23 08:24:34.000 | 364 | 327.3 |  |  |  |  | 2019-05-06 01:30:00.000 | 2019-04-08 09:00:00.000 | 226.378 | 16131.8903 | 2019-05-02 06:00:00.000 | 1.1354 | 14.2188 | 23.875 | 27.6875 | 4.1008 | 675.6813
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-485 | 30.8 | 47.3 | West Qurna | Horizontal | H4_HZ_M/Ma_BF/UC | 2019-05-06 15:00:00.000 | Primary Drilling | SLR-203 | RIH 4-1/2" UPPER COMPLETION STRING. LAND TBG HANGER. PRESURE TEST BACK SIDE TO 1500 PSI, OK. N/D BOP. N/U X-TREE (ADAPTER FLANGE AND LOWER MASTER VALVE). RIG RELEASED AT 00:00 ON 10th OF JUNE, 2019. | PREPARE FOR RIG MOVE. | D9124EEB42B742BA86643AEBA81E8C66 | FILL ANNULUS WITH 1.0 SG INHIBBITED WATER. PRESSURE TEST ANNULUS AGAINST TIE-BACK SEALS/LINER HANGER PACKER TO 1500 PSI FOR 15 MINTES, OK. | 45.35 |  | 2019-06-20 08:24:34.000 | 364 | 327.3 |  |  |  |  | 2019-06-10 00:00:00.000 | 2019-05-06 15:00:00.000 | 239.5013 | 14547.2446 | 2019-06-06 20:30:00.000 | 9.5521 | 20.0833 | 31.2292 | 34.375 | 27.7879 | 465.8224
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-489 ST1 | 30.84 | 47.3 | West Qurna | Horizontal | H4_MMA_HZ_BFUC | 2019-07-17 03:00:00.000 | Primary Drilling | SLR-203 | P/U, M/U 8-1/2'' BHA, DRILLED OUT SHOE TRACK AND 3 M IN NEW FORMATION, CONDUCTED FIT EMW=1.55 SG, OK, DRILLED 8-1/2'' DIRECTIONAL SECTION TO 2278 M. | DRILL 8-1/2'' SECTION. | D9124EEB42B742BA86643AEBA81E8C66 | P/U AND M/U AND RIH 8-1/2" DIR BHA - 8-1/2" MDi616 PDC BIT (S/N: JN9834) - PD 675 X6 8 3/8" Stab CC - PD 675 E-mag Receiver - 6 3/4" InLineFlex - Periscope 675 - Telescope 675 - 6.75" NMDC - 8 1/4" IB STB - 2 STDS 5" HWDP - 6.5" Jar + 1 STD 5" HWDP - 6 STDS OF 4" HWDP | 47.64 |  | 2019-09-02 15:21:36.000 | 364 | 327.3 |  |  |  |  | 2019-08-11 13:30:00.000 | 2019-07-17 03:00:00.000 | 213.2546 | 11637.1395 | 2019-07-31 11:45:00.000 | 6.9687 | 7.7188 | 14.3646 | 25.4375 | 27.3956 | 810.1272
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-491 | 30.8414 | 47.3187 | West Qurna | Horizontal | JK90.5_sadi_hz-7 | 2019-08-13 19:00:00.000 | Primary Drilling | SLR-203 | R/U CASING RUNNING EQUIPMENT. RIH 9-5/8" CASING TO 2015 M. R/U CEMENT EQUIPMENT. CIRCULATE HOLE CLEAN. PERFORM SINGLE STAGE CEMENT JOB. | R/D CEMENT AND CASING EQUIPMENT. LIFT BOP. SET CASING HANGER. CUT CASING. N/U THS. N/U BOP. PERFORM BOP TEST. | D9124EEB42B742BA86643AEBA81E8C66 | R/U CEMENT HEAD AND CEMENT LINES. | 27.85 |  | 2019-09-09 20:30:08.000 | 433 | 326.9 |  |  |  |  | 2019-09-21 00:00:00.000 | 2019-08-13 19:00:00.000 | 246.063 | 15367.4546 | 2019-09-13 00:30:00.000 | 9.625 | 20.4062 | 30.2292 | 38.2083 | 25.1908 | 508.3651
EH | EME | Iraq | D9124EEB42B742BA86643AEBA81E8C66 |  | 79839 | IDS_IRQ_EXXON IRAQ_30 WELLS_WEST QURNA 1 | IDS | Gulf | LSTK | WQ1-494 | 30.8 | 47.3 | West Qurna | Horizontal | H3_Hz_S_LCUC | 2019-10-12 22:00:00.000 | Primary Drilling | SLR-203 | N/U AND PRESSURE TEST BOP, OK. P/U, M.U AND RIH 12-1/4" DIERCTIONAL BHA FROM SURFACE TO 764 M. WORK ON FLOW LINES PLUGGED WITH CEMENT. | CONTINUE DRILLING 12-1/4" SECTION. | D9124EEB42B742BA86643AEBA81E8C66 | DRILLED 12-1/4" SECTION FROM 840 M TO 849 M. - WOB 3-5 ton, FR: 2350 lpm; SPP: 750-850 psi. 40- 50 rpm; Torque: 3-11 klb.ft. - Avg ROP 18 m/hr. On bottom ROP 30 m/hr. - Wash up and ream down one stand before each connection. Survey after connection. - Pump 2 rapid sweep sticks every stand. - Formation: Dammam. - No down-hole losses. | 36.38 |  | 2019-11-17 09:07:00.000 | 433 | 326.9 |  |  |  |  | 2019-10-22 14:00:00.000 | 2019-10-12 22:00:00.000 | 216.5354 | 6610.8926 | 2019-10-21 21:45:00.000 | 0.88542 | 5.7813 | 8.9896 | 9.6667 | 9.1595 | 735.3948
EH | EME | Iraq | BE3B756B797A4A50AC10D8E67A7A5BA6 |  | 273427 | IDS_KEIL-SIBA-2017-T-083-TurnkeyDrilling | IDS | Gulf | LSTK | Siba - 7 | 30.4026 | 48.1347 | SIBA | Vertical | Development | 2018-03-05 18:00:00.000 | Primary Drilling | ZPEC RIG22 | CONTINUED P/U, MU & RIH 8 1/2" CLEAN OUT BHA FROM 21 M TO 3130 M. REAMED DOWN AND UP FROM 3130 M TO 3190 M. (SET LINER HANGER SECTION). PRECAUTIONARY WASHED DOWN FROM 3190 M TO 3225 M (TOC). DRILLED OUT DV TOOL FROM 3225 M TO 3227 M. | PUMP 5 M3 OF HI VIS AND CIRCULAT BOTTOMS UP. CONTINUE RIH TO FC, DRILL PART OF SHOE TRACK, CIRCULATE HOLE CLEAN. POOH TO SURFACE, PERFORM CBL LOG. | BE3B756B797A4A50AC10D8E67A7A5BA6 | CIRCULATED BOTTOM UP, RECOVERED MUD 1.5 SG ON SURFACE. - FR: 550-1430 LPM, SPP: 850-1540 PSI. - NO DOWNHOLE LOSSES: | 96.87 |  | 2018-07-30 18:00:09.000 | 192 | [5 empty] | 2018-07-30 18:00:00.000 | 2018-03-05 18:00:00.000 | 177.1654 | 13615.486 | 2018-05-13 21:45:00.000 | 58.7188 | 39.3229 | 69.1562 | 147 | 39.9447 | 196.8801
EH | EME | Iraq | BE3B756B797A4A50AC10D8E67A7A5BA6 |  | 273427 | IDS_KEIL-SIBA-2017-T-083-TurnkeyDrilling | IDS | Gulf | LSTK | Siba - 9 | 30.402 | 48.105 | SIBA | Vertical | Development | 2018-08-23 08:00:00.000 | Primary Drilling | ZPEC RIG22 | INSTALLED 13-5/8" 5K X 13-5/8" 10K PACKOFF ADAPTER AND 13-5/8” 10K X 11” 10K CASING HEAD SPOOL, PRESSURE TESTED WELL HEAD, NIPPLED UP AND PRESSURE TESTED 13-5/8".10 K BOP, INSTALLED WEAR BUSHING AND P/U M/U 8 1/2" CLEAN OUT BHA. | RIH WITH CLEAN-OUT BHA, D/O DV, RIH TO TOC, D/O SHOE TRACK TO 3474 M, SWEEP & CIRCULATE HOLE CLEAN, POOH FOR CEMENT EVALUATION LOGS. | BE3B756B797A4A50AC10D8E67A7A5BA6 | P/U, M/U AND RIH 8 1/2" CLEAN OUT BHA TO 134 M. - 8-1/2 USED PDC BIT + BIT SUB + FLOAT SUB + 1 X 6 ½ DC + XO 4 ½ IF PIN TO 4 ½ REG BOX + 9-5/8” ROTATING CASING SCRAPER + XO 4 ½ REG PIN TO 4 ½ IF BOX + 13 X 6 ½” DCS + 6-1/2 JAR | 90.94 |  | 2018-11-17 11:45:00.000 | 192 | [5 empty] | 2018-11-17 12:00:00.000 | 2018-08-23 08:00:00.000 | 177.1654 | 13615.486 | 2018-10-13 12:45:00.000 | 12.5 | 29.6146 | 51.1979 | 86.1667 | 14.5068 | 265.9383
EH | EME | Iraq | BE3B756B797A4A50AC10D8E67A7A5BA6 |  | 273427 | IDS_KEIL-SIBA-2017-T-083-TurnkeyDrilling | IDS | Gulf | LSTK | Siba - 8 | 30.4013 | 48.1153 | SIBA | Vertical | Development | 2018-08-22 03:30:00.000 | Primary Drilling | ZPEC RIG23 | RIH TO 3473 M, DRILL OUT CEMENT AND 3 M OF NEW FORMATION, FIT, AND DRILL 8 1/2" SECTION TO 3636 M. | DRILL 8 1/2" SECTION AS PER PROGRAM. | BE3B756B797A4A50AC10D8E67A7A5BA6 | CIRCULATE TO CONDITION THE MUD 1.40 SG. - FR: 1500 LPM, SPP: 1500 PS - SLIP DRILLING LINE. | 88.74 |  | 2018-12-01 23:58:59.000 | 192 | [5 empty] | 2018-12-02 06:00:00.000 | 2018-08-22 03:30:00.000 | 0 | 13566.2734 | 2018-10-22 02:30:00.000 | 30.8854 | 38.9479 | 60.9583 | 102.1042 | 30.2489 | 222.5499
EH | EME | Iraq | BE3B756B797A4A50AC10D8E67A7A5BA6 |  | 273427 | IDS_KEIL-SIBA-2017-T-083-TurnkeyDrilling | IDS | Gulf | LSTK | Siba-05B | 30.4069 | 48.1247 | SIBA | Vertical | Development | 2018-03-10 18:00:00.000 | Primary Drilling | ZPEC RIG23 | CONTINUED RIH W/ CLEAN OUT BHA TO DV, DRILL OUT DV, RECIPROCATE THROUGH DV OK, RIH TO TOC, D/O SHOE TRACK FROM 3410 M TO 3443 M, IN PROGRESS . | CONTINUED DRILL OUT SHOE TRACK TO 3455 M, CIRCULATE HOLE CLEAN, POOH FOR WL, PERFORM CASED HOLE WIRE LOG. | BE3B756B797A4A50AC10D8E67A7A5BA6 | PERFORMED TRIP DRILL, WELL SECURED IN 2 MIN. | 82.99 |  | 2018-05-28 13:14:58.000 | 192 | [5 empty] | 2018-07-30 15:00:00.000 | 2018-03-10 18:00:00.000 | 167.3228 | 13546.5884 | 2018-05-14 17:15:00.000 | 56.3021 | 40.0625 | 64.9688 | 141.875 | 39.6843 | 208.5093
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-007-09-206 | 25.86 | 71.5814 | ABH | Horizontal |  | 2018-06-03 01:45:00.000 | Primary Drilling | Quippo-2 | D/O Shoe Track, Drilled 4 m of new formation from 1340m to 1344m. Performed FIT. Continue drilling 6-1/8" section from 1344m to 1390m | Drill ahead 6-1/8" section. to 2200m | C55259857E34473CB05F79C71FC66C90 | Waiting for decision. - Meanwhile monitored the well in Trip Tank | 20.42 | 20.8 | 2018-06-23 09:58:04.000 | 575.656 | 689.29 |  |  |  |  | 2018-07-11 21:00:00.000 | 2018-06-03 01:45:00.000 | 101.706 | 8628.6092 | 2018-07-01 19:00:00.000 | 7.6667 | 20.0521 | 28.7188 | 38.8021 | 19.7584 | 300.4521
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-009-09-204 | 25.51 | 71.34 | ABH | Horizontal |  | 2018-07-20 07:30:00.000 | Primary Drilling | Quippo-2 | Picked up & R/back 9 Stands 3.5" HWDP. Change Saver sub to 3.5" IF. Conducted BOP test (Variable & Annular against 3.5" DP). RIH with 6 1/8" Drilling BHA. | RIH with 6 1/8" Drilling BHA, Drill out shoe track. Perform FIT. Drill out 6 1/8" Hole to TD. | C55259857E34473CB05F79C71FC66C90 | -Surface tested PD, at 200 GPM/500 psi pressure. | 18.91 |  | 2018-08-07 21:54:49.000 | 593.934 | 689.29 |  |  |  |  | 2018-08-26 19:00:00.000 | 2018-07-20 04:00:00.000 | 98.4252 | 7217.848 | 2018-08-15 20:00:00.000 | 11.125 | 20.1458 | 26.5208 | 37.4792 | 29.6832 | 272.1577
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-011-09-205 | 25.8647 | 71.581 | ABH | Horizontal | Development | 2018-09-01 15:30:00.000 | Primary Drilling | Quippo-2 | Slipped 9m of drill line. Further RIH and tagged cement@1391m. Drilled cement FC , FS , Rat Hole to 1318m. Drilled fresh formation to 1323m. C&C mud/hole. Performed LOT. Drilled to 6-1/8" directional horizontal hole to 1427m. | Drill and survey 6-1/8" directional horizontal hole to well TD. | C55259857E34473CB05F79C71FC66C90 | - POOH with 1 single of DP from 1323m to 1312m, inside shoe. - Connected circulating head and presure tested cement line with low of 500psi/5min and high of 2000psi/10min - OK. - Performed LOT. LOT pressure 591 psi , EMW 13.24 ppg. TVD@shoe 1036.16m , MudWt = 9.9ppg. - B/Off circulating head. | 34.26 |  | 2018-10-05 06:16:34.000 | 555.016 | 689.29 |  |  |  |  | 2018-12-24 00:00:00.000 | 2018-09-01 06:00:00.000 | 0 | 8136.4832 | 2018-09-24 03:00:00.000 | 10.6771 | 14.8958 | 22.4792 | 113.3542 | 9.4192 | 361.9566
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-015-09-203 | 25.865 | 71.58 | ABH | Horizontal | Development | 2018-10-13 12:00:00.000 | Primary Drilling | Quippo-2 | RIH to Top of Float collar, Drilled out shoe track & 3 m new formation. Peformed LOT, surafec pressure 1700, EMW-18.31 ppg. Drill out 6-1/8" hole to 1368 m. PD failed. POOH to change directional tools. | POOH & Change directional tools. RIH to Bottom, Drill out 6-1/8" hole to TD, 2800 m +/-. | C55259857E34473CB05F79C71FC66C90 | Performed Kick drill. -Close BOP. -Installed FOSV in Open position, Close FOSV. -Response time:4 min. -Opened BOP -Opened FOSV & removed. | 21.94 | 21.94 | 2018-11-03 22:32:32.000 | 600.837 | 689.29 |  |  |  |  | 2018-11-03 06:00:00.000 | 2018-10-13 12:00:00.000 | 82.021 | 6512.4674 | 2018-10-28 04:15:00.000 | 2.1458 | 9.6354 | 14.6771 | 20.75 | 10.3414 | 443.7167
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-019-09-212 | 25.51 | 71.34 | ABH | Horizontal | Development | 2018-11-20 02:00:00.000 | Primary Drilling | Quippo-2 | Set 7" pack-off seal assembly. Performed maintenance on VFD. P/Up 6-1/8" drilling BHA. | RIH with 6-1/8" drilling assy to bottom, drill shoe track. Perform LOT & drill to TD. | C55259857E34473CB05F79C71FC66C90 | - PJSM prior of RIH with 6-1/8" directional BHA. - P/U and M/U 6-1/8" Bit with DD BHA. *Waiting for Grabber's dies from Quippo-39. | 21.07 | 13.86 | 2018-12-11 01:35:31.000 | 596.75 | 689.29 |  |  |  |  | 2018-12-14 07:00:00.000 | 2018-11-20 02:00:00.000 | 101.706 | 8727.0344 | 2018-12-06 14:45:00.000 | 4.9479 | 10.7188 | 16.5312 | 24.2083 | 20.4389 | 527.9113
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-026-06-110 | 25.8869 | 71.56 | ABH | Horizontal |  | 2019-01-10 16:30:00.000 | Primary Drilling | Quippo-2 | RIH WITH 6-1/8" DIRECTIONAL ASSEMBLY TO TAG CEMENT TOP @1268.5 M. DRILL SHOE TRACK TO 1292 M AND FRESH FORMATION TO 1297 M. CONDUCTED LOT. DRILLED AND SURVEYED 6-1/8" SECTION TO @1497 M. | CONTINUE TO DRILL AND SURVEY 6-1/8" SECTION TO WELL TD @2800 M. | C55259857E34473CB05F79C71FC66C90 | P/UP AND M/UP 6-1/8" DIRECTIONAL BHA. LOADED RA SOURCE IN MWD TOOL. * Dull Grading of Bit (IN) : 0 - 1 - WT - G - X - I - NO - TD | 22.04 | 14.44 | 2019-02-01 01:04:09.000 | 396 | 689.29 |  |  |  |  | 2019-03-04 06:00:00.000 | 2019-01-10 16:30:00.000 | 101.706 | 7742.7824 | 2019-02-25 09:30:00.000 | 0.85417 | 4.2396 | 45.7083 | 52.5625 | 1.625 | 169.3954
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-028-06-103 | 25.887 | 71.569 | ABH | Horizontal |  | 2019-01-19 05:30:00.000 | Primary Drilling | Quippo-2 | R/BK STANDS OF 4" DP, 3.5" HWDP & 4-3/4" DC. P/Up & RIH WITH 6-1/8" DRILLING ASSY. DRILLED SHOE TRACK. | DRILL 6-1/8" HOLE TO TD. | C55259857E34473CB05F79C71FC66C90 | RIH 6.125" BHA ON 3.5" DP TO 900 M. -RIH 6.125" BHA on 3.5" DP single by single. -All the Joints were drifted with 1.95 inch drift during picking up. -Flushed with water & Air prior to Pick up. -M/Up TQ for 3.5"" DP 13000 ft.lb. -Filled sting at every 15 joints. -P/U & M/U- 15 joints/hr. | 21.72 | 14.41 | 2019-02-09 17:12:36.000 | 396 | 689.29 |  |  |  |  | 2019-02-04 01:45:00.000 | 2019-01-19 05:30:00.000 | 111.5486 | 7739.5016 | 2019-01-30 06:15:00.000 | 2.3021 | 7.3542 | 11.0312 | 15.8438 | 14.5299 | 701.5979
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-032-04-212 | 25.92 | 71.57 | ABH | Horizontal |  | 2019-04-11 04:00:00.000 | Primary Drilling | Quippo-2 | RIH 7" CASING TO 1181 M. LANDED. PERFORMED CEMENT JOB, BUMPED PLUG. PRESSURE TESTED CASING TO 4500 PSI-15 MIN. INSTALLED PACK-OFF & TESTED. P/U AND M/UP 6" BHA AND RIH TO 1156 M.DRILLED SHOE TRACK , RAT HOLE , 3 M FRESH FORMATION TO 1188 M. | DRILL 6" HOLE TO TD. | C55259857E34473CB05F79C71FC66C90 | RIH WITH 6" BHA ON 3.5" DP TO 1122 M. | 18.62 | 14.6 | 2019-05-01 00:54:00.000 | 396 | [5 empty] | 2019-07-11 00:00:00.000 | 2019-04-11 04:00:00.000 | 0 | 6233.596 | 2019-07-05 22:45:00.000 | 0 | 3.5625 | 85.7812 | 90.8333 | 0 | 72.6685
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-033-04-210 | 25.923 | 71.574 | ABH | Horizontal |  | 2019-04-15 11:00:00.000 | Primary Drilling | Quippo-2 | DRILLED 6" DIRECTIONAL HOLE FROM 1438 M TO 1913 M. | WORK ON STRING TO CLEAR PACK OFF. DRILL 6" HOLE TO WELL TD +/- 2223 M. C & C MUD. POOH WITH 6" BIT. | C55259857E34473CB05F79C71FC66C90 | DRILLED 6" DIRECTIONAL HOLE FROM 1438 M TO 1550 M. - Drilled at controlled ROP of 20-35 m/hr for build up with DLS of 4 deg till 1505m. - Drilling Parameters: FR = 230-235 gpm, SPP = 2100-2200 psi, WOB =8-14 klbs, RPM=120 ; TQ (off/on-btm) =2/4 Kft.lb. -P/up-85 klbs, S/O-65 klbs, R/W-73 klbs. -Avg-ROP- 25 m/hr, Avg-ROP (On-Btm)-30-40 m/hr. -Wash Up/Ream Down one single in every stand drilled. -M.Wt (in/Out)-9.6/9.6 ppg, ECD - 10.7-10.75 ppg. -Formation: Barmer Hill -Lithology: - Siltstone - 100%. - CT-CT : 6.29 M ; 6.27 M RT ; 0.47 M ABV. | 21.9 | 14.41 | 2019-04-30 14:13:00.000 | 396 | [5 empty] | 2019-06-29 07:00:00.000 | 2019-04-15 11:00:00.000 | 108.2677 | 6532.1524 | 2019-06-24 04:45:00.000 | 2.5417 | 4.8646 | 69.7396 | 74.8333 | 3.3964 | 93.6649
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-034-04-209 | 25.9261 | 71.5738 | ABH | Horizontal | Development | 2019-04-18 05:15:00.000 | Primary Drilling | Quippo-2 | RIH WITH 8.5" DRILLING BHA TO 602 M, DRILLING SHOE TRACK. | DRILLED 8.5" HOLE TO TD. CIRCULATED HOLE CLEAN. PERFORMED DROP GYRO . POOH TO SURFACE. | C55259857E34473CB05F79C71FC66C90 | PJSM, M/U & RIH WITH 8.5" DRILLING BHA TO 37.34 M. -M/U 8.5" PDC Bit (MDI519LBPX/JP 4476) with PD. -M/U Direction tools single by single & RIH to 37.34 m. | 18.08 | 14.41 | 2019-05-06 01:49:39.000 | 396 | [5 empty] | 2019-06-17 01:30:00.000 | 2019-04-18 05:15:00.000 | 0 | 6505.9057 | 2019-06-10 13:30:00.000 | 3.6875 | 3.0104 | 53.3438 | 59.8438 | 6.1619 | 121.9619
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-035-04-203 | 25.9232 | 71.5739 | ABH | Horizontal | Development | 2019-04-24 20:15:00.000 | Primary Drilling | Quippo-2 | RIH WITH 8.5" DRILLING BHA TO 569 M, DRILLED SHOE TRACK. | DRILLED 8.5" HOLE TO TD. CIRCULATED HOLE CLEAN. PERFORMED DROP GYRO . POOH TO SURFACE. | C55259857E34473CB05F79C71FC66C90 | WASHED DOWN FROM 531 M TO 569 M & TAGGED FLOAT COLLAR. -FR:250 gpm, SPP-1050-1100 psi, RPM 20-40, -Tagged Float Collar at 569 m with 5 klbs. Confirmed Float Collar at 569 m by tagging (with pumps) twice. | 20.11 | 13.46 | 2019-05-09 03:23:20.000 | 396 | [5 empty] | 2019-06-03 16:30:00.000 | 2019-04-24 20:15:00.000 | 111.5486 | 6348.4254 | 2019-05-29 07:15:00.000 | 3.1771 | 4.5521 | 34.4583 | 39.8438 | 7.9739 | 184.2348
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-037-04-202 | 25.923 | 71.574 | ABH | Horizontal | Development | 2019-04-27 12:15:00.000 | Primary Drilling | Quippo-2 | PERFORMED USIT-CBL-VDL LOGS AND R/D WIRELINE TOOLS.WAITING ON TUBING ANCHOR FOR UPPER COMPLETION MEANWHILE P/U AND M/U 4" DP, 3-1/2" DP STAND & L/D 5" DP. PRESSURE TESTED LOWER COMPLETION TO 3000 PSI/15 MIN. | M/A FOR AND RIH WITH 4-1/2" UPPER COMPLETION. DISPLACE WELL WITH WATER AND PERFORM INFLOW TEST. DISPLACE WELL WITH BRINE. STRING IN , LAND 4-1/2" TUBING HANGER , TEST STRING. INSTALL TWCV. RELEASE RIG. | C55259857E34473CB05F79C71FC66C90 | WAITING ON TUBING ANCHOR FOR UPPER COMPLETION. -Meanwhile P/U & M/U 4" DP (14#, S-135) stands- 3 stands. -All the Joints were drifted with 2.3 inch drift during picking up. -Flushed with water prior to Pick up. -M/Up TQ for 4" DP 19000 ft.lb -Total 4" stands in Derrick- 45. | 13.08 | 9.31 | 2019-05-12 20:42:36.000 | 396 |  | 20190520101001 |  |  |  | 2019-05-21 13:00:00.000 | 2019-04-27 12:15:00.000 | 111.5486 | 4022.3098 | 2019-05-17 08:00:00.000 | 3.6771 | 5.4583 | 19.8229 | 24.0312 | 15.3013 | 202.9121
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-038-04-201 | 25.923 | 71.574 | ABH | Build & Hold |  | 2019-05-01 20:00:00.000 | Primary Drilling | Quippo-2 | P/UP AND M/UP TUBULAR FOR 4-1/2” LINER RUN . P/UP, M/UP AND RIH 6” DD BHA TO 26 M. FURTHER RIH 6” DD BHA ON 4-3/4” DC AND 4” DP TO TAG FC AT 992 M. DRILLED FC , CEMENT , SHOE AND RAT HOLE TO 1022 M. DRILLED FRESH FORMATION TO 1025 M, C&C MUD. PERFORMED LOT , EMW = 15.51 PPG. DRILLED 6” HOLE TO 1084 M. | DRILL 6” HOLE TO WELL TD +/- 1310 M. C&C MUD/HOLE. POOH WITH 6” AND AND L/D. P/UP , M/UP AND RIH WITH 4-1/2” LINER TO BOTTOM. | C55259857E34473CB05F79C71FC66C90 | DRILLED 3 M OF FRESH FORMATION FROM 1022 M TO 1025 M , C&C HOLE/MUD FOR LOT. - FR - 210 GPM ; SPP = 1560-1700psi | 13.08 | 9.31 | 2019-05-14 00:00:00.000 | 396 | [5 empty] | 2019-05-12 16:00:00.000 | 2019-05-01 20:00:00.000 | 109.9081 | 4166.6668 | 2019-05-09 13:15:00.000 | 0.91667 | 5.6146 | 7.7188 | 10.8333 | 8.4615 | 539.8111
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-039-05-201 | 25.897 | 71.578 | ABH | Horizontal | Horizontal | 2019-05-17 12:00:00.000 | Primary Drilling | Quippo-2 | RIH WITH 7" 29 PPF L80 13 CR CASING TO 1193M. R/UP CEMENT HEAD , C & C HOLE. CARRIED OUT CEMENT JOB. SET 7" PACK OFF. M/UP 4" DP STAND. | RIH WITH 6" BIT TO TAG FLOAT COLLAR. DRILL SHOE TRACK AND 3 M FRESH FORMATION. PERFORM LOT. DRILL 6" SECTION TO WELL TD +/- 2450 M. | C55259857E34473CB05F79C71FC66C90 | M/A , P/UP , R/B 4" DP STANDS - 2 STANDS. | 19.74 | 12.68 | 2019-06-07 23:00:00.000 | 396 | [5 empty] | 2019-08-06 06:00:00.000 | 2019-05-17 12:00:00.000 | 101.706 | 8038.058 | 2019-07-27 22:00:00.000 | 7.3646 | 7.4479 | 71.4167 | 80.75 | 9.1202 | 112.5516
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-040-05-202 | 25.89 | 71.578 | ABH | Horizontal |  | 2019-05-23 00:00:00.000 | Primary Drilling | Quippo-2 | RIH UPPER COMPLETION. STING IN TO LOWER COMPLETION, PRESSURE TESTED ANNULUS TO 1000 PSI/15 MIN-OK.DISPLACE WELL WITH WATER. PERFORMED INFLOW TEST. DISPLACE WELL WITH BRINE. PRESSURE TESTED COMPLETION ASSEMBLY AS PER PROGRAM. INSTALL TWCV, PRESSURE TESTED TO 3000 PSI/15 MIN. RELEASED THE RIG FOR SKID TO SLOT 203. | SKID TO SLOT 203. SPUD ABH-042-05-203. | C55259857E34473CB05F79C71FC66C90 | JET WASHED WELLHEAD PROFILE AND BOP CAVITY. -M/U jet wash tool & jet washed tubing hanger area. -Flowrate: 155 GPM , SPP 482 PSI. -Reciprocate string inside BOP till well head profile. -Flushed side out let valves. -POOH, Laid down the same after jet washing. | 19.95 | 13.05 | 2019-06-14 10:12:27.000 | 396 | [5 empty] | 2019-08-17 22:15:00.000 | 2019-08-01 20:45:00.000 | 1570.21 | 7844.4884 | 2019-08-12 12:15:00.000 | 1.6146 | 2.5104 | 81.5104 | 86.9271 | 1.8574 | 96.2391
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-042-05-203 | 25.8977 | 71.5783 | ABH | Horizontal | Horizontal | 2019-05-26 09:30:00.000 | Primary Drilling | Quippo-2 | RIH WITH 7" 29 PPF L80 13 CR CASING TO BTM, CEMENTED AS PER PROG. SET 7" PACK OFF. P/U , M/U 6" DRILLING BHA. RIH TO 518 M. | DRILL 6" HOLE TO TD. | C55259857E34473CB05F79C71FC66C90 | PJSM PRIOR TO P/UP 6" DRILLING BHA. | 20.93 | 13.66 | 2019-06-14 22:15:00.000 | 396 | [5 empty] | 2019-09-01 00:00:00.000 | 2019-08-19 12:30:00.000 | 1707.6772 | 8241.4701 | 2019-08-27 05:30:00.000 | 1.5104 | 3.8438 | 92.8333 | 97.6042 | 1.5475 | 88.7771
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-012-03-111 | 25.88 | 71.58 | ABH | Horizontal |  | 2018-09-26 04:00:00.000 | Primary Drilling | Quippo-38 | Started P/O 5" DP for wiper trip, POOH rom 586m to 450m. Observed T/Pull at 556m - 10Klbs; 545m - 15Klbs; 529m - 10Klbs; 486m - 10klbs. Cleared the same with reciprocation. P/O 5" DP from 450m to 393m. Observed T/PULL between 414m to 395m. Couldn't be cleared by reciprocation. Connected TDS and cleared it. POOH up to 89m and RIH from 89 to 567m, Observed H/UP at 427m - 10Klbs; 432m - 10Klbs; 446m - 10Klbs. Reamed down to clear the tight spot. Reached bottom, pumped 35bbls of high visc pill, flow check and POOH up to surface. R/U WFD casing handling too. Performed dummy run with landing joint and casing hanger with stick up 0.72m. | Run 9 5/8" Casing till bottom followed by cementing job. B/O, POOH & L/D landing joint. WOC. N/D Divertor. | C55259857E34473CB05F79C71FC66C90 | Continue POOH 5" DP up to 89m. No T/Pull observed during this interval. | 19.9 | 13.43 | 2018-10-15 21:41:59.000 | 396 | 689.29 |  |  |  |  | 2019-01-19 15:00:00.000 | 2018-09-26 04:00:00.000 | 88.56 | 7975.722 | 2018-12-03 22:30:00.000 | 11.3021 | 16.7604 | 68.7708 | 115.4583 | 9.7889 | 115.9754
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-013-03-106 | 25.8803 | 71.5808 | ABH | Horizontal | Development | 2018-10-07 06:00:00.000 | Primary Drilling | Quippo-38 | Spud the well ABH 113-03-106, D/dn from 28 to 59m, Observed flow line chocked. Cleaned, modified and installed it back. Continue drilling, D/dn from 59m to 117m. | Drill 12 1/4" surface section to TD, clean until shakers clean. POOH and L/D BHA. | C55259857E34473CB05F79C71FC66C90 | Conduct Pre Spud meeting. Spud the well ABH-013-03-106 at 06:00 Hrs, on 07th Oct 2018. Tagged bottom at 28m and drilled 12.25" phase from 28m to 59m MD. * Parameters: WOB 5-10Klbs, RPM 40-60, Flow 400-500 GPM, SPP on Bottom 350psi, SPP off bottom 330psi, Avg Rop: 10m/hr, P/Up 40klbs, S/Off 40Klbs, Rot 40Klbs, Off bottom torque 1-1.5kftlbs, On bottom torque 2-3Klbs. *Formation: 10% Clay, 40% Sandstone, 50% Limestone. | 21.84 | 14.4 | 2018-10-28 20:09:01.000 | 396 | 689.29 |  |  |  |  | 2018-10-11 02:00:00.000 | 2018-10-07 06:00:00.000 | 91.8635 | 1893.0447 | 2018-10-09 12:30:00.000 | 0.36458 | 0.52083 | 2.2708 | 3.8333 | 9.5109 | 833.6344
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-014-03-107 | 25.8803 | 71.5809 | ABH | Deviated |  | 2018-10-12 10:30:00.000 | Primary Drilling | Quippo-38 | Drilled 6 1/8" DIRECTIONAL HOLE FROM 1235M TO 1654M. | CONTINUE DRILLING AHEAD AS PER DIRECTIONAL PLAN UP TO SECTION TARGET DEPTH. | C55259857E34473CB05F79C71FC66C90 | DRILLED 6 1/8" DIRECTIONAL HOLE FROM 1297M TO 1320M. Drilling Parameters: * FR 230 gpm, SRPM 90, WOB 16-20 klbs; SPP 2020 psi, TRQ OFF/ON Bottom 2.0/4.5 klbs*ft, P/U 122 klbs, S/O 86 klbs, R/O 107 klbs. * Instantaneous ROP: 22 m/hr. Average ROP: 18.4 m/hr. * ECD: 10.2 ppg. * Formation: Barmer Hill-6. * Lithology: 100% Siltstone. Note:- Drilled with controlled ROP as per well placement team, maximum 25m/hr. | 13.05 | 13.05 | 2018-10-25 01:05:50.000 |  | 689.29 |  |  |  |  | 2018-12-23 09:30:00.000 | 2018-10-12 10:30:00.000 | 101.706 | 7998.6879 | 2018-12-16 22:45:00.000 | 1.3854 | 5.0313 | 65.5104 | 71.9583 | 1.9253 | 122.098
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-017-03-101 | 25.8802 | 71.58 | ABH | Horizontal |  | 2018-10-18 23:00:00.000 | Primary Drilling | Quippo-38 | RIH 6 1/8" DIR BHA. TAG FC & PERFORM DRILL LINE SLIP & CUT. DRILL OUT TOP PLUG, BOTTOM PLUG, FLOAT SHOE, SHOE TRACK CEMENT & FLOAT SHOE. DRILL 3 M FRESH FORMATION TO 1487 M. CONDUCT LOT-EMW= 14.29 PPG. DRILL 6 1/8" DIR HOLE TO 1655 M. | DRILL 6 1/8" DIR HOLE TO SECTION TD. | C55259857E34473CB05F79C71FC66C90 | STRING FILL UP & CHECKED FOR MWD COMMUNICATION SIGNAL * M/U TDS to 3 1/2" DP stand and filled up string. * MWD signal test-OK. | 19.3 |  | 2018-11-06 07:04:59.000 | 396 | 689.29 |  |  |  |  | 2019-01-16 03:45:00.000 | 2018-10-18 23:00:00.000 | 101.706 | 7824.8034 | 2019-01-06 19:30:00.000 | 5.7083 | 10.0833 | 79.8542 | 89.1979 | 6.3996 | 97.9887
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-029-08-113 |  |  | ABH | Horizontal | Development | 2019-02-13 19:30:00.000 | Primary Drilling | Quippo-38 | RIH 6.125" DIR BHA AND TAG FC AT 1198 M. DRILL PLUGS, COLLAR, SHOE TRACK, RAT HOLE, 3 M NEW FORMATION AND PERFORM LOT. DRILL 6.125" DIR HOLE TO 1350 M. | DRILL 6.125" DIR HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | LOAD RA SOURCE INTO LWD TOOL | 21.72 | 14.41 | 2019-03-06 17:12:36.000 | 396 | 689.29 |  |  |  |  | 2019-04-14 18:00:00.000 | 2019-02-13 19:15:00.000 | 98.4252 | 7545.932 | 2019-04-08 02:15:00.000 | 7.7708 | 10.8021 | 53.2812 | 59.9375 | 12.9649 | 141.6245
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-030-08-112 |  |  | ABH | Horizontal | Development | 2019-02-17 00:00:00.000 | Primary Drilling | Quippo-38 | RIH 6 1/8" DIR BHA TO THE TOP OF FC DEPTH. DRILL SHOE TRACK AND 3 M FRESH FORMATION. CONDUCTED LOT. DRILLED 6 1/8"SECTION UP TO 1470 M. | DRILL 6 1/8" DIR HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | DRILLED 6 1/8" DIRECTIONAL HOLE FROM 1421 M TO 1470 M. * Parameters: WOB: 20-24 klbs, RPM: 90, Flow: 220 gpm, SPP: 2050 psi, Onbottom torque: 9 klbs-ft, Off -bottom torque: 6 klbs-ft. P/Up :- 132 klbs , Rot :- 98 Klbs , S/Off 75 klbs, MW: 9.4 ppg. * Inst ROP 29.8 m/hr; Avg ROP 12.5 m/hr. * ECD 10.14 ppg. * Total Bit drilling hrs - 5.5 * Last survey: 1443.69 m, Incl 79.97 deg, Azim 99.73 deg * Ct-Ct distance: 22 m ( Geo steering as per WSG ) * Formation:- Barmer Hill, Lithology :- 100 % Siltstone. * No Cavings & no down hole losses observed during drilling. Note:- Drilling with controlled ROP as per DD instructions. | 21.79 | 14.41 | 2019-03-10 18:51:36.000 | 396 | 689.29 |  |  |  |  | 2019-03-24 10:30:00.000 | 2019-02-17 00:00:00.000 | 104.9869 | 6528.8716 | 2019-03-19 12:00:00.000 | 2.6354 | 6.0417 | 30.5 | 35.4375 | 7.4368 | 214.0614
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-031-08-110 |  |  | ABH | Horizontal | Development | 2019-02-20 19:00:00.000 | Primary Drilling | Quippo-38 | RIH 6 1/8" DIR BHA TO THE TOP OF FC DEPTH. DRILL SHOE TRACK AND 3 M FRESH FORMATION. CONDUCTED LOT. DRILLED 6 1/8"SECTION UP TO 1469 M. | DRILL 6 1/8" DIR HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | DRILLED 3 M OF FORMATION FROM 1213 M TO 1216 M FOR THE LOT. * Parameters: WOB: 18-20 klbs, RPM: 80, Flow: 220 gpm, SPP: 1800 psi,Torque: 4 klbs-ft. * Made 3 passes through shoe then pulled 6 1/8" bit inside 7" casing | 21.83 | 14.41 | 2019-03-13 19:52:48.000 | 396 | 689.29 |  |  |  |  | 2019-03-08 09:30:00.000 | 2019-02-20 18:00:00.000 | 98.4252 | 7677.1656 | 2019-03-02 20:30:00.000 | 0.16667 | 5.7604 | 10.0625 | 15.6042 | 1.0681 | 762.9481
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-036-08-201 | 25.9052 | 71.5694 | ABH | Horizontal | Development | 2019-04-26 01:00:00.000 | Primary Drilling | Quippo-38 | DRILLED OUT PLUGS, COLLAR, SHOE TRACK, RAT HOLE, 3 M NEW FORMATION AND PERFORMED LOT. DRILLED 6.125" DIR HOLE TO 1414 M. | DRILL 6.125" DIR HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | WASH DOWN AND TAG BOTTOM AT 1064 M. DRILLED OUT SHOE TRACK & RAT HOLE UP TO 1092 M * Downlink to RSS prior to drilling. * Drilled out top plug, bottom plug and float collar. * Drilled out shoe track cement and shoe. * Flowrate: 200 gpm, RPM: 40, WOB: 9 klbs, SPP: 1660 psi, TRQ Off/On bottom: 3/4 klbs-ft | 21.82 | 14.21 | 2019-05-20 00:02:26.000 | 396 | [5 empty] | 2019-05-15 07:30:00.000 | 2019-04-26 00:45:00.000 | 104.9869 | 8103.6748 | 2019-05-09 12:45:00.000 | 2.8958 | 8.5417 | 13.4896 | 19.2708 | 15.027 | 600.7357
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-041-02-112 |  |  | ABH | Horizontal | Development | 2019-05-24 22:00:00.000 | Primary Drilling | Quippo-38 | CIRCULATED PRIOR TO LOT. PERFORMED LOT. DRILLED 6" DIR HOLE FROM 1413 M TO 1792 M. | DRILL 6" HOLE TO SECTION TD ( APPROX 2707 M). | C55259857E34473CB05F79C71FC66C90 | DRILLED 6" DIR HOLE FROM 1581 M TO 1690 M * Flowrate: 230 gpm, SPP: 2310 psi, SRPM: 90, WOB: 15 klbs, P/U 80 klbs S/O 45 klbs R/O 62 klbs TRQ Off/On 4/8 klb-ft * Instantaneous ROP: 31.76 m/hr, Average ROP: 18.17 m/hr * ECD 10.86 ppg. * Formation: Barmer Hill-12 * Lithology: 100% siltstone * No cavings & down hole losses observed during drilling. | 22.02 | 14.1 | 2019-06-12 13:00:00.000 | 396 | [5 empty] | 2019-08-10 11:00:00.000 | 2019-05-24 22:00:00.000 | 98.4252 | 8645.0134 | 2019-08-04 13:00:00.000 | 3.0729 | 6.6146 | 71.625 | 77.5417 | 3.9629 | 120.6983
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-044-02-111 |  |  | ABH | Horizontal | Development | 2019-05-30 03:30:00.000 | Primary Drilling | Quippo-38 | DRILLED 6" DIR HOLE FROM 1758 M TO 2096 M. OBSERVED LOSSES, PUMPED LCM PILL POOH 6" DIR BHA UP TO 1541 M. | POOH & CURE LOSSES. RIH TO BOTTOM AND DRILL 6" HOLE TO SECTION TD ( APPROX 2596 M). | C55259857E34473CB05F79C71FC66C90 | DRILLED 6" DIR HOLE FROM 1758 M TO 1866 M. * Flowrate: 225 gpm, SPP: 2340 psi, SRPM: 90, WOB: 12 klbs, P/U 90 klbs S/O 46 klbs R/O 66 klbs TRQ Off/On 7/9 klb-ft * Instantaneous ROP: 32.65 m/hr, Average ROP: 18 m/hr * ECD 11.49 ppg. * Formation: Barmer Hill-12 * Lithology: 100% siltstone * No cavings & down hole losses observed during drilling. Note:- * Drilling with controlled ROP as per DD/well placement team instructions. | 21.81 | 13.53 | 2019-06-16 07:30:00.000 | 396 | [5 empty] | 2019-07-25 08:30:00.000 | 2019-05-30 03:30:00.000 | 101.706 | 8100.394 | 2019-07-20 12:00:00.000 | 2.8854 | 6.0833 | 51.3542 | 56.2083 | 5.1334 | 157.7359
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-045-02-104 | 25.896 | 71.565 | ABH | Horizontal | Development | 2019-06-04 17:30:00.000 | Primary Drilling | Quippo-38 | RIH 12.25" DIR BHA UP TO 698.5 M. CIRCULATE & POOH TO SURFACE. RIH 9.625" CSG TO BOTTOM I.E UP TO 698.5 M, CIRCULATE AND CEMENT THE SAME. RIG RELEASED TO ABH 046-02-104 AT 00:00 HRS, 08/6/2019 | PREPARE FOR SPUD AND SPUD THE WELL ABH-046-02-103 AND SKID TO NEXT SLOT#103. | C55259857E34473CB05F79C71FC66C90 | POOH 12.25" DIR BHA FROM 698.5 TO 199 M. * POOH 26 stds of 5" DP up to 199 m. * Observed tight spot at 595 m of 20-25 kips, cleared the same by reciprocation. * Hole kept full of mud during tripping out. " Tripping out speed is 8 stds/hr. | 20.99 | 13.86 | 2019-06-23 05:16:00.000 | 396 |  | 20190607180435 |  |  |  | 2019-07-10 05:15:00.000 | 2019-06-04 17:30:00.000 | 101.706 | 8671.2601 | 2019-07-03 05:30:00.000 | 2.9583 | 5.5 | 28.5 | 35.4896 | 8.3358 | 304.2547
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-046-02-103 | 25.53 | 71.33 | ABH | Horizontal | Development | 2019-06-08 19:30:00.000 | Primary Drilling | Quippo-38 | SPUD THE WELL ABH-046-02-103 AT 19:30 HRS. DRILL 12.25" DIR HOLE FROM 32 TO 71 M | DRILL 12.25" DIR HOLE TO SECTION TD( TO BE CONFIRMED BY WSG). POOH 12.25" DIR BHA, RIH 9.625" CSG TO BOTTOM AND CEMENT. | C55259857E34473CB05F79C71FC66C90 | DRILL 12.25" DIR HOLE FROM 34 TO 71 M. * Drilling Parameters( Controlled parameters to avoid choking of flow line) * Flowrate: 450-460 gpm, SRPM: 40, WOB 3 klbs; SPP: 320 psi, TRQ OFF/ON 1/2 klbs-ft, P/U 45 klbs, S/O 45 klbs, R/O 45 klbs. * Formation: Thumbli. * Instantaneous ROP: 18 m/hr, Average ROP: 13.5 m/hr. * Lithology: 100% clay | 20.48 | 13.23 | 2019-07-10 11:35:57.000 | 396 | [5 empty] | 2019-06-24 16:00:00.000 | 2019-06-08 19:30:00.000 | 104.9869 | 6817.5855 | 2019-06-20 12:00:00.000 | 1.5312 | 7.1875 | 11.6875 | 15.8542 | 9.6583 | 583.3228
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-047-07-212 |  |  | ABH | Horizontal | Development | 2019-08-26 11:00:00.000 | Primary Drilling | Quippo-38 | POOH AND LAY DOWN 6" DIR BHA. R/U WTF TRS. RIH 4.5" LINER ASSEMBLY TO 698 M. | RIH 4.5" LINER WITH HANGER ASSEMBLY TO BOTTOM, SET HANGER AND CEMENT THE SAME. POOH AND LAY DOWN HANGER RUNNING TOOL. | C55259857E34473CB05F79C71FC66C90 | CIRCULATED 3 X BOTTOMS' UP AT 1659 M. * Circulated 3 x BU with full stand rotation and reciprocation Flowrate: 225 gpm, SPP: 2200 psi, SRPM: 90. | 20.08 | 13.43 | 2019-09-15 01:51:30.000 | [6 empty] | 2019-09-14 11:00:00.000 | 2019-08-26 11:00:00.000 | 111.5486 | 7519.6853 | 2019-09-08 16:30:00.000 | 2.1667 | 8.8438 | 13.2292 | 19 | 11.4035 | 568.4172
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-008-07-101 | 25.875 | 71.572 | ABH | Horizontal |  | 2018-07-08 18:00:00.000 | Primary Drilling | Quippo-39 | Changed BOP pipe ram from 5" to 3 1/2". Completed BOP pressure test. P/U and M/Up 6 1/8" PDC bit with RSS & MWD/LWD tools as per BHA. Done SHT at 210GPM & 1280 psi. RIH up to 740m. Performed kick drill. | RIH up to 1170.0m. Wash down and tag top of float collar. Drill shoe track & 3m formation. C&C mud. Carry out LOT/FIT. Drill 6 1/8" section as per plan. | C55259857E34473CB05F79C71FC66C90 | M/up 6 1/8" PDC bit & 4 3/4" PD RSS & MWD/LWD tools. RIH up to 30 m. | 20.27 |  | 2018-08-08 06:28:48.000 | 587.747 | 593.934 |  |  |  |  | 2018-08-12 00:00:00.000 | 2018-07-08 18:00:00.000 | 108.2677 | 8267.7168 | 2018-08-03 06:00:00.000 | 3.3646 | 16.4896 | 25.5 | 34.25 | 9.8236 | 324.2242
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-010-07-112 | 25.875 | 71.5708 | ABH | Horizontal | Development | 2018-08-23 21:00:00.000 | Primary Drilling | Quippo-39 | 12.25in Section TD @ 637m MD, Wipertrip and C&C prior to POOH. | POOH and L/D BHA, R/U casing handling equipments, Run 9-5/8" casing. | C55259857E34473CB05F79C71FC66C90 | RIH from 178 to 619m, Hole free while RIH. Wash down from 619m to 637m. Pumped 25 bbls of high viscus pill and started circulation at Flow: 730 GPM, SPP: 1470 psi, RPM 50. | 22.12 |  | 2018-09-14 02:52:48.000 | 615.16 | 689.29 |  |  |  |  | 2018-09-21 07:00:00.000 | 2018-08-23 21:00:00.000 | 108.2677 | 3868.1104 | 2018-09-01 22:00:00.000 | 20.0938 | 5.4271 | 9.0417 | 28.4167 | 70.7111 | 427.8094
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-010z-07-112 | 25.875 | 71.571 | ABH | Horizontal |  |  | Primary Drilling | Quippo-39 | Continued sidetracking with SDMM BHA from 651.0m to 684.0m. Circulated till shakers clean prior to POOH to change the BHA. POOH. Lay down MWD-Motor BHA. | Pick up & make up PDC bit with RSS. Pick up and make up LWD BHA. Record LWD data in open hole till 684.0m. Resume drilling as per drilling program. | C55259857E34473CB05F79C71FC66C90 | Pick and Make up PDC Bit (SN:- JN5592) with RSS. Pick up and make up pub joint to perform SHT for RSS. | 22.62 |  | 2018-10-13 14:50:28.000 | 593.934 | 689.29 |  |  |  |  | 2018-10-09 12:00:00.000 | 2018-09-21 07:00:00.000 | 2135.8268 | 4986.8768 | 2018-09-26 14:30:00.000 | 12.0208 | 2.3438
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-016-07-110 | 25.875 | 71.5711 | ABH | Horizontal |  | 2018-10-16 21:00:00.000 | Primary Drilling | Quippo-39 | POOH and rack back 57 stands of 3 1/2" DP. Performed BOP test .OK. P/U and M/U 13 stands of 3 1/2" HWDP. P/U and M/U RSS-LWD BHA. Perform SHT. OK. RIH BHA to 370m. | RIH 6 1/8" Directional BHA to bottom. Changeover mud with 9.4 PPG SOBM. Drill float collar. Drill cement , shoe & 3m of new formation. Perform LOT. Drill 6 1/8" section as per plan. | C55259857E34473CB05F79C71FC66C90 | Loaded R/A source in ADN 475 | 19.65 |  | 2018-11-04 15:29:48.000 | 581.532 | 689.29 |  |  |  |  | 2018-11-17 12:00:00.000 | 2018-10-16 21:00:00.000 | 104.9869 | 7775.5908 | 2018-11-10 21:15:00.000 | 4.0104 | 11.1771 | 25.0104 | 31.625 | 12.6812 | 310.8941
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-018-07-109 | 25.8751 | 71.5711 | ABH | Horizontal | Development | 2018-10-22 21:00:00.000 | Primary Drilling | Quippo-39 | RIH 6 1/8' Directional BHA to 1589m TOC, drill FC, show track and 3 m of new formation to 1620m. Perform LOT(Lot pressure 1643 psi,TVD: 1008.68 m,MW: 9.04 ppg, EMW: 18.95 ppg, Pumped: 1.5 bbls, returned: 0.8 bls) Continued drill ahead 6 1/8" hole from 1620m to 1853mMD (1044.5mTVD) | Continue drill ahead 6 1/8" hole from 1620m to TD of the well. | C55259857E34473CB05F79C71FC66C90 | Drilled 3 M of new formation till 1620 m. | 21.83 |  | 2018-11-12 19:56:03.000 | 613.271 | 689.29 |  |  |  |  | 2018-12-02 09:00:00.000 | 2018-10-22 18:00:00.000 | 101.706 | 8316.9294 | 2018-11-26 19:00:00.000 | 1.5312 | 7.5417 | 34.9167 | 40.5 | 3.7809 | 238.1937
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-020-01-207 |  |  | ABH | Horizontal | Development | 2018-12-14 08:30:00.000 | Primary Drilling | Quippo-39 | RIH. DRILL 7" CSG SHOE TRACK. CIRCULATE. LOT. DRILL 6-1/8" DIRECTIONAL HOLE TO 1807 M. | DRILL 6-1/8" DIRECTIONAL HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | CIRCULATE CONDITION MUD PRIOR TO LOT at 200 GPM PR. 2200 PSI. -In and out mud wt. 9.4 ppg. | 24 | 14.12 | 2019-01-06 23:59:59.000 | 396 | 689.29 |  |  |  |  | 2019-03-25 19:30:00.000 | 2018-12-14 08:30:00.000 | 101.706 | 7874.016 | 2019-03-20 08:30:00.000 | 2.1667 | 8.1667 | 96 | 101.4583 | 2.1355 | 82.021
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-021-01-205 |  |  | ABH | Horizontal | Horizontal | 2018-12-19 12:30:00.000 | Primary Drilling | Quippo-39 | SKID THE WELL ABH-021-01-205. DRILLED 8.5" HOLE TO 550 M | DRILL 8.5" HOLE TO TD, 1248M +/-. | C55259857E34473CB05F79C71FC66C90 | M/U 8-1/2'' RR PDC BIT SR. NO. JN 5592, TYPE 516, MAKE SMITH, NOZZLE 3 X 13, 2 X 14 DIRECTIONAL HOLE ASSY. RIH TO 37 MTS. BHA : 8-1/2'' PDC BIT + PD + NEOSCOPE + TELESCOPE + NMDC. | 21.63 | 14.08 | 2019-01-08 15:06:36.000 | 396 | 689.29 |  |  |  |  | 2019-04-19 00:00:00.000 | 2018-12-19 12:30:00.000 | 101.706 | 4137.1392 | 2019-04-14 17:45:00.000 | 7.0937 | 5.8646 | 116.2188 | 120.4792 | 5.8879 | 35.5979
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-021z-01-205 |  |  | ABH | Horizontal | Horizontal | 2019-04-19 23:00:00.000 | Primary Drilling | Quippo-39 | TEST PACK OFF SEAL. INSTALL WEAR BUSHING. M/U 6-1/8" DIR. BHA. RIH TO 1010M. W.O.C. RIH. CLEAN OUT 7" SHOE TRACK. DRILL NEW FORMATION TO 1216 MTS. CIRC. PERFORM LOT. DRILL 6-1/8" DIR. HOLE TO 1228 MTS. | DRILL 6-1/8" DIR. HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | CONT. RIH 6-1/8" DIRECTIONAL ASSY. ON 3-1/2" DP FROM 1010 M TO 1184 M. TOP OF FLOAT COLLAR. -Precautionary wash down last stand. | 19.01 | 11.54 | 2019-05-08 00:12:04.000 | 396 | [5 empty] | 2019-05-03 09:00:00.000 | 2019-04-19 07:30:00.000 | 1318.8977 | 7086.6144 | 2019-04-28 03:00:00.000 | 5.2187 | 4.4896 | 8.1667 | 13.4167 | 38.8975 | 867.7487
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-023-01-208 | 25.9145 | 71.5733 | ABH | Horizontal | Horizontal | 2018-12-26 18:30:00.000 | Primary Drilling | Quippo-39 | SKID TO SLOT 208, RIG UP, SPUDDED THE WELL ABH-023-01-208 @ 18:30HRS. DRILLED FROM 31 M TO 93 M.CIRCULATED HOLE CLEAN AND POOH TO ADD MWD , NMDC , DC AND JAR IN THE BHA. | DRILL 12.25" HOLE AS PER DIRECTIONAL PLAN TO TD. C & C . POOH. | C55259857E34473CB05F79C71FC66C90 | PRE SPUD SAFETY MEETING , SPUD SLOT 208 AS WELL ABH-023-01-208 AND DRILLED 12.25" DIRECTIONAL HOLE FROM 32 M TO 93 M. Flow Rate: 430-600 gpm, SPP: 350-550 psi,. WOB: 2- 10 klb, Surface RPM: 40-60, On Bottom RPM:150, Torque 1-3Kftlbf, P/Up 48 Klbs, S/Off 45 klbs ,Rot 46 klbs. ROP(avg): 20 m/hr, ROP(Inst): 10-30 m/hr. Bit Hours: 2.22 hrs. Cumm. hrs. on jar :70 hrs. Formation: Akli Formation, Lithology: Claystone interbedded with Limestone | 21.66 | 14.03 | 2019-01-16 15:43:48.000 | 396 | 689.29 |  |  |  |  | 2018-12-29 14:30:00.000 | 2018-12-26 18:30:00.000 | 104.9869 | 1692.9134 | 2018-12-28 11:00:00.000 | 0.42708 | 0.6875 | 1.6875 | 2.8333 | 15.0735 | 1003.208
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-024-01-211 | 25.9143 | 71.573 | ABH | Horizontal | Horizontal | 2018-12-30 09:30:00.000 | Primary Drilling | Quippo-39 | RIH 6 1/8" DIR BHA TO THE TOP OF FC DEPTH. DRILL SHOE TRACK AND 3 M FRESH FORMATION. CONDUCTED LOT. DRILLED 6 1/8" SECTION UP TO 1547 M. | ONCE STRIKE IS OVER, RIH TO BOTTOM AND DRILL 6 1/8" DIR HOLE AS PER PLAN. | C55259857E34473CB05F79C71FC66C90 | DRILLED 3 M OF FORMATION FROM 1419 M TO 1422 M FOR THE LOT. * Parameters: WOB: 8-10 klbs, RPM: 80, Flow: 215 gpm, SPP: 2100 psi,Torque: 4 klbs-ft. * Made 3 passes through shoe then pulled 6 1/8" bit inside 7" casing | 21.62 | 14.1 | 2019-01-20 14:52:12.000 | 396 | 689.29 |  |  |  |  | 2019-02-10 22:00:00.000 | 2018-12-30 09:30:00.000 | 101.706 | 7119.4228 | 2019-02-05 17:15:00.000 | 11.1354 | 15.5208 | 37.3229 | 42.5208 | 26.1881 | 190.752
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-025-01-212 | 25.9142 | 71.5733 | ABH | Horizontal | Horizontal | 2019-01-02 20:30:00.000 | Primary Drilling | Quippo-39 | RIH 6 1/8" DIRECTIONAL BHA TO 1174.8 M.TAGGED FLOAT COLLAR . DRILL OUT SHOE TRACK & NEW FORMATION UP TO 1205 M.CIRCULATED.PERFORMED LOT. EMW= 13.7 PPG. DRILLED 6 1/8" DIRECTIONAL HOLE TO 1430 M. | DRILL 6 1/8" DIRECTIONAL HOLE AS PER PLAN TO SECTION TD (2800 M.) | C55259857E34473CB05F79C71FC66C90 | RIH 6 1/8" RSS BHA ASSY. ON 3-1/2" DP SINGLES TO 1174.84 M.TAGGED FLOAT COLLAR. DEPTH MATCHING WITH TALLY. -Drift 3-1/2" drill pipe with 2" drift while RIH. -Washed down between 1163 m to 1174.8 m. Flow :200 GPM , SPPA : 2000 psi. | 21.72 | 14.14 | 2019-01-23 17:12:36.000 | 396 | 689.29 |  |  |  |  | 2019-01-19 15:00:00.000 | 2019-01-02 20:30:00.000 | 101.706 | 8389.1079 | 2019-01-14 12:30:00.000 | 1.6042 | 6.5625 | 11.6667 | 16.7708 | 9.5652 | 719.0664
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-039-05-201 | 25.897 | 71.578 | ABH | Horizontal | Horizontal | 2019-05-17 12:00:00.000 | Primary Drilling | Quippo-39 | SPUDDED WELL WITH 12 1/4" DIRECTIONAL BHA. DRILLED 12 1/4'' HOLE FROM 33 M TO 51 M. OBSERVED TOTAL LOSSES. SPOTTED 33 BBL OF 50 PPB LCM PILL. DRILLED UP TO 59 M. OBSERVED POOR ROP. POOH 12 1/4" BHA TO SURFACE TO CHECK THE CONDITION OF BIT. RIH WITH OEDP. SPOTTED 25 BBL OF 120 PPB LCM PILL. | RIH WITH 12 1/4" DIRECTIONAL BHA. DRILL 12 1/4" DIRECTIONAL HOLE UP TO SECTION TD (PLANNED - 530 M). | C55259857E34473CB05F79C71FC66C90 | POOH 12.25" BHA TO SURFACE. Bit Grading :- 1-2-WT-A-X-I-BU-BHA | 19.74 | 12.68 | 2019-06-07 23:00:00.000 | 396 |  | 20190519002519 |  |  |  | 2019-05-22 04:30:00.000 | 2019-05-17 12:00:00.000 | 101.706 | 1720.8006 | 2019-05-19 06:30:00.000 | 2.4062 | 0.85417 | 1.7708 | 4.6875 | 51.3333 | 971.7462
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-040-05-202 | 25.89 | 71.578 | ABH | Horizontal |  | 2019-05-23 00:00:00.000 | Primary Drilling | Quippo-39 | CIRC PRIOR TO POOH. SPOTTED HI-VIS AT 478.6 M. POOH DIRECTIONAL BHA TO SURFACE. R/BCK BHA. M/A FOR RIH 9 5/8'' CSG 40 # K-55. RIH 9 5/8'' CSG TO 475.5 M (SHOE). LANDED CSG HANGER. CIRC PRIOR TO CMT JOB. P-TESTED LINES. PUMPED CMT JOB AS PER PLAN. PLUG BUMPED. TESTED CSG AT 2000 PSI, 15 MINS. HOLDING GOOD. CHECKED FLOATS. R/D CMT HEAD. R/D FLOW LINE, BELL NIPPLE AND RISER. REIG RELEASED FOR SLOT-203 ON 24-MAY-19 AT 20:00 HRS. | SKID TO SLOT 203. SPUD WELL_ABH-042-05-203. | C55259857E34473CB05F79C71FC66C90 | R/BCK 12 1/4" SECTION DIRECTIONAL TOOLS R/Bck NMDC & Telescope. P/U and M/U 4" 10'pub joint & X/O with Pony NMDC. Connected with TDS. Drained Motor. L/D Bit ; Grading :- 1-2-CT-N-X-I-NO-TD. | 19.95 | 13.05 | 2019-06-14 10:12:27.000 | 396 | [5 empty] | 2019-05-24 20:00:00.000 | 2019-05-23 00:00:00.000 | 104.9869 | 1570.21 | 2019-05-24 00:00:00.000 | 0.020833 | 0.083333 | 1 | 1.8333 | 1.1364 | 1570.21
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-042-05-203 | 25.8977 | 71.5783 | ABH | Horizontal | Horizontal | 2019-05-26 09:30:00.000 | Primary Drilling | Quippo-39 | DRILLED 12 1/4'' DIRECTIONAL HOLE F/278 M T/520.5 M. CIRC PRIOR TO POOH. SPOTTED HI-VIS PILL. FLOW CHECK. POOH & R/BCK DIRECTIONAL BHA. M/A TO RIH 9 5/8'' CSG. RIH 9 5/8'' CSG TO 517.5 (SHOE).LANDED CSG ON CASING HANGER. CIRC PRIOR TO CMT JOB. | SKID TO SLOT 204 AND SPUD WELL_BH08-028-05L. | C55259857E34473CB05F79C71FC66C90 | RACK BACK 12 1/4" SECTION DIRECTIONAL TOOLS Rack back NMDC & Telescope. Pick up and M/Up 4" 10'pub joint & X/O with Pony NMDC. Connected with TDS. Drained Motor. Bearing gap 6 mm.Bit Grading :- 1-2-BT-A-X-I-NO-TD. | 20.93 | 13.66 | 2019-06-14 22:15:00.000 | 396 | [5 empty] | 2019-05-27 01:15:00.000 | 2019-05-25 09:30:00.000 | 101.706 | 1707.6772 | 2019-05-26 09:30:00.000 | 0.041667 | 0.072917 | 0 | 0.65625 | 6.3492 | inf
EH | SEA | India | C55259857E34473CB05F79C71FC66C90 |  | 488415 | IN - Cairn - ABH | IDS | Asia | LSTK | ABH-043-05-204 | 25.8977 | 71.578 | ABH | Horizontal | Development | 2019-05-27 16:30:00.000 | Primary Drilling | Quippo-39 | DRILL 8-1/2" DIRECTIONAL HOLE TO 1283.5 MTS. SECTION TD. CIRC. POOH. DROP GYRO. POOH. RECORDED GYRO SURVEY WHILE POOH. L/D BHA. REMOVE WEAR BUSHING. DUMMY RUN HGR. R/U AND RUN 7" CSG AS PER TALLY TO 778 MTS. | RUN 7" CSG AS PER TALLY TO BTM. LAND HGR. CIRC. R/U AND PERFORM CMT JOB. BUMP PLUG. R/D CMT HEAD AND L/D LANDING JT. INSTALL PACK OFF SEAL. TEST SAME. M/U 6" DIRECTIONAL ASSY. RIH. | C55259857E34473CB05F79C71FC66C90 | RIH 7" L80 JFE BEAR 29 PPF CSG TO 778 MTS WITHOUT ANY OBSTRUCTION. -Observed no losses during RIH 7" csg. -Fill up every joint and top up evey 5 joint of csg. | 20.34 | 13.33 | 2019-06-16 08:13:48.000 | 396 | [5 empty] | 2019-06-25 11:00:00.000 | 2019-05-27 16:45:00.000 | 101.706 | 7874.016 | 2019-06-07 02:30:00.000 | 0.51042 | 5.6667 | 10.4167 | 28.7708 | 1.7741 | 755.9055
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 51-04-111 (INF-08) | 25.2887 | 71.7568 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2018-12-28 15:30:00.000 | Primary Drilling | JE-14 | LANDED CASING HANGER ON WELL HEAD AFTER REPEATED ATTEMPTS. CIRCULATED HOLE CLEAN PRIOR TO CEMENT JOB. WHILE STARTING TO PUMP CEMENT, BATCH MIXER ENGINE FAILED. DISCARDED CEMENT SLURRY. CIRCULATED OUT AND DUMPED PREVIOUS MUD AND SPACER INSIDE HOLE. RECTIFIED BATCH MIXER ENGINE. PREPARED SACRIFICIAL MUD AND CEMENT SLURRY. COMPLETED CEMENT JOB AS PER PROGRAM. BUMPED PLUG AND PRESSURE TESTED CASING SUCCESSFULLY. | N/UP X-MAS TREE AND RELEASE RIG TO NEXT LOCATION-51-04-112. | DFBE2409356C47F7A424A3DE2D89EA6B | TROUBLESHOOT TO START BATCH MIXER ENGINE. - Batch mixer engine stopped working. - Pumped out and dumped cement slurry with Supervac. - Restarted and tested engine. Found OK. | 31.85 | 19.54 | 2019-02-11 17:14:24.000 | 372 | 847.15 |  |  |  |  | 2019-06-23 00:00:00.000 | 2019-06-06 00:00:00.000 | 8851.7063 | 12347.4741 | 2019-06-15 22:30:00.000 | 3.9896 | 4.7812 | 169.2917 | 176.3542 | 2.2623 | 72.9361
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 52z-04-112 (INF-09) | 25.28 | 71.76 | RDG (Block: RJ-ON 90/1) | Build & Hold | Development | 2018-12-21 15:00:00.000 | Primary Drilling | JE-14 | TIME DRILLED FROM 2827 M TO 2855 M. ATTEMPT TO SIDETRACK FAILED. DECIDED TO POOH TO SURFACE TO CHANGE BHA. POOH 24 STDS 4" D/P UP TO 2390 M. | POOH TO SURFACE AND CHANGE BHA. L/DN POWER DRIVE AND PDC BIT. M/UP MUD MOTOR AND TCR BIT. RIH TO BOTTOM. RESUME TIME DRILLING. | DFBE2409356C47F7A424A3DE2D89EA6B | TIME DRILLING FROM 2840 M TO 2845 M. - Time drilled at 1 m/hr from 2840 m to 2845 m. - Discharge- 230 gpm, SPP- 3400 psi, rpm- 100. - Drill cuttings sample: @2842 m- 10-15 % formation. @2843 m- 15-20% formation. @2844 m- 20% formation. | 31.67 | 18.99 | 2019-01-21 16:05:24.000 | 372 | 847.15 | 20190301113335 |  |  |  | 2019-07-27 07:00:00.000 | 2019-06-26 02:00:00.000 | 8930.4465 | 11558.3993 | 2019-07-14 04:30:00.000 | 23.4271 | 11.8021 | 204.5625 | 217.6667 | 10.7628 | 56.503
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 53-04-113 (INF-12) | 25.2885 | 71.7569 | RDG (Block: RJ-ON 90/1) | S Shaped |  | 2018-12-13 05:30:00.000 | Primary Drilling | JE-14 | COMPLETED MOBILIZATION PHASE. NIPPLE DOWN X-MAS TREE. NIPPLE UP BOP. RETRIEVE PACK OFF ASSEMBLY & 4.5" CASING HANGER. | MAKE UP BHA & RIH ON 4" XT39 DP TO TOP OF CEMENT. DRILL SHOE TRACK. CARRY OUT LOT. DRILL 6" OPEN HOLE TO CORING DEPTH. | DFBE2409356C47F7A424A3DE2D89EA6B | RIG DOWN X MAS TREE. - Checked and found no pressure in annular before rig down X-mas tree. - Continued to rig down X-mas tree by Cameron team. - Installed TWCV. - Remove threaded flange. - Installed fast lock hub & drilling adapter on well head. | 42.25 |  | 2019-01-24 05:56:25.000 | 372 | 847.15 |  |  |  |  | 2019-09-07 09:00:00.000 | 2018-12-13 05:30:00.000 | 91.8635 | 12785.4335 | 2019-08-26 17:30:00.000 | 12.6562 | 29.5417 | 256.5 | 268.1458 | 4.7199 | 49.8457
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 62-07-203 (INF-07) | 25.283 | 71.733 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2019-04-02 19:00:00.000 | Primary Drilling | JE-14 | DRILLED SHOE TRACK, SHOE & RAT HOLE FROM 2847 M TO 2858 M. DRILL 4 M 6" FRESH FORMATION FROM 2858 M TO 2862 M. CIRCULATED HOLE CLEAN & CARRIED OUT LOT. EMW: 17.41 PPG. DRILLED 6" OPEN HOLE FROM 2862 M TO 3068 M. | DRILL AHEAD 6" OPEN HOLE TO SECTION TD 3840 M. | DFBE2409356C47F7A424A3DE2D89EA6B | POOH FROM 2862 M TO 2848 M. - POOH to inside of shoe for carrying out LOT. - Racked back one stand of 4" DP. | 30.12 | 19.09 | 2019-05-02 02:50:24.000 | 372 | 847.15 |  |  |  |  | 2019-05-13 21:00:00.000 | 2019-04-02 19:00:00.000 | 104.9869 | 12591.8639 | 2019-05-04 08:30:00.000 | 15.1146 | 20.9167 | 31.5625 | 41.0833 | 36.7901 | 398.9501
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 66z-07-201 (INF-06) | 25.297 | 71.75 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2019-01-16 01:00:00.000 | Primary Drilling | JE-14 | DRILLED 6" DIRECTIONAL HOLE UP FROM 2870 M TO 3098 M. | POOH TO SURFACE FOR BIT CHECK. RIH WITH NEW BIT AND RESUME DRILLING. DRILL AHEAD 6" DIRECTIONAL HOLE TO PLANNED SECTION TD AT 3782 M. | DFBE2409356C47F7A424A3DE2D89EA6B | DRILLED FROM 2990 M TO 3056 M. Drilling parameters: Inst. ROP 10-15 m/hr; Average ROP: 12 m/hr WOB- 12 T, RPM-125, GPM- 200, SPP- 3500 psi, RPM 120, Torque off BTM 5-6 kft-lbs. Torque on BTM 10k ft-lbs. Lithology: 100% Weathered Volcanic. | 34.58 | 20.72 | 2019-02-19 13:59:24.000 | 372 | 847.15 |  |  |  |  | 2019-03-21 04:00:00.000 | 2019-01-16 00:00:00.000 | 101.706 | 12007.8744 | 2019-02-26 07:15:00.000 | 33.0729 | 30.2396 | 41.2604 | 64.125 | 51.5757 | 291.0265
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 67-07-202 (INF-4) | 25.2969 | 71.75 | RDG (Block: RJ-ON 90/1) | S Shaped | Inclined Gas Producer | 2018-11-30 09:00:00.000 | Primary Drilling | JE-14 | LOT. REPAIR TDS. DRILL 6" DIRECTIONAL HOLE FROM 2831 M TO 3096 M. | DRILL 6" DIRECTIONAL HOLE AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | 1/2 HR. WHILE M/U TDS CONNECTION. BENT MWD STRAINER HANDLE WHICH WAS INSIDE DP. REPLACED SAME. 1/2 HR. EXCESS TIME TAKEN FOR CONNECTION DUE TO PUMP ISSUE. | 32 | 19.51 | 2019-01-01 00:00:00.000 | 372 | 847.15 |  |  |  |  | 2019-01-10 15:00:00.000 | 2018-11-30 09:00:00.000 | 95.1444 | 12598.4256 | 2018-12-31 20:00:00.000 | 12.4375 | 19.3229 | 31.4583 | 41.25 | 30.1515 | 400.4798
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | RAAG-068-05-109 (INF-16) | 25.16 | 71.45 | RDG (Block: RJ-ON 90/1) | S Shaped | S-type | 2019-03-30 06:00:00.000 | Primary Drilling | JE-32 | DRILL SHOE TRACK & 3 M NEW FORMATION TO 2842 M, PERFORM LOT, RESULTANT MWE 16.52 PPG. DRILLED 6" HOLE FROM 2842 M TO 2976 M WITH AVERAGE ROP OF 9 M/HR. MP#3 BREAKDOWN, REPAIRS ONGOING. | DRILL 6" HOLE FROM 2976 M TO CORING POINT. CIRCULATE HOLE CLEAN AND POOH. M/U CORING ASSEMBLY AND RIH. | DFBE2409356C47F7A424A3DE2D89EA6B | CONTINUE DRILLING 6" HOLE FROM 2889 M TO 2969 M. * WOB 12-14 klbs, RPM 100-120, Torque 7-9 kft.lbs, Flow 220 gpm, SPP 3500 psi, ROP 8 m/hr. * PU/ROT/SO Wt: 185/ 165/ 145 klbs * Recorded SCRs * Formation gas peak 2.7% at 2925 m. * Formation: 0-10% Claystone, 10-50% Siltstone, 50-90% * Wash up and Ream down x 1 single before every connection. | 39.27 | 29.53 | 2019-05-27 08:43:12.000 | 372 | [5 empty] | 2019-06-01 08:30:00.000 | 2019-03-30 06:00:00.000 | 98.4252 | 12398.2944 | 2019-05-22 21:30:00.000 | 19.5729 | 40.7604 | 53.6458 | 63.1042 | 31.0168 | 231.1138
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 43-11-108 (INF 23) |  |  | RDG (Block: RJ-ON 90/1) | S Shaped | DEVLOPMENT | 2019-04-12 11:00:00.000 | Primary Drilling | JE-32 | TAGGED TOP OF CEMENT AT 2963 M, 1.6 M ABOVE 7" FLOAT COLLAR. PRESSURE TEST 7" CASING TO 4500 PSI/ 15 MINS OK. DRILL CEMENT, 7" CASING SHOE TRACK AND FRESH FORMATION TO 3007 M. PERFORMED LOT JOB, RESULT 16.62 PPG EMW. DRILL 6" HOLE FROM 3007 M TO 3118 M. | FIX ELMAGCO BRAKE. RIH AND DRILL 6" HOLE FROM 3118 M TO CORING POINT. | DFBE2409356C47F7A424A3DE2D89EA6B | R/D CEMENTING LINES. | 28.04 |  | 2019-05-10 01:04:37.000 | 372 | 847.15 |  |  |  |  | 2019-09-10 13:30:00.000 | 2019-04-12 11:00:00.000 | 98.4252 | 12368.7668 | 2019-08-27 08:00:00.000 | 15.0729 | 26.0208 | 136.875 | 151.1042 | 9.9752 | 90.3654
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 70-05-106 (INF -26) | 25.2686 | 71.7589 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2019-10-06 13:30:00.000 | Primary Drilling | Quippo-2 | P/U , M/U AND RACK BACK 30 STANDS OF 4" DP STANDS ON DERRICK. CHANGED SAVER SUB FROM 5" DP TO 4" XT-39. MA , P/U AND RIH 6" DIRECTIONAL DRILLING BHA TO 30 M. RIH 6" DD BHA ON 4-3/4" DC AND 3-1/2" HWDP TO 300 M. PERFORMED SHALLOW HOLE TEST OF MWD TOOLS - OK. FURTHER RIH 6" DD BHA 0N 4" DP TO 1284M IN SINGLE. | RIH 6" DD BHA ON 4" DP IN SINGLES TO 2890 M. WASH DOWN LAST STAND TO TAG FLOAT COLLAR @ 2921 M. DRILL SHOE TRACK , RAT HOLE AND FRESH FORMATION . PERFORM LOT. DRILL 6" HOLE AS PER DD TO WELL TD. | DFBE2409356C47F7A424A3DE2D89EA6B | RIGGED UP PNEUMATIC SLIP. | 34.37 | 26.85 | 2019-11-07 19:08:25.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-10-06 13:30:00.000 | 108.2677 | 11108.9242 | 2019-10-21 13:30:00.000 | 1.2812 | 9.3333 | 15 | 15.4375 | 8.2996 | 740.5949
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | RAAG 45-01-201 | 25.4455 | 75.769 | RDG (Block: RJ-ON 90/1) | Deviated |  | 2019-07-09 13:00:00.000 | Primary Drilling | Quippo-4 | SPUD THE WELL & DRILLED 12 1/4” DIRECTIONAL HOLE FROM 36 TO 69 M. OBSERVED PRESSURE SHOOT-UP WHILE DRILLING. POOH TO CHECK THE STRING. FOUND IBOP MALFUNCTIONING. TROUBLE SHOOTED THE SAME. RIH. RESUMED DRILLING & DRILLED DOWN TO 100 M. | DRILL AHEAD 12 1/4” DIRECTIONAL HOLE AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | SPUDDED THE WELL RAAG 45-01-201 (INF-13) & DRILL AHEAD 12 1/4” DIRECTIONAL HOLE. * Tagged the new formation at 36 m by 13:00 hrs. * Drill ahead from 36 m to 49 m. * Drilling Parameters: * WOB: 1- 5 Klbs, * RPM: 30 - 50, Torque off bottom: 0.5 & on bottom: 1.0 Klbs-ft, * Flow: 220 gpm, SPP off bottom: 160 & on bottom: 210 psi, * Hook load P/U: 30, S/O: 30, Rot: 30 Klbs * ROP avg: 20 & on bottom: 30 m/hr. * Down-hole losses: No. | 35.19 | 19.54 | 2019-08-13 04:33:36.000 | 372 | [5 empty] | 2019-07-16 16:00:00.000 | 2019-07-09 13:00:00.000 | 118.1102 | 3559.7114 | 2019-07-13 15:00:00.000 | 1.4479 | 1.5 | 4.0833 | 7.125 | 20.3216 | 871.7661
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | RAAG 46-01-205 | 25.279 | 71.7701 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2019-06-18 18:00:00.000 | Primary Drilling | Quippo-4 | SPUDDED WELL RAAG-46-01-205 AT 1800 HRS. DRILLED 12 1/4" HOLE TO 123M. | DRILL 12 1/4" DIRECTIONAL HILE TO SECTION TD + / - 1070 M AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | OBSERVED LEAKAGE FROM MUD PUMP STRAINER. REPAIRED SAME. | 32.72 |  | 2019-07-21 10:33:36.000 | 372 | [5 empty] | 2019-06-24 20:00:00.000 | 2019-06-18 18:00:00.000 | 108.2677 | 3513.7796 | 2019-06-22 04:00:00.000 | 0.5 | 0.45833 | 3.4167 | 6.0833 | 8.2192 | 1028.4233
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | RAAG 48-01-203 | 25.278 | 71.77 | RDG (Block: RJ-ON 90/1) | Deviated | Development | 2019-07-02 17:30:00.000 | Primary Drilling | Quippo-4 | DRILLED 12-1/4" DIRECTIONAL HOLE FROM 128 TO 437 M IN SLIDING AND ROTARY MODE. | DRILL 12 1/4" DIRECTIONAL HOLE AS PER PLAN TO SECTION TD + / - 1064M | DFBE2409356C47F7A424A3DE2D89EA6B | DRILLING HAD TO BE STOPPED AS TDS UNIT ENGINE TRIPPED. * Quippo PME team started troubleshooting TDS engine. * Changed oil , air and fuel filter. * Cleaned all diesel lines. * String was kept under circulation at 560-600 gpm and reciprocated while working on TDS. | 30.2 | 19.54 | 2019-08-01 04:48:00.000 | 372 |  | 20190706045140 |  |  |  | 2019-07-07 17:30:00.000 | 2019-07-02 17:30:00.000 | 101.706 | 3477.6904 | 2019-07-05 05:00:00.000 | 0.55208 | 0.45833 | 2.4792 | 5 | 11.0417 | 1402.7659
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | RAAG 50-01-204 (INF 21) |  |  | RDG (Block: RJ-ON 90/1) |  |  | 2019-06-26 10:00:00.000 | Primary Drilling | Quippo-4 | SPUD WELL RAAG-50-01-204(INF21) AT 1000HRS. AND TAGGED BOTTOM AT 33M. DRILLED 12 1/4" DIRECTIONAL HOLE FROM 33M TO 198 M. | DRILL 12 1/4" DIRECTIONAL HOLE TO SECTION TD + / - 1070M | DFBE2409356C47F7A424A3DE2D89EA6B | DRILLED 12 1/4" DIRECTIONAL HOLE FROM 105M TO 198M IN ROTARY MODE. * Parameters : WOB: 2-5 Kips, RPM: 50-60, Flow: 500-720 gpm, Off bottom SPP: 750-1350psi, On bottom SPP: 850-1450 psi, Off bottom Torque: 1.0 Klbs-dt, On bottom torque: 2.5 Klbs/ft., P/u wi:44 Klbs, S/Off wt: 38 Klbs, Rot WT: 43 Klbs * Avg ROP: 13 m/hr., On bottom ROP: 26 m/hr. * Pumped 10 bbl Hi Vis at every stand to facilitate hole cleaning. * Bit Hours[ 24 hrs / cumulative]: [ 9.78 / 9.78] * Circulating time[ 24 hrs / Cumulative]: [11.9 / 11.9] * Ct-Ct from plan at 161.64m MD: 0.07m, 0.07m Left, 0.0m Above * Cleaned strainers of MP#1. * No losses were observed while drilling. * ROP was controlled between 25-30m/hr to avoid the gumbo problem. | 680.5 |  | 2021-05-06 12:00:00.000 | 372 | [5 empty] | 2019-07-01 09:30:00.000 | 2019-06-26 10:00:00.000 | 108.2677 | 3520.3413 | 2019-06-29 00:00:00.000 | 0.10417 | 0.125 | 2.5833 | 4.9792 | 2.0921 | 1362.7128
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 40-08-102 (INF-30) | 25.262 | 71.767 | RDG (Block: RJ-ON 90/1) | S Shaped |  | 2018-04-12 20:30:00.000 | Primary Drilling | Quippo-4 | N/U annular BOP. Tightened connection on all BOP flanges. N/U Bell Nipple. P/T BSR and TWCV to 500/4500 psi or 5/10 min-ok. R/U catwalk and V door. | Retrieve and L/D tubing hanger and TWCV. Retrieve and L/D 4 1/2" kill string. M/U test plug and P/T BOP stack and standpipe manifold. Install wear bushing and M/U 3 1/2" DP stands. | DFBE2409356C47F7A424A3DE2D89EA6B | Tightened connections on all 4 BOP flanges. | 16.09 |  | 2018-04-28 02:04:40.000 | 880.577 | 847.15 |  |  |  |  | 2018-10-02 14:00:00.000 | 2018-04-12 20:30:00.000 | 95.1444 | 12053.8064 | 2018-10-02 14:00:00.000 | 23.3542 | 58.8021 | 172.7292 | 172.7292 | 13.5207 | 69.7844
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 41-08-103 (INF-27) | 25.2617 | 71.7669 | RDG (Block: RJ-ON 90/1) | Build & Hold | J-type | 2018-06-24 04:30:00.000 | Primary Drilling | Quippo-4 | Continued drilling shoe track, rat hole and 3 m of fresh formation. Circulation and conditioned mud to 10.8 ppg. Performed LOT. Maximum pressure applied 3550 psi, MWE 18 ppg. Relogged 30 m inside shoe. Drilled 6" section to 3072m. Changing of MP#1 and 2 liner to 4 1/2". | Change liners of MP#1 and 2 to 4 1/2". Test mud pumps and drill 6" section to coring point. | DFBE2409356C47F7A424A3DE2D89EA6B | Changed MP#1 and MP#2 liner from 5" to 4 1/2" - in progress. | 31.92 |  | 2018-07-25 22:09:40.000 | 448.514 | 847.15 |  |  |  |  | 2018-09-02 12:00:00.000 | 2018-06-24 04:30:00.000 | 0 | 12631.234 | 2018-08-21 17:30:00.000 | 8.9063 | 39.0313 | 58.5417 | 70.3125 | 12.6667 | 215.7649
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 42-08-109 (INF-31) | 25.2615 | 71.7672 | RDG (Block: RJ-ON 90/1) | S Shaped |  | 2018-10-09 19:00:00.000 | Primary Drilling | Quippo-4 | Drill 6" hole from 3351 m to 3595 m with average ROP of 23 m/hr. | Drill 6" hole as per plan to well TD ~ 3700m. POOH and L/D 3-1/2" DP and BHA in singles. | DFBE2409356C47F7A424A3DE2D89EA6B | Drill 6" hole from 3415 m to 3555 m. * On bottom ROP 8 - 70 m/hr, Average ROP 21 m/hr * Parameters: WOB 14-22 klbs, Flow 205 gpm, SPP 3500 psi, RPM 105 - 120, Torque Off/On: 7/ 11.5 kft.lbs * P/U Wt 194 klbs Rot Wt 168 klbs S/O Wt 146 klbs * Geoservices Gastrap injection at 3553m, ok * Survey at 3541.73 m: Inc 15.99 deg, Azi, 172.47 deg C-C distance from plan: 1.25 m, 0.3 m above plan, 1.22 m right of plan * Formation: Weathered Basalt 100% * Background gas: 0.4 - 0.6% | 31.41 |  | 2018-11-09 09:44:32.000 | 479.453 | 847.15 |  |  |  |  | 2018-11-23 14:00:00.000 | 2018-10-09 21:00:00.000 | 0 | 12139.108 | 2018-11-13 11:00:00.000 | 5.0938 | 20.0417 | 34.6667 | 44.7917 | 11.3721 | 350.1666
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 43-11-108 (INF 23) |  |  | RDG (Block: RJ-ON 90/1) | S Shaped | DEVLOPMENT | 2019-04-12 11:00:00.000 | Primary Drilling | Quippo-4 | SPUD WELL RAAG-43-11-108 (INF23) AT 1100 HRS. DRILLED 12 1/4" DIRECTIONAL HOLE FROM 30 M TO 197 M | DRILL 12 1/4" DIRECTIONAL HOLE TO SECTION TD (+ / - 1104 M). | DFBE2409356C47F7A424A3DE2D89EA6B | MWD SIGNAL ISSUES. STAGED PUMPS TO RESOLVE THE ISSUE. | 28.04 |  | 2019-05-10 01:04:37.000 | 372 | 847.15 |  |  |  |  | 2019-04-20 19:00:00.000 | 2019-04-12 11:00:00.000 | 98.4252 | 3622.0474 | 2019-04-15 10:00:00.000 | 2.7188 | 0.83333 | 2.9583 | 8.3333 | 32.625 | 1224.354
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 47-01-206 (R-39) | 25.279 | 71.7702 | RDG (Block: RJ-ON 90/1) | S Shaped |  | 2019-06-12 14:00:00.000 | Primary Drilling | Quippo-4 | DRILLED 12 ¼” DIRECTIONAL HOLE FROM 190 M TO 492 M. FURTHER DRILLING IN PROGRESS. | CONTINUE DRILLING 12 ¼” DIRECTIONAL HOLE AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | DRILLED 12 1/4" DIRECTIONAL HOLE FROM 190 M TO 215 M. * Parameters: WOB 2-7 Kibs, RPM 30-50, Torque Off: 0.5 & On: 2 kft.lbs, Flow 720-730 gpm, SPP Off: 1200 & On: 1450 psi. * String Wt - P/U: 57, S/Off: 48 & Rot : 55 Klbs, * ROP - On bottom: 34.5 & Avg: 16.5 m/hr * Formation: Clay stone: 60, Sand stone: 30 & Lime stone: 10 %. * Pumped hivis at regular intervals to facilitate hole cleaning. * Increased flow / Precautionary jetting flow line, to avoid chocking. * Controlled ROP < 35 MPH. | 26.14 |  | 2019-07-08 03:16:37.000 | 372 | [5 empty] | 2019-06-17 16:30:00.000 | 2019-06-12 14:00:00.000 | 108.2677 | 3487.5329 | 2019-06-15 03:45:00.000 | 0.14583 | 0.20833 | 2.5729 | 5.1042 | 2.8571 | 1355.4784
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 49-01-207 (R-40) | 25.2789 | 71.7703 | RDG (Block: RJ-ON 90/1) | Deviated | Development | 2019-06-03 06:15:00.000 | Primary Drilling | Quippo-4 | DRILL 12 /4” DIRECTIONAL HOLE FROM 280 TO 772 M. FURTHER DRILLING IN PROG. | CONTINUE DRILL 12 /4” DIRECTIONAL HOLE AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | DRILL 12 ¼” DIRECTIONAL HOLE FROM 386 M TO 487 M. * Parameters: WOB: 2-11 Kibs, RPM 40, Torque Off: 2 & On: 3 kft.lbs, Flow 685 gpm, SPP Off: 1400 & On: 1500 psi. * Hook Load: Up: 75/Rot: 70/Slack: 66 Kbs, * ROP: 17 m/hr (Avg) and 46 m/hr (On bott) * Lithology : Clay stone 30-40% & Sand stone 60-70%. | 23.3 |  | 2019-06-26 07:12:00.000 | 372 | [5 empty] | 2019-06-10 11:00:00.000 | 2019-06-03 06:15:00.000 | 72.1785 | 3569.5539 | 2019-06-06 02:15:00.000 | 1.1771 | 0.26042 | 2.8333 | 7.1979 | 16.3531 | 1259.8426
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 51-04-111 (INF-08) | 25.2887 | 71.7568 | RDG (Block: RJ-ON 90/1) | S Shaped | Development | 2018-12-28 15:30:00.000 | Primary Drilling | Quippo-4 | REPAIRED TDS. DRILL SHOE TRACK AND 3 M NEW FORMATION. CONDUCTED LOT.VALUE IS 16.13 PPG. DRILLED 8-1/2" SECTION.TO 1191 M. | DRILL 8-1/2" DIRECTIONAL HOLE TO SECTION TD. | DFBE2409356C47F7A424A3DE2D89EA6B | DRILLED SHOE TRACK FROM 1080.5 M TO 1085.3 M. * Parameters: WOB: 8 Klbs, RPM: 65, Flow: 430 gpm, SPP: 1680 psi | 31.85 | 19.54 | 2019-02-11 17:14:24.000 | 372 | 847.15 |  |  |  |  | 2019-01-24 14:00:00.000 | 2018-12-28 15:30:00.000 | 101.706 | 8851.7063 | 2019-01-20 15:30:00.000 | 10.2083 | 16.9479 | 23 | 26.9375 | 37.8964 | 384.8568
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 52z-04-112 (INF-09) | 25.28 | 71.76 | RDG (Block: RJ-ON 90/1) | Build & Hold | Development | 2018-12-21 15:00:00.000 | Primary Drilling | Quippo-4 | RIH 6" RSS TELEPACER BHA TO 1106M AND TAGGED TOP OF CEMENT AT 2756M. DRILLED CEMENT, SHOE TRACK AND 3 M OF NEW FORMATION TO 2821 M. CIRCULATED HOLE CLEAN; POOH 6" RSS TELEPACER BHA IN CASING SHOE AND R/U FOR LEAK OF TEST JOB. | PULL 6" RSS TELEPACER BHA IN CASING SHOE AND CONDUCT LEAK OFF TEST. DRILL 6" HOLE AS PER PLAN. | DFBE2409356C47F7A424A3DE2D89EA6B | RIH 6" RSS TELEPACER BHA FROM 1416 M TO 1608 M ON 3-1/2" DP SINGLES. * Drifted and hammered 3-1/2" singles prior to RIH | 31.67 | 18.99 | 2019-01-21 16:05:24.000 | 372 | 847.15 |  |  |  |  | 2019-03-04 11:30:00.000 | 2018-12-21 14:30:00.000 | 108.2677 | 11266.4046 | 2019-02-25 19:00:00.000 | 16.1979 | 22.5833 | 66.1667 | 72.8542 | 22.2333 | 170.2731
EH | SEA | India | DFBE2409356C47F7A424A3DE2D89EA6B |  | 483243 | IN - Cairn - RDG | IDS | Asia | LSTK | Raag 53-04-113 (INF-12) | 25.2885 | 71.7569 | RDG (Block: RJ-ON 90/1) | S Shaped |  | 2018-12-13 05:30:00.000 | Primary Drilling | Quippo-4 | WAIT ON INSPECTED 5" HWDP. P/U & M/U 8 ½" DIRECTIONAL BHA. RIH 8 ½" DIRECTIONAL BHA ON 5" DP TO 922 M. FURTHER RIH IN PROGRESS. | RIH 8 ½" DIRECTIONAL BHA ON 5" DP TO 941 M. FROM 941 M WASHED DOWN AND TAGGED TOC AT 1137 M. CHANGED OVER WELL VOLUME TO 11 PPG SOBM. DIESEL GENERATOR # 1 SEIZED. WAIT ON DIESEL GENERATOR (IN PROGRESS). | DFBE2409356C47F7A424A3DE2D89EA6B | PICK-UP & RIH 8 ½" DIRECTIONAL BHA TO 27 M. * P/U BHA std & M/U bit * RIH to 18.2 1m and inserted MWD probe. * Continued P/U & M/B BHA & RIH to 27 m. | 42.25 |  | 2019-01-24 05:56:25.000 | 372 | 847.15 |  |  |  |  | 2019-03-22 16:30:00.000 | 2018-12-13 05:30:00.000 | 91.8635 | 9360.2365 | 2019-03-14 16:30:00.000 | 0.9375 | 4.5938 | 91.4583 | 99.4583 | 0.94261 | 102.3443
EH | EUR | Italy | 81B8C8EBACE443B4B4C5577C744AD18E | 454 | 195508 | Italgas Italy UGS | IDS | Europe | LSTK | Cornegliano B02 | 45.2867 | 9.4813 | Cornegliano | Deviated |  | 2016-09-11 00:00:00.000 | Primary Drilling | HH 200 LP Drilling | Pump wash pills and Displace well to 1.23sg Di-Pro mud. Clean/Wash flowline sections. Drill out shoetrack, rathole and Drill 3m of new formation to 1369m | Circulate homogenize mud Mwin=Mwout=1.23sg. Perform FIT to 1.51sg. Drill 8-1/2" hole from 1369m to +/- 1464m (well TD) | 81B8C8EBACE443B4B4C5577C744AD18E | Circulate until shaker clean - Parameters: 1600lpm, 85 bars | 20.61 |  | 2019-07-16 12:30:00.000 | 80 | 80 |  |  |  |  | 2019-07-27 00:00:00.000 | 2019-07-02 22:00:00.000 | 2946.1943 | 4806.4306 | 2019-07-15 17:30:00.000 | 0.85417 | 10.4375 | 1037.7292 | 1049 | 0.081427 | 4.6317
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | RA-0736 | 29.889 | 47.202 | Raudhatain | Deviated | Producer | 2018-07-10 18:00:00.000 | Primary Drilling | KDC-42 | CONT. DRILLING 10 FT OF NEW FORMATION TO 9,363 FT. CIRCULATION, PERFORM FIT TO EMW 13 PPG, DROP GYRO, POOH TO SURFACE, M/U & RIH w/ 8 ½” RSS PD ARCHER BHA TO 6,772 FT. | RIH w/ 8 ½” RSS PD ARCHER BHA TO BTM @ 9,363 FT & DRILL AHEAD 8 ½” SECTION AS PER PLAN. | 5F71655AF1A049689136BF22FEF9F924 | PERFORMED FIT TO 13 PPG EMW, OK. - P/U bit inside shoe. - Checked circulation thru choke to trip tank. - Performed FIT to 1680 psi with 9.4 ppg MW (EMW 13 ppg). - Pumped @3/4 bpm until reached 1,680 psi/15 min, OK. - Volume Pumped / Returned = 4.9 / 4.9 bbl. - Completed IDS-WC-CL-001 Before the FIT checklist. | 49 | 27.08 | 2018-08-28 06:02:31.000 | 227 | [5 empty] | 2018-09-16 19:30:00.000 | 2018-07-10 18:00:00.000 | 45 | 11100.0004 | 2018-09-09 11:30:00.000 | 25.7917 | 44.7708 | 60.7292 | 68.0625 | 37.8941 | 182.7787
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0699 | 29.48 | 47.52 | Sabriyah | Horizontal | Mauddud | 2017-12-20 12:00:00.000 | Primary Drilling | KDC-42 | DRILL AHEAD 16" HOLE SECTION TO TD AT 6015 FT, CHC, FLOW CHECK,WIPER TRIP TO SHOE. | CONT WIPER TRIP TO SHOE, CHC,FLOW CHECK, TRIP IN BACK TO BOTTOM, CHC,FLOW CHECK,DROP GYRO,POOH,LD 16" BHA | 5F71655AF1A049689136BF22FEF9F924 | CONTINUE DRILLING 16" SECTION TD WITH MOTOR FROM 5996 FT TO 6015 FT (MUTRIBA) - Formation: Mutriba - WOB: 30-50 klbs, RPM 90-100, TRQ: 4-10 klb.Ft - FR: 900 gpm, SPP: 3100-3200 psi - On Bottom ROP: 9.3 fph, Average ROP: 7.6 fph. - Pumped 30 bbls polymer pill each stand. - Drilled off 2-3 min after every stand. - Washed up/reamed down one stand to control inclination - MW in&out = 9.9 ppg - Dynamic downhole losses: 10 bph. - Sample Lithology: 5996-6015 : Limestone 100% ** Notes: - Drilled Footage (Daily/Total) = 19 / 4780 ft - O/B Drilling Time (Daily/Total) = 2.04 / 99.04 hrs - Total Drilling Time (Daily/Total) = 2.5 / 113.25 hrs - O/B ROP (Daily/Total) = 9.3 / 48.26 fph - Avg ROP (Daily/Total) = 7.6 / 42.20 fph - Total KRev 16" TCI bit SN RG5587: 1096 KRev. | 42.42 | 28.65 | 2018-01-31 16:04:48.000 | [6 empty] | 2018-01-31 02:00:00.000 | 2017-12-20 12:00:00.000 | 46 | 11903.0004 | 2018-01-29 18:00:00.000 | 9.8333 | 27.6667 | 40.25 | 41.5833 | 23.6473 | 295.7267
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0748 | 29.808 | 47.842 | Sabriyah | Horizontal | Mauddud Injector | 2018-03-26 12:00:00.000 | Primary Drilling | KDC-42 | POOH LINER HANGER RUNNING TOOL & L/D SAME. P/U & RIH 7" X 9-5/8" CSG TANDEM SCRAPERS C/O BHA. DRILL OUT CMT TO 20 FT ABOVE F.S. CIRCULATE HOLE CLEAN. | SLIP & CUT DRILLING LINE. POOH WITH CLEAN OUT BHA TO SURFACE & L/D SCRAPERS. L/D EXCESS DP's. P/T BOP. R/U WIRELINE FOR CBL-VDL-USIT. | 5F71655AF1A049689136BF22FEF9F924 | CONT. RIH 6-1/8" CLEAN OUT BHA FROM 1486 FT TO 6422 FT - Filled up string every 15 stands. - Break circulation every 3,000 ft. - Monitored well on trip tank, filled up trip sheet. | 41.99 | 24.11 | 2018-05-07 05:45:36.000 | [6 empty] | 2018-05-19 17:00:00.000 | 2018-03-26 12:00:00.000 | 46 | 9846.0003 | 2018-05-18 22:30:00.000 | 14.9896 | 36.4479 | 53.4375 | 54.2083 | 27.6518 | 184.2526
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0754 | 29.8591 | 47.8176 | Sabriyah | Horizontal | Mauddud Producer | 2018-02-10 08:00:00.000 | Primary Drilling | KDC-42 | CIRCULATION HOLE CLEAN. PERFORMED 7" LINER CEMENT JOB. SET TOP PACKER. REVERSE CIRCULATED & DISPLACED HOLE TO 11 PPG OBM. POOH RUNNING TOOL & L/D. P/U 6-1/8" TANDEM SCRAPERS C/O BHA AND RIH TO 7393 FT. | CONTINUE RIH 7 X 9-5/8" CSG TANDEM SCRAPERS C/O BHA. DRILL OUT CMT TO 20 FT ABOVE F.S. CHC. POOH TO SURFACE & L/D SCRAPERS. L/D EXCESS DP's. P/T BOP. R/U WIRELINE FOR CBL-VDL-USIT. | 5F71655AF1A049689136BF22FEF9F924 | PJSM PRIOR TO P/U 6 1/8" CLEAN OUT BHA. - Reviewed JSA & Job procedures for mechanical lifting using crane. - Briefed crew of safe handling of BHA, DP. | 42.01 | 28.22 | 2018-03-24 06:14:24.000 | [6 empty] | 2018-03-17 00:00:00.000 | 2018-02-10 08:00:00.000 | 52 | 11020.0004 | 2018-03-15 20:15:00.000 | 2.6667 | 21.3125 | 33.5104 | 34.6667 | 7.6923 | 328.853
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0799 | 29.841 | 47.877 | Sabriyah | Deviated | Zubair Producer | 2018-05-29 17:30:00.000 | Primary Drilling | KDC-42 | CONTINUE DRILL SHOE TRACK UNTIL 20 FT ABOVE SHOE,CASING TEST,CONT D/A SHOE TRACK +10 FT, FIT. POOH, L/D 8-1/2" CLEAN OUT BHA, PJSM, M/U 8-1/2" DIRECTIONAL BHA, RIH. | CONTINUE RIH, TAG BOTTOM,CONT DRILLING AHEAD 8-1/2" HOLE SECTION AS PER PROGRAM | 5F71655AF1A049689136BF22FEF9F924 | TDS SERVICE | 49 | 27.72 | 2018-07-17 06:02:31.000 | [6 empty] | 2018-07-01 02:00:00.000 | 2018-05-29 17:30:00.000 | 55 | 10810.0003 | 2018-06-24 03:00:00.000 | 4.75 | 14.5938 | 25.3958 | 32.3542 | 14.6813 | 425.6604
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | RA-0730 | 29.55 | 47.52 | Raudhatain | Deviated | Producer | 2018-06-16 16:00:00.000 | Primary Drilling | KDC-57 | WAIT ON CEMENT. RUN 9-5/8'' IBC-CBL-VDL LOG. | POOH & L/D 9-5/8'' IBC-CBL LOG. WAIT ON DECISION. M/U & RIH CLEAN OUT ASSEMBLY. | 5F71655AF1A049689136BF22FEF9F924 | WAIT ON CEMENT - Wind speed 45-55 km/hr. - Sand storm ,low visibility. - Suspended crane operations. | 49 | 26.79 | 2018-08-04 05:54:18.000 | [6 empty] | 2018-07-29 23:00:00.000 | 2018-06-16 16:00:00.000 | 57 | 11240.0004 | 2018-07-20 08:00:00.000 | 6.75 | 22.4479 | 33.6667 | 43.2917 | 15.5919 | 333.8614
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | RA-0734 | 29.55 | 47.52 | Raudhatain | Deviated | Producer | 2018-08-08 15:00:00.000 | Primary Drilling | KDC-57 | CONT. POOH 7" SCRAPER CLEAN OUT BHA TO SURFACE. RETRIEVE WEAR BUSHING. N/U SHOOTING NIPPLE. CONT. WOC. R/U WIRE LINE. RECORD CEMENT EVALUATION LOG. R/D WIRE LINE. | CONT. R/D WIRE LINE. N/D SHOOTING NIPPLE & N/U BELL NIPPLE. PRESSURE TEST 7'' LINER. M/U & RIH 6-1/8'' DIRECTIONAL DRILLING BHA. DRILL LANDING COLLAR & SHOE TRACK. PRESSURE TEST 7'' LINER. CONT. D/O SHOE TRACK. DISPLACE WELL TO TRUCORE OBM. DRILL AHEAD 6-1/8'' SECTION TO TD AS PER PROGRAM. | 5F71655AF1A049689136BF22FEF9F924 | N/D BELL NIPPLE & INSTALL SHOOTING NIPPLE - Monitor well on trip tank | 42.7 | 24.07 | 2018-09-19 22:48:00.000 | 214 | [5 empty] | 2018-09-13 10:00:00.000 | 2018-08-08 15:00:00.000 | 57 | 9182.0003 | 2018-09-10 19:30:00.000 | 3.3333 | 23.5833 | 33.1875 | 35.7917 | 9.3132 | 276.6704
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0769 | 29.53 | 47.53 | Sabriyah | Horizontal | SAMA | 2017-12-13 17:00:00.000 | Primary Drilling | KDC-57 | M/U 6-1/8" TANDEM SCRAPER BHA & RIH TO 7957 FT (TOP OF LANDING COLLAR). DRILL OUT SHOE TRACK TO 8053 FT (20 FT ABOVE SHOE). CIRCULATE HOLE CLEAN. POOH & L/D TANDEM SCRAPER BHA. P/U & M/U 4" DP. | P/U & M/U 4" DP. PERFORM CEMENT BOND LOG FOR 7" & 9-5/8" CASING. M/U 6-1/8" DIRECTIONAL DRILLING BHA & RIH. DRILL 6-1/8" HORIZONTAL SECTION AS PER PROGRAM. | 5F71655AF1A049689136BF22FEF9F924 | MAKE UP 6-1/8" TANDEM SCRAPER BHA. - 6-1/8" Bit - Bit Sub with float valve - 3 x 4" HWDP - Held PJSM - Change handling equipment to 4" | 41.98 | 27.54 | 2018-01-23 05:31:12.000 | [6 empty] | 2018-01-08 15:30:00.000 | 2017-12-12 17:00:00.000 | 50 | 10980.0004 | 2018-01-07 11:00:00.000 | 0.45833 | 16.7917 | 24.75 | 25.9375 | 1.7671 | 443.6364
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0770 | 29.53 | 47.53 | Sabriyah | Horizontal | Producer | 2018-03-07 16:00:00.000 | Primary Drilling | KDC-57 | CONT. RIH TANDEM SCRAPER BHA TO TOP OF LANDING COLLAR. DRILL OUT SHOE TRACK TO 8003 FT (20 FT ABOVE SHOE). CIRCULATE HOLE CLEAN. POOH TO SURFACE. P/U & M/U 39 joints of 4" DP. WOC | WOC. PERFORM CEMENT BOND LOG FOR 7" & 9-5/8" CASING. M/U 6-1/8" DIRECTIONAL DRILLING BHA & RIH. DRILL 6-1/8" HORIZONTAL SECTION AS PER PROGRAM. | 5F71655AF1A049689136BF22FEF9F924 | HELD PRE JOB SAFETY MEETING PRIOR TO P/U TANDEM SCRAPER BHA - Change handling equipment to 4'' | 42.03 | 23.17 | 2018-04-18 06:42:10.000 | [6 empty] | 2018-04-15 00:00:00.000 | 2018-03-07 16:00:00.000 | 57 | 11550.0004 | 2018-04-13 18:00:00.000 | 7.5417 | 26.9167 | 37.0833 | 38.3333 | 19.6739 | 311.4607
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0771 | 29.53 | 47.53 | Sabriyah | Horizontal | Horizontal | 2018-01-18 16:00:00.000 | Primary Drilling | KDC-57 | RIH WITH 7" & 9-5/8" TANDEM SCRAPER BHA TO 7000 FT. SCRAPE CASING F/ 7000 FT TO 8175 FT. CIRC. HOLE CLEAN. POOH TO 800 FT. | POOH BHA & L/D SCRAPERS. N/U SHOOTING NIPPLE. R/U & PERFORM CEMENT BOND LOG FOR 7" & 9-5/8" CASING. | 5F71655AF1A049689136BF22FEF9F924 | CIRCULATE HOLE CLEAN - FR: 500 gpm, SPP: 2300 psi. - MW in & out: 11.00 ppg. | 40.4 | 25.1 | 2018-02-27 15:36:00.000 | [6 empty] | 2018-02-25 00:00:00.000 | 2018-01-18 16:00:00.000 | 50 | 10750.0003 | 2018-02-23 20:30:00.000 | 5.2917 | 24.9583 | 36.1875 | 37.3333 | 14.1741 | 297.0639
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0792 | 29.55 | 47.52 | Sabriyah | Horizontal | Producer | 2018-04-23 17:30:00.000 | Primary Drilling | KDC-57 | RECORD 7" LINER CEMENT EVALUATION LOGS. R/D LOGGING TOOLS. INSTALLED WEAR BUSHING. N/D SHOOTING NIPPLE. ATTEMPTED TO PRESSURE TEST LINER, NOT HOLDING. WAIT FOR PACKER. RIH 7" CHAMP PACKER TO 4,70 FT. FIX DRAWWORKS (IN PROGRESS). | RIH AND SET 7" PACKER ABOVE LANDING COLLAR AND EVALUATE LINER INTEGRITY. | 5F71655AF1A049689136BF22FEF9F924 | RECORD CEMENT BOND LOG FOR 7" LINER. - R/U Cement bond logging tools for 7" liner. - Record CBL-VDL-GR-CCL on Tractor for 7" liner F/ 8,258 ft to 7,269 ft (TOL). - Recorded USIT F/8,288 ft 7,269 ft - Repeat pass F/8,280 ft 7980 ft. - Recorded GR up to surface. | 42.03 | 23.17 | 2018-06-04 06:42:10.000 | [6 empty] | 2018-06-04 03:30:00.000 | 2018-04-23 17:30:00.000 | 57 | 11320.0004 | 2018-06-03 05:00:00.000 | 10.2917 | 29.5417 | 40.4792 | 41.4167 | 24.8491 | 279.65
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | RA-0716 | 29.8851 | 47.7103 | Raudhatain | Deviated | Natural Flow / ESP | 2018-05-10 17:30:00.000 | Primary Drilling | Sinopec-295 | CONT'D PERFORMING CMT JOB, LIFTED BOP & SET CSG HANGER SLIPS, CUT CSG, N/D BOP, N/U THS & P/T SAME, N/U BOP & P/T SAME, M/U & RIH w/ 8-1/2" CLEAN OUT BHA TO TOC @ 8940 FT, DRILLED OUT CMT TO 9000 FT, CHC. | P/T CSG TO 2000 PSI, CONT. D/O CMT & XCD BIT WHILE DISPLACING WELL TO 9.6 PPG OBM, DRLD 10' NEW FORMATION, PERFORM F.I.T. TO 13 PPG EMW, DROP GYRO & POOH CLEAN OUT BHA TO SURFACE, M/U & RIH 8-1/2" RSS ARCHER BHA, DRILL AHEAD 8-1/2" SECTION AS PER PLAN. | 5F71655AF1A049689136BF22FEF9F924 | HELD PJSM PRIOR TO P/U 8 ½” CLEAN OUT BHA. - Discussed job procedure, JSA & risk controls. - Completed IDS-DRL-CL-002 After-Verify Spud Section Requirements CL. - Completed IDS-E&T-CL-001 After-Verify Bit Specifications CL. - Completed IDS-HCT-CL-002 After-Review Trip In Readiness CL. | 49 | 26.79 | 2018-06-28 05:54:18.000 | [6 empty] | 2018-06-12 23:00:00.000 | 2018-05-10 17:30:00.000 | 63 | 10560.0003 | 2018-06-06 14:00:00.000 | 4.4167 | 17.0208 | 26.8542 | 33.2292 | 13.2915 | 393.2351
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0714 | 29.8189 | 47.8358 | Sabriyah | Horizontal | Mauddud Single Producer Horizontal Well with SSICD Completion | 2018-03-09 18:00:00.000 | Primary Drilling | Sinopec-295 | CONT'D RIH w/ TANDEM SCRAPERS C/O ASSY. F/ 5080 FT TO TOL @ 6741 FT, WASHED DOWN FROM TOL TO TOC @ 7656 FT, DRILLED OUT CMT TO 7718 FT (20 FT ABOVE F.S), CHC, POOH TO SURFACE & L/D SCRAPERS BHA, L/D 8-1/4" DC's FROM MAST, P/T BOP STACK, M/U & R/B 3-1/2" DP STD's ... IN PROGRESS | CONT. R/B 3-1/2" DP STD's, SLIP & CUT DRLG LINE, R/U & RIH WL LOGGING FOR 7" & 9-5/8" USIT-CBL-VDL-GR-CCL LOG, POOH & R/D WL, P/T LINER AGAINST BLIND RAMS, INSTALL WEAR BUSHING, P/U & M/U 6-1/8" VTX BHA, RIH TO TOC @ 7718 FT, DRILL OUT CMT & F.S. WHILE DISPLACING WELL TO FLO-PRO WBM, DRILL AHEAD 6-1/8" SECTION AS PER PLAN. | 5F71655AF1A049689136BF22FEF9F924 | CONT’D RIH 6-1/8" TANDEM SCRAPERS C/O BHA F/ 1515 FT T/ 5080 FT. - Break circulation every 3,000 ft. - Monitored well on trip tank & trip sheet. | 42 | 23.32 | 2018-04-20 05:57:44.000 | [6 empty] | 2018-04-07 09:00:00.000 | 2018-03-09 18:00:00.000 | 53 | 10644.0003 | 2018-04-06 07:00:00.000 | 0.25 | 17.2917 | 27.5417 | 28.625 | 0.87336 | 386.469
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0757 | 29.8198 | 47.8781 | Sabriyah | Horizontal | Mauddud Producer | 2017-11-20 08:00:00.000 | Primary Drilling | Sinopec-295 | CONT'D POOH TO SURFACE & L/D SCRAPERS, L/D EXCESS 5" DP's & HWDP's, R/U & RIH WL LOGGING FOR 7" & 9-5/8" USIT-CBL-VDL-GR-CCL LOG, POOH & R/D WL, P/U & M/U 6-1/8" VTX BHA, RIH TO TOC @ 7833 FT. | P/T 7" LINER TO 2500 PSI, DRILL OUT REMAINING SHOE TRACK WHILE DISPLACING WELL TO 8.8 PPG FLO-PRO WBM, DRILL AHEAD 6-1/8" SECTION FOR 150 FT BELOW THE SHOE IN SLIDING MODE, CHC, POOH TO SURFACE TO ADD LWD TOOLS. | 5F71655AF1A049689136BF22FEF9F924 | RETRIEVED WEAR BUSHING | 42 | 34.23 | 2018-01-01 05:56:32.000 | [6 empty] | 2017-12-22 00:30:00.000 | 2017-11-20 08:00:00.000 | 56 | 11940.0004 | 2017-12-20 19:30:00.000 | 1.6042 | 18.6146 | 30.4792 | 31.6875 | 5.0625 | 391.743
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0772 | 29.8536 | 47.7833 | Sabriyah | Horizontal | Mauddud Producer | 2017-12-31 13:00:00.000 | Primary Drilling | Sinopec-295 | CONT'D RIH TANDEM SCRAPERS C/O BHA, TAGGED ON TOC @ 8457 FT, DRILLED OUT CMT TO 20 FT ABOVE F.S., CHC, WAIT ON WEATHER, POOH TO SURFACE & L/D SCRAPERS, RETRIEVED WEAR BUSHING, N/D BELL NIPPLE & N/U SHOOTING NIPPLE. | M/U & R/B 3-1/2" DP STD's IN MAST, R/U & RIH WL LOGGING FOR 9-5/8" & 7" CBL, N/D SHOOTING NIPPLE, INSTALL WB, P/T CSG TO 2500 PSI, M/U & RIH 6-1/8" DRILLING BHA. | 5F71655AF1A049689136BF22FEF9F924 | FLOW CHECK; WELL STATIC. - Installed DP wiper. Pumped Slug Pill. - Completed IDS-HCT-CL-001 After-Review Trip Out Readiness CL. | 42 | 30.09 | 2018-02-11 06:04:23.000 | [6 empty] | 2018-01-24 01:00:00.000 | 2017-12-31 13:00:00.000 | 56 | 10396.0003 | 2018-01-23 10:45:00.000 | 1.4167 | 14.2083 | 22.9062 | 23.5 | 6.0284 | 453.8499
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0773 | 29.8599 | 47.8872 | Sabriyah | Horizontal | Mauddud Injector | 2018-02-01 06:00:00.000 | Primary Drilling | Sinopec-295 | WAIT ON WEATHER. CONT. RIH 8.5'' CLEAN OUT BHA. TAG TOL. CHC. POOH. M/U & RIH TANDEM SCRAPERS C/O BHA TO 7,745 FT. | CONT. WASH DOWN & SCRAPE 7'' LINER. TAG LANDING COLLAR. DISPLACE WELL TO 11 PPG OBM. POOH TO SURFACE & L/D SCRAPERS, P/U, M/U & R/B 3-1/2" DP STD's, R/U & RIH WL LOGGING FOR 9-5/8" & 7" CBL. | 5F71655AF1A049689136BF22FEF9F924 | CHANGE HANDLING TOOLS TO 3-1/2'' | 42 | 24.55 | 2018-03-15 06:00:55.000 | [6 empty] | 2018-03-03 00:30:00.000 | 2018-02-01 06:00:00.000 | 60 | 10338.0003 | 2018-03-02 08:00:00.000 | 4.0417 | 18 | 29.0833 | 29.7708 | 13.5759 | 355.4613
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0793 | 29.882 | 47.8396 | Sabriyah | Deviated | Injector | 2018-04-15 16:00:00.000 | Primary Drilling | Sinopec-295 | CONT' TO P/T 13-5/8" 5K BOP STACK. M/U & RIH w/ 12-1/4" CLEAN OUT BHA. DRILL OUT DV PLUG. P/T INTEGRITY ACROSS D.V. CONT' TO DRILL AHEAD SHUT OFF PLUG, FC, & SHOE TRACK TO 2O FT ABOVE F.SHOE. CHC. P/T 13-3/8" CSG. DRILL OUT SHOE, 10 FT NEW FORMATION. CHC, PERFORM F.I.T. EMW 12.5 PPG. POOH & L/D 12-1/4" CLEAN OUT BHA. P/U, M/U & RIH 12-1/4" VTX BHA TO 185 FT. | CONT' RIH 12-1/4" VTX BHA TO BTM. DRILL AHEAD 12-1/4" SECTION AS PER PLAN. | 5F71655AF1A049689136BF22FEF9F924 | WASHED DOWN F/ 5,175 FT T/ 5,212 FT (TOC). - Tagged on TOC @ 5,212 ft w/ 10 Klbs. - FR: 400 gpm; SPP: 135 psi. | 30.65 | 17.15 | 2018-05-15 21:34:40.000 | [6 empty] | 2018-05-07 00:30:00.000 | 2018-04-15 16:00:00.000 | 62 | 8945.0003 | 2018-05-02 01:00:00.000 | 1.3958 | 7.6042 | 16.375 | 21.3542 | 6.5366 | 546.2596
EH | NME | Kuwait | 5F71655AF1A049689136BF22FEF9F924 | 730 | 77238 | KOC LSTK | IDS | Gulf | LSTK | SA-0803 | 29.8649 | 47.8181 | Sabriyah | S Shaped | Zubair Dump Flood Water Injector Well | 2018-06-17 15:00:00.000 | Primary Drilling | Sinopec-295 | CONT'D P/T BOP, L/D TEST ASSY, INSTALLED WB, WAIT ON WEATHER, M/U & RIH w/ 8 ½” CLEAN OUT BHA TO DVT PLUG @ 8748 FT, DRILLING OUT DVT CLOSING PLUG ... in progress | CONT. DRILLING OUT DVT CLOSING PLUG, P/T 9-5/8" CSG TO 2000 PSI, CONT. RIH TO B.C. @ 9215 FT, DRILL OUT SHOE TRACK TO 20 FT ABOVE XCD BIT, P/T 9-5/8" CSG TO 2000 PSI, CONT. DRLG OUT SHOE TRACK, XCD BIT & 10 FT NEW FORMATION, PERFORM FIT, DROP GYRO & POOH TO SURFACE, M/U & RIH w/ 8 ½” VTX BHA, DRILL AHEAD 8 ½” SECTION AS PER PLAN. | 5F71655AF1A049689136BF22FEF9F924 | P/U & M/U 8 ½” CLEAN OUT BHA, RIH TO 1017 FT. - M/U RR 8 ½” PDC Bit, MDi616LPXG, S/N: JM5470, Noz: 6 x 14. - Bit Sub (with Float Valve & Totco Ring). - 6 jts x 6 ½” DC's. - 18 jts x 5” HWDP’s. - 6 ½” Hydra Jar (S/N: WDAH-02959). - 8 jts x 5" HWDP’s. * Below Jar WT. = 33 Klbs. * Total BHA WT. = 43 Klbs. | 49 | 26 | 2018-08-05 06:05:58.000 | [6 empty] | 2018-08-16 07:00:00.000 | 2018-06-17 15:00:00.000 | 61 | 10808.0003 | 2018-08-02 19:30:00.000 | 15.7292 | 30.5208 | 46.1875 | 59.6667 | 26.3617 | 234.0027
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-131 | 27.3341 | 48.9615 | ABU HADRIYA | Horizontal | PML | 2019-02-25 19:00:00.000 | Primary Drilling | AD-57 | CONT'D RIH 6-1/8" VTX BHA F/ 1190 FT TO 4300 FT, CHANGED SAVER SUB, SLIP & CUT DRLG LINE, CONT'D RIH TO BTM @ 13,917 FT WHILE RE-LOGGING LAST 150 FT, DRILLED AHEAD 6-1/8" SECTION L0 MOTHER BORE TO 13,970 FT, ADN TOOL NOT WORKING, POOH TO 4000 FT. | CONT. POOH TO SURFACE, CHANGE ADN TOOL, RIH BACK TO BTM, RESUME DRILLING 6-1/8" SECTION L0 MOTHER BORE AS PER PLAN TO TD @ +/- 17,141 FT. | 62481F155524482FBF7BCF291DA70620 | POOH 6-1/8" VTX BHA TO 11,340 FT. - MONITORED WELL ON TRIP TANK & TRIP SHEET. - POOH SPEED = 19 STD's/HR. | 120.8 | 91.53 | 2019-07-29 00:29:15.000 | 281 | 463.96 | 20190426135104 |  |  |  | 2019-07-29 13:00:00.000 | 2019-02-25 19:00:00.000 | 0 | 18373.0006 | 2019-07-01 20:00:00.000 | 76.0938 | 89.6563 | 126.0417 | 153.75 | 49.4919 | 145.7693
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-141 | 27.3112 | 49.0175 | ABU HADRIYA | Horizontal | PHZ | 2019-08-07 23:30:00.000 | Primary Drilling | AD-57 | P/T 7" LINER, DRILL OUT SHOE TRACK TO 20' ABOVE F/S, P/T 7" LINER, CONT. DRLG OUT SHOE TRACK & 5' NEW FORMATION WHILE DISPLACING WELL TO LSND MUD, FLOW CHECK, DRILL 6-1/8" HOLE SECTION TO 12,184 FT. | DRILL 6-1/8" HOLE SECTION AS PER PLAN TO TD AT 14,114 FT. | 62481F155524482FBF7BCF291DA70620 | DRLD 5 FT NEW FORMATION OF 6-1/8" SECTION F/ 11,500 FT TO 11,505 FT. - WOB: 5-10 KLB, RPM: 40, TRQ: 4-6 K FT-LB. - FR: 250 GPM, SPP: 2300-2350 PSI. - CONT'D DISPLACING WELL TO 76 PCF LSND MUD. | 35.31 | 46.11 | 2019-09-11 12:22:17.000 | 281 | 405.5747 |  |  |  |  | 2019-09-26 16:00:00.000 | 2019-08-07 23:30:00.000 | 0 | 14114.0005 | 2019-09-18 10:00:00.000 | 10.8333 | 29.7292 | 41.4375 | 49.6875 | 21.8029 | 340.6094
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-614 | 27.3353 | 49.0074 | ABU HADRIYA | Horizontal | PWI | 2018-12-29 22:00:00.000 | Primary Drilling | AD-57 | DRILL 6 1/8" SECTION F/ 11,855 FT TO 13,279 FT | DRILL 6 1/8 SECTION TO 16,204 FT TD. | 62481F155524482FBF7BCF291DA70620 | DRILLED 6 1/8" HOLE F/ 11542 FT TO 11855 FT W/ 72 PCF LSND MUD TREATED W/ 4% LUBRICANT (DIESEL+ LUBE) - WOB 10-20 KLB, 290 GPM, 3000-3350 PSI, 80-100 RPM, 7-8 KLB-FT, MOTOR DIFFERENTIAL 350-450 PSI. - OPTIMIZED PARAMETERS TO MITIGATE SnS. - ON BTM ROP= 70-90 FT/HR - PUMP TANDEM PILLS 10 BBL LOW-VIS 20 BBL HI-WT EVERY STAND - CONNECTION: BACK-REAM 30 FT, TAKE T&D MEASUREMENTS, REAM DOWN AND MAKE CONNECTION - TAKE SURVEY AFTER CONNECTION - FORMATION - ARBA3 - LAST SURVEY: MD 11654.00 FT, INC 88.07°, AZIMUTH 353.36°, TVD 8814.99 FT - TRAJECTORY INFORMATION: 17' ABOVE / 19' LEFT. | 38.52 | 33.55 | 2019-02-14 11:55:30.000 | 301 | 446.51 |  |  |  |  | 2019-02-14 12:00:00.000 | 2018-12-29 22:00:00.000 | 0 | 16204.0005 | 2019-02-04 07:15:00.000 | 1.2188 | 21.7813 | 36.3854 | 46.5833 | 2.6163 | 445.3433
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-615 | 27.2903 | 49.0254 | ABU HADRIYA | Horizontal | PWI | 2018-10-25 15:00:00.000 | Primary Drilling | AD-57 | DRILL 6-1/8" SECTION FROM 9985 FT TO 10870 FT. | DRILL 6-1/8" SECTION TO 14613 FT SECTION TD. | 62481F155524482FBF7BCF291DA70620 | DRILL OUT CEMENT, FS, RATHOLE, AND 10FT OF FORMATION FROM 9940 TO 9978FT. - WOB 4-6 KLB, 240 GPM, 2200 PSI, 40 RPM, 4.5 KFT.LB, MOTOR DIFFERENTIAL 200-250 PSI. - 100FT/HR MAX ROP AS PER GOC | 36.84 | 30.07 | 2018-12-22 05:00:00.000 | 439.64 | 439.64 |  |  |  |  | 2018-12-22 04:00:00.000 | 2018-10-25 15:00:00.000 | 0 | 14664.0005 | 2018-12-14 01:15:00.000 | 3.9167 | 34.3542 | 49.4271 | 57.5417 | 6.8067 | 296.6795
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-629 | 27.335 | 49.0086 | ABU HADRIYA | Horizontal | PWI | 2019-10-06 05:45:00.000 | Primary Drilling | AD-57 | CONT'D DRLD 12-1/4" SECTION WITH ROTARY BHA TO 5310 FT. | CONT. DRLG 12-1/4" SECTION AS PER PLAN TO +/- 6262 FT (50' ABOVE SHU'AIBA). | 62481F155524482FBF7BCF291DA70620 | CONT'D DRLG 12 ¼” VERTICAL HOLE F/ 5135' TO 5202'. - CONTROLLED ROP AT 50 FPH. - WOB: 10-30 KLB, SRPM: 100-120, DRLG TRQ: 5-10 FT-LB. - FR: 880 GPM, SPP: 3250 PSI. - INTERVAL = 67 FT, AV ON BOTTOM. ROP = 50 FPH. - PUMPED 20 BBL's HI-VIS PILL TWICE EVERY STD. - MAINTAINED 25 PPB LCM IN ACTIVE SYSTEM - WASHED UP & REAMED DOWN 15’ BEFORE CONNECTION. - MW IN & OUT = 80 PCF. - NO DOWNHOLE LOSSES. | 33.75 | 33.75 | 2019-11-11 08:40:18.000 | [6 empty] | 2019-10-22 06:00:00.000 | 2019-10-06 04:00:00.000 | 0 | 5316.0002 | 2019-10-21 06:00:00.000 | 0 | 9.8229 | 15.0104 | 16.0104 | 0 | 354.1541
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FDHL-154 |  |  | FADHILI | Deviated | PHZ +P | 2019-02-25 17:30:00.000 | Primary Drilling | AD-58 | COMPLETED EXTENDED FLOW CHECK @ 10,302 FT (10 FT INSIDE LOWER FADHILI), WELL STATIC. DRILL AHEAD 6 1/8" SECTION AS PER PLAN TO 10,342 FT. CIRCULATED 1 x B/U. PERFORMED EXTENDED FLOW CHECK AS PER ARAMCO (50 FT INSIDE LFDR), WELL STATIC. RESUMED DRILLING DIRECTIONAL 6 1/8" SECTION AS PER GOC TO 10,607 FT. | CONT/ DRILLING AHEAD DIRECTIONAL 6 1/8" SECTION AS PER GOC PROJECTED TD @ 10,627 FT. | 62481F155524482FBF7BCF291DA70620 | **OUT OF SCOPE. CONT. DRILLING DIRECTIONAL 6 1/8" HOLE FROM 10,517 FT TO 10607 FT. - FORMATION: LOWER FADHILI, TOP @10,292 MD / 9,637 FT TVDSS. - WOB 20-25 KLB, FR: 250 GPM, SPP: 2370-2630 PSI. - RPM: 80-90 RPM, TRQ: 5.2 KLBS*FT, MOTOR DIFF. PRES.: 100-450 PSI. - ROP: 8 FT/HR - ADDED 4% LUBE 167 INTO ACTIVE. - OBSERVED LOW ROP FROM 10,510 FT, APPLIED MAX PARAMETERS 25 KLBS WOB @350-450 PSI DIFF. PRESSURE. - MW IN = 77 PCF, MW OUT = 77 PCF. - NO DOWNHOLE LOSSES. - LAST SURVEY: MD 10,502 FT, INC 35.46°, AZIMUTH 44.01°, TVD 9,944.69 FT. - COMPARISON TO PLAN: 0.64 FT ABOVE, 3.6 FT LEFT OF PLAN. - DRILLED FOOTAGE (DAILY/TOTAL), FT = 305/363 - TOTAL DRILLING TIME (DAILY/TOTAL), HR = 21.25/26.75 - AVERAGE ROP (DAILY/TOTAL), FT/HR = 14/13.5 - 4-3/4" HYDRO JAR ROT HR (DAILY/TOTAL): 22.75/27.75 | 124.99 | 55.73 | 2019-09-13 23:45:00.000 | 281 | 485.5937 |  |  |  |  | 2019-09-12 12:00:00.000 | 2019-02-25 17:00:00.000 | 0 | 15700.0005 | 2019-07-31 22:45:00.000 | 38.3646 | 125.3438 | 156.2188 | 198.7708 | 19.3009 | 100.5001
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FDHL-627 | 27.0006 | 49.2255 | FADHILI | Horizontal | PWI | 2018-11-09 15:00:00.000 | Primary Drilling | AD-58 | DRILL OUT CEMENT. P/T 7" LINER @20 FT ABOVE CSG SHOE. D/OUT CMT .SHOE & 10 FT FORMATION. DISPLACE WELL TO 88 PCF LSND MUD. DRILL 6-1/8" SECTION AS PER PROGRAM. | DRILL 6-1/8" SECTION AS PER PROGRAM. | 62481F155524482FBF7BCF291DA70620 | FLOW CHECK, WELL STATIC. - TOOK SCR'S WITH BOTH MP'S. | 73.96 | 64.37 | 2019-02-10 21:42:00.000 | 301 | 412.07 |  |  |  |  | 2019-02-10 17:00:00.000 | 2018-11-09 15:00:00.000 | 0 | 17572.0006 | 2019-01-07 12:15:00.000 | 5.9688 | 36.6875 | 58.8854 | 93.0833 | 6.4123 | 298.4101
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | KRSN-130 | 27.1864 | 49.1981 | KHURSANIYAH | Deviated | EVOB | 2019-09-28 20:00:00.000 | Primary Drilling | AD-58 | DRILL 121/4" F/ 3525 FT TO 4329 FT, CIRC HOLE CLEAN CONT. DRILL TO 4370 FT | CONT, DRILLING 12-1/4" SECTION TO TD @3982 FT, CHC, SPOT CASING GO PILL, POOH TO SURFACE | 62481F155524482FBF7BCF291DA70620 | DRILLED 12¼" VERTICAL SECTION W/ 77 PCF MUD FROM 3,885 FT TO 4329 FT (50 FT ABOBE TOP OF SHUAIBA). - WOB=5-15 KLBS, FR=700 GPM, RPM=100, SPP=1900 - 2000 PSI, TQ=2-6 KLB-FT. - AVG ROP = 38 FT/HR. - FORMATION TOP KHAFJI : 3966 FT - PUMP 20 BBL HI-VIS PILL EVERY 45 FT - WASH UP & REAM DOWN 1JT BEFORE CONNECTION. - TAKE SURVEYS 30 FT OFF BTM - MAINTAIN 40 PPB LCM IN ACTIVE SYSTEM. - NO LOSSES. | 56.44 | 45.02 | 2019-11-22 19:03:36.000 | [6 empty] | 2019-10-22 02:30:00.000 | 2019-09-28 20:00:00.000 | 42 | 4938.0002 | 2019-10-20 15:30:00.000 | 4.4583 | 15.4896 | 21.8125 | 23.2708 | 19.1585 | 226.384
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-150 |  |  | ABU HADRIYA | Horizontal | PHZ | 2019-08-07 08:00:00.000 | Primary Drilling | AD-62 | CONT. DRILL AHEAD 6 1/8" DIR HOLE TO WELL TD OF 13096 FT. CHC, PERFORM SHORT WIPER TRIP TO 12192 FT. DISPLACE WELL TO 74 PCF VIS-BRINE. EXTENDED FLOW CHECK, POOH 6 1/8" VORTEX BHA TO 11377 FT. | CONT. POOH 6 1/8" VORTEX BHA TO SURFACE, RUN & JET BOP. P/U & RIH CLEAN OUT BHA TO 9998 FT. DISPLACE CH TO 74 PCF INHIBITED BRINE. POOH. | 62481F155524482FBF7BCF291DA70620 | SERVICED TOP DRIVE. | 41.9 | 37.43 | 2019-09-28 03:00:00.000 | 281 | 376.32 |  |  |  |  | 2019-09-28 03:00:00.000 | 2019-08-07 08:00:00.000 | 0 | 13096.0004 | 2019-09-20 13:30:00.000 | 6.3958 | 31.8542 | 44.2292 | 51.7917 | 12.3492 | 296.0942
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-618 | 27.2902 | 49.0243 | ABU HADRIYA | Horizontal | PWI | 2018-06-06 15:30:00.000 | Primary Drilling | AD-62 | CONT. RIH 6 1/8" DIR BHA, DRILL SHOE TRACK AND 6 1/8" HOLE SECTION TO 12745 FT | DRILL 6 1/8'' HOLE SECTION TO 16168 FT MD, PLANNED TD. | 62481F155524482FBF7BCF291DA70620 | SETTING MWD/LWD TOOLS AND SENDING DOWN LINKS TO RSS. | 48.15 | 31.01 | 2018-09-09 12:45:00.000 | 439.64 | [5 empty] | 2018-09-16 11:00:00.000 | 2018-06-06 15:00:00.000 | 0 | 16168.0005 | 2018-09-02 06:15:00.000 | 36.0417 | 62.8125 | 87.6146 | 101.8125 | 35.4 | 184.5355
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-626 |  |  | ABU HADRIYA | Horizontal | PWI | 2019-01-21 01:00:00.000 | Primary Drilling | AD-62 | CONT. DRILL AHEAD 6 1/8" SECTION FROM 9950 FT TO 11320 FT WITH 75 PCF LSND MUD. | CONT. DRILL AHEAD 6 1/8" SECTION TO WELL TD AT PER PLAN P11. | 62481F155524482FBF7BCF291DA70620 | SEND DOWNLINK TO INCREASE STEERING RATIO - NO ACCEPTED. CHANGED TO COLLAR RPM MODE - OK. | 36.85 | 32.11 | 2019-03-07 18:15:00.000 | 301 | 423.21 |  |  |  |  | 2019-03-07 22:30:00.000 | 2019-01-21 01:00:00.000 | 0 | 14440.0005 | 2019-02-27 20:00:00.000 | 2.0417 | 25.3333 | 37.7917 | 45.8958 | 4.4485 | 382.0948
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ABHD-627 | 27.29 | 49.025 | ABU HADRIYA | Horizontal | PWI | 2018-09-20 20:00:00.000 | Primary Drilling | AD-62 | DRILL AHEAD 6 1/8'' HORIZONTAL SECTION AS PER P6 FROM 12209 FT TO 13750 FT WITH 74 PCF LSND MUD. | CONT. DRILL AHEAD 6 1/8'' HORIZONTAL SECTION AS PER P6 TO SECTION TD OF 15789 FT MD. | 62481F155524482FBF7BCF291DA70620 | DRILLED AHEAD 6 1/8" NEW FORMATION F/ 12209 FT TO 12219 FT. (CONTROLLED PARAMETERS) - FR: 245 GPM, SPP: 2450 PSI, SRPM: 40 RPM(+ DHM ROT 127),, WOB 5-10 KLB & TQ: 6-8 KLB-FT. | 36 | 31.31 | 2018-11-22 06:45:45.000 | 439.64 | 439.64 |  |  |  |  | 2018-11-27 11:30:00.000 | 2018-09-20 20:00:00.000 | 30.6 | 15789.0005 | 2018-11-13 04:00:00.000 | 13.4792 | 39.2188 | 53.3333 | 67.6458 | 19.9261 | 296.0438
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FDHL-630 |  |  | FADHILI | Horizontal | PWI | 2019-03-19 04:00:00.000 | Primary Drilling | AD-62 | CONT. DRILL CMT FROM 11900 TO 12056 FT, DISPLACE HOLE TO 69 PCF MUD. P/T 7" LINER. DRILL CMT & 6 1/8" HOLE TO 12090 FT FORFORM FLOW CHECK. CONT. DRILL 6 1/8" HOLE TO 12111 FT. PERFORM FLOW CHECK. DISPLACE HOLE TO 70 PCF, PEFORM FLOW CHECK. | STABILIZE WELL. CONTINUED DRILLING 6 1/8'' HOLE SECTION TO 12280 FT. CIRC. POOH TO CHANGE TO 6 1/8'' TRIPLE COMBO L0 BHA. RIH & DRILL AHEAD 6 1/8'' HOLE. | 62481F155524482FBF7BCF291DA70620 | OUT OF SCOPE : AT 12111 FT. PERFORMED FLOW CHECK. NOTICED SLIGHT RETURNS 0.08 BBL/HR DECREASED TO 0.03 BBL/HR. POOH TO SHOE. SHUT IN WELL. - OBSERVED SHUT IN PRESSURES 1HR. SICP = 0 PSI. - OPEN WELL THRU CHOKE, OBSERVED WELL FOR 1.5 HRS : RETURNS DECREASED GRADUALLY F/ 0.1 BPH TO STATIC - PRECAUTIONARY DECIDED TO INCREASE MW TO 70 PCF. ** MIXED & PREPARED 70 PCF HOLE DISPLACEMENT VOLUME. | 90.69 | 83.52 | 2019-07-28 10:30:00.000 | 301 | 311.22 |  |  |  |  | 2019-07-31 11:00:00.000 | 2019-03-19 04:00:00.000 | 0 | 17034.0005 | 2019-06-28 18:30:00.000 | 35.2083 | 74.5938 | 101.6042 | 134.2917 | 26.2178 | 167.6506
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | KRSN-138 |  |  | KHURSANIYAH | Horizontal | PHZ | 2019-10-11 12:30:00.000 | Primary Drilling | AD-62 | P/U & M/U 16" ROTARY BHA. RIH. DRILL OUT 18 5/8" SHOE TRACK TO 470 FT, P/T CSG. DRILL AHEAD 16" HOLE TO 1234 FT. CHC. | CONT DRILL AHEAD 16" HOLE TO +/- 2881 FT. | 62481F155524482FBF7BCF291DA70620 | DRILLED 16" VERTICAL HOLE F/ 497 FT TO 548 FT. - CONTROLLED FR & RPM FOR 2 STD's BELOW SHOE. - WOB: 5 KLB, RPM 50 , DRLG TRQ: 2-5 KFT-LB. FR: 730 -830 GPM, SPP: 900 PSI. - PUMPED 30 BBL's MID STAND & 60 HI-VIS PILL BEFORE CONNECTION. - WASHED UP & REAMED DOWN ONE JOINT. - MW IN & OUT = 65 PCF. - SURFACE VIBRATION, ADJUST PARAMETERS ACCORDINGLY - AV. ROP = 34 FPH. - NO DOWNHOLE LOSSES. - FORMATION: RUS. | 36.38 | 32.5 | 2019-11-17 11:50:24.000 | [6 empty] | 2019-10-22 05:00:00.000 | 2019-10-11 12:30:00.000 | 36 | 2600.0001 | 2019-10-22 05:00:00.000 | 0.36458 | 7.6771 | 10.6875 | 10.6875 | 3.4113 | 243.2749
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-3034 | 25.7182 | 49.286 | AIN DAR | Horizontal | PHZ | 2019-03-16 09:00:00.000 | Primary Drilling | AD-63 | CONTINUE RIH W/ 6 1/8'' RSS ASSY. ON 4'' D/P T/ 9,900 FT, CONNECT X/O & 5'' D/P STDS, WASH DWN, TAG T.O.C @ 10,096 FT D/O T/ 20 FT ABOVE F.SHOE, PERFORMED CIT, DISPLACE THE HOLE T/ 66 PCF LSND MUD, DRILL 5 FT INTO NEW FM T/ 10,355 FT, FLOW CHECK, DRILL 6 1/8'' HZ SECTION W/ VORTEX RSS W/ LWD F/ 10,355 FT T/ 10,650 FT. | CONTINUE DRLG 6 1/8'' HZ SECTION T/ +/- 13,970 FT STD AS PER GOC. | 62481F155524482FBF7BCF291DA70620 | DRLG 6 1/8'' HZ SECTION W/ RSS VORTEX BHA F/ 10,355 FT T/ 10,410 FT. - FR:260 GPM , P.P: 2,450 PSI. - WOB: 5-10 KLB, RPM: 60, TQ: 7 KLB.FT . - DRILL OFF 3 MIN, REAM UP 15 FT AT 5-8 FT/MIN SPEED W/ 40 RPM UP & DWNW/ 60. - AVG ROP: 38 FT/HR. - M.WT IN=M.WT OUR= 67 PCF. | 35.49 | 31.67 | 2019-05-06 16:30:03.000 | 281 | 496.98 |  |  |  |  | 2019-05-07 00:30:00.000 | 2019-03-16 09:00:00.000 | 31 | 13970.0004 | 2019-04-23 00:30:00.000 | 3.6875 | 26.3646 | 37.6458 | 51.6458 | 7.14 | 371.0902
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-3036 | 25.7183 | 49.2858 | AIN DAR | Horizontal | PHZ | 2019-05-24 05:00:00.000 | Primary Drilling | AD-63 | DRILL 6-1/8" HOLE F/ 10,760 FT T/ 12,400 FT. | DRILL TO 12622 FT. PERFORM WIPER TRIP AND ADD MORE 4" DP. DRILL 6-1/8" HOLE TO SECTION TD (+/- 14,175 FT). | 62481F155524482FBF7BCF291DA70620 | DRILL 6 -1/8'' HZ SECTION F/ 10,760 FT T/ 10,875 FT WITH CONTROLLED PARAMETER. (BHA) - FR= 280 GPM , SPP= 2,450 PSI. - WOB=5-10 KLB, RPM= 50, TQ=7 KLB.FT . - AVG ROP=46 FT/HR. - M.WT IN=M.WT OUR= 66 PCF. - NO LOSSES. - REAM UP/DOWN 20 FT AFTER DRILL OFF | 36.67 | 32.72 | 2019-07-08 13:57:51.000 | 281 | 457.75 |  |  |  |  | 2019-07-08 00:00:00.000 | 2019-05-24 05:00:00.000 | 31 | 14648.0005 | 2019-06-26 20:00:00.000 | 2.6979 | 23.9271 | 33.625 | 44.7917 | 6.0233 | 435.6283
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-3038 |  |  | AIN DAR | Horizontal | PHZ | 2019-07-16 11:00:00.000 | Primary Drilling | AD-63 | DRILL HZ SECTION TO F/ 9,065 FT T/ 9,751FT, WASH PIPE LEAKING, POOH INSIDE 7'' CSG SHOE T/ CHANGE WASH PIPE, CONTINUE DRLG 6 1/8'' HZ SECTION F/ 9,751 FT T/ 9,873 FT. | DRILL HZ SECTION TO +/- 11,884FT. PERFORM WIPER TRIP AND ADD MORE 4" DP. DRILL 6-1/8" HOLE TO SECTION TD (+/- 13,148 FT). | 62481F155524482FBF7BCF291DA70620 | R/B 5X5'' D/P STD & RIH W/ 9 JTS X 4'' D/P IN SINGLES T/ 9,030 FT (ON GOING). - CHANGE ELEVATOR & SLIPS F/ 5'' T/ 4''. | 44 | 34.84 | 2019-09-14 17:40:20.000 | 281 | 472.95 |  |  |  |  | 2019-09-10 10:00:00.000 | 2019-07-16 11:00:00.000 | 31 | 13148.0004 | 2019-08-20 19:15:00.000 | 17.625 | 23.7917 | 35.3438 | 55.9583 | 31.4966 | 372.0035
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-3039 |  |  | AIN DAR | Horizontal | PHZ | 2019-09-19 12:00:00.000 | Primary Drilling | AD-63 | CONTINUE DRILL 8-1/2'' PILOT HOLE TO CORING POINT AT 6,680 FT, CHC, POOH 4 STDS T/ 6,350 FT, RE-LOG @ 6,365 FT | CONTINUE RELOG T/ 6,680 FT, CHC, POOH W/ 8-1/2'' BHA T/ SURFACE, RIH W/ CORING ASSY. | 62481F155524482FBF7BCF291DA70620 | DRLG 8½" VERTICAL HOLE F/ 5,853 FT TO 6,350 FT W/ 81 PCF LOW CHLORIDE NACL POLY MUD. - WOB: 15-25 KLB, FR:570 GPM, SPP: 2,400 PSI. - RPM: 100 , DRLG TRQ: 3-6 K FT-LB. - AV. ROP: 79.5 FT/HR. - DRLD OFF, BACK REAM 15 FT, RECORD T&D, REAM DOWN, MAKE CONNECTION, TAKE SURVEY. - SWEEP HOLE W/ 30 BBL HI VIS EVERY 3 STDS. - HITH FM @ 5,804 FT. - NO LOSSES. - FM TOPS: ABAR@ 6279 FT TVD, ARBB @ 6312 FT TVD | 61.25 | 51.62 | 2019-11-21 07:03:28.000 | [6 empty] | 2019-10-22 01:00:00.000 | 2019-09-19 12:00:00.000 | 31 | 8498.0003 | 2019-10-15 10:15:00.000 | 0.45833 | 19.4375 | 25.9271 | 32.5417 | 1.4085 | 327.7654
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-598 | 25.99 | 49.267 | AIN DAR | Horizontal | PHZ | 2018-07-06 22:00:00.000 | Primary Drilling | AD-63 | FIN'D DRILLING 6 1/8'' SIDETRACK T/ 8,205',FLOW CHECK , POOH T/ SURFACE,HELD PJSM , P/U & M/U 6 1/8'' VORTEX DIRECTIONAL BHA W / LWD. SAFETY: PTW:5, JSA: 8 , STOP CARDS: 14 | RIH W/ 6 1/8'' DIRECTIONAL VORTEX ASSY.. W/ LWD (GAMMA-NEUTRON-DENSITY) T/ BTM, WASH DOWN LAST STD, CONT'D DRLG T/ +/- 11,330'. | 62481F155524482FBF7BCF291DA70620 | ROTATING DRILLING F/ 8,130' / ,8140' AS PER DD INSTRUCTIONS. - FR: 250 GPM , RPM: 30 , P.P:2,200 , TQ: 4-4.5 KLB.FT , WOB: 10-15 KLB. -PUMPED TANDEM PILL (10 BBL LOW VIS/20 BBL HI WT VIS) @ THE BEGINING OF STAND FOR HOLE CLEANING. | 33.74 | 30.65 | 2018-09-05 15:46:48.000 | 472.14 | [5 empty] | 2018-09-11 13:00:00.000 | 2018-07-06 22:00:00.000 | 0 | 11330.0004 | 2018-08-27 14:30:00.000 | 13.8229 | 37.1146 | 51.6875 | 66.625 | 20.7473 | 219.2019
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-700 | 25.86 | 49.13 | AIN DAR | Vertical | EV | 2018-11-22 19:00:00.000 | Primary Drilling | AD-63 | DRILL OUT SHOE TRACK AND P/T 9-5/8" TO 1100 PSI 20 FT ABOVE FS. DISPLACE MUD TO 80 PCF. DRILL 8-1/2" VERTICAL HOLE TO 7088 FT (STD). SWEEP HOLE WITH HVP AND CHC IN PROGRESS. | CONT CHC. POOH WITH 8-1/2" DRILLING BHA TO 540 FT. M/U STRING MILL AND CSG SCRAPPER. RIH FOR WIPER TRIP AND CLEAN OUT RUN FOR 9-5/8" CSG. POOH TO SURFACE AND L/D BHA. PROCEED WITH W/L RUN AS PER PROGRAM. | 62481F155524482FBF7BCF291DA70620 | DRILL 8-1/2" VH FROM 6,515 FT TO 7,088 FT (STD). - FR=550 GPM; SPP=2000 PSI; - WOB=10-25 KLBS; RPM=100; TQ=6-8 KFT.LBS - WASH UP & REAM DWN EVERY STD DRILLED. - RECORD SURVEY EVERY DRILLED STD. - SWEEP HOLE WITH 20 BBL HVP ERVERY 2 STD. - AV. ROP=36.4 FPH - NO LOSSES. - MAX GAS READING REACHED=36 %. | 61.79 | 51.43 | 2019-02-21 15:33:36.000 | 203 | 339.95 |  |  |  |  | 2019-02-21 11:00:00.000 | 2018-11-22 19:00:00.000 | 31 | 7088.0002 | 2019-02-04 04:30:00.000 | 14.8958 | 62.0104 | 73.3958 | 90.6667 | 16.4292 | 96.5722
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | ANDR-3022 | 25.9222 | 49.2422 | AIN DAR | Horizontal | PHZ LFDL | 2019-09-23 23:00:00.000 | Primary Drilling | AD-68 | CONT DRILLING 6-1/8" HORIZONTAL HOLE F/12,475' T/13,007'. TROUBLESHOT D&M TOOLS. CHC WITH 3 TANDEM PILL. POOH T/XXX'. | CONTINUE POOH AND CHANGE ALL D&M TOOLS. RIH TO BTM AND RESUME DRILLING 6-1/8" HORIZONTAL HOLE SECTION' T/15,350 (STD). | 62481F155524482FBF7BCF291DA70620 | RECORDED SCR. - MEANWHILE ROTATING STRING 40 RPM. | 36.3 | 36.3 | 2019-11-03 06:00:00.000 | [6 empty] | 2019-10-22 01:30:00.000 | 2019-09-23 23:00:00.000 | 0 | 13007.0004 | 2019-10-21 13:30:00.000 | 1.0208 | 17.3542 | 27.6042 | 28.1042 | 3.6323 | 471.197
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-213 | 26.2703 | 49.1664 | FAZRAN | Horizontal | PWI | 2019-05-03 15:30:00.000 | Primary Drilling | AD-68 | CONT WASH DOWN TO TOL. P/T 7" LINER PKR. RIH TO TOC. P/T 7" LINER. D/O CMT UNTIL 20' ABOVE 7" LINER SHOE. P/T 7" LINER. D/O SHOE TRACK WHILE DISPLACE TO LSND 78 PCF MUD. DRILLING 6-1/8" HORIZONTAL HOLE F/8,227' T/8,540'. | CONT DRILLING 6-1/8" HORIZONTAL HOLE AS PER PLAN#6 T/10,917’ (STD). | 62481F155524482FBF7BCF291DA70620 | DRILLED NEW FORMATION F/8,227' T/8,234' (7'). WITH CONTROLLED PARAMETERS. - FR: 250 GPM, SPP: 2,200 PSI, RPM: 30-40, WOB: 10-15 KLB, TQ: 3.0-4.0 KFT.LB, DIFF P: 380 PSI. | 27.45 | 23.14 | 2019-06-18 23:58:57.000 | 281 | 317.35 |  |  |  |  | 2019-06-19 00:00:00.000 | 2019-05-03 15:30:00.000 | 0 | 10917.0003 | 2019-06-11 09:30:00.000 | 9.5729 | 28.6562 | 38.75 | 46.3542 | 20.6517 | 281.729
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-301 | 26.2692 | 49.1702 | FAZRAN | Horizontal | PML | 2019-06-26 08:00:00.000 | Primary Drilling | AD-68 | CONT. P/U & M/U 12-1/4" ROTARY BHA AND RIH TO TOC. DRILL SHOE TRACK, DRILL AHEAD 12-1/4" HOLE T/4,220'. CIRC BTM UP. CONT DRILLING 12-1/4" HOLE BY SINGLE T/4,340'. OBSERVED TOTAL LOSSES. PUMPED 150 BBL MUD CAP. BLIND DRILLING 12-1/4" HOLE T/4,391'. OBSERVED WELL FLOWING AFTER FLOW CHECK. SHUT IN THE WELL. | BULLHEAD 100 BBL MUD CAP INTO FM. FLOW CHECK. CONT BLIND DRILLING 12-1/4" VETICAL HOLE TO +/- 4,733' (STD). SWEEP & CIRC HOLE. PERFORM WIPER TRIP. POOH & L/D 12-1/4" BHA. RUN 9-5/8" CSG AND CMT SAME. | 62481F155524482FBF7BCF291DA70620 | DRILL 12-1/4" VERTICAL HOLE F/ 3,384' T/4,220' (50' ABOVE SHUAIBA). - WOB: 6-15 KLB, FR: 700-750 GPM, SPP: 1350-1450 PSI, RPM: 95, TQ (OFF/ON TBM): 3-11 KFT*LBS. - AVG ROP: 107.8 FPH. - 100% RETURN. - ERRATIC TQ OBSERVED. - PUMP 30 BBLS HVP EACH STAND. - DRILL OFF 2-3 MIN'S. - REAM UP/ DOWN LAST SINGLE. - KCL/ SALT POLYMER MUD 73 PCF IN/OUT. - LOADED ACTIVE SYSTEM W/ 10 PPB F-M & NUT PLUG 10 PPB OF LCM. - TOP OF SAFANIYA FM AT 3,448'. | 48.48 | 46.21 | 2019-08-22 21:54:38.000 | [6 empty] | 2019-07-20 19:00:00.000 | 2019-06-26 08:00:00.000 | 0 | 4730.0002 | 2019-07-13 07:30:00.000 | 24.3958 | 13.1458 | 16.9792 | 24.4583 | 99.7445 | 278.5767
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-315 | 26.2334 | 49.185 | FAZRAN | Horizontal | PHZ | 2019-07-31 16:30:00.000 | Primary Drilling | AD-68 | DRILLED 6-1/8" HOLE F/ 7,960' T/ 9,613' (1,653'' PROGRESS). ADDED 2% DIESEL & INCREASED LUBE TO 3% IN 78 PCF ACTIVE MUD SYSTEM. | CONT. DRILL AHEAD 6-1/8" HOLE SECTION AS PER DIRECTION PLAN TO 11,677' MD/ 7096' TVD. | 62481F155524482FBF7BCF291DA70620 | SERVICE & LUBE TDS - PERFORM DROP OBJECT SURVEY. - RECORD SCR ON SWACO AND STAND PIPE MANIFOLD FOR BOTH MUD PUMPS | 38.95 | 38.95 | 2019-09-13 09:15:00.000 | 281 | 399.2123 |  |  |  |  | 2019-09-13 12:00:00.000 | 2019-07-31 16:00:00.000 | 0 | 11657.0004 | 2019-09-02 08:45:00.000 | 3.7396 | 23.2396 | 32.6771 | 43.8125 | 8.5354 | 356.7332
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-316 | 26.2071 | 49.1626 | FAZRAN | Horizontal | PHZ | 2019-02-23 20:00:00.000 | Primary Drilling | AD-68 | CONT DRILLING DIR HOLE F/9,427' T/10,506'. CIRCULATING HOLE CLEAN WHILE WAITING WIND SPEED SLOW DOWN. RESUMED DRILLING 6-1/8" DIR HOLE F/10,506' T/10,819'. PERFORMED FLOW CHECK. CIRCULATE MEANWHILE INCREASING MUD WEIGHT TO 69 PCF. | DRILLING 6-1/8" DIRECTIONAL HOLE T/13,355’ (STD). | 62481F155524482FBF7BCF291DA70620 | CIRCULATE AND INCREASE MUD WEIGHT TO 68 PCF IN/OUT. | 38.37 | 32.3 | 2019-04-24 09:45:36.000 | 281 | 427.89 |  |  |  |  | 2019-04-24 00:30:00.000 | 2019-02-23 20:00:00.000 | 0 | 13209.0004 | 2019-04-08 09:30:00.000 | 4.6771 | 27.8646 | 43.5625 | 59.1875 | 7.9021 | 303.2195
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-318 | 26.2287 | 49.1857 | FAZRAN | Horizontal | PHZ | 2018-12-20 12:00:00.000 | Primary Drilling | AD-68 | DRILLED 6-1/8" HOLE F/ 11,016' T/ 11,378', CHC, POOH, REPLACE 5" DP BY 4" DP, RIH, CONTINUED DRILLING F/ 11,378' T/ 11,820'. | DRILL 6-1/8" HOLE F/ 11,820' TO 13,716' (STD PLAN#6). | 62481F155524482FBF7BCF291DA70620 | CHANGE PIPE HANDLING EQ TO 5", MU 4-1/2" IF X XT-39 X/O. | 38.5 | 29.68 | 2019-01-27 12:44:03.000 | 281 | 444.31 |  |  |  |  | 2019-02-11 00:00:00.000 | 2018-12-20 12:00:00.000 | 0 | 13716.0004 | 2019-01-25 08:30:00.000 | 3.5625 | 22.5729 | 35.8542 | 52.5 | 6.7857 | 382.5497
EH | KSA | Saudi Arabia | 62481F155524482FBF7BCF291DA70620 |  | 485712 | KSA IDS Saudi - AFK Oil LSTK | IDS | KSA | LSTK | FZRN-704 | 26.252 | 49.165 | FAZRAN | Vertical | EV | 2018-09-24 12:30:00.000 | Primary Drilling | AD-68 | CONT M/U & RIH 6-1/8" CORING BHA#1 T/8,733'. ACTIVATE FASTBALL. START CUT CORE F/8,733' T/8,763'. CIRC HOLE. POOH 6-1/8" CORING BHA#1 T/5,810'. CIRC HOLE. RESUMED POOH 6-1/8" CORING BHA#1 T/5,073' FLOW CHECK AND CIRCULATE B/U. POOH T/3,095'. | CONT POOH 6-1/8" CORING BHA#1. L/D 30' OF CORE. P/U & M/U 6-1/8" CORING BHA#2 & RIH WITH SAME TO BTM AT 8,763'. CIRCULATE HOLE. START CUT CORE F/8,763' T/8,823'. CIRC HOLE. POOH 6-1/8" CORING BHA#2 TO SURFACE. | 62481F155524482FBF7BCF291DA70620 | OUT OF SCOPE: STOP ROTATION, AND P/U CORE ASSEMBLY WITH 5 KLBs O/P, CUT THE CORE AND POOH ONE STAND, RACK BACK SAME. | 40.18 | 34.94 | 2018-11-30 22:34:12.000 | 383.41 | 383.41 |  |  |  |  | 2018-12-08 04:30:00.000 | 2018-09-24 12:30:00.000 | 0 | 9020.0003 | 2018-11-15 20:00:00.000 | 2.5208 | 44.875 | 52.3125 | 74.6667 | 3.3761 | 172.4253
EH | KSA | Saudi Arabia | 9862E474E3C047A2955A274ABBB573D1 |  | 469230 | KSA SWS Drilling Project | IDS | KSA | Other | S-64601 | 22.3147 | 51.0072 | RAK | Vertical | Water Well | 2018-10-30 14:30:00.000 | Primary Drilling | XDEC-62 | Cont to N/U BOP., P/T, RIH w/ 8 1/2" BHA., COC. | Cont. COC Drill 8 1/2" Hole, Test well for flow. | 9862E474E3C047A2955A274ABBB573D1 | HPJSM, N/U 21-1/4"-2M Annular BOP w/ Mud cross & Invasion lines, function test. | 23.98 |  | 2018-11-23 04:30:00.000 | [6 empty] | 2018-11-25 12:00:00.000 | 2018-10-30 13:30:00.000 | 0 | 3002.0001 | 2018-11-24 14:00:00.000 | 1.1875 | 14.5208 | 24.9792 | 25.8958 | 4.5857 | 120.1802
EH | KSA | Saudi Arabia | 9862E474E3C047A2955A274ABBB573D1 |  | 469230 | KSA SWS Drilling Project | IDS | KSA | Other | S-64701 | 21.7241 | 51.0155 | RAK | Vertical | Water Well | 2019-01-01 08:00:00.000 | Primary Drilling | XDEC-62 | WIPER TRIP, POOH, RUN& CMT 7" CASING, W.O.C | N/D & N/U WELL HEAD, BOP, L/D D/C , D/P, RIH W/ 6 1/8" BHA | 9862E474E3C047A2955A274ABBB573D1 | HPJSM , L/D 10X 6 1/2" D/C + 5X 5" HWDP+73 X5" D/P. | 26.05 |  | 2019-01-18 05:00:00.000 | [6 empty] | 2019-01-18 00:00:00.000 | 2019-01-01 05:00:00.000 | 0 | 3220.0001 | 2019-01-16 23:30:00.000 | 1.0417 | 9.6146 | 15.6458 | 16.6667 | 6.25 | 205.8056
EH | KSA | Saudi Arabia | 9862E474E3C047A2955A274ABBB573D1 |  | 469230 | KSA SWS Drilling Project | IDS | KSA | Other | S-96801 | 19.9066 | 53.3417 | RAK | Vertical | Water Well | 2019-03-10 12:00:00.000 | Primary Drilling | XDEC-62 | *PWS company completed tubular and handling tools inspection *16" hole section: drilled to 118' from RKB, 98' BGL., RIH 3 Jts of 13 3/8" Csg and cement job completed | N/UP BOP' RIH , COC, DRILL 12-1/4'' HOLE | 9862E474E3C047A2955A274ABBB573D1 | ROTARY DRILL 16'' HOLE WITH 100 % RETURN TO 118' RKB ( 13-3/8'' CSG POINT). | 19.01 |  | 2019-03-28 14:12:00.000 | [6 empty] | 2019-03-24 05:00:00.000 | 2019-03-10 12:00:00.000 | 0 | 1510 | 2019-03-22 03:30:00.000 | 0 | 7.0208 | 11.6458 | 13.7083 | 0 | 129.6601
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1111 |  |  | Khurais (KHRS) | Vertical | EV | 2019-01-10 00:00:00.000 | Primary Drilling | Daqing-45 | CONT. POOH 8-1/2" ROTARY BHA TO SURFACE & R/B SAME - R/U & PERFORM WL LOGGING RUN # 1 (FMI-MSIP-PPC-GR)- POOH & L/D TOOLS- R/U & PERFORM WL LOGGING RUN #2 (AIT-TLD-HGNS-MCFL-NEXT- GR ) IN PROGRESS. | CONT. PERFORM WL LOGGING AS PER PLAN. | 620FB696A58F41B8AD6F32AA43E2DAA3 | POOH 8-1/2" ROTARY DRILLING BHA TO 5,416 FT (INSIDE 9-5/8" CSG SHOE). - POOH AT CONTROLLED SPEED IN OH. - TRIPPING SPEED: 7 SPH. - OH IN GOOD CONDITION. - MONITORED WELL ON TT, OK | 27.01 | 22.56 | 2019-02-10 13:45:00.000 | 360 | 350.33 |  |  |  |  | 2019-02-10 15:00:00.000 | 2019-01-10 00:00:00.000 | 35 | 5875.0002 | 2019-01-27 22:45:00.000 | 1.625 | 10.5104 | 17.9479 | 31.625 | 5.1383 | 327.3361
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1112 |  |  | Khurais (KHRS) | S-shape | EV | 2019-02-16 02:00:00.000 | Primary Drilling | Daqing-45 | CONT. TO DRILL OUT DV TO 3,388 FT, NO PROGRESS - POOH & CHANGED 8-1/2" BIT FROM PDC TO TCI BIT - RIH & CONT'D DRILLING OUT DV TO 3,389 FT - RIH & TAGGED BAFFLE PLATE @ 5,346 FT - P/T 9-5/8" CSG - DRILLED OUT BAFFLE PLATE & SHOE TRACK TO 5,487 FT - P/T 9-5/8" CSG - DRILLED OUT SHOE TRACK, FS, & RAT HOLE TO 5,517 FT - DRILLED 8-1/2" SECTION TO 5,706 FT. | CONT. TO DRILL 8-1/2" SECTION TO 5,911 FT (STD) FOLLOWING PLAN #3 - CHC - WIPER TRIP TO 9-5/8" CSG SHOE - RIHB TO BTM - CHC - DROP GYRO - POOH & L/D 8-1/2" ROTARY BHA - RUN WL LOGGING. | 620FB696A58F41B8AD6F32AA43E2DAA3 | CIRCULATED & ENSURED CLEAR PATH. - FR: 580-600 GPM; SPP: 1,425 PSI. - TOOK SCRs. - OBSERVED NO DOWN HOLE LOSSES. | 26.22 | 22.35 | 2019-03-19 11:29:54.000 | 360 | 351.22 |  |  |  |  | 2019-03-19 16:00:00.000 | 2019-02-16 02:00:00.000 | 35 | 5911.0002 | 2019-03-07 18:45:00.000 | 3.5208 | 12.8333 | 19.6979 | 31.5833 | 11.1478 | 300.0825
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1114 |  |  | Khurais (KHRS) | S-shape | EV | 2018-12-09 05:00:00.000 | Primary Drilling | Daqing-45 | CONT'D TO DRILL OUT 9-5/8" CSG SHOE TRACK - DRILLED 8-1/2" FORMATION TO 5,945 FT (TD) FOLLOWING PLAN #6 - CHC - PERFORMED WIPER TRIP TO 9-5/8" CSG SHOE - RIHB TO BTM - CHC - DROPPED GYRO - POOH & L/D 8-1/2" ROTARY DRILLING BHA - PERFORMED WL LOGGING RUN #1 (AIT-TLD-HGNS-MCFL-ADT-NEXT-GR), IN PROGRESS. | CONT. TO PERFORM WL LOGGING RUN #1 & 2 (FMI-MSIP-PPC-GR) - PERFORM CONDITIONING TRIP - PERFORM WL LOGGING RUN #3 (CMR-HNGS-GR). | 620FB696A58F41B8AD6F32AA43E2DAA3 | FLOW CHECKED THE WELL. - WELL STATIC. | 27 | 22.53 | 2019-01-05 00:00:00.000 | 360 | [5 empty] | 2019-01-04 15:30:00.000 | 2018-12-09 05:30:00.000 | 0 | 5945.0002 | 2018-12-25 12:45:00.000 | 1.3958 | 10.2917 | 16.3229 | 26.4375 | 5.2797 | 364.2119
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1404 | 25.2232 | 47.997 | Khurais (KHRS) | Horizontal | PML | 2017-12-05 19:00:00.000 | Primary Drilling | Daqing-45 | CONT. POOH 8-1/2" DIR ASSAY TO SURFACE & L/D DIR TOOLS- P/U, M/U & RIH NEW 8-1/2" DIR ASSAY TO 1,470 FT- SHALLOW TESTED DIR TOOLS,OK- CONT RIH 8-1/2" DIR ASSAY TO 8,266 FT- RE-LOG FR/8,266 FT TO 8,404 FT- DRILLED 8-1/2" L0 HOLE FR/8,404 FT TO 9,260 FT (IP) | DRILL 8-1/2" L0 SEC TO STD (19,500 FT). | 620FB696A58F41B8AD6F32AA43E2DAA3 | L/D 8-1/2" DIR ASSAY TO 300 FT (IP) | 90.56 | 86.93 | 2018-04-01 06:30:00.000 |  |  | 20180203122602 |  |  |  | 2018-03-31 14:00:00.000 | 2017-12-05 19:00:00.000 | 35 | 19500.0006 | 2018-02-06 22:45:00.000 | 16.0833 | 45.1563 | 63.1562 | 115.7917 | 13.8899 | 308.7581
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1611 |  |  | Khurais (KHRS) | Vertical | EV | 2019-03-31 14:30:00.000 | Primary Drilling | Daqing-45 | CONT. TO D.O. SHOE TRACK TO 5,504 FT - CHC - PT 7" LINER, OK - D.O. REMAINING SHOE TRACK & 10 FT OF NEW FORMATION TO 5,540 FT - FLOW CHECK, OK - DRILL 6-1/8" HOLE TO 5,920 FT. | CONT. TO DRILL 6-1/8" HOLE TO 5,951 FT (STD AS PER GOC) - CHC - WIPER TRIP TO 7" LINER SHOE - RIHB TO BTM - CHC - POOH & L/D 6-1/8" MOTOR BHA - RUN SLB WL LOGGING AS PER RDD LOGGING PROGRAM. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8" HOLE FROM 5,650 FT TO 5,920 FT. - FR: 250 GPM, SPP: 1,900-2,300 PSI. - DIFF PRESSURE: 200-400 PSI. - WOB: 20-25 KLB, RPM: 80-100; TQ: 3-6 KLB-FT. - PUWT: 121 KLB; RWT: 120 KLB: S/O WT: 119 KLB - DRILLED OFF (2) MINS EACH STD DOWN. - REAMED UP DOWN (15) FT PRIOR TO CONNECTION. - PUMPED (15) BBLS OF HI-VIS PILL EVERY TWO STDs. - O.B ROP: 15-40 FPH; OVERALL AVG ROP: 23 FPH. - OBSERVED NO DOWN HOLE LOSSES. - LAST MWD SURVEY: @ 5,850 FT MD: 1.91 INC; 123.3 AZM, 5,489.32 FT TVD. - CT-CT TO PLAN #2: 2.8 FT. | 23.01 | 21.82 | 2019-04-27 17:57:00.000 | 360 | 369.86 |  |  |  |  | 2019-04-27 16:00:00.000 | 2019-03-31 14:30:00.000 | 0 | 5951.0002 | 2019-04-17 06:45:00.000 | 2.4375 | 13.0625 | 16.6771 | 27.0625 | 9.0069 | 356.837
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1614 |  |  | Khurais (KHRS) | S-shape | EV | 2018-11-10 08:15:00.000 | Primary Drilling | Daqing-45 | CONT. DRILLED 6-1/8" DIR HOLE TO 5,960 FT (STD).- CHC- PERFORMED WIPER TRIP TO 7" LINER SHOE- RIH TO BTM- CHC- POOH 6-1/8" DIR ASSAY TO SURFACE & L/D DIR ASSAY- R/U WIRELINE & RIH AIT-TLD-CNL-GR (RUN#1) WL LOGS TO BTM. PERFORM WL LOGGING (RUN#1) IN PROGRESS. | CONT. PERFORM WIRELINE LOGS (THREE RUNS). | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8” HOLE FROM 5,575 FT TO 5,585 FT WITH CONTROLLED PARAMETERS: - FR: 250 GPM, SPP: 1700 PSI. - DIFF PRESSURE: 200 PSI, - WOB: 5 KLB, RPM: 50; TQ : 4 KFT-LB. - NO DOWN HOLE LOSSES. | 24.01 | 21.85 | 2018-12-04 01:42:00.000 | 341.83 | [5 empty] | 2018-12-04 00:30:00.000 | 2018-11-10 07:45:00.000 | 35 | 5960.0002 | 2018-11-26 09:00:00.000 | 0.46875 | 12.3542 | 16.0312 | 23.6771 | 1.9798 | 371.7739
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-371 |  |  | Khurais (KHRS) | Horizontal | PML | 2018-09-02 11:00:00.000 | Primary Drilling | Daqing-45 | CONT. SHALLOW TESTED TOOLS, OK- RIH 6-1/8" DIR ASSAY TO 6,527 FT - RE-LOG AS PER GOC TO 6,608 FT- DISPLACED WELL TO 58 PCF AOM - DRILLED SHOE TRACK & 10 FT OF NEW FORMATION TO 6,646 FT - FLOW CHECKED WELL- DRILLED 6-1/8" DIR HOLE TO 7,785 FT. | CONT. DRILL 6-1/8" DIR HOLE TO 8,617 FT (STD)- CHC- POOH 6-1/8" DIR ASSAY TO SURFACE & L/D DIR BHA. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8” HOLE FROM 6,633 FT TO 6,646 FT WITH CONTROLLED PARAMETERS: - FR: 250 GPM, SPP: 2000 PSI. - DIFF PRESSURE: 250 PSI, - WOB: 2 - 8 KLB, RPM: 50; TQ : 3 - 4 KFT-LB. - NO DOWN HOLE LOSSES. | 49.79 | 37.95 | 2018-11-03 23:13:41.000 | 546.88 | [5 empty] | 2018-11-03 00:00:00.000 | 2018-09-02 11:00:00.000 | 35 | 8841.0003 | 2018-10-21 03:30:00.000 | 4.3333 | 37.2396 | 48.6875 | 61.5417 | 7.0413 | 181.5867
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-453 |  |  | Khurais (KHRS) | Horizontal | PML | 2018-04-08 23:00:00.000 | Primary Drilling | Daqing-45 | DRILL OUT NEW FORMATION TO 8,500 FT- FLOW CHECK WELL- DRILLED 6-1/8" SEC TO 9,778 FT- WORKED ON LEAKING STAND PIPE - CONT. DRILL 6-1/8" SEC TO 10,000 FT (IP). | CONT. DRILL 6-1/8" SEC TO 11,730 FT (STD) | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8"” HOLE FROM 8,500 FT TO 9,540 FT WITH CONTROLLED PARAMETERS: - CONTROLLED PARA TO CONTROL TRAJECTORY. - FR: 300 GPM, SPP: 3900 PSI. - DIFF PRESSURE: 400 PSI, - WOB: 10-20 KLB, RPM: 80; TQ : 5-9 KFT-LB. - PUWT: 136 KLB; RWT: 116 KLB. - DRILLED OFF 3 MINS EACH STD DOWN. - REAMED UP DOWN 20 FT PRIOR TO CONNECTION. - PUMPED 15/15 BBLS OF TANDEM PILL EVERY THREE STD. - OB ROP : 120 FPH; OVERALL AVG ROP: 65 FPH. - OBSERVED NO DOWN HOLE LOSSES. | 81.02 | 65.79 | 2018-07-18 02:08:24.000 | [6 empty] | 2018-07-18 12:00:00.000 | 2018-04-08 23:00:00.000 | 35 | 11729.0004 | 2018-06-04 13:00:00.000 | 9.5 | 41.4792 | 56.5833 | 100.5417 | 9.4488 | 207.2872
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-794 |  |  | Khurais (KHRS) | Horizontal | PWI | 2018-07-24 11:00:00.000 | Primary Drilling | Daqing-45 | CONT. DRILL 6-1/8" SEC TO 8,048 FT- CHC-TOOK PRESSURE POINTS WITH STETHOSCOPE- FLOW CHECK WELL, OK- POOH 6-1/8" DIR ASSAY INSIDE 7" CSG SHOE- WAITED ON DECISION- DECIDED TO R/D MPD & DISPLACE WELL TO 80 PCF SALT POLY. MUD- RIH TO BTM- DISPLACED WELL TO 80 PCF MUD- FLOW CHECKED WELL,OK- RESUME DRILLING 6-1/8" DIR HOLE TO 8,410 FT- CHC PRIOR TO PRESSURE POINT. | TOOK PRESSURE POINTS WITH STETHOSCOPE- DRILL 6-1/8" DIR HOLE TO 11,154 FT (STD). | 620FB696A58F41B8AD6F32AA43E2DAA3 | OUT OF SCOPE: DECIDED TO RELEASE MPD BACK PRESSURE TO ZERO. - OPENED MPD CHOKE SLOWLY IN 30 PSI INCREMENT TO FULL MAKING BACK PRESSURE ZERO. | 30 | 22.5 | 2018-08-27 23:48:13.000 | [6 empty] | 2018-08-27 22:00:00.000 | 2018-07-24 10:30:00.000 | 35 | 11154.0004 | 2018-08-25 13:30:00.000 | 1.375 | 21.4271 | 32.1042 | 34.4583 | 3.9903 | 347.4315
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1030 | 25.265 | 48.075 | Khurais (KHRS) | Vertical | Evaluation / Production | 2019-09-22 08:00:00.000 | Primary Drilling | Daqing-46 | D/O SHOE TRACK TO 5,377 FT (30 FT ABOVE FS). P/T 9-5/8" CSG TO 2,000 PSI. D/O REMAINING SHOE TRACK, FS, & RAT HOLE WHILE DISPLACING HOLE TO 77 PCF WBM. DRILLED 8-1/2" NEW FORMATION TO 5,416 FT. CHC. POOH & L/D 8-1/2" CLEAN OUT BHA. M/U & RIH 8-1/2" CORING BHA#1. PERFORMED CORE DRILL RUN #1 TO 5,433 FT (17 FT CORED), CORE JAMMED. BROKE CORE & CIRC. BTM UP IN PROGRESS. | CONT. TO CIRC. BTM UP. POOH 8-1/2" CORE BHA#1 AND RETRIEVE CORE SAMPLES. P/U, M/U & RIH 8-1/2" CORE BHA#2. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 8-1/2" NEW FORMATION FROM 5,409 FT TO 5,416 FT. - WOB: 15-25 KLB; FR: 450 GPM; RPM: 80; SPP: 800 PSI; TQ: 4-6 KLB.FT. - AVG ROP: 28 FT/HR. - OBSERVED NO DOWN HOLE LOSSES. | 30.09 | 26.38 | 2019-10-23 19:25:12.000 | [6 empty] | 2019-10-22 12:30:00.000 | 2019-09-22 08:00:00.000 | 40 | 5780.0002 | 2019-10-11 20:45:00.000 | 1.8854 | 14.6979 | 19.5312 | 30.1875 | 6.2457 | 295.936
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1401 | 25.099 | 48.105 | Khurais (KHRS) | Horizontal | PML | 2017-08-20 15:00:00.000 | Primary Drilling | Daqing-46 | CONT. RIH 8 1/2' VORTEX BHA TAG CMT. P/T CASING. H2S ALARM. DRILL CMT, PLUG, FC & CMT. H2S ALARM. DISPLACE HOLE WITH NEW MUD. DRILL CMT ABOVE F/S. P/T CASING. DRILL CMT, FS & NEW HOLE. FLOW CHECK. DRILL 8 1/2" L1 DIR. HOLE TO TD 10060 FT. | CONT. DRILL 8 1/2" L1 DIR. HOLE TO TD @+-17817 FT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 8-1/2” L1 HORZ HOLE FROM 9009 FT TO 10060 FT WITH FULL PARAMETERS - FR: 590 GPM, SPP: 3150 PSI. - DIFF PRESSURE: 500 PSI. - WOB: 15-22 KLB, RPM: 100; TQ: 7-11 KFT-LB. - PUWT: 205 KLBS, SOWT: 160 KLBS, RWT: 182 KLBS - DRILLED OFF (4) MINS EACH STD DOWN. - REAM UP & DOWN (15) FT PRIOR TO CONNECTION. - PUMPED 15/30 BBLS TANDEM PILLS EACH (4) STDs DRILLED. - OB ROP: 90- 200 FPH; AVG ROP: 95.54 FPH. - DOWNLINK AS PER DD. - OBSERVE NO DOWN HOLE LOSSES. WELL TRAJECTORY: - LAST SURVEY @ 9803' MD; 6909.67' TVD; 89.83 INCL; 349.66 AZI. - WELL PATH: (3) FT RIGHT & (1.5) FT ABOVE PLAN # 11 | 68.02 | 68.02 | 2018-02-15 02:49:24.000 | [6 empty] | 2017-11-16 16:00:00.000 | 2017-08-20 14:30:00.000 | 0 | 17986.0006 | 2017-11-05 03:15:00.000 | 5.9375 | 49.4583 | 76.5104 | 88.0417 | 6.744 | 235.0791
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1402 | 25.198 | 48.077 | Khurais (KHRS) | Horizontal | PML | 2017-11-24 06:00:00.000 | Primary Drilling | Daqing-46 | DRILLING 8-1/2" L0 DIR. HOLE FROM 9628 FT TO 10870 FT. CHC. POOH 8-1/2"DIR. BHA TO 4940 FT. | CONT POOH 8-1/2"DIR BHA TO SURFACE & L/D. P/U, M/U & RIH 8-1/2' DIR. BHA TO BOTTOM. CONTINUE DRILLING 8-1/2" L0 DIR. HOLE TO +- 19553 FT AS PER GOC. | 620FB696A58F41B8AD6F32AA43E2DAA3 | TAKE SCR-PP. | 56.02 | 45.51 | 2018-01-23 13:04:30.000 | 546.88 | [5 empty] | 2018-01-23 14:00:00.000 | 2017-11-24 22:00:00.000 | 0 | 19554.0006 | 2017-12-25 09:15:00.000 | 3.9271 | 15.9896 | 31.1354 | 60.3333 | 6.509 | 628.0308
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1406 |  |  | Khurais (KHRS) | Horizontal | PML | 2018-12-09 23:00:00.000 | Primary Drilling | Daqing-46 | DRILL 8 1/2" SECTION FROM 9148 FT TO 11348 FT. | CONTINUE TO DRILL 8 1/2" SECTION TO TD. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 8 1/2" SECTION FROM 9062 FT TO 9148 FT. - DRILL WITH CONTROLLED PARAMETERS UNTIL BHA IN OPEN HOLE. - WOB 5-10K LBS, SPP 2600-2900 PSI, 40 RPM, 10K FT/LBS TQ, 500-550 GPM. | 74.55 | 40.8 | 2019-03-24 11:45:00.000 | 573 | 503.63 |  |  |  |  | 2019-03-24 13:00:00.000 | 2018-12-09 23:00:00.000 | 0 | 16607.0005 | 2019-02-04 03:30:00.000 | 28.2917 | 38.9583 | 56.1875 | 104.5833 | 27.0518 | 295.564
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1704 |  |  | Khurais (KHRS) | Horizontal | PWI ML | 2019-06-07 19:30:00.000 | Primary Drilling | Daqing-46 | RIH & TAG CEMENT @ 8220 FT. CLEAN OUT CEMENT TO 8,632 FT (TOP OF LANDING COLLAR). P/T 7'' LINER TO 700 PSI / 15 MIN - OK. DRILL OUT SHOE TRACK TO 8,760 FT (30 FT ABOVE SHOE). P/T 7'' LINER TO 700 PSI / 15 MIN - OK. DRILL OUT REMAINING OF SHOE TRACK TO 8,793 FT & DISPLACE TO 68 PCF NON DAMAGING POLYMER MUD. DRILL AHEAD 6-1/8'' L0 AS PER PLAN TO 9,450 FT. | DRILL 6-1/8'' L0 AS PER PLAN TO 12,000 FT. POOH TO RE-POSITION WWT PROTECTORS. RIH BACK TO BOTTOM. DRILL AHEAD 6-1/8'' L0 AS PER PLAN TO 15,671 FT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6 1/8" L0 DIR. HOLE WITH CONTROLLED PARAMETERS F/ 8,793 FT TO 8,980 FT. - INCREASE DRILLING PARAMETERS GRADUALLY UNTIL BHA OUT OF SHOE - FR: 290 GPM, SPP: 2,250 - 2,750 PSI, DIFF: 400-500 PSI, RPM: 40-90, WOB: 10-20 KLB, TQ: 7 - 9 KLB*FT. - AVG ROP: 70 FT/HR. - TAKE SURVEY AFTER EVERY CONNECTION. - AT KELLY DOWN DRILL OFF 2 MIN, R/U & R/D 15 FT. - SENT DOWNLINK TO RSS AS PER DIRECTIONAL PLAN. - NO LOSSES | 44.56 | 33.57 | 2019-07-26 03:00:00.000 | 541 | 567.23 |  |  |  |  | 2019-07-26 02:30:00.000 | 2019-06-07 19:30:00.000 | 36 | 17601.0006 | 2019-07-03 15:45:00.000 | 4.7292 | 15.4375 | 25.8438 | 48.2917 | 9.7929 | 681.0544
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1737 |  |  | Khurais (KHRS) | Horizontal | PWI ML | 2018-09-18 23:00:00.000 | Primary Drilling | Daqing-46 | CONTINUE TO LD DP FROM MAST. RELEASE THE RIG @11:00 HRS ON 4 DEC 2018. | GENERAL RIG DOWN FROM KHRS 1737 AND RIG MOVE TO KHRS 1406. | 620FB696A58F41B8AD6F32AA43E2DAA3 | L/D 50 STANDS OF DP AND HWDP FROM DERRICK. | 48.34 | 39.67 | 2018-12-03 11:03:00.000 | 778.7 | [5 empty] | 2018-12-04 11:00:00.000 | 2018-09-18 23:00:00.000 | 0 | 19956.0006 | 2018-11-22 17:30:00.000 | 20.9271 | 43.4479 | 64.7708 | 76.5 | 27.3557 | 308.1017
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-266 | 25.287 | 48 | Khurais (KHRS) | Horizontal | PHZ | 2018-01-31 06:30:00.000 | Primary Drilling | Daqing-46 | CONTINUE POOH TO FROM 1800 FT TO SURFACE AND REPLACE MWD, ARC, ADN TOOLS . RIH WITH VORTEX BHA. RELOG FROM 5750 FT TO 5865 FT. DRILLED 8-1/2” L0 HORZ HOLE FROM 5865 FT TO 6450 FT | CONTINUE DRILLING 8-1/2” L0 HORZ HOLE FROM 6450 FT TO 10560 FT SECTION TD AS PER PLAN 11 | 620FB696A58F41B8AD6F32AA43E2DAA3 | POOH 8-1/2" VORTEX BHA FROM 1800 FT TO 359 FT.(TOP OF BHA) - MONITOR THE WELL WITH TRIP TANK. - PULLING SPEED: 20 SPH. | 22.95 | 16.75 | 2018-03-01 13:30:45.000 | [6 empty] | 2018-02-28 22:00:00.000 | 2018-01-31 05:00:00.000 | 0 | 10560.0003 | 2018-02-24 08:30:00.000 | 2.0313 | 15.4375 | 24.0833 | 28.6458 | 7.0909 | 438.4775
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-358 |  |  | Khurais (KHRS) | Horizontal | PML | 2019-08-02 10:00:00.000 | Primary Drilling | Daqing-46 | CONT. DRILLED 6-1/8" DIR HOLE TO 9405 FT (SEC TD)- CHC- FLOW CHECK WELL, OK- POOH TO 7'' LINER SHOE- FLOW CHECK WELL,OK- POOH TO SURFACE & L/D 6-1/8" BHA- P/U, M/U & RIH 7" CLEAN OUT BHA TO 5,200 FT. | CONT. RIH 7" CLEAN OUT BHA TO 6,150 FT & SCRAPE BOTH WINDOW DEPTH- CHC - POOH C/O ASSY TO SURFACE & L/D SAME- P/U & RIH 7'' WHIPSTOCK ASSEMBLY TO SETTING DEPTH- SET WHIPSTOCK- MILL L1 WINDOW- CHC- POOH TO SURFACE. | 620FB696A58F41B8AD6F32AA43E2DAA3 | CIRCULATED HOLE CLEAN - SWEPT HOLE WITH TANDEM PILL(20/20 BBL LO VIS/HI WT) - CIRCULATED HOLE CLEAN FOR (3) BOTTOMS UP. - FR: 280 GPM, SPP: 2,700 PSI, TQ: 2-3 KFTLBS. - REAM UP/DOWN: 80/100 RPM - NO DYNAMIC LOSSES. - CIRCULATED TILL SHAKERS CLEAN. | 50.02 | 32.2 | 2019-09-15 20:00:00.000 | 424 | 328.49 |  |  |  |  | 2019-09-15 20:00:00.000 | 2019-08-02 10:00:00.000 | 40 | 10011.0003 | 2019-09-05 13:15:00.000 | 0.71875 | 21.4792 | 34.1354 | 44.4167 | 1.6182 | 293.2731
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-553 |  |  | Khurais (KHRS) | Horizontal | PML | 2019-04-09 00:00:00.000 | Primary Drilling | Daqing-46 | D/O LC, CMT & FLOAT COLLAR TO 7390 FT. CHC. P/T CASING. D/O F/S & NEW FM TO 7,424 FT. FLOW CHECK. DRILL 6-1/8'' L0 SECTION W/ VORTEX BHA TO 8,315 FT, OBSERVE OIL LEAK AT TDS. CIRCULATE HOLE CLEAN. FLOW CHECK. POOH TO 7'' LINER SHOE. REPAIR TDS. RIH TO BOTTOM. RESUME DRILLING TO 8400 FT | DRILL AHEAD 6-1/8'' L0 AS PER PROGRAM TO 9,933 FT. CHC. SPOT FRESH OBM. POOH 6-1/8" DIRECTIONAL BHA TO SURFACE. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8" L0 HORIZONTAL SECTION W/ VORTEX BHA FROM 7473 FT TO 8,315 FT. - WOB :7-15 KLB, SRPM: 70-100, BRPM: 259-296, TQ: 2.5-5.8 KLB.FT, FR 270-280 GPM, SPP : 2400-2950 PSI, DIFF: 150-700 PSI - AVG ROP: 99 FT/HR. - ON BTM ROP LIMITED TO 250 FT/HR AS PER LWD TOOL. - REAM UP & REAM DOWN 10 FT PER EACH STAND DRILLED. - SENT DOWNLINK TO ADJUST TRAJECTORY AS PER PROGRAM. - OBSERVED OIL LEAK AT TDS MOTOR BRAKE, DECIDED TO POOH TO SHOE & FIX IT. | 14 |  | 2019-04-23 05:00:00.000 | 424 | 370.7 |  |  |  |  | 2019-05-31 12:00:00.000 | 2019-04-09 13:30:00.000 | 0 | 9981.0003 | 2019-05-18 13:15:00.000 | 5.7396 | 26.8125 | 39.5521 | 52.5 | 10.9325 | 252.3508
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-599 | 24.8798 | 48.215 | Khurais (KHRS) | Horizontal | PML | 2018-03-08 13:30:00.000 | Primary Drilling | Daqing-46 | RIH WITH 6-1/8" DIRECTIONAL BHA. DRILLING DRILL 6 1/8" SECTION FROM 7675 TO 8710 FT | DRILLING DRILL 6 1/8" SECTION TO ±13136 FT | 620FB696A58F41B8AD6F32AA43E2DAA3 | SERVICE TOP DRIVE. | 52.25 | 41.08 | 2018-05-10 03:04:12.000 | [6 empty] | 2018-05-09 23:00:00.000 | 2018-03-08 13:30:00.000 | 0 | 13333.0004 | 2018-04-25 09:00:00.000 | 4.2083 | 30.5208 | 47.8125 | 62.3958 | 6.7446 | 278.8601
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-765 | 25.047 | 47.998 | Khurais (KHRS) | Horizontal | PWI | 2018-05-16 05:00:00.000 | Primary Drilling | Daqing-46 | DRILL 6-1/8" DIR. HOLE SECTION TO 6859 FT. STICK TEST. DRILL 6-1/8" DIR. HOLE SECTION TO 6953 FT. CIRCULATE. RECORD PRESSURE POINT AT 6805 FT AND 6810 FT. DRILL 6-1/8" DIR. HOLE SECTION TO 7050 FT. CIRCULATE. STICK TEST. RECORD PRESSURE POINT AT 6800 FT. DRILL 6-1/8" DIR. HOLE SECTION TO 7235 FT. | CONTINUE DRILLING 6-1/8" DIRECTIONAL HOLE SECTION TO TD +/- 9800 FT WITH MPD APPLICATION. | 620FB696A58F41B8AD6F32AA43E2DAA3 | POOH WITH 6 1/8" DIRECTIONAL BHA TO 6565 FT. | 26.68 | 17.9 | 2018-06-11 21:18:42.000 | [6 empty] | 2018-07-12 21:00:00.000 | 2018-05-16 05:00:00.000 | 0 | 10294.0003 | 2018-06-20 18:30:00.000 | 10.4167 | 28.1458 | 35.5625 | 57.6667 | 18.0636 | 289.4622
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-767 |  |  | Khurais (KHRS) | Horizontal | PWI | 2018-07-19 18:30:00.000 | Primary Drilling | Daqing-46 | DISPLACE TO 88 PCF MUD. DRILL 6-1/8" SECTION TO 9002 FT. SHUT DOWN THE OPERATION AS PER ARAMCO. | DRILL 6 1/8" SECTION TO 9100 FT. TAKE FORMATION PRESSURE TEST. POOH TO SHOE TO MIX KILL MUD. | 620FB696A58F41B8AD6F32AA43E2DAA3 | CONT DISPLACE 110PCF MUD TO 88PCF SALT POLYMER MUD. - CLEAN ALL SURFACE LINES. - FR=250GPM; SPP=2600PSI. | 28 | 19.6 | 2018-09-11 09:30:00.000 | [6 empty] | 2018-09-11 00:30:00.000 | 2018-07-19 18:30:00.000 | 35 | 11337.0004 | 2018-09-08 16:00:00.000 | 9.8958 | 35.4375 | 50.8958 | 53.25 | 18.5837 | 222.7491
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1034 | 25.17 | 47.98 | Khurais (KHRS) | Vertical | Evaluation/Producer | 2019-09-23 06:30:00.000 | Primary Drilling | Daqing-47 | CON'T TO DRILL 8.5'' SECTION TO 5370 FT (SECTION TD).CIRCULATE HOLE CLEAN.PERFORMED WIPER TRIP TO 9 5/8" CASING SHOE.POOH 8 1/2" BHA TO SURFACE AND L/D SAME.WL RUN AS PER PROGRAM. | WL RUN AS PER PROGRAM | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 8-1/2" HOLE F/4987 FT TO 5005 FT. - DRILLED WITH CONTROLLED PARAMETERS. - 10 FT INTO NEW FORMATION. - FR: 500 GPM / SPP: 1300 PSI. - WOB: 10-15 KLBS / RPM: 40-60 / TQ: 2-4 KFT.LB. - RECORDED SCR. | 27.01 | 21.86 | 2019-10-23 08:30:24.000 | [6 empty] | 2019-10-22 00:30:00.000 | 2019-09-23 06:30:00.000 | 0 | 5370.0002 | 2019-10-06 08:15:00.000 | 2.0208 | 9.7396 | 13.0729 | 28.75 | 7.029 | 410.7729
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1403 | 25.26 | 47.993 | Khurais (KHRS) | Horizontal | PML | 2018-11-08 08:30:00.000 | Primary Drilling | Daqing-47 | CON'T TO DRILL 8 1/2" HS FROM 11,160 FT TO 13,127 FT AT REPORT TIME. | CON'T TO DRILL OUT 8 1/2" HS AS PER KHRS-1403 L0 PLAN-12 ASM 05-DEC-2018 PROPOSAL REPORT. TD AT 16,580 FT +/- MD. | 620FB696A58F41B8AD6F32AA43E2DAA3 | RESUME DRILLING FROM 11,160 FT TO 12,751 FT WITH FULL CIRCULATION. - WOB: 15 - 25 KLBS. FR: 600 GPM. SPP: 3400-3800 PSI. - SURFACE RPM: 100. TQ: 6-19 KFT.LB. - MOTOR DIFFERENTIAL PRESSURE: 450-550 PSI. - AVERAGE ROP: 91 FT/HR - ON-BOTTOM ROP: 200-300 FT/HR. - SWEPT THE HOLE WITH LOW-VIS / HI-WEIGHT PILLS EVERY 3 STANDS DRILLED. - DOWN-LINK AS PER TRAJECTORY REQUIREMENT FROM GOC. - AT KD DRILL OFF FOR 4 MINS. - REAMED-UP/DOWN BETWEEN 10 FT AND FULL STAND WHEN REQUIRED AT KD. - RELOG AS PER GOC REQUIREMENT FROM 12 661 FT TO 12 702 FT. | 68 | 56.3 | 2019-02-23 05:00:00.000 | 573 | 505.67 |  |  |  |  | 2019-02-23 00:00:00.000 | 2018-11-08 08:30:00.000 | 0 | 17231.0006 | 2019-01-19 21:00:00.000 | 22.3438 | 48.5938 | 72.5208 | 106.6458 | 20.9514 | 237.6007
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1702 | 25.258 | 47.99 | Khurais (KHRS) | Horizontal | PWI ML | 2018-08-29 15:45:00.000 | Primary Drilling | Daqing-47 | DRILLED 6 1/8" HS FROM 8922 FT TO 11 334 FT WITH FULL RETURNS AT REPORT TIME. | CONTINUE DRILLING 6-1/8” HOLE TO ± 11,500 FT-MD.CBU.PERFORM WIPER TRIP TO RE-POSITION DP PROTECTORS. CONTINUE TO TRIP IN AND DRILL 6 1/8" HS AS PER KHRS-1702 L0 PLAN-07 ASM 18-SEP-2018 PROPOSAL REPORT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8" HOLE SECTION FROM 9645 FT TO 11 334 FT WITH FULL RETRUNS. - WOB: 18 Klbs. FR: 270 GPM. SPP: 3100 psi. - Surface RPM: 100. TQ: 5-11 kFt.lb. - Motor Differential Pressure: 350-550 psi. - DD Downlink, as needed - Average ROP: 105 ft/hr - On-Bottom ROP: 150-200 ft/hr. - Observed medium-high SnS. - Sweep hole with 15 bbls low-vis/ 15 bbl hi-weighted pills every 5 stands drilled. - At the Kelly down, drill off 2-3 minutes. - Ream-up and ream down 15 ft off-bottom with same as drilling RPM and flow rate. - Last survey: 11 081 ft-MD / 6698.51 ft-TVD / 89.0 Deg-Inc / 333.67 Deg-Azm. Deviation from plan: 5.7 ft left - 0.3 ft below. | 37.69 | 34.68 | 2018-10-27 18:18:00.000 | 778.7 | [5 empty] | 2018-10-28 20:00:00.000 | 2018-08-29 15:45:00.000 | 40 | 16916.0005 | 2018-10-11 11:30:00.000 | 14.6875 | 30.2396 | 42.8229 | 60.1771 | 24.4071 | 395.0221
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1761 | 25.15 | 47.98 | Khurais (KHRS) | Horizontal | PWI ML | 2017-12-31 17:45:00.000 | Primary Drilling | Daqing-47 | DRILLED 6-1/8''" HOLE FROM 17,870 FT TO 18,460 FT STD. CIRCULATED HOLE CLEAN.FLOW CHECK WELL STATIC.POOH 1ST 10 STANDS.FLOW CHECK.WELL STATIC.CONTINUED PERFORM WIPER TRIP TO 13,600 FT .HOLE IN GOOD CONDITION.TRIP BHA BACK TO BOTTOM AND ENCOUNTER OBSTRUCTION AT 14,902 FT. CON'T TO REAM DOWN TO 15,756 FT AT REPORT TIME. | CON'T TO TRIP TO BOTTOM.CIRCULATE AND DISPLACE WELL WITH 66 PCF BRINE.POOH 6 1/8" BHA TO SURFACE. | 620FB696A58F41B8AD6F32AA43E2DAA3 | WIPER TRIP-CONTINUED POOH 6-1/8 VORTEX BHA FROM 17,500 FT TO 13,600 FT ON ELEVATORS. - Hole in good condition. - Monitor well via trip tank. | 45 | 35.81 | 2018-02-10 06:35:04.000 | [6 empty] | 2018-02-09 03:00:00.000 | 2017-12-31 16:00:00.000 | 0 | 18460.0006 | 2018-01-25 11:30:00.000 | 0.09375 | 14.4583 | 24.7396 | 39.3854 | 0.23803 | 746.1727
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1765 | 25.054 | 48.124 | Khurais (KHRS) | Horizontal | PWI ML | 2019-06-14 22:00:00.000 | Primary Drilling | Daqing-47 | CON'T TO DRILL L1 FROM 11,396 FT TO 11,881 FT.CBU.B/REAM TO 7" LINER SHOE AND CON'T TO PULL STRING ON ELEVATORS TO SPACE OUT WWT PROTECTORS TO 4550 FT.TRIP BACK TO BOTTOM ON ELEVATORS(WASH/REAM DOWN LAST TWO STANDS) AND CON'T TO DRILL 6 1/8" L1 HS TO 12,100 FT AT REPORT TIME. | CON'T TO DRILL TO 14,406 FT.PULL STRING TO SPACE OUT WWT PROTECTORS AND CON'T TO TRIP IN TO DRILL 6 1/8" L1 HS AS PER KHRS-1765 L1 PLAN-13. +/- 17,124 FT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | **OUT OF SCOPE** **SPACE OUT PIPES WITH WWT PROTECTORS.** ATTEMPTED TO POOH WITH 6 1/8" DIRECTIONAL BHA ON ELEVATOR , NO SUCCESS. - BACK REAMED FROM 11517 FT TO 9071 FT (INSIDE 7" LINER SHOE) - FR: 240 GPM, SPP: 2000 PSI, RPM: 40. - OBSERVED SOFT BACK REAMING. | 63.73 | 51.42 | 2019-08-15 05:00:00.000 | 541 | 502.8 |  |  |  |  | 2019-08-15 04:30:00.000 | 2019-06-14 22:00:00.000 | 35 | 17232.0006 | 2019-07-28 04:30:00.000 | 3.1771 | 31.5313 | 43.2708 | 61.2708 | 5.1853 | 398.2359
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-179 | 25.39 | 48 | Khurais (KHRS) | Horizontal | PHZ | 2019-03-03 02:00:00.000 | Primary Drilling | Daqing-47 | CON'T TO DRILL 8 1/2" HS WITH 58 PCF OBM TILL 7017 FT .OBSERVED DYNAMIC LOSSES AT 200 BPH AT 7017 FT.SWITCH TO WATER AND GEL SWEEPS.CON'T TO DRILL 8 1/2" HS TO 8824 FT AT REPORT TIME WITH 150-200 BPH LOSSES. | DRILL 8 1/2" HS AS PER PLAN KHRS-179 PLAN-8 ASM 18MAR19 PROPOSAL REPORT. TD 9114 FT +/- | 620FB696A58F41B8AD6F32AA43E2DAA3 | CON'T TO DRILLED OUT INTO NEW FORMATION FROM 6260 FT TO 6272 FT WITH CONTROLLED PARAMETERS. - FR: 600 GPM / SPP: 2830 PSI. - WOB: 5 - 8 KLBS / RPM: 40 / TQ: 5 - 7 KFT.LB. - RECORDED SCR. | 23.17 | 20.2 | 2019-03-31 15:39:27.000 | 453 | 502.7 |  |  |  |  | 2019-03-31 20:00:00.000 | 2019-03-03 16:30:00.000 | 0 | 9114.0003 | 2019-03-24 09:00:00.000 | 1.8958 | 12.4688 | 21.2917 | 28.75 | 6.5942 | 428.0548
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-241 | 25.26 | 48.015 | Khurais (KHRS) | Horizontal | PML | 2018-04-22 17:00:00.000 | Primary Drilling | Daqing-47 | DRILLED 6-1/8" L0 SECTION FROM 7457 FT TO 8285 FT (ENCOUNTERED TOTAL LOSSES). CONTINUED TO DRILL BLIND FROM 8285 FT TO 8960 FT. | CONTINUE DRILLING 6-1/8” HOLE TO ± 9982 FT-MD / 4879.00 FT-TVD (AS PER DIRECTIONAL PLAN #13). | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8” HOLE FROM 8285 FT TO 8716 FT WITH TOTAL LOSSES. - WOB: 10 - 20 Klbs. FR: 250 - 260 GPM. SPP: 700-900 psi. - Surface RPM: 80. Downhole RPM: 256. TQ: 5 - 7 kFt.lb. - Motor Differential Pressure: 100 - 150 psi. - Average ROP: 62 ft/hr - On-Bottom ROP: 60 - 120 ft/hr. - Pumped 15 bbls low-vis/ 15 bbl hi-weighted pills every 3 stands drilled. - Cont'd to pump 1.0 bpm mud cap into annulus. - At each kelly down: Drilled off 3 - 5 minutes. Reamed-up and reamed-down full stand. - Checked for drops. | 43.68 | 31.04 | 2018-06-05 12:00:00.000 | [6 empty] | 2018-06-05 12:00:00.000 | 2018-04-22 15:00:00.000 | 0 | 10852.0003 | 2018-05-26 19:30:00.000 | 2.375 | 22.6667 | 34.1042 | 43.7917 | 5.4234 | 318.2016
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-265 | 25.2665 | 48.0192 | Khurais (KHRS) | Horizontal | PML | 2018-03-15 19:00:00.000 | Primary Drilling | Daqing-47 | CONTINUED TO RIH WITH 6-1/8” L0 DIRECTIONAL BHA WASHING DOWN TO 5808 FT, RE-LOG AS PER GOC TO 5958 FT. RIH WASHING DOWN TO 6020 FT, AND TAGGED TOC ABOVE LANDING COLLAR. P/T CASING, OK. DRILLED OUT CEMENT, PLUGS, AND CEMENT FROM 6020 FT TO 6240 FT. CIRCULATED HOLE CLEAN, AND P/T CASING, OK. DRILLED OUT CEMENT, FLOAT SHOE AND 10 FT RAT HOLE WITH CONTROLLED PARAMETERS TO 6276 FT. FLOW CHECK. DRILLED 6-1/8" HOLE SECTION TO 6830 AT REPORT TIME. | CONTINUE DRILLING 6-1/8” L0 HOLE SECTION TO 8675 FT-MD. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6 1/8” HOLE FROM 6276 FT TO 6830 FT. - Drilled with controlled parameters until BHA out of casing. - WOB: 10 - 20 Klbs. FR: 270 GPM. SPP: 2150-2550 psi. - Surface RPM: 100. Downhole RPM: 275. TQ: 5 - 7 kFt.lb. - Motor Differential Pressure: 250 - 400 psi. - Average ROP: 60 ft/hr - On-Bottom ROP: 80 - 120 ft/hr. - Pumped 15/15 bbl lo-vis/hi-weighted sweep every 5 stands drilled. - No downhole losses. - At each kelly down: Drilled off 3 - 5 minutes. Reamed-up and reamed-down 10 to 15 ft. - Last survey: 6675 ft-MD / 4871 ft-TVD / 91.03 Deg-Inc / 163 Deg-Azm. Deviation from plan: 0.3 ft Below – 11 ft Right - 11 Ct-Ct. | 36.05 | 26.31 | 2018-04-19 02:17:54.000 | [6 empty] | 2018-04-19 00:15:00.000 | 2018-03-15 17:30:00.000 | 40 | 9790.0003 | 2018-04-13 05:45:00.000 | 0.38542 | 18.7604 | 28.4479 | 34.2188 | 1.1263 | 344.1377
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-355 | 25.1116 | 48.0212 | Khurais (KHRS) | Horizontal | ARBD PHZ | 2019-08-22 19:00:00.000 | Primary Drilling | Daqing-47 | RIH 8-1/2" DIRECTIONAL BHA AND TAG CEMENT ABOVE DV. P/T 9-5/8" CASING. DRILL OUT DV. RIH AND TAG CEMENT ABOVE SHOETRACK. P/T 9-5/8" CASING. DRILLED OUT SHOETRACK TO 30 FT ABOVE SHOE. P/T 9-5/8" CSG. DRILLED OUT REMAINING SHOETRACK WHILE DISPLACING TO OBM. DRILL 8-1/2" SECTION. | CONTINUE DRILLING 8-1/2" SECTION TO TD. CIRCULATE HOLE CLEAN. POOH BHA TO SURFACE. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 8-1/2" HOLE F/6,333 FT TO 6,343 FT. - DRILLED WITH CONTROLLED PARA. - FR: 500 GPM / SPP: 2,000 PSI. - WOB: 5 - 8 KLBS / RPM: 40 / TQ: 5 - 7 KFT.LB. - RECORDED SCR. | 25.02 | 18.09 | 2019-09-17 17:00:00.000 | 453 | 289.81 |  |  |  |  | 2019-09-17 17:00:00.000 | 2019-08-22 19:00:00.000 | 40 | 8048.0003 | 2019-09-11 09:30:00.000 | 2.6146 | 11.4688 | 19.6042 | 25.9167 | 10.0884 | 410.525
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-478 | 25.09 | 40.023 | Khurais (KHRS) | Horizontal | PML | 2019-04-07 10:30:00.000 | Primary Drilling | Daqing-47 | DRILL 22" TO HOLE TO SECTION TD AT 1295 FT. | CHC, WIPER TRIP, CHC. POOH, RUN AND CEMENT 18 5/8" CASING. WAIT ON CEMENT. CUT 18 5/8" CASING, WELD ON C-PLATES TO 18 5/8" x 24" ANNULUS, WELD 21 1/4" WELD NECK FLANGE ONTO 18 5/8" CASING. MAKE UP 21 1/4" DIVERTER WITH MUD CROSS, BELL NIPPLE AND FLOW LINE. CONNECT VENT LINES. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 22" HOLE F/ 251 FT TO 372 FT WITH SPUD MUD AND CONTROLLED PARAMETERS. - FR: 450 GPM; SPP: 500 PSI. - WOB: 20 - 35 KLB; RPM: 60 ,TQ: 6 - 8 KFT-LB. - PUMPED (50) BBLS OF HI-VIS EACH 45 FT DRILLED. - WASHED UP & REAMED DOWN 1 JOINT FOR EACH STD DRILLED. - OBS RETURNS ON CELLAR. - OBS VERY HARD FORMATION F/ 370 FT TO 375 FT. ROP DROPPED TO 2 FT/HR | 45.02 | 32.79 | 2019-05-22 09:00:00.000 | 546.88 | [5 empty] | 2019-04-11 19:00:00.000 | 2019-04-07 10:30:00.000 | 0 | 1295 | 2019-04-09 05:00:00.000 | 2.4062 | 0.77083 | 1.7708 | 4.3542 | 55.2632 | 731.2941
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-479 | 25.01 | 48.112 | Khurais (KHRS) | Horizontal | PML | 2019-04-19 17:00:00.000 | Primary Drilling | Daqing-47 | DRILL 6-1/8'' L0 TO TD AT 10219 FT.CBU AND DISPLACE SAME WITH FRESH OBM.POOH 6 1/2" BHA TO TOP OF 7" LINEAR AND CIRCULATE SAME.POOH 6 1/2" BHA TO 256 FT AT REPORT TIME. | CONTINUE TO POOH 6 1/8" BHA TO SURFACE AND L/D SAME. WHIPSTOCK RUN,SET SAME AND MILL WINDOW FOR L1. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILLED 6-1/8" L0 HORIZONTAL SECTION W/ VORTEX BHA FROM 9,302 FT TO 10,219 FT. - WOB :10-15 KLB, RPM: 50-100, TQ: 3-8 KLB.FT, FR 270-280 GPM, SPP : 3100 PSI, DIFF: 400-500 PSI - ON BOTTOM ROP: 300-320 FT/HR. - AVG ROP: 141 FT/HR. - REAM UP & REAM DOWN 10 FT PER EACH STAND DRILLED. - TAKE SURVEY BEFORE CONNECTION. - CONTROL ROP AND SWITCH TO AUTO-DRILLER WHEN D/LINK TO RSS. WELL TRAJECTORY AS PER GOC REQUIREMENT: - LAST SURVEY: MD 10,111 FT; INC 89.72°; AZI 160.51°, TVD: 5411.74 FT. - WELL TRAJECTORY: 18 FT BELOW, 4 FT RIGHT | 45.05 | 33.86 | 2019-06-08 19:00:00.000 | 424 | 387.36 |  |  |  |  | 2019-06-08 19:00:00.000 | 2019-04-19 17:15:00.000 | 0 | 12136.0004 | 2019-05-26 10:30:00.000 | 6.25 | 23.0417 | 36.7292 | 50.0833 | 12.4792 | 330.4186
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-484 | 25.054 | 48.016 | Khurais (KHRS) | Horizontal | PML | 2018-06-12 00:00:00.000 | Primary Drilling | Daqing-47 | CONTINUED TO DRILL BLIND FROM 8766 FT TO 9111 FT (6-1/8" L0 SECTION TD). CIRCULATED HOLE CLEAN. WIPER TRIP.CIRCULATED HOLE CLEAN. POOH 6-1/8" DIRECTIONAL BHA TO 6711 FT (INTO 7" LINER ).WAITED ON WEATHER DUE TO SAND STORM.CON'T TO POOH TILL TO 4877 FT AT REPORT TIME. | CON'T TO POOH & L/D 6-1/8" DIRECTIONAL BHA. RUN WL ON TLC. | 620FB696A58F41B8AD6F32AA43E2DAA3 | FLOW CHECK WELL IN TOTAL LOSS. - Cont'd to pump 1.0 bpm mud cap into annulus. | 56.69 | 42.64 | 2018-08-22 20:37:30.000 | [6 empty] | 2018-08-23 07:30:00.000 | 2018-06-11 23:00:00.000 | 40 | 10618.0003 | 2018-08-07 15:45:00.000 | 10.5 | 44.25 | 56.6562 | 72.3125 | 14.5203 | 187.4109
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1031 | 25.0942 | 47.9994 | Khurais (KHRS) | S-shape | EV | 2019-03-03 19:00:00.000 | Primary Drilling | Daqing-48 | DRILL 8-1/2" HOLE F/ 5520 FT TO STD @ 5983 FT AS PER GOC. CHC. WIPER TRIP. CHC. POOH 8-1/2" BHA & L/D SAME. | WIRELINE LOGGING OPERATIONS. | 620FB696A58F41B8AD6F32AA43E2DAA3 | FLOW CHECK - WELL STATIC. | 26.89 | 23.24 | 2019-03-31 19:16:48.000 | 360 | 352.77 |  |  |  |  | 2019-03-31 20:00:00.000 | 2019-03-03 19:00:00.000 | 35 | 5983.0002 | 2019-03-18 11:45:00.000 | 2.5208 | 10.1458 | 14.6979 | 28.0417 | 8.9896 | 407.0645
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1035 | 25.0442 | 48.0231 | Khurais (KHRS) | Vertical | EV | 2019-08-27 05:00:00.000 | Primary Drilling | Daqing-48 | CONT. D/O SHOE TRACK, P/T CSG, DRILL 8 1/2" SECTION TO WELL TD, POH WIPER TRIP, CIRC, POOH, R/B BHA, RUN WL LOGS RUN # 1 | CONT. WL LOGGING OPERATION. | 620FB696A58F41B8AD6F32AA43E2DAA3 | ROTARY DRILL 8 1/2" HOLE F/ 5,147 FT TO 5,157 FT. - FR: 500 GPM, SPP: 1300 PSI, RPM: 70, TQ: 2-4 KFT-LBS, WOB: 12-15 KLBS. - RECORD SCR'S. | 27 | 20.32 | 2019-09-23 19:39:27.000 | 360 | 352.7 |  |  |  |  | 2019-09-23 11:00:00.000 | 2019-08-27 05:00:00.000 | 42 | 5556.0002 | 2019-09-10 16:45:00.000 | 0.9375 | 10.3854 | 14.4896 | 27.25 | 3.4404 | 383.4479
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1330 | 25.2242 | 48.0572 | Khurais (KHRS) | Horizontal | PML | 2018-11-23 05:00:00.000 | Primary Drilling | Daqing-48 | RIH, PRESSURE TEST #2, D/O CEMENT F/C & SHOE TRACK TO 9063 FT ( 30 FT above TOP of F/S ), PRESSURE TEST#3, D/O SHOETRACK,DISPLACE WELL WITH 63 PCF,CLEAR RATHOLE TO 9100 FT, FLOW CHECK, DRILL 8-1/2" HS L0 TO 9930 FT | CONT DRILL 8-1/2" HS L0 TO TD. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 8 1/2" L0 SECTION F/ 9100 FT TO 9110 FT WITH CONTROLLED PARAMETERS. FR: 450-550, SPP: 1900-2250 PSI WOB: 10, RPM:40, TQ: 10-12 KFTLBS. | 81.99 | 68.23 | 2019-02-13 04:49:12.000 | 573 | 507.07 |  |  |  |  | 2019-02-23 07:00:00.000 | 2018-11-23 05:00:00.000 | 35 | 17477.0006 | 2019-01-24 08:15:00.000 | 6.9375 | 38.5833 | 62.1354 | 92.0833 | 7.5339 | 281.2728
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-1749 | 25.2258 | 48.0714 | Khurais (KHRS) | Horizontal | PWI ML | 2018-09-21 15:45:00.000 | Primary Drilling | Daqing-48 | DRILL 6 1/8" L0 HOLE F/ 10200 FT TO/ 12545 FT. | DRILL 6 1/8" L0 HOLE TO +/- 13200 FT. CHC. POOH TO RE POSITION THE WWT PROTECTORS. DRILL TO SECTION TD @ +/- 15442 FT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6 1/8" L0 DIR. HOLE WITH VORTEX BHA F/ 9965 FT TO/ 10040 FT, WITH CONTROLLED PARAMETERS TILL DIR. TOOLS OUT OF CASING. - FR: 280 GPM, SPP: 2200-2600 PSI, DIFF: 300-400 PSI, RPM: 40, WOB: 5-19 KLB, TQ: 4-10 KLB*FT. - AV. ROP: 50 FPH. - TAKE SURVEY AFTER EVERY CONNECTION. - AT KELLY DOWN DRILL OFF 2 MIN, R/U & R/D 5 FT. - DOWNLINK AS PER DD. | 40.99 | 33.01 | 2018-11-01 04:51:54.000 | 778.7 | [5 empty] | 2018-11-12 04:30:00.000 | 2018-09-21 15:00:00.000 | 37 | 18156.0006 | 2018-11-01 06:15:00.000 | 2.1875 | 25.8437 | 40.6042 | 51.5312 | 4.245 | 447.1462
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-361 |  |  | Khurais (KHRS) | Horizontal | PML | 2019-06-02 11:00:00.000 | Primary Drilling | Daqing-48 | CONT. D/OUT CMT & SHOE TRACK TO 6,661 FT, CIRCULATE, P/T LINES, P/T CSG TO 2,000 PSI WATER EQUIVALENT, PRESSURE HOLDS, DISPLACE TO 58 PCF OBM WHILE D/OUT CMT, FLOAT SHOE TO 6,673 FT (GOT TOTAL MUD LOSSES), PUMP MUD CAP IN ANNULUS, DRILL10 FT NEW FORMATION, CIRC., FLOW CHECK, POOH DIR. BHA TO SURFACE, L/D BHA, RIH OEDP 2 3/8" DP & 4" DP ON 5" DP TO 6,600 FT, TRIED TO CIRCULATE, STRING PLUG, TROUBLESHOOT, NO SUCCESS. | POOH, CHECK STRING, RIH TAPERED STRING, PERFORM FIRST CMT PLUG, WOC, WASH DOWN TO 6,600 FT, PERFORM SECOND CMT PLUG, WOC, | 620FB696A58F41B8AD6F32AA43E2DAA3 | CIRCULATE HOLE. - PUMP 0.5 BBL/MIN 68 PCF MUD CAP USING TT. | 70.13 | 34.07 | 2019-08-19 15:00:00.000 | 424 | 379.44 |  |  |  |  | 2019-08-19 13:00:00.000 | 2019-06-02 11:00:00.000 | 40 | 12067.0004 | 2019-08-03 00:15:00.000 | 3.4375 | 48.0208 | 61.5521 | 78.0833 | 4.4023 | 196.0454
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-488 | 25.0986 | 48.0011 | Khurais (KHRS) | Horizontal | PML | 2018-08-01 08:00:00.000 | Primary Drilling | Daqing-48 | DRILL 6 1/8" L0 FROM 9123 FT TO 9676 FT (TD). CHC. POOH AND L/D 6-1/8" L0 DIR BHA. | P/U, M/U & RIH 6-1/8" L0 REAMING BHA. REAM DOWN FROM 6829FT TO 8900 FT. CHC. POOH REAMING BHA. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6 1/8" L0 FROM 9123 FT TO L0 SECTION TD @ 9767 FT - FR: 290 GPM, SPP: 3300 PSI. - DIFF PRESSURE: 250-350 PSI. - WOB: 8-12 KLB, RPM: 100; TQ: 6-10 KLB.FT. - AV ROP: 92 FT/HR; - PUWT: 192 KLBS, SOWT: 130 KLBS, RWT: 163 KLBS. ** OBSERVE 10 BPH DYNAMIC LOSSES. - PUMP SWEEPS EVERY 5 STANDS DRILLED. - REAM UP-DOWN 10 FT EACH STAND DRILLED. - SCR EVERY 500 FT DRILLED - DD DOWNLINKING, AS REQUIRED WITH RPM @ CONTROLLED ROP. - CONTROL ROP INTERMITTENTLY TO MAINTAIN TRAJECTORY AS PER GOC. LAST SURVEY @ 9670 FT; INCL: 92.27; AZIM: 148.45°; TVD: 5090.73 FT WELL PATH: 10.16 FT ABOVE, 2.61 FT LEFT FROM THE PLAN #8. - TVD MAINTAINED AS PER GOC INSTRUCTIONS. | 45 | 26.1 | 2018-09-15 08:30:00.000 | [6 empty] | 2018-09-15 08:00:00.000 | 2018-08-01 06:30:00.000 | 40 | 9767.0003 | 2018-08-24 12:00:00.000 | 1.0625 | 14.7292 | 23.1667 | 45 | 2.3611 | 421.5971
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-560 |  |  | Khurais (KHRS) | Horizontal | PML | 2018-03-02 02:30:00.000 | Primary Drilling | Daqing-48 | CON'T DRILL SHOE TRACK. RE-LOG, AS PER GOC. DRILL L0 SECTION TO 7782 FT. | CON'T DRILLING L0 SECTION TO ±9363 FT. | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6 1/8" L0 F/ 7050 FT TO 7200 FT W/ CONTROLLED PARAMETERS TILL THE BHA IS BELOW F/S. - FR: 270 GPM, SPP: 3000 PSI. - DIFF PRESSURE: 300 PSI. - WOB: 10-15 KLB, RPM: 60; TQ: 5-7 KLB*FT. - AV ROP: 38 FT/HR - PUMP SWEEPS EVERY STAND DRILLED. - REAM UP-DOWN 10 FT EACH STAND DRILLED. - NO LOSSES | 62.29 | 28.53 | 2018-05-02 13:51:10.000 | [6 empty] | 2018-05-02 21:00:00.000 | 2018-03-02 02:30:00.000 | 0 | 10050.0003 | 2018-04-22 01:30:00.000 | 19.2604 | 38.5208 | 50.9583 | 61.7708 | 31.1804 | 197.22
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-595 | 24.785 | 48.244 | Khurais (KHRS) | Horizontal | PML | 2017-11-21 05:00:00.000 | Primary Drilling | Daqing-48 | DRILL 6-1/8" L0 LATERAL FR/ 7414 FT TO 7958 FT. OBSERVE TIGHT HOLE WHILE TAKING UP/DN WEIGHT. CIRC TO CONDITION THE HOLE. RESUME DRILL 6-1/8" L0 LATERAL TO 9000 FT. | DRILL 6-1/8" L0 LATERAL | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6-1/8" DIR HOLE FROM 7414 FT TO 7435 FT WITH CONTROLLED PARAMETERS - FR: 270 GPM, SPP: 2720 PSI. - DIFF PRESSURE: 150 PSI. - WOB:3-5 KLB, RPM: 50 ; TQ: 1 - 6 KFT-LB. - PUWT: 153 KLBS, S/O 129 KLBS; RWT: 145 KLBS - DOWNLINK AS PER DD TO CONTROL TRAJECTORY. - OBSERVE NO DOWN HOLE LOSSES | 66.77 | 49.4 | 2018-02-17 01:30:00.000 | [6 empty] | 2018-02-23 05:00:00.000 | 2017-11-21 05:00:00.000 | 0 | 12491.0004 | 2017-12-31 14:00:00.000 | 17.2604 | 30.1875 | 40.375 | 94 | 18.3621 | 309.3746
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-598 | 24.8746 | 48.1961 | Khurais (KHRS) | Horizontal | PML | 2018-05-08 14:00:00.000 | Primary Drilling | Daqing-48 | DRILLING 6 1/8" HOLE SECTION FROM 9170 FT TO 10014 FT, SWEEP & CIRC HOLE , CONTINUE DRILLING 6 1/8" HOLE SECTION TO 11360 FT. | CONT DRILL 6 1/8” L0 WITH VORTEX BHA TO FTD | 620FB696A58F41B8AD6F32AA43E2DAA3 | DRILL 6 1/8" L0 LATERAL F/ 10014 FT TO 11360 FT. - WOB: 10-15 KLBS, RPM: 100, OFF BTM TQ: 4-6.5 KFTLBS, ON BTM TQ: 7-9.5 KFTLBS. FR: 290 GPM, SPP: 3200 PSI, DIFF: 350-450 PSI. - AV ROP: 93.8 FT/HR. - PUMP 15/15 BBLS SWEEPS EVERY 5 STDS. - DRILL OFF 4 MIN & REAM 10 FT EACH STAND. -DOWNLINK & MAINTAIN TRAJECTORY AS PER GOC. - NO DYNAMIC LOSSES OBSERVED. - CONTROLLED ROP INTERMITTENTLY FOR THE TRAJECTORY. - PER PLAN: 9.5’ ABOVE AND 10.5’ RIGHT OF THE PLAN, GOC REQUEST TO BE 8' ABOVE THE PLAN. | 51.63 | 34.42 | 2018-06-25 23:30:00.000 | [6 empty] | 2018-06-25 20:00:00.000 | 2018-05-08 14:00:00.000 | 35 | 14108.0005 | 2018-06-03 18:00:00.000 | 0.0625 | 15.6562 | 26.1667 | 48.25 | 0.12953 | 539.1593
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | KHRS-795 | 25.1606 | 47.97 | Khurais (KHRS) | Horizontal | PWI | 2018-07-02 03:00:00.000 | Primary Drilling | Daqing-48 | DRILL 6 1/8" HOLE F/ 7000 FT TO 7220 FT, CIRCULATE HOLE CLEAN, PERFORM STICK TEST, CAN'T FREE STRING WITHOUT ROTATION, DRILL 6 1/8" HOLE F/ 7220 FT TO 7313 FT, CONT DO STICK TEST,CAN'T FREE STRING WITHOUT ROTATION, CIRCULATE HOLE CLEAN, PUMP OUT TO 6806 FT,DURING TRIP OUT PERFORM STICK TEST AND 0-D TEST. PUMP OUT TO 6592 FT, FUNCTION TEST STETHOSCOPE INSIDE THE CASING.CIRC AND MIX 79 PCF MUD.DISPLACE HOLE WITH 79 PCF MUD IN PROGRESS. | DISPLACE HOLE WITH 79 PCF MUD, FLOW CHECK,CONT MIX 71 PCF MUD AND DISPLACE TO HOLE, FLOW CHECK. RIH AND CIRC,DRILL AHEAD AND PERFORM FORMATION PRESSURE TEST AS INSTRUCTION. | 620FB696A58F41B8AD6F32AA43E2DAA3 | CONT DRILL 6 1/8" HOLE F/ 7000 FT TO 7220 FT - FR: 260 GPM, SPP:2800-2900 PSI - WOB: 15-20 KLB; RPM: 120; TQ: 5-12KLB.FT. - AVG ROP:37 FT/HR. ON BTM ROP: 52 FT /HR - DRILLED OFF 4 MINUTES, WASHED UP AND REAMED DOWN 15 FT EVERY STAND DRILLED. - PUMP 15 / 15 BBL LO-VIS / HI WT PILL EVERY 5 STANDS. | 21.12 | 16.41 | 2018-07-24 01:46:38.000 | [6 empty] | 2018-07-24 01:00:00.000 | 2018-07-02 03:00:00.000 | 45 | 9717.0003 | 2018-07-21 13:00:00.000 | 0.20833 | 12.8438 | 19.4167 | 21.9167 | 0.95057 | 500.4464
EH | KSA | Saudi Arabia | 620FB696A58F41B8AD6F32AA43E2DAA3 | 479 | 102007 | Khurais LSTK | IDS | KSA | LSTK | MZLJ-1011 |  |  | Mazalij (MZLJ) | Vertical | EV | 2019-09-30 22:00:00.000 | Primary Drilling | Daqing-48 | CONT. RIH 8 1/2" ROTARY BHA, D/O DV, P/T CSG, D/O SHOE TRACK, P/T CSG, DRILL 8 1/2" SECTION TO STD @ 5514 FT, CIRCULATE, WIPER TRIP TO SHOE, CIRC., POOH TO SURFACE, L/D BHA, R/U WIRE LINE. | WIRE LINE LOGGING OPERATION RUN # 1 (FMI/MSIP) & RUN # 2 (AIT/TLD/HGNS). | 620FB696A58F41B8AD6F32AA43E2DAA3 | CIRCULATE HOLE CLEAN W/ 2 X CYCLES. - PUMP 2 X HIVIS PILL. - 600 GPM, 1450 PSI, 40 RPM. | 26 | 20.4 | 2019-10-23 19:15:00.000 | [6 empty] | 2019-10-21 22:15:00.000 | 2019-09-30 22:00:00.000 | 39 | 5514.0002 | 2019-10-13 20:00:00.000 | 0.64583 | 9.3854 | 12.9167 | 21.0104 | 3.0739 | 426.8903
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | KHRS-1407 | 25.0706 | 48.0194 | Khurais (KHRS) | Horizontal | PML | 2019-02-25 11:30:00.000 | Primary Drilling | AD-53 | DRILL 8-1/2" DIR. HOLE FROM 11,132 FT TO 11,512 FT AS PER PLAN-P12, CHC, #1 SHORT WIPER TRIP, CONT. DRILL 8-1/2" DIR. HOLE FROM 11,512 FT TO 13,026 FT AS PER PLAN-P12, CHC, #2 SHORT WIPER TRIP. | CONT. #2 SHORT WIPER TRIP, DRILL 8-1/2" DIR. HOLE AS PER PLAN-P12 TO 14,543 FT, CHC, PERFORM 3RD SHORT WIPER TRIP, CONT. DRILL 8-1/2" DIR. HOLE AS PER PLAN-P12. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB VORTEX DRLG 8-1/2" HOLE WITH 65 PCF OBM MUD WITH 100% RETURN TO 13,026 FT. ** CUMULATIVE TIME FOR DOWNLINK (DAILY / TOTAL): 2/4.5 HOURS. ** SWEPT HOLE WITH 15 BBL LO VIS/20 BBL HVWP EVERY 3 STANDS DRILLED. ** BACK REAM & REAM DOWN 15-30 FT OF STD DRILLED. ** TOOK SURVEY EVERY STAND DRILLED. ** WELL PATH: 5.01 FT RIGHT & 0.44 FT BELOW THE PLAN. ** DRILLING PARAMETERS: - WOB: 10-20 KLBS. - RPM:100 & TQ: 10-16 KLB-FT. - FR: 560-590 GPM & PRESSURE: 3,650-4,150 PSI. - P/U WT: 215 KLBS, S/O WT: 165 KLBS, RWT: 173 KLBS. - AVG. ROP: 108.35 FPH. | 72 | 64 | 2019-05-03 20:56:45.000 | 573 | 461.85 |  |  |  |  | 2019-04-28 16:00:00.000 | 2019-02-25 11:00:00.000 | 35 | 19408.0006 | 2019-04-17 20:30:00.000 | 2.7812 | 30.4583 | 51.375 | 62.1875 | 4.4724 | 377.7713
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | KHRS-1703 | 25.2815 | 48.0581 | Khurais (KHRS) | Horizontal | PWI ML | 2019-06-20 12:00:00.000 | Primary Drilling | AD-53 | RIH BACK TO BTM MEANWHILE CHECK & TIGHT NRP (HOLE IN GOOD CONDITION) & RESUME DRILLING 6-1/8" HZ.S W/ 6-1/8" RSS-MTR-LWD VORTEX BHA TO 16,040 FT AS PER PLAN#10 & GOC. | CONT. DRILLING 6-1/8" HZ.S W/ 6-1/8" RSS-MTR-LWD VORTEX BHA TO TD@ 18,528 FT AS PER PLAN#10 & GOC, CHC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB RSS DRILLING 6-1/8" HZ HOLE WITH 66 PCF NON-DAMAGING SALT POLYMER MUD WITH 100% RETURN FROM 14,335 FT TO 14,780 FT. - SWEPT HOLE WITH 15/15 BBLS LO/HI-WT PILLS EVERY 3 STD. - BACK REAM & REAMED DOWN 10-15 FT OFF BTM. - TOOK SURVEY EVERY STAND DRILLED. ** DRILLING PARAMETERS: - WOB : 10-25 KLBS - RPM:100 & TQ: 8 - 12 KLB-FT. - FR: 290 GPM & PRESSURE: 2,950 - 3,500 PSI - AVG. ROP: 105 FPH. | 50 | 48 | 2019-08-09 05:00:28.000 | 541 | 544.12 |  |  |  |  | 2019-08-08 12:00:00.000 | 2019-06-20 11:30:00.000 | 38 | 18845.0006 | 2019-08-02 04:00:00.000 | 14.3646 | 27.4479 | 42.6667 | 49 | 29.3155 | 441.6797
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | KHRS-487 | 25.07 | 48.0863 | Khurais (KHRS) | Horizontal | PML | 2019-08-16 17:00:00.000 | Primary Drilling | AD-53 | CONT.SLB VORTEX DRLG 6-1/8" HZ SECTION WITH COMPLETE LOSS, F/ 11,130 FT TO STD @ 12,564 FT. | CONTINUE CHC, PERFORM WIPER TRIP, POOH, L/D DRLG BHA, RIH WITH SLB WL, FMI & CALIPER LOG ON TLC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | RESUME SLB VORTEX DRILLING 6-1/8" HZ HOLE WITH WATER & GEL SWEEP & NO RETURN F/ 11,130 FT TO 11,640 FT. - SWEPT HOLE WITH 20 BBLS HW-HV PILLS EVERY STD. - BACK REAM & REAMED DOWN 10-15 FT OFF BTM. - TOOK SURVEY EVERY STAND DRILLED BEFORE CONNECTION. - SEND DOWN-LINK OFF-BTM TWICE EVERY STAND TO CORRECT AZIMUTH AS PER GOC. ** DRILLING PARAMETERS: - WOB : 15-20 KLBS - RPM:40-80 & TQ: 6 - 9.5 KLB-FT. - FR: 290 GPM & PRESSURE: 1,400 - 1,700 PSI - AVG. ROP: 72 FPH. | 78 | 77.07 | 2019-11-01 01:45:45.000 | [6 empty] | 2019-10-22 00:30:00.000 | 2019-08-16 17:00:00.000 | 35 | 12564.0004 | 2019-09-19 04:00:00.000 | 0.35417 | 21.7083 | 33.4583 | 66.3125 | 0.53409 | 375.5118
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | KHRS-518 | 25.2601 | 48.0306 | Khurais (KHRS) | Horizontal | PML | 2019-05-05 22:00:00.000 | Primary Drilling | AD-53 | DRILL 8-1/2" HOLE SECTION WITH VORTEX BHA F/ 6,265 FT TO 8,660 FT. | CONT DRILL 8-1/2" HOLE SECTION WITH VORTEX BHA TO TD @ 10,257 FT. CHC. DISPLACE HOLE TO BRINE. POOH TO SURFACE. RUN 9-5/8" C/O ASSY. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DIR. DRLG 8-1/2" L1 HZ HOLE SECTION WITH VORTEX BHA WITH 58 PCF OBM WITH 100% RETURN FROM 7,450 FT TO 8,660 FT. - DRILL WITH CONTROLLED ROP FOR DENSITY IMAGE LOG QUALITY AS PER GOC REQUEST. - CUMULATIVE TIME FOR DOWNLINK (DAILY / TOTAL): 4 / 5 HRS. - BACK REAM & REAM DOWN 10-15 FT OF STD DRILLED. - TOOK SURVEY EVERY STAND DRILLED. - WELL PATH: 6.5 FT BELOW & 9 FT LEFT TO THE PLAN AS PER GOC REQUEST. ** DRILLING PARAMETERS: - WOB: 30-35 KLBS. - RPM:100 & TQ: 8-13 KLB-FT. - FR: 590-600 GPM & PRESSURE: 3,000-3,150 PSI. - P/U WT: 175 KLBS, S/O WT: 135 KLBS, RWT: 150 KLBS. - AVG. ROP: 100 FPH. | 41.01 | 39.62 | 2019-06-15 05:21:19.000 | 424 | 444.49 |  |  |  |  | 2019-06-13 04:00:00.000 | 2019-05-05 21:30:00.000 | 35 | 10257.0003 | 2019-06-08 21:30:00.000 | 0 | 22.2917 | 33.9792 | 38.25 | 0 | 301.8614
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | MZLJ-315 | 24.489 | 48.1 | Mazalij (MZLJ) | Horizontal | PML | 2018-07-24 20:00:00.000 | Primary Drilling | AD-53 | CONTINUE DRILL 6 1/8" L0 HOLE SECTION AS PER PLAN FROM 7850 FT TO 8250 FT. PUMP LOVIS/HIWT PILLS & CIRCULATE HOLE CLEAN. WIPER TRIP FROM 8,250 FT TO 7,750 FT. HOLE IN GOOD CONDITION. CONTINUE DRILL 6 1/8" L0 HOLE SECTION AS PER PLAN FROM 8250 FT TO 8,770 FT. . | CONTINUE DRILL 6 1/8" L0 HOLE SECTION AS PER PLAN. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | HPJSM. POH (ON ELEVATOR) WITH 6 1/8" DIRECTIONAL BHA FROM 8,250 FT TO 7,750 FT. - HOLE IN GOOD CONDITION, HAD NO EXCESS DRAG OBSERVED. - MONITOR WELL ON TRIP TANK WHILE POH, WELL TAKE CORRECT METAL DISPLACEMENT. . | 57.9 | 44.38 | 2018-10-08 15:54:00.000 | 428.24 | 428.24 |  |  |  |  | 2018-10-18 21:00:00.000 | 2018-07-24 20:00:00.000 | 35 | 10442.0003 | 2018-09-18 05:00:00.000 | 4.2188 | 41.9792 | 55.375 | 86.0417 | 4.9031 | 188.5689
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | MZLJ-677 | 24.1802 | 48.1129 | Mazalij (MZLJ) | Horizontal | PWI | 2018-10-25 21:30:00.000 | Primary Drilling | AD-53 | CONTINUE RIH WHILE M/U WWT NON ROTATING PROTECTOR & TAG HARD CMT @ 3,800 FT. C/O CMT & FLOATING, P/T CSG, DRILL 23 FT NEW FORMATION WITH LOW ROP, DECIDED TO POH & CHECK THE BIT. | CHECK & CHANGE BIT, M/U 6-1/8” MOTORIZED-RSS/LWD BHA & RIH TO 7” LNR SHOE@ 4,136 FT, N/D BELL NIPPLE, M/U RCD BEARING, DRILL 6-1/8" HOLE SECTION AS PER PLAN 2.0 & GOC TO 10,348 FT. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6-1/8" H.S W/ MOTORIZED-RSS/LWD ASSY WITH LOW ROP, MEANWHILE MAKE DRILL-OFF TEST & APPLY DIFFERENTS PARAMETER. - DECIDED TO POOH & CHECK BIT. | 40.63 | 37.76 | 2019-02-14 07:28:00.000 | 365 | 462.85 |  |  |  |  | 2019-02-19 13:30:00.000 | 2018-10-25 21:30:00.000 | 35 | 10318.0003 | 2019-01-16 14:30:00.000 | 40.375 | 62.3542 | 82.7083 | 116.6667 | 34.6071 | 124.7516
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-622 | 24.867 | 49.182 | Hawiyah (HWYH) | Horizontal | PHZ | 2018-12-02 14:00:00.000 | Primary Drilling | AD-54 | CONT DRILL OUT CEMENT & SHOE TRACK TO 7,306 FT (30 FT ABOVE LINER SHOE), CHC, P/TEST 7” LINER, DISPLACE HOLE TO 74 PCF LSND MUD, DRILL 15 FT OF FORMATION TO 7,355 FT, FLOW CHECK, DRILL AHEAD 6-1/8” HOLE FROM 7,355 FT TO 8,035 FT WITH VORTEX BHA AS PER DIR PLAN #10. | DRILL AHEAD 6-1/8” HOLE TO 8,800 FT WITH VORTEX BHA AS PER DIR PLAN #10, PERFORM WIPER TRIP, CONT. DRILL 6-1/8” HOLE TO 9,960 FT WITH VORTEX BHA AS PER DIR PLAN #10. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6-1/8" DIRECTIONAL HOLE WITH VORTEX BHA FROM 7,540 FT TO 8,035 FT FOLLOWING DIR PLAN #10. DRILLING PARAMETERS: - WOB: 5-10 KLB, RPM: 100; TQ: 5-7 KFT-LB. - FR: 280 GPM, SPP: 2650-2850 PSI, DIFF PR: 350-400 PSI. - OB ROP = 70-100 FPH; AVG ROP: 45 FPH. - P/U WT: 140 KLB; S/O WT: 113 KLB; ROT WT: 126 KLB. - WASH UP & REAM DOWN 30 FT EACH CONN. - SWEEP HOLE WITH 15 BBL LO-VIS/ 15 BBL HI-WT/HI-VIS PILL EVERY 2 STDS. - NO DOWN HOLE LOSSES. - SURVEY EVERY 45 FT AS PER GOC. LAST SURVEY @ 7,881’: TVD: 6,170.31’, INC: 84.48 DEG, AZI: 113.5 DEG DEVIATION FROM PLAN: 3.9’ BELOW & 1.9’ LEFT | 36.34 | 32.73 | 2019-01-07 03:36:36.000 | 365 | 498 |  |  |  |  | 2019-01-07 02:00:00.000 | 2018-12-02 14:00:00.000 | 35 | 9960.0003 | 2018-12-30 11:15:00.000 | 1.6042 | 17.8021 | 27.8854 | 35.5 | 4.5188 | 357.176
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-662 | 24.735 | 49.14 | Hawiyah (HWYH) | Horizontal | PHZ | 2019-01-15 03:30:00.000 | Primary Drilling | AD-54 | P/TEST 7" LINER - OK. DRILLED OUT L. COLLAR, CMT , F. COLLAR. P/TEST 7" LINER - OK. DRILLED OUT CMT & 7" FLOAT SHOE. DRILL 6-1/8" DIRECTIONAL HOLE WITH VORTEX BHA FROM 6790 FT TO 7070 FT - IN PROGRESS... | CONTINUE DRILLING TO 8,280 FT, PERFORM SHORT WIPER TRIP & RESUME DRLG TO TD 9,422 FT AS PER DIR PLAN#8. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | FLOW CHECK, WELL STATIC & RECORD SCRs. | 34.36 | 29.85 | 2019-02-21 18:00:00.000 | 365 | 471.1 |  |  |  |  | 2019-02-21 19:00:00.000 | 2019-01-15 03:30:00.000 | 40 | 9422.0003 | 2019-02-12 22:45:00.000 | 7.2812 | 20.9479 | 28.8021 | 37.6458 | 19.3414 | 327.1291
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-677 | 24.7511 | 49.1338 | Hawiyah (HWYH) | Horizontal | EV+PHZ combine | 2018-09-25 03:00:00.000 | Primary Drilling | AD-54 | CONT TO DRILL 6-1/8" INTERVAL FROM 7,800 FT TO 8,863 FT. PUMPED TANDEM SWEEP. CIRC AND COND HOLE TWO B/U. FLOW CHECK. PERFORM WIPER TRIP (5 STANDS). RIH AND CONT TO DRILL 6-1/8" INTERVAL FROM 8,863 FT TO 8,900 FT AS PER DIRECTIONAL PLAN #6. | CONT TO DRILL 6-1/8" INTERVAL FROM 8,900 FT TO SECTION TD AS PER DIRECTIONAL PLAN #6. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | CONT TO DRILL 6-1/8” DIRECTIONAL HOLE FROM 7,800 FT TO 8,871 FT FOLLOWING DIRECTIONAL PLAN #6.0. - FR: 280 GPM, SPP: 2,900-3,000 PSI. - DIFF PRESSURE: 350-400 PSI. - WOB: 8-12 KLB, RPM: 100; TQ: 5-7 KFT-LB. - AVERAGE ROP: 57.9 FT/HR. - NO DOWN HOLE LOSSES AND FULL RETURNS OBSERVED. - BACK REAMING UP AT 50 RPM AND REAMING DOWN AT FULL PARAMETERS FOR 15 FT EACH CONNECTION. - PUMPING 20 BBLS OF LOW VIS/HIGH WT SWEEP EVERY THREE STANDS OR AS NEEDED. | 69.32 | 53.42 | 2018-11-26 08:54:00.000 | 500 | 500 |  |  |  |  | 2018-11-25 14:00:00.000 | 2018-09-25 03:00:00.000 | 0 | 9615.0003 | 2018-11-10 20:00:00.000 | 1.875 | 34.0417 | 46.7083 | 61.4583 | 3.0508 | 205.8519
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4037 | 25.1603 | 49.2734 | Uthmaniya (UTMN) | Horizontal | PHZ | 2018-07-27 18:00:00.000 | Primary Drilling | AD-54 | DRILL 6 1/8" HOLE AHEAD FROM 7997 FT TO 8943 FT. HAVE TOTAL LOSS. PUMP 82 PCF MUD CAP FROM ANNULUS AS ANNULAR VOLUME. SWEEP HOLE. PERFORM 5 STDS WIPER TRIP. RIH TO BTM. | DRILL 6 1/8" HOLE AHEAD AS PER PLAN BY WGS | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6-1/8” DIRECTIONAL HOLE FROM 8281 FT TO 8943 FT FOLLOWING PLAN 4.0. - FR: 270-290 GPM, SPP: 2600-3000 PSI. DIFF PRESSURE : 300-370 PSI. - WOB: 10-18 KLB, RPM: 90-100; TQ : 6.0-7.0 KFT-LB. - WASH UP & REAM DOWN 15 FT/STDS. - OB ROP = 77.2 FPH; AVG ROP: 51 FPH - SWEEP HOLE 15BBLS EACH LO-VIS/HI- WEIGHT-HI-VIS PILL AFTER EVERY 3 STDS.. - PERFORMED DOWN LINKING AS PER GOC INSTRUCTIONS. - TOTAL DOWN LINK TIME 130 MIN. - HAVE COMPLETE LOSS @8943 FT. | 37.35 | 54.72 | 2018-09-17 07:30:00.000 | 490.38 | [5 empty] | 2018-09-20 22:45:00.000 | 2018-07-27 18:00:00.000 | 35 | 10790.0003 | 2018-09-06 00:15:00.000 | 4.4687 | 27.8125 | 40.2604 | 55.1979 | 8.0959 | 268.0052
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4039 | 25.299 | 49.341 | Uthmaniya (UTMN) | Horizontal | PML | 2019-06-06 08:00:00.000 | Primary Drilling | AD-54 | D/O CMT TO 20FT, ABOVE F.S, P/T CSG, D/O F.S, FLOW CHECK, DRILL 6-1/8” HS W/ SLB RSS-LWD ASSY TO 7,698 FT, PD TOOL FAILURE (NBI & NBGR NOT RECEIVED), F.C & POH, CHANGED BHA & RIH W/ NEW 6-1/8" SLB RSS-LWD | RE-LOG 150 FT OFF-BTM AS PER GOC & DRILL 6-1/8” HS W/ SLB RSS-LWD ASSY TO L0 TD @ 11,139 FT AS PER PLAN 12 & GOC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILLING 10 FT NEW FORMATION T/7,467 FT. | 54.86 | 47.91 | 2019-07-27 05:00:00.000 | 330 | 384.31 |  |  |  |  | 2019-07-27 17:00:00.000 | 2019-06-06 08:00:00.000 | 40 | 11139.0004 | 2019-07-02 10:15:00.000 | 2.375 | 14.4062 | 26.0938 | 51.375 | 4.6229 | 426.8838
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4040 | 25.091 | 49.217 | Uthmaniya (UTMN) | Horizontal | PML | 2019-02-27 17:30:00.000 | Primary Drilling | AD-54 | CONT. DRILL OUT SHOE TRACK. DRILL 6-1/8" L-0 TO 9500 FT (PLANNED SECTION TD @ 11756 FT). | DRILL 6-1/8" L-0 TO SECTION TD (+/- 11756 ft). | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | FLOW CHECK, WELL STATIC. | 52.33 | 43.96 | 2019-04-25 23:45:00.000 | 330 | 538.02 |  |  |  |  | 2019-04-27 00:00:00.000 | 2019-02-27 17:30:00.000 | 40 | 12013.0004 | 2019-04-11 13:00:00.000 | 1.2708 | 24.4792 | 42.8125 | 58.2708 | 2.1809 | 280.5956
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4048 | 25.203 | 49.287 | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-05-02 11:30:00.000 | Primary Drilling | AD-54 | RIH TO TOC, PERFORM 2ND P-TEST CSG. DRILL OUT CMT & SHOE TRACK. PERFORM 3RD P-TEST CSG 30 FT ABOVE FS. DISPLACE HOLE TO LSDN MUD. DRILL CMT, FS AND RAT HOLE. DRILL 10 FT OF NEW FORMATION TO 7,510 FT. FC - OK. DRILL 6-1/8" SECTION - IN PROGRESS @ 7,520 FT... | DRILL 6-1/8" SECTION TO TD @ 9,635 FT. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | FLOW CHECK, WELL STATIC. | 30.68 | 29.13 | 2019-05-29 23:06:00.000 | 365 | 463.22 |  |  |  |  | 2019-05-30 23:00:00.000 | 2019-05-02 11:30:00.000 | 40 | 9635.0003 | 2019-05-22 16:00:00.000 | 0.28125 | 13.0417 | 20.1875 | 28.4792 | 0.98756 | 477.2756
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4050 | 25.029 | 49.246 | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-08-04 17:00:00.000 | Primary Drilling | AD-54 | CONT POOH TO SURFACE, CHANGE 6-1/8" RSS BHA, RIH, CONT DRILLING 6-1/8" HOLE SECTION TO 10085 FT | CONT DRILLING 6-1/8" HOLE SECTION TO TD +/- 10,665 FT, CHC, PERFORM WIPER TRIP, POOH, L/D BHA, RUN MECHANICAL CALIPER ON TLC | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | PJSM , POOH & L/D 6 1/8" RSS-LWD BHA. - RETRIEVED R/A SOURCE. - BIT DULL: 1-1-WT-A-X-I-NO -BHA. - DOWNLOAD LWD DATA. - CONT PUMPING 71 PCF MUD CAP AT 1-2 BPM FROM BACKSIDE. | 36.89 | 33 | 2019-08-16 03:20:34.000 | 365 | 381.42 |  |  |  |  | 2019-09-08 05:00:00.000 | 2019-08-04 17:00:00.000 | 40 | 11400.0004 | 2019-08-28 00:15:00.000 | 1.3646 | 13.7083 | 23.3021 | 34.5 | 3.9553 | 489.2267
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4804 | 25.4 | 49.8 | Uthmaniya (UTMN) | Horizontal | PWI | 2019-09-13 14:00:00.000 | Primary Drilling | AD-54 | CONT. DISPLACE WELL TO 85 PCF MUD, CONDUCT PORE PRESSURE TEST, DRILL 6-1/8” DIRECTIONAL HOLE WITH RSS BHA USING MPD SYSTEM TO 9,450 FT. | DRILL 6-1/8” DIRECTIONAL HOLE TO +/- 12,307 FT (SECTION TD) WITH 85 PCF LSND MUD USING MPD SYSTEM (DIR PLAN #5). | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | PUMPED TANDEM PILLS AND CIRCULATED HOLE CLEAN. | 37 | 30.83 | 2019-09-16 21:29:29.000 | [6 empty] | 2019-10-21 15:00:00.000 | 2019-09-13 14:00:00.000 | 40 | 12807.0004 | 2019-10-08 18:00:00.000 | 0 | 15.0521 | 25.1667 | 38.0417 | 0 | 508.8874
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-1474 | 24.102 | 49.053 | Haradh (HRDH) | Horizontal | PHZ | 2019-08-01 22:00:00.000 | Primary Drilling | SINO-35 | DRILL 6-1/8" HOLE W/ SLB RSS TO 7841'- SLOW ROP, POOH TO SURFACE, M/U NEW 6-1/8" BIT & RSS BHA, RIH TO 7200'. | CONT. RIH TO BTM @ 7841'. DRILL 6-1/8" HOLE W/ SLB RSS TO +/- 10929 AS PER PLAN# 12. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB RSS DRLG 6-1/8" HOLE W/ 76 PCF LSND MUD, 100% RETURN TO 7841'. • CUMULATIVE DOWNLINKING DAILY / TOTAL: 0.5/ 0.5 HR'S. • CONTROLLED DRLG PARAMETERS TILL BHA OUT OF SHOE • EXPERIENCE SLOW ROP , DECISION MADE TO POOH & CHANGE BIT • DRLG PARAMETERS: - WOB: 13-20 KLBS, RPM: 50, FR 250-280 GPM, PRESSURE: 1950 PSI, ON BTM TQ: 3-5 KLB-FT. - AV. ROP : 9.6 FPH. | 27 | 22.63 | 2019-08-30 23:00:00.000 | 365 | 455.38 |  |  |  |  | 2019-09-03 00:00:00.000 | 2019-08-01 20:00:00.000 | 35 | 10929.0003 | 2019-08-25 06:30:00.000 | 1.5 | 13.6354 | 23.3542 | 32.0833 | 4.6753 | 467.9679
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-288 |  |  | Haradh (HRDH) | Horizontal | PHZ | 2019-09-06 16:00:00.000 | Primary Drilling | SINO-35 | DRILL 6-1/8" HOZ HOLE TO 8112'- HAD TOTAL LOSS , CONT. BLIND DRLG 6-1/8" HOZ HOLE W/ WGS & MUD CAP IN BACK SIDE TO 8670'. | DRILL 6-1/8" HOZ HOLE TO +/- 9700'. CHC, WIPER TRIP TO CSG SHOE, RIH, CHC, POOH. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB RSS DRLG 6-1/8" HOLE W/ TOTAL LOSSES W/ WGS TO 8670'. - SWEEP HOLE W/ 15 BBL HVP EVERY SINGLE DRILLED. - PUMP 1 BPM 84 PCF MUD CAP IN BACK SIDE. - BACK REAM / REAM DOWN LAST SINGLE DRILLED. - CUMULATIVE DOWNLINKING DAILY/TOTAL: 2/2.5 HR'S. - DRLG PARAMETERS: - WOB: 10-19 KLBS, RPM: 50-140, FR: 250-280 GPM, PRESSURE:1550- 1750 PSI, ON BTM TQ: 3-6 KLB-FT. - AV. ROP : 52 FPH. - LAST SURVEY: MD: 8606', TVD: 6508.2', INC: 91.20, AZI: 43.43. | 31.51 | 26.34 | 2019-10-07 17:07:36.000 | [6 empty] | 2019-10-13 00:00:00.000 | 2019-09-06 15:30:00.000 | 35 | 9700.0003 | 2019-09-30 23:00:00.000 | 5.4583 | 16.1667 | 24.2917 | 36.3333 | 15.0229 | 399.3139
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-525 | 24.2635 | 48.9787 | Haradh (HRDH) | S-shape | EV | 2019-05-04 23:00:00.000 | Primary Drilling | SINO-35 | CHC, PT CSG,COC DRILL SHOE TRACK MEANWHILE DISPLACE HOLE TO 78 PCF MUD, DRILL 6-1/8" HOLE TO 6826 FT, OBSERVED SLOW ROP, POOH TO SURFACE, CHANGE BIT , RIH WITH 6-1/8" PDC BIT AND ASSEMBLY TO 1810 FT | CON. RIH WITH BHA TO 6826 FT , DRILL 6-1/8" HOLE TO +/-7055 FT ,CHC, WIPER TRIP TO CSG SHOE, RIH CHC, POOH, RUN WIRE LINE LOGGING. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILLED 6-1/8” HOLE FROM 6,703 FT TO 6,826FT * EXPERIENCED VERY SLOW ROP , CONSULT OFFICE FOR POOH AND CHANGE THE BIT * NO DOWN HOLE LOSSES OBSERVED. DRILLING PARAMETERS. - FR: 310 GPM, SPP: 970 - 1000 PSI. - WOB: 25-30 KLB, RPM: 100; TQ: 2.7-3.6 KLB-FT. | 35.68 | 30.17 | 2019-06-13 19:30:00.000 | 352 | 352.75 |  |  |  |  | 2019-06-17 00:00:00.000 | 2019-05-04 23:00:00.000 | 35 | 7055.0002 | 2019-06-03 19:00:00.000 | 3.25 | 22.2917 | 29.8333 | 43.0417 | 7.5508 | 236.4805
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-558 | 24.3809 | 49.1368 | Haradh (HRDH) | Horizontal | PHZ | 2019-03-18 08:00:00.000 | Primary Drilling | SINO-35 | CON.DRILL 6-1/8" HZ HOLE TO 9329 FT. | CONT. DRILL 6-1/8" HZ HOLE TO +/-10813'.SWEEP & CHC , WIPER TRIP TO CSG SHOE.RIH, CHC, DISPLACE HOLE TO 79 PCF BRINE, SPOT MUDZYME , POOH TO SURFACE. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB VORTEX DRLG 6-1/8" HOLE W/ 79 PCF LSND MUD, 100% RETURN TO 8530'. | 29.92 | 25.36 | 2019-04-23 14:00:00.000 | 365 | 540.65 |  |  |  |  | 2019-04-29 00:30:00.000 | 2019-03-18 08:00:00.000 | 35 | 10813.0003 | 2019-04-18 08:00:00.000 | 7.5208 | 23.0312 | 31 | 41.6875 | 18.041 | 348.8065
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-561 | 24.1453 | 48.58 | Haradh (HRDH) | Horizontal | PHZ | 2019-06-21 11:00:00.000 | Primary Drilling | SINO-35 | CHECK TOOL,M/U & RIH 6-1/8" RSS BHA TO BTM, D/A 6-1/8" HOLE TO 8395'. | CONT D/A 6-1/8" HOLE TO TD. SEC TD @10891'. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | POOH W/ 8-1/2" SLB RSS DRLG BHA TO TOP OF BHA @ 379' | 30.79 | 27.01 | 2019-07-24 10:02:06.000 | 365 | 390.47 | 20190714095939 |  |  |  | 2019-07-29 01:45:00.000 | 2019-06-21 09:30:00.000 | 35 | 11140.0004 | 2019-07-14 16:00:00.000 | 1.6667 | 15.1146 | 23.2083 | 37.6146 | 4.4309 | 480
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-649 |  |  | Hawiyah (HWYH) | Horizontal | PHZ | 2019-10-17 08:30:00.000 | Primary Drilling | SINO-35 | CONT RIH TO 1210 FT. DRILL 17" HS W/ ROTARY BHA TO TD SECTION @ 1747 FT, CHC, POOH. | CONT POOH TO SURFACE , L/D 17” ROTARY BHA, RUN 13-3/8” CSG,CEMENT JOB,WOC, CUT 13-3/8" & 18-5/8" CSG, N/U & WELD CHH, N/U & P/T BOP | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | P/U & M/U 17" TC BIT & RIH TO 1000 FT. - PUMP 1 BPM IN ANNULUS. | 29.99 | 27.12 | 2019-11-17 08:30:10.000 | [6 empty] | 2019-10-22 00:30:00.000 | 2019-10-17 08:30:00.000 | 35 | 1747.0001 | 2019-10-22 00:30:00.000 | 0 | 1.8646 | 4.6667 | 4.6667 | 0 | 374.3572
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-593 | 25.3836 | 49.29 | Shedgum | Horizontal | PHZ | 2018-03-13 15:00:00.000 | Primary Drilling | SINO-35 | VORTEX DRILLING 6-1/8" HZ HOLE WITH 81 PCF LSND MUD TO 9600-FT | CONT. DRLG 6-1/8" HZ HOLE TO TD @ +/- 12000' | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | PERFORMED FLOW CHECK, WELL STATIC- OK. | 61.98 | 26.94 | 2018-05-06 23:44:58.000 | 510 | [5 empty] | 2018-04-23 00:00:00.000 | 2018-03-13 15:00:00.000 | 0 | 12006.0004 | 2018-04-12 07:15:00.000 | 6.5833 | 18.4896 | 29.6771 | 40.375 | 16.3055 | 404.5546
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-594 | 25.47 | 49.3 | Shedgum | Horizontal | PHZ | 2018-08-06 09:00:00.000 | Primary Drilling | SINO-35 | RIG DOWN RCD SYSTEM .P/U & RIH WITH Milling BHA . CHC @ LINER SHOE, RIH IN OPEN HOLE GOT SUCK @ 8130 FT , FREE STRING, CHC , REAM DOWN . | CONT. RIH WITH MILLING BHA, POH, P/U & RIH WITH 6-1/8" REAMING BHA . | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | RIH MILLING ASSY WITH PRECAUTION INSIDE 7" LINER. ** GOT 10 KLBS WEIGHT AT 3038 FT ** RECORD PARAMETERS BEFOR START MILLING - PICK UP WEIGHT 98 KLBS - SLACK OFF WEIGHT 96 KLBS - TORQUE OFF BOTTOM 450 LB-FT @ 40 RPM - CIRCULATING PRESSURE AT 100, 150, 200, 270 GPM ARE RESPECTIVELY 80, 150, 250, 400 PSI | 19.93 |  | 2018-08-26 03:21:36.000 | 510 | [5 empty] | 2018-10-02 00:30:00.000 | 2018-08-06 09:00:00.000 | 0 | 12100.0004 | 2018-09-02 22:00:00.000 | 18.5417 | 17.0833 | 27.5417 | 56.6458 | 32.7326 | 439.3344
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-595 | 25 | 49 | Shedgum | Horizontal | PHZ | 2018-12-23 11:00:00.000 | Primary Drilling | SINO-35 | DRLD 6-1/8" HZ HOLE TO 10,330 FT | CONT, DRLG 6-1/8" HZ HOLE TO ± 11,904 FT. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SLB VORTEX DRILLING 6-1/8" HZ HOLE WITH 85 PCF LSND MUD TO 9743' | 36.96 | 29.63 | 2019-02-02 18:35:06.000 | 365 | 551.6 |  |  |  |  | 2019-02-05 02:15:00.000 | 2018-12-23 11:00:00.000 | 35 | 11694.0004 | 2019-01-20 07:45:00.000 | 3.8542 | 15.3229 | 27.8646 | 43.6354 | 8.8327 | 419.6725
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-597 | 25.47 | 49.3 | Shedgum | Horizontal | PHZ | 2018-10-04 20:00:00.000 | Primary Drilling | SINO-35 | CONT. DRLG 6-1/8" HZ HOLE FROM 9060' TO 10,525'. | CONT. DRLG 6-1/8" HZ HOLE TO TD @ ± 13,000'. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | OBSERVED MUD WT OUT 83 PCF & MWT WT IN 85 PCF, PERFORMED FLOW CHECK, WELL STATIC-OK. | 69.98 | 67.93 | 2018-12-16 13:00:00.000 | 510 | 510 |  |  |  |  | 2018-12-16 13:00:00.000 | 2018-10-04 19:00:00.000 | 35 | 12997.0004 | 2018-11-02 23:15:00.000 | 36.6771 | 17.1354 | 29.1354 | 72.7083 | 50.4441 | 446.0894
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-599 | 25.83 | 49.39 | Shedgum | Horizontal | PHZ | 2018-06-08 00:30:00.000 | Primary Drilling | SINO-35 | P/T UPR , OK, PJSM, P/U & RIH WITH SLB 6-1/8" VORTEX BHA, RELOG, VORTEX DRLG 6-1/8" HOZ HOLE TO 8330 FT | CONT. VORTEX DRLG 6-1/8" LATERAL TO TD AS PER PLAN 12 | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | VORTEX DRILLING 6-1/8" HZ HOLE W/ 85 PCF LSND MUD TO 8196. ** CONTROLLED DRLG PARAMETERS TILL VORTEX BHA CAME OUT OF SHOE. ** CONTROLLED DRLG PARAMETERS FOR HOLE TRAJECTORY ** SWEPT HOLE WITH 15/15 BBLS HVP EACH 2 STANDS DRILLED. DRILLING PARAMETERS: ** WOB : 5-10 KLBS ** RPM : 60 & FR 270 GPM ** PR ON BTM-2200 PSI & PR OFF BTM 2500 PSI ** ON BTM TQ : 5-6 KLB-FT & OFF BTM TQ : 2-3 KLB-FT ** AV. ROP : 30 FPH | 50.66 | 46.06 | 2018-08-01 07:12:00.000 | 510 | [5 empty] | 2018-07-31 19:00:00.000 | 2018-06-08 00:30:00.000 | 40 | 12142.0004 | 2018-07-22 11:30:00.000 | 0.47917 | 27.7396 | 44.4583 | 53.7708 | 0.89113 | 273.1097
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-739 | 25.7926 | 49.518 | Shedgum | Horizontal | PWI | 2018-04-30 13:30:00.000 | Primary Drilling | SINO-35 | VORTEX DRLG 6-1/8" LATERAL HOLE WITH 89 PCF LSND MUD & 95 % RETURN FROM 9813' TO 10583'. | CONT. VORTEX DRLG 6-1/8" LATERAL HOLE TO TD @ +/- 11,312', CHC, DISLACE HOLE TO 91 PCF BRINE, POOH TO SURFACE & L/D VORTEX BHA MEANWHILE L/D 4" DP SINGLE BY SINGLE. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | VORTEX DRILLING 6-1/8" HZ HOLE WITH 89 PCF LSND MUD TO 10,180' & 100 % RETURN. ** SWEPT HOLE WITH 15/15 BBLS LO/HI-WT PILLS EACH 3 STANDS DRILLED. ** REAMED UP & REAMED DOWN 10 FT EACH STAND DRILLED. ** D&M TAKE SURVEY EVERY CONNECTION THAT EXTENDED CONNECTION TIME. ** DRILLING PARAMETERS: - WOB : 10-15 KLBS - RPM : 90 & FR 280 GPM - PR ON BTM: 3600 PSI & PR OFF BTM: 3220 PSI - ON BTM TQ : 5-7 KLB-FT & OFF BTM TQ : 2-3 KLB-FT - AV. ROP : 37 FPH | 27.23 | 20.94 | 2018-06-02 06:06:00.000 | 471.88 | [5 empty] | 2018-06-02 04:30:00.000 | 2018-04-30 13:00:00.000 | 35 | 11386.0004 | 2018-05-31 01:30:00.000 | 0.39583 | 17.6042 | 30.5 | 32.625 | 1.2133 | 373.3115
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | SDGM-740 | 25 | 49 | Shedgum | Horizontal | PWI | 2019-02-08 04:00:00.000 | Primary Drilling | SINO-35 | CON.DRILL 6-1/8" HZ HOLE TO TD 11921 FT. SWEEP & CHC , WIPER TRIP TO CSG SHOE,RIH, CHC. | DISPLACE HOLE TO 87 PCF BRINE, SPOT MUDZYME , POOH TO SURFACE,L/D BHA. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SWEPT TANDEM PILL AND CIRCULATE HOLE CLEAN WITH 15 LO/15 BBLS WT HVP ** CIRCULATE HOLE CLEAN 3 TIMES BOTTOMS ** REAM UP WITH 40 RPM AND REAM DOWN WITH 100 RPM ** FR : 250-GPM-2500-PSI ** RPM : 40-100 , TQ : 5-7 KFT-IB ** NO MUD LOSS OBSERVED. SCR'S @ 11,921' ( MD) / 7,509'(TVD) ,MW=85 PCF ** SPM 20/ 30/ 40 ** MP1 85 X 600psi / 130 X 1000psi / 170 X 1550psi ** MP2 85 X 600psi / 130 X 1030psi / 170 X 1560psi ** MP3 85 X 600psi / 130 X 1040psi / 170 X 1580psi | 28.29 | 20.95 | 2019-03-10 13:50:15.000 | 365 | 596.05 |  |  |  |  | 2019-03-14 05:00:00.000 | 2019-02-08 04:00:00.000 | 35 | 11921.0004 | 2019-03-07 12:00:00.000 | 0.61458 | 16.0417 | 27.3333 | 34.0417 | 1.8054 | 436.1342
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-1460 | 23.9708 | 49.0628 | Haradh (HRDH) | Horizontal | PML | 2018-03-07 16:30:00.000 | Primary Drilling | SINO-6 | DRILLED, LOGGED AND SURVEYED 6-1/8" HORIZONTAL SECTION (L0) FROM 15,225 FT TO 16,300 FT. BACKREAMED UP AND REAMED DOWN ONE JOINT PER STAND DRILLED. PUMPED 15 BBLS OF LOW VIS FOLLOWED BY 15 BBLS OF HIGH VIS/HIGH WT PER TWO STANDS. MAINTAINED 7% LUBRICITY (DIESEL) IN THE ACTIVE SYSTEM. | CONT TO LOG, DRILL, AND SURVEY THE L0 LATERAL (MOTHERBORE) WITH THE 6-1/8" DIRECTIONAL ASSEMBLY FROM 16,300 FT TO 16,780 FT (STD). | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | TOOK SLOW CIRCULATING RATES AT 30, 40, AND 50 STROKES BEFORE DRILLING AHEAD. | 126.37 | 56.85 | 2018-09-24 19:50:24.000 | 472.19 | [5 empty] | 2018-09-25 03:00:00.000 | 2018-03-07 16:30:00.000 | 30 | 16780.0005 | 2018-05-28 15:15:00.000 | 60.6979 | 59.9167 | 81.9479 | 201.4375 | 30.1324 | 204.7642
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HRDH-556 | 24.266 | 49.082 | Haradh (HRDH) | Horizontal | PHZ | 2018-10-06 00:00:00.000 | Primary Drilling | SINO-6 | CONT. DRILL AHEAD 6-1/8" DIRECTIONAL HOLE AS PER PLAN TO WELL TD (10,536 FT), TRY TO CHC - NO SUCCESS, POOH TO SURFACE. | P/U & M/U REAMING BHA AND RIH ON 4" DP TO BOTTOM, CLEAR TIGHT SPOTS (IF ANY). CIRCULATE HOLE CLEAN.PERFORM WIPER TRIP TO SHOE. DISPLACE MUD WITH BRINE & SPOT MUDZYME IN OPEN HOLE. POOH TO SURFACE FOR CASING CLEAN OUT RUN. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | FLOW CHECK - WELL STATIC. | 27.04 | 21.17 | 2018-11-09 06:22:53.000 | [6 empty] | 2018-11-09 00:00:00.000 | 2018-10-06 00:00:00.000 | 35 | 10536.0003 | 2018-11-02 12:15:00.000 | 4.1354 | 18.1146 | 27.5104 | 34 | 12.163 | 382.9822
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-633 | 24.744 | 49.151 | Hawiyah (HWYH) | Horizontal | EV | 2018-11-20 23:00:00.000 | Primary Drilling | SINO-6 | CONT CLEAN OUT CEMENT, PLUGS & SHOE TRACK. DRILL 6-1/8" DIRECTIONAL HOLE SECTION FROM 7914 FT TO 8870 FT. | CONT. DRILL 6-1/8" DIRECTIONAL HOLE SECTION AS PER PLAN 5. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | PUMP 50 BBLS HI-VIS PILL AND P/U STRING TO CONFIRM STRING FREE. - IMMEDIATELY PUMP 84 PCF MUD CAP INTO ANNULUS. | 70.7 | 58.9 | 2019-02-03 14:00:00.000 | 365 | 526.14 |  |  |  |  | 2019-02-04 01:00:00.000 | 2018-11-20 23:00:00.000 | 37 | 10970.0004 | 2019-01-17 22:30:00.000 | 5.6771 | 41.5938 | 57.9792 | 75.0833 | 7.561 | 189.2059
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-650 | 24.7666 | 49.1832 | Hawiyah (HWYH) | Horizontal | EV+PHZ combine | 2019-04-24 15:30:00.000 | Primary Drilling | SINO-6 | DRILL 10 FT NEW FORMATION, CHC,PERFORME EXTENDED FLOW CHECK –WELL STATIC-, CONT DRILLING FROM 7494 TO 8092 FT | DRILL 6-1/8" HOLE SECTION TO +/- 10407 FT | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 10 FT OF NEW FORMATION WITH CONTROLLED PARAMETERS. | 63.8 | 53.04 | 2019-06-27 15:19:03.000 | 365 | 667.75 |  |  |  |  | 2019-06-26 12:00:00.000 | 2019-04-24 15:30:00.000 | 36 | 10429.0003 | 2019-05-23 17:00:00.000 | 1.9792 | 15.9896 | 29.0625 | 62.8542 | 3.1488 | 358.8473
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-664 |  |  | Hawiyah (HWYH) | Horizontal | PHZ |  | Primary Drilling | SINO-6 | RIG ACCEPTED AT 03:30 HRS ON 22ND OCT. 2019. HELD PJSM & SPUD WELL AT 04:00 HRS. DRILL 22" HOLE FROM 35 FT TO 40 FT. | CONT. DRILL 22" HOLE SECTION TO SECTION TD. CIRCULATE. POOH 22" ROTARY BHA. R/U & RIH 18 5/8" CSG. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SPUD WELL & DRILL 22" HOLE FROM 35 FT TO 40 FT. - SPUD WELL AT 04:00 HRS. - TAGGED BOTTOM AT 35 FT. - DRILLED 22" VERTICAL HOLE SECTION W/ ROTARY BHA FROM 35 FT TO 40 FT WITH FULL RETURNS. - DRILLING PARAMETERS: FR: 250~400 GPM, RPM: 10, WOB:2~20 KIPS, SPP: 50~70 PSI, TQ: 1~3.5 KLB-FT. | 30.01 | 27.13 | 2019-11-21 05:07:27.000 | [6 empty] | 2019-10-22 09:30:00.000 | 2019-10-22 03:30:00.000 | 0 | 62 | 2019-10-22 09:30:00.000 | 0 | 0.020833
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-666 |  |  | Hawiyah (HWYH) | Horizontal | PHZ | 2019-09-13 11:30:00.000 | Primary Drilling | SINO-6 | CONT. DRILL 6 1/8" HOLE SECTION FROM 9470 FT TO SECTION TD AT 9611 FT. CIRCULATE. POOH TO 6 1/8" RSS BHA TO 7" SHOE. RIG MAINTENANCE. POOH 6 1/8" RSS BHA TO SURFACE & LD. JET WH. MU & RIH 6 1/8" REAMER BHA. | CONT. RIH 6 1/8" REAMER BHA & REAM TO TD. DISPLACE WELL TO 78 PCF OBM. WIPER TRIP. POOH & LD 6 1/8" REAMER BHA. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | PUMP HEAVY SLUG. | 28.01 | 24.79 | 2019-10-13 11:40:12.000 | [6 empty] | 2019-10-13 10:30:00.000 | 2019-09-13 11:00:00.000 | 0 | 9611.0003 | 2019-10-07 08:00:00.000 | 2.3542 | 15.2604 | 23.8542 | 29.9583 | 7.8581 | 402.9066
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-669 | 24.7122 | 49.1277 | Hawiyah (HWYH) | Horizontal | PHZ | 2019-07-03 05:00:00.000 | Primary Drilling | SINO-6 | CONT. DRILL 6 1/8" SECTION F/ 7167 FT TO 7876 FT. | CONT. DRILL 6 1/8" SECTION AS PER PROGRAM. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HOLE FROM 7167 FT TO 7377 FT: - PARAMETERS: FR: 260-280 GPM, SPP: 2450- 2850 PSI, WOB: 15-20 KLBS, RPM: 60-125, TQ: 4-7 KFT/LBS. - OBSERVED HIGH SHOCKS (2-3) FROM PERISCOPE & HIGH STICK / SLIP. - WASH UP/REAM DOWN 15 FT PRIOR TO CONNECTION. - PUMP 15 BBLS HI-VIS PILL EACH STAND. - AV. ROP: 15.5 FPH. | 51.02 | 26.57 | 2019-09-05 10:49:12.000 | 365 | 425.3 |  |  |  |  | 2019-09-07 04:00:00.000 | 2019-07-03 05:00:00.000 | 37 | 11398.0004 | 2019-08-28 06:00:00.000 | 28.3438 | 42.0938 | 56.0417 | 65.9583 | 42.9722 | 203.3844
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-671 | 24.8149 | 49.1657 | Hawiyah (HWYH) | S-shape | EV | 2019-02-11 10:00:00.000 | Primary Drilling | SINO-6 | CONT DRILL 6-1/8" HOLE SECTION TO TD @ 6844 FT, CIRCULATE HOLE CLEAN, POOH TO 6530 FT, RE-LOGGING FROM 6530 FT TO 6310 FT @ 55 FT/HR. Cont POOH TO CASING SHOE & RIH TO 6427 FT. | CONT RIH TO BOTTOM, CHC, POOH TO SURFACE, LOGGING OPERATION | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | RESUME DRILLING 6-1/8" HOLE SECTION FROM 6279 FT TO 6350 FT. - TORQUE 3800-5400FT.LB; RPM 50-110 RPM; 200-250GPM; SPP 2100-2300 PSI; WOB 10-18 KB. - AVG ROP: 23.66 FPH. - WASH UP & REAM DOWN 15 FT ON EACH DRILLED STAND. - SURVEY EVERY 90 FT AS PER GOC. - NO DOWN HOLE LOSSES. | 30 | 23.53 | 2019-04-13 22:15:21.000 | 342.2 | 342.2 |  |  |  |  | 2019-04-14 10:30:00.000 | 2019-02-11 09:30:00.000 | 0 | 6844.0002 | 2019-03-28 20:00:00.000 | 21.0313 | 35.6042 | 45.4167 | 62.0208 | 33.91 | 150.6936
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-651 | 24.6654 | 49.1104 | Hawiyah (HWYH) | Horizontal | PHZ | 2018-09-27 01:00:00.000 | Primary Drilling | SP-53 | CARRY OUT INTEGRITY PRESSURE TEST AT 7469 FT. DRILL OUT CEMENT TO 7502 FT. DISPLACE OLD MUD 75 PCF BY 72 PCF LSND. FLOW CHECK. DRILL 6.125" HORIZONTAL TO 7632 FT. OBSERVE PROBLEM WITH D & M RESISTIVITY TOOL. ATTEMPT TO TROUBLE SHOOT - NO SUCCESS. POOH 6 1/8" VORTEX BHA TO SURFACE & L/D D & M TOOLS. P/U, M/U & RIH 6 1/8" VORTEX BHA & RIH TO 341 FT. | RIH 6 1/8" VORTEX BHA TO BOTTOM & DRILL 6.125" HORIZONTAL HOLE TO TD. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | RECORD SCR'S, FLUSH KILL LINE, CHOKE MANIFOLD AND MUD GAS SEPARATOR WITH NEW DRILLING FLUID. 30 SPM 40 SPM 50 SPM MP 1 630 910 1430 MP 3 620 890 1450 | 30.46 | 23.24 | 2018-11-01 15:05:12.000 | 500 | 500 |  |  |  |  | 2018-11-07 17:00:00.000 | 2018-09-27 01:00:00.000 | 35 | 10863.0003 | 2018-10-28 06:00:00.000 | 4.6875 | 19.1979 | 31.2083 | 41.6667 | 11.25 | 348.0801
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | HWYH-663 | 24.7212 | 49.1585 | Hawiyah (HWYH) | Horizontal | PHZ | 2018-08-23 08:00:00.000 | Primary Drilling | SP-53 | DRILL OUT SHOE TRACK. FLOW CHECK. DRILL 6 1/8" HOLE AS PER GOC TO 8065 FT. | DRILL 6 1/8" HOLE AS PER GOC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6-1/8” DIRECTIONAL HOLE FOLLOWING GOC FROM 7020 FT TO 8065 FT. - TRY TO BUILD TO 90.4 DEG WITHOUT SUCCESS AS PER GOC. - OBSERVED TRAJECTORY DROPPING TO 88.5 DEG - CONTROL OB ROP TO ALLOW BUILD TRAJECTORY AS PER GOC INSTRUCTION TO 7230 FT. - FLOW RATE: 280 GPM, SPP: 2350 PSI., DIFF PRESSURE :250-350 PSI. - WOB: 10-20 KLB, RPM: 60-100; TQ : 4-7 K FT-LB. - P/U WT: 135 KLB, S/D, WT: 110 KLB , RT WT: 124 KLB. - REAM UP AND DOWN ONE JOINT EACH STAND . - AT STAND DOWN CIRCULATE FOR 3 MINS & DRILL OFF. - CONNECTION AND DOWN LINK TIME 8 HR FROM START DRILLING. - ON BTM ROP = 79 FPH; AVG ROP: 49 FPH. - LAST SURVEY: MD: 7871’, TVD: 6255.78’, INC: 87.49ᵒ, AZI: 108.88ᵒ, DLS: 1.6ᵒ. - DISTANCE 2.28’ BELOW AND 0.86’ LEFT OF THE PLAN. - NO DOWN HOLE LOSSES. | 29.99 | 26.41 | 2018-09-19 00:21:00.000 | 526.14 | 526.14 |  |  |  |  | 2018-09-20 10:00:00.000 | 2018-08-23 09:00:00.000 | 35 | 9328.0003 | 2018-09-13 23:30:00.000 | 0.98958 | 14.1354 | 21.6458 | 28.0833 | 3.5237 | 430.9375
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4026 | 25.2495 | 49.3053 | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-04-08 00:00:00.000 | Primary Drilling | SP-53 | DRILL 6 1/8" HOLE TO 7334 FT. POOH TO SURFACE TO CHANGE BHA. RIH WITH NEW BHA. | RIH TO BTM. CONT. DRILL 6 1/8" HZ HOLE. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | FLOW CHECK IN NEW FORMATION, WELL STATIC. | 30.01 | 27.01 | 2019-05-13 04:48:00.000 | 365 | 504.89 |  |  |  |  | 2019-05-15 01:00:00.000 | 2019-04-08 00:00:00.000 | 35 | 10532.0003 | 2019-05-03 04:00:00.000 | 3.9896 | 15.375 | 25.1667 | 37.0417 | 10.7705 | 418.4901
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4031 | 25.2451 | 49.1926 | Uthmaniya (UTMN) | Horizontal | PML | 2018-04-18 13:00:00.000 | Primary Drilling | SP-53 | CONT RIH W/ 6 1/8" VORTEX BHA & TAG TOC. P/T 7" LNR. C/OUT CMT AND FLOATS TO 30 FT ABOVE F.S. & P/T LNR. CONT C/OUT CMT & F/S WHILE DISPLACE HOLE TO NEW 79 PCF MUD. DRILL 6 1/8" DIRECTIONAL HOLE FROM 8400 TO 8750 FT. | CONT. DRILL 6 1/8" DIRECTIONAL HOLE FOLLOWING PLAN 3. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | SETTING MWD/LWD TOOLS AND SENDING DOWN LINKS. . | 38.21 | 54.47 | 2018-05-26 09:58:06.000 | 575.86 | [5 empty] | 2018-06-30 19:30:00.000 | 2018-04-18 13:00:00.000 | 0 | 12154.0004 | 2018-06-14 03:30:00.000 | 10.25 | 39.5208 | 56.6042 | 73.2708 | 13.9892 | 214.7192
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4038 | 25.1 | 49.1 | Uthmaniya (UTMN) | Horizontal | PML | 2018-11-14 11:00:00.000 | Primary Drilling | SP-53 | CIRCULATE HOLE & DISCUSS WITH OFFICE TROUBLE WITH RSS + DRILL 6.125 HORIZONTAL HOLE TO 8446 FT + CIRULATE TO CLEAN HOLE + FLOW CHECK + POH TO SURFACE & LD BHA. RIH KILL STRING. SLB D & M DUMPING DATA & PROGRAMMING TOOLS. | PREPARE 6 1/8" BHA TOOLS & RIH. DRILL 6.125" HOLE AHEAD AS PER PLAN. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HORIZONTAL HOLE FROM 8237 FT TO 8446 FT. **TAKE SURVEY AFTER EVERY CONNECTION. **WOB:20 KLB, FLOW: 280 GPM, SPP: 2450 PSI, RPM: 85, TORQUE: 7-8 FT-KLB, MW: 77 PCF. **NO LOSSES DOWN HOLE. | 54.25 | 41.62 | 2019-01-15 08:00:00.000 | 365 | 486.55 |  |  |  |  | 2019-01-16 08:00:00.000 | 2018-11-14 11:00:00.000 | 35 | 11126.0004 | 2018-12-19 08:30:00.000 | 5 | 19.9896 | 34.8958 | 62.875 | 7.9523 | 318.8346
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4041 | 24.19 | 49.16 | Uthmaniya (UTMN) | Horizontal | PHZ | 2018-07-09 19:30:00.000 | Primary Drilling | SP-53 | DRILL 6 1/8" DIRECTIONAL HOLE F/ 7660 FT TO 7687 FT. RESISTIVITY LOG SHOWED 7" LNR SHOE DEEPER BY 16 FT. INVESTIGATE AND DECIDED POOH TO CHECK 4" DP MEASUREMENT. DISCOVERED 4" DP HAS 18 FT DIFFERENT. ADJUSTED DEPTH AND RIH TO BTM AT 7670 FT. DRILL 6 1/8" DIRECTIONAL HOLE FROM 7670 FT TO 7794 FT. POOH R/B 5" DP FOR SPACE OUT, RIH WITH 4" DP. CON. DRILL 6 1/8" DIRECTIONAL HOLE FROM 7794 TO 7900 FT. | DRILL 6 1/8" DIRECTIONAL HOLE FOLLOWING PLAN #4 AND GOC INSTRUCTION. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6-1/8” DIRECTIONAL HOLE FROM 7670 FT (CORRECT BTM DEPTH) TO 7794 FT FOLLOWING PLAN 4. | 29.12 | 24.46 | 2018-08-14 18:34:36.000 | 490.38 | [5 empty] | 2018-08-15 00:00:00.000 | 2018-07-09 19:30:00.000 | 36 | 9634.0003 | 2018-08-06 08:15:00.000 | 2.1875 | 17.8958 | 27.5312 | 36.1875 | 6.0449 | 349.9296
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4042 | 25.29 | 49.21 | Uthmaniya (UTMN) | Horizontal | PML | 2019-01-24 20:30:00.000 | Primary Drilling | SP-53 | RIH 6 1/8" VORTEX BHA ON 4" DP, P/TEST LNR AS PER PROGRAM. DRILL OUT SHOE TRACK , MEANWHILE DISPLACE TO FRESH MUD, FLOW CHECK. DRILL 6 1/8" HOLE. | DRILL 6 1/8" HZ HOLE. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HZ HOLE IN ROTARY MODE 10 FT IN NEW FM FROM 8160 FT TO 8170 FT. | 49.67 | 36.39 | 2019-03-23 13:30:00.000 | 330 | 492.97 |  |  |  |  | 2019-03-31 10:00:00.000 | 2019-01-24 20:30:00.000 | 35 | 11262.0004 | 2019-03-20 14:00:00.000 | 6.3333 | 34.9792 | 54.7292 | 65.5625 | 9.66 | 205.7769
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4045 |  |  | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-06-28 11:30:00.000 | Primary Drilling | SP-53 | DRILL 6 1/8" HOLE AS PER DIRECTIONAL PLAN & GOC TO 8976 FT. CIRCULATE TO CLEAN HOLE. POOH TO LINER SHOE. RIH ON 15 STDS OF 4" DPS & 5" DP STANDS BTM. DRILL AHEAD 6.125" HOLE FROM 8976 FT TO 9273 FT AS PER PLAN & GOC. REPLACED ROTARY HOSE. DRILL 6 1/8” HOLE FROM 9273 FT TO 9450 FT. | DRILL 6 1/8" HOLE AS PER DIRECTIONAL PLAN & GOC TO WELL TD AT 10,117 FT. CIRCULATE. PERFORM WIPER TRIP TO 8976 FT (IF REQUIRED). POOH TO SURFACE. PERFORM CALIPER-FMI LOGGING ON TLC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HZ HOLE FROM 8946 FT TO 8976 FT WITH 78 PCF LSND MUD. - DRILLING PARAMETERS: WOB 15-20 KLB, RPM: 100 -140, TORQUE: 7-8.5 KLB-FT, FLOW: 280 GPM, SPP: 2550 PSI. | 28.29 | 25.57 | 2019-07-29 02:24:00.000 | 365 | 407.94 |  |  |  |  | 2019-07-29 19:30:00.000 | 2019-06-28 11:00:00.000 | 34 | 10117.0003 | 2019-07-21 17:15:00.000 | 2.6146 | 16.5521 | 23.2396 | 31.3333 | 8.3444 | 435.3348
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4047 | 25.25 | 49.28 | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-05-21 05:00:00.000 | Primary Drilling | SP-53 | DRILL OUT PLUG/LC, CMT, FLOATS & SHOE TRACK TO 7520 FT. CIRC. P/T LINER. DRILL OUT RAT HOLE WHILE DISPLACE TO 77 PCF FRESH LSND MUD. DRILL 6 1/8" HOLE AS PER DIRECTIONAL PLAN & GOC TO 7741 FT. | DRILL 6 1/8" HOLE AHEAD AS PER DIRECTIONAL PLAN & GOC. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HZ HOLE FROM 7556 FT TO 7746 FT WITH 77 PCF LSND MUD AND FULL CIRCULATION. - DRILLING PARAMETERS:- WOB 10-25 KLB, RPM: 50-100, TORQUE: 3-5.5 KLB-FT, FLOW: 270 GPM, SPP: 2000-2250 PSI. - RECORDED SCR OF MUD PUMPS AT 7566 FT. - DRILL WITH CONTROLLED PARAMETERS WHILE BHA IN CASED HOLE. - PERFORM DOWN LINKING AS REQUIRED BY GOC. - RECORDED SURVEY EVERY STAND & AS REQUIRED. - OBSERVED HIGH SHOCKS & SS - ADJUSTED DRILLING PARAMETERS ACCORDINGLY. - TOTAL DOWN LINKING TIME & TIME FOR GOC: 2.75 HRS. | 26.34 | 26.34 | 2019-06-16 13:15:00.000 | 365 | 516.34 |  |  |  |  | 2019-06-22 04:00:00.000 | 2019-05-21 19:45:00.000 | 35 | 10747.0003 | 2019-06-11 08:15:00.000 | 0.25 | 13.4271 | 21.1354 | 31.9583 | 0.78227 | 508.483
EH | KSA | Saudi Arabia | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 |  | 463066 | Khurais_SG_ABQQ Oil LSTK 2017 | IDS | KSA | LSTK | UTMN-4049 |  |  | Uthmaniya (UTMN) | Horizontal | PHZ | 2019-08-05 16:00:00.000 | Primary Drilling | SP-53 | DRILL 6 1/8" HZ HOLE F/ 7055 TO 7169 FT. D&M LOST COMMUNICATION. POOH 6 1/8" RSS BHA TO SURFACE. P/U NEW D&M TOOLS AND RIH TO 6800 ft, SEND DOWN LINK. | CONT. RIH TO BTM. DRILL 6 1/8" HZ HOLE. | 5D3AFA633B7E4EA9A9B54C943E8A6AB0 | DRILL 6 1/8" HZ HOLE FROM 7055 FT TO 7169 FT WITH 81 PCF LSND MUD AND FULL CIRCULATION. - OBSERVED D&M LWD (ABI & GR) LOST COMMUNICATION, TROUBLESHOOTING NO SUCCESS, DECISION MADE TO POOH AND CHANGE TOOLS. - DRILLING PARAMETERS:- WOB 15-20 KLB, RPM: 120, TORQUE: 3-7.5 KLB-FT, FLOW: 290 GPM, SPP: 2850 PSI. - LAST SURVEY AT 7103 FT , INC 80.67 , AZM 111.83, DLS 0.76 DEG - JAR HOURS: 18.5 HRS. | 35.68 | 33.04 | 2019-10-12 21:18:01.000 | [6 empty] | 2019-10-22 00:15:00.000 | 2019-08-05 16:00:00.000 | 36 | 10659.0003 | 2019-09-23 14:15:00.000 | 18.2292 | 34.1042 | 48.9271 | 77.3438 | 23.569 | 217.8548
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2016H | -38.21 | -68.66 | Bajada de Palo | Horizontal | Horizontal | 2018-07-31 12:00:00.000 | Primary Drilling | Nabors-695 | BAJO HTA - CONTACTO CEMENTO EN 2138 MTS - REALIZO SIMULACRO - PRUEBA DE CASING - ROTO CEMENTO - REALIZO FIT (OK). | PERFORAR FASE AISLACION CON PARAMETROS DE CIA DIRECCIONAL | 0A0663F710DE458E85421D2B3B010BA7 | CAMBIA PIN DE CONEXION DE TOP DRIVE. | 25.38 |  | 2018-08-25 09:00:00.000 | 571 | [5 empty] | 2018-10-22 05:30:00.000 | 2018-07-31 00:00:00.000 | 0 | 18884.515 | 2018-10-14 08:00:00.000 | 7.3021 | 18.6771 | 74.8333 | 82.7292 | 8.8265 | 252.3543
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2014H | -38.2255 | -68.677 | Bajada de Palo | Horizontal | Horizontal | 2018-07-06 22:00:00.000 | Primary Drilling | Nabors-F19 | SACO TREPANO AXEBLADE 6 1/8 A SUPERFICIE, CAMBIA TREPANO Y VORTEX, BAJA TREPANO MDI516 CON VORTEX A 3203 M | BAJAR TREPANO MDI516 CON VORTEX A FONDO PERFORADO + ROLLOVER + CONTINUAR PERFORANDO FASE HORIZONTAL SEGUN PROGRAMA. | 0A0663F710DE458E85421D2B3B010BA7 | CORRE Y CORTA CABLE DE PERFORACION AL TAMBOR PRINCIPAL 36 MTS. | 26.85 |  | 2018-08-02 20:24:00.000 | 571 | [5 empty] | 2018-12-16 13:45:00.000 | 2018-07-07 00:00:00.000 | 0 | 18881.2342 | 2018-12-13 07:00:00.000 | 10.9062 | 22.625 | 159.375 | 162.6562 | 6.7051 | 118.4705
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2015H | -38.2236 | -68.6769 | Bajada de Palo | Horizontal | horizontal | 2018-08-03 09:00:00.000 | Primary Drilling | Nabors-F19 | REALIZA SKID DEL POZO MDM-2014 AL POZO MDM-2015 DISTANCIA 10 MTRS + MONTA CONJUNTO BOP Y SISTEMA UBD SIN TERMINAR | PROBAR CONJUNTO BOP + ARMAR Y BAJAR BHA DIRECCIONAL | 0A0663F710DE458E85421D2B3B010BA7 | REALIZA ROLL OVER DE AGUA POR LODO PARA PERFORAR DENSIDAD 1900 GR/LT | 23.57 |  | 2018-08-25 13:40:48.000 | 623 | [5 empty] | 2019-01-09 04:45:00.000 | 2018-08-03 09:00:00.000 | 0 | 18727.0347 | 2019-01-05 06:30:00.000 | 5.6875 | 17.6875 | 154.8958 | 158.8229 | 3.581 | 120.9008
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2029H | -38.22 | -68.66 | Bajada de Palo | Horizontal | horizontal | 2018-11-15 10:15:00.000 | Primary Drilling | Nabors-F19 | REALIZA PRUEBA DE STACK DE BOP Y MANIFOLD CON 350 PSI Y 8000 PSI, MAS PRUEBA LINEAS DE MPD CON 500 PSI Y 4000 PSI, ARMA CONJUNTO DIRECCIONAL DE CIA SLB + ENROSCA TREPANO DE 6 1/8" SMITH N° JP2703A TIPO: SDI611UEPX BOQUILLAS 6 X 10/32 + BAJA HERRAMIENTA ARMANDO DE PLAYA HASTA 1093 MTS | BAJAR ARMANDO HASTA 2118 MTS, RETIRAR CAMPANA DE VIAJE Y MONTAR BEARING, REALIZAR ROLL OVER DE LODO BASE OIL 1900 GRS/LTS X AGUA TRATADA | 0A0663F710DE458E85421D2B3B010BA7 | PRUEBA CIERRE PARCIALSUPERIOR, HCR Y KILL LINE CON 350 PSI Y EN ALTA 6000 PSI OBSERVANDO PERDIDA EN TAPA DE CIERRE TOTAL | 28.49 |  | 2018-12-11 11:39:57.000 | 623 | [5 empty] | 2019-02-12 20:00:00.000 | 2018-11-15 00:00:00.000 | 0 | 15196.8509 | 2019-02-02 06:30:00.000 | 10.7708 | 10.1667 | 78.8438 | 89.4062 | 12.0471 | 192.7464
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2032H | -38.22 | -68.66 | Bajada de Palo | Horizontal | Horizontal | 2018-11-19 00:00:00.000 | Primary Drilling | Nabors-F19 | COLOCA WEAR BUSHING, ARMA BHA DIRECCIONAL CIA SLB MAS TORQUEA TREPANO 6 1/8" JP 3909-SDI 611, BAJA HERRAMIENTA HASTA 700 MTS MAS REALIZA PRUEBA DE HTA DIRECCIONAL OK 220 GAL 900 PSI (AGUA), BAJA HERRAMIENTA Y CONTACTA CIELO CEMENTO EN 2154 MTS, RELAIZA ROLL OVER POR LODO 1950 GRS/LTS, RETIRA CAMPANA DE VIAJE MAS COLOCA BEAERING, REALIZA SIMULACRO DE SURGENCIA, PERFORA CEMENTO Y ELEMENTOS DE FLOTACION, PERFORA HASTA 2217 MTS, CIRCULA SOBRE FONDO, REALIZA PRUEBA DE FORMACION CON 1070 PSI, LODO 1950 G/L UNA DENSIDAD EQUIVALWENTE DE 2300 G/L OK, PERFORA HASTA 2219 MTS | PERFORAR FASE AISLACION SEGUN PROGRAMA | 0A0663F710DE458E85421D2B3B010BA7 | CIA SLB PRUEBA FUNCIONAMIENTO DE MOTOR DE FONDO CON 220 GALONES 900 PSI (AGUA) CON BOMBA N°1 | 28.49 |  | 2018-12-17 11:39:57.000 | 623 | [5 empty] | 2019-03-18 16:00:00.000 | 2018-11-19 16:00:00.000 | 0 | 17076.7722 | 2019-03-16 05:15:00.000 | 4.3021 | 11.3229 | 117.2188 | 119.6667 | 3.5951 | 145.6829
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2033H | -38.22 | -68.66 | Bajada de Palo | Horizontal | Horizontal | 2018-11-21 22:30:00.000 | Primary Drilling | Nabors-F19 | BAJO TREPANO 6 1/8 CON BHA DIRECCIONAL A 2150M DONDE ENCONTRÓ CIMA DE CEMENTO, INSTALO BEARING, DESPLAZO AGUA POR LODO 1620 GR/LTO, REBAJA CEMENTO Y ACCESORIOS HASTA 2221 M ( ZAPATO DE 7” ) PERFORO A 2229 M, REALIZO FIT A 2300 GR/LTO, PERFORA A 2256 M | CONTINUAR PERFORANDO FASE AISLASION SEGUN PROGRAMA. | 0A0663F710DE458E85421D2B3B010BA7 | BAJA HERRAMIENTA DEL PEINE DE 57 MTRS A 160 MTRS | 28.49 |  | 2018-12-19 11:39:57.000 | 623 | [5 empty] | 2019-04-04 23:45:00.000 | 2018-11-21 22:00:00.000 | 0 | 16963.5832 | 2019-04-03 19:30:00.000 | 1.2917 | 9.125 | 132.875 | 134.0521 | 0.96356 | 127.6657
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2061H | -38.2223 | -68.6541 | Bajada de Palo | Horizontal | Productor | 2019-04-12 20:00:00.000 | Primary Drilling | Nabors-F19 | SACO HERRAMIENA POR CAMBIO DE BHA DIRECCIONAL HASTA L.P. , REALIZO ROLL OVER, FLOW CHEK POZO ESTATICO , CONT. SACANDO HERRAMIENTA AL PEINE HASTA 800 MTS , FLOW CHEK POZO ESTATICO , RETIRO BERING , COLOCO CAMAPANA DE VIAJE, DESARMO CONJUNTO DIRECCIONAL A PLAYA , RETIRO TREPANO, ARMO BHA DIRECCIONAL SISTEMA ROTARIO VORTEX CON TREPANO HYPER BLADE DE 6 1/8", BAJO HASTA 800 MTS , RETIRO CAMPANA DE VIAJE, COLOCO BERING , BAJA TIROS DEL PEINE CON BHA DIRECCIONAL SISTEMA ROTARIO VORTEX DE 800 MTS A 1680 MTS S/T. | BAJAR CON BHA DIRECCIONAL SISTEMA ROTARIO VORTEX Y TREPANO 6 1/8" HYPER BLADE HASTA ULTIMO FONDO PERFORADO 4476 MTS Y CONTINUAR PERFORANDO FASE AISLACION RAMA HORIZONTAL SEGUN PROGRAMA. | 0A0663F710DE458E85421D2B3B010BA7 | COMPAÑIA SCHLUMBERGER DE MPD RETIRA CAMPANA DE VIAJE Y COLOCA BERING | 25.47 |  | 2019-05-07 11:16:48.000 | 623 | [5 empty] | 2019-06-12 12:30:00.000 | 2019-04-12 21:00:00.000 | 0 | 19527.5597 | 2019-06-09 10:30:00.000 | 3.2813 | 11.3229 | 57.6042 | 60.6875 | 5.4068 | 338.9956
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2064H | -38.2223 | -68.6537 | Bajada de Palo | Horizontal | Horizontal | 2019-04-07 08:45:00.000 | Primary Drilling | Nabors-F19 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | BAJA HERRAMIENTA DESDE 63 MTS HSTA 698 MTS | 25.47 |  | 2019-05-02 11:16:48.000 | 623 | [5 empty] | 2019-08-10 00:00:00.000 | 2019-04-07 18:45:00.000 | 0 | 19872.0479 | 2019-08-05 00:00:00.000 | 0.88542 | 6.875 | 119.6354 | 124.6354 | 0.71041 | 166.1051
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2025H | -38.223 | -68.671 | Bajada de Palo | Horizontal | Horizontal | 2018-10-10 08:45:00.000 | Primary Drilling | Petreven H-103 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | Rota cemento + elementos de flotación desde 407 m, hasta 431 m, circula hasta observar formación en zaranda. | 27.81 |  | 2018-11-06 19:29:16.000 | [6 empty] | 2018-11-13 07:00:00.000 | 2018-10-10 08:45:00.000 | 0 | 7155.512 | 2018-11-11 17:45:00.000 | 0.625 | 3.1667 | 32.375 | 33.9271 | 1.8422 | 221.0197
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2026H | -38.223 | -68.671 | Bajada de Palo | Horizontal | Horizontal | 2018-10-12 18:00:00.000 | Primary Drilling | Petreven H-103 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | CIA. SLB REALIZA REUNION OPERATIVA Y DE SEGURIDAD PREVIO A ARMADO DE CONJUNTO DIRECCIONAL. | 27.57 |  | 2018-11-08 13:42:14.000 | [6 empty] | 2018-11-07 15:15:00.000 | 2018-10-12 19:15:00.000 | 0 | 7129.2653 | 2018-11-05 12:30:00.000 | 0.47917 | 2.25 | 23.7708 | 25.8854 | 1.8511 | 299.9165
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2027H | -38.223 | -68.671 | Bajada de Palo | Horizontal | Horizontal | 2018-10-16 20:00:00.000 | Primary Drilling | Petreven H-103 | Armo y realizo PH a BOP´s + manifold, soldador acondiciona caño lateral.Arma y baja conjunto direccional desde 0 m, hasta 420 m, contacta cielo de cemento. | Continuar con programa. | 0A0663F710DE458E85421D2B3B010BA7 | Turno entrante realiza reunion previa a la maniobra. | 29.02 |  | 2018-11-13 00:28:48.000 | [6 empty] | 2018-11-01 00:00:00.000 | 2018-10-15 02:45:00.000 | 0 | 7112.8611 | 2018-10-30 03:15:00.000 | 0.14583 | 2.0729 | 13.3021 | 15.1667 | 0.96154 | 534.7178
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2028H | -38.223 | -68.671 | Bajada de Palo | Horizontal | Horizontal | 2018-10-16 20:00:00.000 | Primary Drilling | Petreven H-103 | ARMO BHA / BAJO Y CONSTO CIELO CEMENTO EN 413 MTS / CIRCULO / REALIZO HERMETICIDAD DE CASING CON 1100 PSI (OK) / ROTO CEMENTO Y ELEMENTOS DE FLOTACION / PERFO 3 MTS DE FORMACION / REALIZO FIT (DENS. 1060 GR/LT) - P.SUP: 195 PSI, ESTABILIZA 190 PSI - DEC: 1374 GR/LT.- / PERFORAR DE 426 A 905 MTS.- | PERFORAR A TD SEGUN PROGRAMA.- | 0A0663F710DE458E85421D2B3B010BA7 | REALIZA SERVICIO DE TOP DRIVE.- | 28.98 |  | 2018-11-13 23:28:19.000 | [6 empty] | 2018-10-25 18:30:00.000 | 2018-10-17 04:30:00.000 | 0 | 7191.6013 | 2018-10-23 15:00:00.000 | 1 | 3.7917 | 6.7917 | 8.9375 | 11.1888 | 1058.8861
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2030H | -38.22 | -68.66 | Bajada de Palo | Horizontal | horizontal | 2018-11-17 14:00:00.000 | Primary Drilling | Petreven H-103 | REALIZA ROLL OVER, MAS SACA HERRAMIENTA REALIZANDO CONTROL DE LLENADO POR CAMBIO DE HERRAMIENTA DIRECCIONAL, ARMA CONJUNTO NUEVO DE BHA DIRECCIONAL, MAS BAJA HASTA 500 MTS RETIRA CAMPANA DE VIAJE Y COLOCA BEARING, REALIZA PRUEBA DE HERRAMIENTA DIRECCIONAL CON VARIOS CUADALES 210, 220 Y 230 GAL CON RESULTADO NEGATIVO, SACA HERRAMIENTA HASTA 211 MTS REALIZA FLOW CHECK MAS ESPERA HERRAMIENTA | CAMBIAR HERRAMIENTA DIRECCIONAL Y BAJAR NUEVAMENTE HASTA ULTIMA PROFUNDIDAD ALCANZADA PARA CONTINUAR PERFORANDO SEGUN PROGRAMA | 0A0663F710DE458E85421D2B3B010BA7 | REALIZA ALINEACION POR CIRCUITO CHICO A PILDORA Y KILL LINE PARA LLENADO DE POZO | 28.49 |  | 2018-12-15 11:39:57.000 | 623 | [5 empty] | 2019-03-03 00:00:00.000 | 2018-11-17 14:00:00.000 | 0 | 17818.242 | 2019-02-27 17:00:00.000 | 2.1562 | 10.7708 | 102.125 | 105.4167 | 2.0455 | 174.4748
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2062H | -38.2223 | -68.654 | Bajada de Palo | Horizontal | Productor | 2019-04-11 12:00:00.000 | Primary Drilling | Petreven H-103 | PRUEBA BOP Y MPD + PRUEBA HERMETICIDAD DE CAÑERIACON 4000 PSI OK + ARMA Y BAJA BHA DIRECCIONAL PROBANDO CONJUNTO EN 1060 MTRS OK + BAJA CONTACTANDO CEMENTO EN 2195 MTRS + REALIZA CONVERSION DEJANDO POZO CON LODO DE PERFORACION 1900 GRS/LTRS + ROTA CEMENTO SIN TERMINAR. | PERFORAR FASE AISLACION SEGUN PROGRAMA | 0A0663F710DE458E85421D2B3B010BA7 | BAJA HERRAMIENTA ARMANDO EN SIMPLE DE PLAYA DE 1060 MTRS HASTA 1100 MTRS | 25.47 |  | 2019-05-05 11:16:48.000 | 623 | [5 empty] | 2019-06-30 04:00:00.000 | 2019-04-10 20:00:00.000 | 0 | 19101.0505 | 2019-06-25 14:00:00.000 | 0.35417 | 8.8854 | 75.0833 | 79.6667 | 0.44456 | 254.398
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2063H | -38.2223 | -68.6539 | Bajada de Palo | Horizontal | Horizontal | 2019-04-09 18:00:00.000 | Primary Drilling | Petreven H-103 | REALIZA WALKING DEL POZO MDM-2062(h) AL POZO MDM-2063(h) DISTANCIA 10 MTRS + ACONDICIONA MONTAJE DE EQUIPO + MONTA Y PRUEBA BOP Y SISTEMA UBD + ARMA Y BAJA BHA DIRECCIONAL SIN TERMINAR. | PERFORAR FASE AISLACION SEGUN PROGRAMA | 0A0663F710DE458E85421D2B3B010BA7 | TESTEA LINEA PRIMARIA, SECUNDARIA , CABEZAL Y BASTON Y HCR CON 350 PSI Y 4000 PSI OK | 25.47 |  | 2019-05-04 11:16:48.000 | 623 | [5 empty] | 2019-07-21 00:00:00.000 | 2019-04-09 18:00:00.000 | 0 | 20603.6752 | 2019-07-18 06:00:00.000 | 7.0417 | 12.1868 | 99.5 | 102.25 | 6.8867 | 207.0721
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | BMo-3071D | -38.216 | -68.566 | Bajada de Palo | S Shaped | Verical | 2018-11-09 00:00:00.000 | Primary Drilling | Quintana-12 | SACA SONDEO AL PEINE / BAJA HTA ARMANDO DE PLAYA HASTA 146MTS / CONTINUA BAJANDO HTA DEL PEINE HASTA 2300MTS / RETIRA CAMPANA DE VIAJE Y COLOCA BEARING / REALIZA PRUEBA DE HERMETICIDAD DE CAÑERIA S/T. | REALIZAR SIMULACRO CON PERSONAL DE EQUIPO Y MPD , ROTAR CEMENTO COLLAR Y ZAPATO 2/3 MTS DE FORMACION , CIRCULAR REALIZAR PRUEBA DE FIT CON 3370 PSI EQUIVALENTE A 2200 G/L / PERFORAR TRAMO AISLACION CON TRE 6.1/8" | 0A0663F710DE458E85421D2B3B010BA7 | REALIZA CHARLA DE SEGURIDAD CON EL TURNO ENTRANTE | 26.17 |  | 2018-12-05 04:09:07.000 | 500 | [5 empty] | 2018-12-03 00:00:00.000 | 2018-11-09 00:00:00.000 | 0 | 11591.2077 | 2018-11-28 16:30:00.000 | 3.1354 | 11.4271 | 19.6875 | 24 | 13.0642 | 588.7598
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | BMo-3072 | -38.233 | -68.5 | Bajada de Palo | Vertical | vertical | 2018-10-05 07:00:00.000 | Primary Drilling | Quintana-12 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | ARMA DESDE PLAYA SONDEO EN SIMPLES DESDE 160 HASTA 1303 MTS TOTAL DE 120 B/S ARMADAS | 23 |  | 2018-10-30 23:57:07.000 | 500 | [5 empty] | 2018-11-05 10:00:00.000 | 2018-10-08 01:00:00.000 | 0 | 11679.7904 | 2018-10-29 12:00:00.000 | 2.1354 | 12.2708 | 24.2083 | 31.125 | 6.8608 | 482.4698
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | BMo-3073 | -38.201 | -60.507 | Bajada de Palo | Vertical | Directional | 2018-09-03 22:30:00.000 | Primary Drilling | Quintana-12 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | PERFORA DESDE 351 MTS HASTA 865 MTS | 23.75 |  | 2018-09-26 17:53:45.000 | 500 | [5 empty] | 2018-10-05 00:00:00.000 | 2018-09-03 22:30:00.000 | 0 | 11610.8928 | 2018-09-29 03:00:00.000 | 3.1875 | 16.2708 | 25.1875 | 31.0625 | 10.2616 | 460.9784
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2013H | -38.216 | -68.666 | Bajada de Palo | Horizontal | Horizontal | 2018-06-15 04:00:00.000 | Primary Drilling | Quintana-12 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | ABRE POZO, MAS RETIRA CAMPANA DE VIAJE MAS COLOCA BEARING ( EN SIMULTANEO REALIZA FLOW CHECK POZO ESTATICO) | 29.36 |  | 2018-07-14 08:34:40.000 | 571 | [5 empty] | 2018-11-15 18:30:00.000 | 2018-06-15 03:00:00.000 | 0 | 18523.6226 | 2018-11-10 03:00:00.000 | 7.6875 | 22.0625 | 147.9583 | 153.6042 | 5.0047 | 125.1949
WH | LAS | Argentina | 0A0663F710DE458E85421D2B3B010BA7 |  | 523808 | LAS-ACH-ARG-Vista Oil & Gas-Bajada del P | IDS | MCA | AFE Assurance | MdM-2031P | -38.2236 | -68.6655 | Bajada de Palo | Horizontal | horizontal | 2018-07-18 11:30:00.000 | Primary Drilling | Quintana-12 |  |  | 0A0663F710DE458E85421D2B3B010BA7 | REALIZA CHARLA DE SEGURIDAD PREVIA A ARMAR PM DE PLAYA HERMANANDO | 29.55 |  | 2018-08-16 13:18:07.000 | 623 | [5 empty] | 2018-09-04 00:00:00.000 | 2018-07-18 11:30:00.000 | 0 | 9251.9688 | 2018-08-09 10:45:00.000 | 14.2292 | 15.6146 | 21.9688 | 47.5208 | 29.943 | 421.1422
SAM | LAS | Brazil | B3B88C40F2944FDB90E866EF013C02E8 |  | 450329 | LAS_BRU_BRZ_IDS_Rosneft_Solimones Basin | IDS | MCA | Other | 1-RNB-004-AM | 5.3451 | 66.5749 | Solimoes | Vertical | Vertical | 2019-05-12 00:00:00.000 | Primary Drilling | RNB-2 |  |  | B3B88C40F2944FDB90E866EF013C02E8 | Drillout Cement f/ 1736 m t/ 1780 m with FR 350 gpm, 1300 psi , 2-3 Kft-lb, 40 rpm, 12 Klb ( Shoe @ 1776 m ). | 57.58 |  | 2019-07-10 13:54:36.000 | 245 | [5 empty] | 2019-06-26 06:00:00.000 | 2019-05-14 12:00:00.000 | 0 | 6856.9556 | 2019-06-19 19:00:00.000 | 0.8125 | 17.4375 | 38.7917 | 45.25 | 1.7956 | 176.7636
WH | MCA | Mexico | FFC84DF89C7A44B0900BC8D2599A152A | 383 | 39680 | MCA Aguas Profundas Pemex MEX | IDS | MCA | AFE Assurance | BUKMA 1 | 20.0375 | -94.7277 | Perdido | Deviated |  | 2018-01-09 00:00:00.000 | Primary Drilling | Centenario | METIÓ BNA. 2500M, PROBO TR´S 1500PSI, METIÓ BNA. 6967M, REBAJÓ CEMENTO7015M, PROBÓ TR´S 1500PSI. | REBAJAR CEMENTO Y ZAPATA A 7025M, RECONOCER PI A 17070M, PERFORAR A 7120M, PRUEBA LOT, SACAR BNA A SUPERFICIE, PROG. TOMA DE INFORMACIÓN. | FFC84DF89C7A44B0900BC8D2599A152A | METIÓ BNA PDC 8 ½”/PWD(ECOSCOPE)/MWD CON TP COMB. 5”- 5 7/8” DE 2170 A 2500M. NOTA: CALIBRA INTERIOR DE TP CON 3 ½” CON CIRCUITO CERRADO EN TANQUE DE VIAJES, REGISTRO CORRECTO DESPLAZAMIENTO DE VOLUMEN DE ACERO. | 98.67 |  | 2018-04-16 16:00:37.000 | [6 empty] | 2018-05-05 00:00:00.000 | 2018-01-08 12:00:00.000 | 8979.6591 | 24202.7567 | 2018-04-20 20:00:00.000 | 30.5417 | 80.6042 | 101.8333 | 116 | 26.329 | 237.6703
WH | MCA | Mexico | FFC84DF89C7A44B0900BC8D2599A152A | 383 | 39680 | MCA Aguas Profundas Pemex MEX | IDS | MCA | AFE Assurance | KETSIN 1EXP | 25.1544 | -95.593 | Perdido | Deviated |  | 2018-04-17 12:00:00.000 | Primary Drilling | Muralla IV | ANCLO COLGADOR TR, CEMENTO TR 9 5/8", ACIVO Y PROBO BL, SACO SOLTADOR SUP. ELIMINO CABEZA CEM, ARMO Y METIO BNA PDC 8½ CON SARTA LISA 6½" A 1376M. | BAJAR SARTA DRILL OUT 8 ½" A 2500M, PROBAR TR, BAJAR A 4500M, PROBAR BOPS, BAJAR A 7350M, | FFC84DF89C7A44B0900BC8D2599A152A | ARMO Y METIO A 304M, BARRENA PDC 8½", PORTABARRENA Y VCP 6¾", 12 DRILL COLLAR 6½, MARTILLO HIDRAULICO 6½, 4 DRILLES 6½" Y 12 DPHW 5" REGISTRANDO DESPLAZAMIENTO CON EL TANQUE DE VIAJES. | 69 |  | 2018-08-01 00:02:48.000 | [6 empty] | 2018-08-14 08:00:00.000 | 2018-05-24 00:00:00.000 | 8700.7877 | 25590.552 | 2018-08-02 00:00:00.000 | 5.25 | 56.2708 | 106.5 | 118.8333 | 4.418 | 240.2869
WH | MCA | Mexico | FFC84DF89C7A44B0900BC8D2599A152A | 383 | 39680 | MCA Aguas Profundas Pemex MEX | IDS | MCA | AFE Assurance | KILI 1 EXP | 24.5827 | -96.6314 | Perdido | Vertical |  | 2018-08-21 12:00:00.000 | Primary Drilling | Muralla IV | SACO STINGER SUP, METE BNA. TRIC. 8 ½”-SARTA LISA 2261.50M, PROBO TR, REBAJA CEM Y ACC´S 2271M, VIAJE CORTO BL 9 7/8”, LIMPIO POZO, REBAJA CEMENTO 2277M. | REBAJAR CEMENTO 2292M, CIRCULAR 1.50 GR/CC, PROBAR TR, REBAJAR CEM, ZAPATA, RECONOCER 2304M, PERFORAR 2314M, CIRCULAR, PRUEBA GOTEO, SACAR SUP, ARMAR Y PROBAR SARTA PERFORAR ETAPA 8 ½”. | FFC84DF89C7A44B0900BC8D2599A152A | REBAJA TAPONES, COPLE FLOTADOR Y CEMENTO CON CONSISTENCIA A 2271 M; INCREMENTO DENSIDAD A 1.50 GR/CC; DONDE SUSPENDE POR FALTA DE AVANCE. | 38.65 |  | 2018-10-03 15:32:23.000 | [6 empty] | 2018-09-22 00:00:00.000 | 2018-08-26 00:00:00.000 | 2783.7927 | 8300.5252 | 2018-09-15 06:30:00.000 | 1.1042 | 16.9167 | 24.7708 | 31.5 | 3.5053 | 335.0927
WH | MCA | Mexico | FFC84DF89C7A44B0900BC8D2599A152A | 383 | 39680 | MCA Aguas Profundas Pemex MEX | IDS | MCA | AFE Assurance | KOKITL 1 EXP | 24.999 | -95.883 | Perdido | Vertical |  | 2018-10-10 00:00:00.000 | Primary Drilling | Muralla IV | CON SARTA 8 ½” 750M, APLICA GUIA GO-NO-TC-0015-2015, BAJO BNA.4602M, REBAJA COPLE Y CEMENTO A 4639M, CIRCULA, PROBO TR 9-5/8”, REBAJO ZAPATA, RECONOCIO 4650M, PERFORO 4655M, CIRCULO, PRUEBA FIT | SACAR BNA.SUP, REG.CBL-GR, ARMAR Y PROBAR SARTA ETAPA 8 ½”, METER 500M, PROBAR SARTA, METER BNA. 4655M, PERFORAR ETAPA 8 ½” 5330M | FFC84DF89C7A44B0900BC8D2599A152A | REBAJO A 4639 M. ACCESORIOS Y CEMENTO CON CONSISTENCIA, PSB 10 TON, 45 RPM, 4-6 K#/PIE, 108 EPM, 452 GPM, 2590 PSI; ACONDICIONANDO COLUMNAS A 1.57 G/CC. | 48.98 |  | 2018-11-23 23:31:29.000 | [6 empty] | 2018-12-16 09:30:00.000 | 2018-10-06 06:30:00.000 | 0 | 17696.851 | 2018-11-28 22:00:00.000 | 3.2292 | 45.6667 | 49.9167 | 67.3958 | 4.7913 | 354.5279
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 107 | 19.6062 | -92.3359 | Ayatsil | Deviated | Direccional | 2017-10-10 12:00:00.000 | Primary Drilling | Pemex-6029 |  |  | 32FC5334F69A4202A3E790522DCA86EA | 'EFECTUO JUNTA DE SEGURIDAD CON PERSONAL INVOLUCRADO EN LA REALIZACION DE TUBING PUNCHER. | 65.25 |  | 2018-04-15 06:00:00.000 |  |  | 20180422231915 |  |  |  | 2018-07-30 00:00:00.000 | 2018-02-09 16:30:00.000 | 544.6194 | 14593.1763 | 2018-07-15 23:30:00.000 | 42.625 | 105.625 | 278.4792 | 292.5 | 14.5726 | 52.4031
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 185 | 19.607 | -92.336 | Ayatsil | Deviated | Direccional | 2019-03-20 12:00:00.000 | Primary Drilling | Pemex-6029 |  |  | 32FC5334F69A4202A3E790522DCA86EA | 'BOMBEO 5 M3 DE BACHE VISCOSO DE 1.03*400 Y CIRCULO LIMPIANDO POZO CON MOVIMIENTOS RECIPROCANTES DE SARTA, CON PERDIDA PARCIAL DE +/- 30 M3 | 70 |  | 2019-06-03 23:57:15.000 | 250 | [5 empty] | 2019-07-19 00:00:00.000 | 2019-03-26 03:00:00.000 | 544.6194 | 14911.4178 | 2019-07-15 19:30:00.000 | 3.2917 | 61.0833 | 117.3125 | 120.5 | 2.7317 | 127.1085
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 208 | 19.606 | -92.607 | Ayatsil | Deviated | Direccional | 2018-08-16 17:00:00.000 | Primary Drilling | Pemex-6029 |  |  | 32FC5334F69A4202A3E790522DCA86EA | 'ARROJO CANICA DE 1", ESPERO GRAVITACION, CONECTO TOP DRIVE BOMBEO Y VERIFICO PESOS DE SARTA. | 55.45 |  | 2018-10-10 10:42:14.000 | [6 empty] | 2018-12-05 12:00:00.000 | 2018-08-21 05:00:00.000 | 524.9344 | 14625.9847 | 2018-11-30 03:30:00.000 | 8.75 | 65.25 | 105.4375 | 110.7917 | 7.8977 | 138.7171
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 300 | 19.6068 | -92.336 | Ayatsil | Deviated | Direccional | 2019-08-19 00:00:00.000 | Primary Drilling | Pemex-6029 | REALIZO DESPLAZAMIENTO DEL LODO DE E.I DE 1.84 GR/CC POR LBAM DE 1.03 GR/CC, REALIZO LIMPIEZA DE PRESA DE ASENTAMIENTO PRIMER FRENTE DE TEMBLORINAS | TYERMINAR LIMPIEZA DE PRESA DE ASENTAMIENTO , REBAJAR CEMENTO ACESSORIOS | 32FC5334F69A4202A3E790522DCA86EA | " CON SARTA LISA Y BNA 10 5/8"" A 4226 MTS, REALIZÓ LIMPIEZA EN PRESAS DE LODO, PREPARATIVOS PARA DESPLAZAMIENTO DE FLUIDO LEI X LBAM. " | 90.7 |  | 2019-11-17 16:51:54.000 | 197 | [5 empty] | 2019-10-21 00:00:00.000 | 2019-08-19 00:00:00.000 | 524.9344 | 14222.4415 | 2019-10-21 00:00:00.000 | 1.0208 | 43.25 | 63 | 63 | 1.6204 | 225.753
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL DL1 | 19.6069 | -92.336 | Ayatsil | Deviated | Direccional | 2016-04-24 00:00:00.000 | Primary Drilling | Pemex-6029 |  |  | 32FC5334F69A4202A3E790522DCA86EA | CON BARRENA DE 6-1/2" TRICONICA Y SARTA NAVEGABLE ROTATORIA, PERFORA A 4071 MTS, RECORD DE BARRENA: 6 MTS CORTADOS EN 1.50 HRS, ULTIMOS 3 MTS: 15-19-18 MINS, PSB: 4-5 TON, RPM: 80, TORQUE: 8-10 KLBS-FT, GASTO: 280 GPM, PRESION DE BBEO: 2600 PSI, DEC: 1.058 GR/CC) BOMBEANDO 5 M3 DE BACHE VISCOSO DE 1.03 GR/CC X 350 SEGS EN CADA TRAMO PERFORADO Y REPASA 2 VECES MISMO Y UTILIZA TUBO FRIO. | 35.11 |  | 2019-02-03 02:42:08.000 | 218 | [5 empty] | 2019-02-26 00:00:00.000 | 2019-01-05 03:00:00.000 | 11335.3022 | 13917.3233 | 2019-02-19 06:00:00.000 | 6.1458 | 40.4583 | 1031.25 | 1038 | 0.59208 | 13.4956
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 155 | 19.6368 | -92.332 | Ayatsil | Deviated | Direccional | 2018-10-21 15:00:00.000 | Primary Drilling | Pemex-9022 | METIO SARTA ROTATORIA NAVEGABLE CON BNA. TRICONICA DE 6 1/2" DE 1400 MTS A 3783 MTS. LLENANDO INT. CADA 500 MTS. Y ROMPIENDO CIRCULACION CADA 1000 MTS. OBSERVA DESPLAZAMIENTO NORMAL A TANQUE DE VIAJES Y CUANTIFICANDO MISMO. NOTA: (16:00-16:45 HRS) EFECTUO SIMULACROS DE HOMBRE AL AGUA, HOMBRE LESIONADO Y DERRAME DE HIDROCARBUROS | CON BNA. TRIC. 6 1/2" Y SARTA NAV-ROT A 3783 MD; CIRCULAR T.A. CON LODO DE E.l. 1.04 GR/CC Y EFECTUAR DESPLAZAMIENTO DE LODO E.l. POR FLUIDO SP BRECHA .1.04 GR/CC | 32FC5334F69A4202A3E790522DCA86EA | METIO SARTA ROTATORIA NAVEGABLE CON BNA. TRICONICA DE 6 ½" DE 730 MTS A 1400 MTS. OBSERVA DESPLAZAMIENTO NORMAL A TANQUE DE VIAJES. | 74.96 |  | 2019-01-13 23:03:50.000 | 191 | [5 empty] | 2019-02-27 10:30:00.000 | 2018-10-31 03:30:00.000 | 0 | 12956.0372 | 2019-02-20 16:30:00.000 | 27.6667 | 97.1875 | 122.0625 | 128.8125 | 21.4782 | 106.1426
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 177 | 19.6374 | -92.332 | Ayatsil | Deviated | Direccional | 2019-03-25 12:00:00.000 | Primary Drilling | Pemex-9022 |  |  | 32FC5334F69A4202A3E790522DCA86EA | CON BARRENA TRICONICA DE 6-1/2" (517) A 4718 MTS Y PREVENTOR SUPERIOR CERRADO. CON UNIDAD DE ALTA PRESIÓN REALIZÓ PRUEBA DE INTEGRIDAD A T.R. DE 7-5/8" A TRAVES DE E.A.. BOMBEÓ 2.5 BLS DE LODO E.I. 1.84 GR/CC A GASTO CONSTANTE DE 0.5 BPM Y ALCANZANDO UNA PRESIÓN DE PRUEBA DE 540 PSI SUSPENDIO BOMBEO Y OBSERVO DURANTE 10 MIN EN. EA MANTENIENDOSE Y ESTABILIZANDOSE PRESION EN 502 PSI. DESFOGÓ PRESIÓN A O PSl OBSERVANDO MISMA VOLUMETRÍA DE RETORNO PRUEBA SATISFACTORIA | 83.12 |  | 2019-06-17 02:58:33.000 | 219 | [5 empty] | 2019-08-16 17:30:00.000 | 2019-03-27 00:00:00.000 | 564.3045 | 16272.9664 | 2019-07-05 19:30:00.000 | 45.0833 | 81.4792 | 102.3125 | 144.2292 | 31.2581 | 159.0516
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 197 | 19.6367 | -92.3322 | Ayatsil | Deviated | Direccional | 2018-05-27 00:00:00.000 | Primary Drilling | Pemex-9022 | Rabajo cemento y accesorios hasta 4170 m. Perforo hasta 4195 m. Trato de acondicionar agujero. Levanta BNA a 2600 m. | Sacar a superficie. Armar BHA de corte de nucleos. Cortar de 4195 a 4200 m. Sacar | 32FC5334F69A4202A3E790522DCA86EA | CON BNA TRIC. 6 1/2" Y SARTA NAVEGABLE ROTATORIA 4 3/4" CÍA SBL. PERFORA DE 4170 A 4176 M. RECORD: 6 MT/PERF, 01:35 HR/PERF, ULT3.= 16-20-16 MIN. CONDICIONES: PSB.= 4-5 TON, ROT.= 60 RPM, TORQ.= 14-15 KFT-LB, Q.= 228 GPM, PB.= 1620 PSI. DENS. 1.03 GR/CC. DEC.= 1.039 GR/CC. (DURANTE LA OPERACIÓN SE OBSERVAN NIVELES ESTABLES). NOTA: SE PERFORO CON HERRAMIENTA LWD EN TIEMPO REAL, REGISTRANDO DE 4170 A 4176 M (6 M). | 61.55 |  | 2018-08-05 13:05:13.000 | [6 empty] | 2018-10-05 20:30:00.000 | 2018-06-05 03:00:00.000 | 557.7428 | 14271.654 | 2018-09-29 12:00:00.000 | 37.6875 | 100.25 | 125.5 | 131.8542 | 28.5827 | 113.7184
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 131 | 19.6353 | -92.357 | Ayatsil | Deviated | Direccional | 2018-09-13 00:00:00.000 | Primary Drilling | Pemex-9023 | CONT. ARMANDO TP POR LINGADAS Y ACOPIO DE MATERIALES. ARMO BNA. TRIC. 26" CON BHA PENDULAR. PERFORO DE 175 A 221 M. OBS, DANO EN TUBO EN CONEXION | REEMPLAZAR TUBOS DANADOS Y SUSTITUTO DE TOP DRIVE. CONT. PERFORANDO HASTA 300 M. | 32FC5334F69A4202A3E790522DCA86EA | CON SARTA PENDULAR Y BNA DE 28" 175 PERFORO @ 221 MD CON UN RECORD DE 46 METROS EN 00:39 HRS, ULTIMOS 3: 1-1-1, PSB = 1-3 TON, 60 RPM, TORQE = 1-3 KLB*PIE, Q = 900 GPM, 154 EPM, PBBA= 930 PSI. BOMBEANDO 15 M3 DE BACHE DE LODO BENTONITICO DE 1.06 GR/CM3 X 130 SEG CADA LINGADA PERFORADA. *** DONDE AL REALIZAR CONEXION DE 3ER. LING. DE T.P. 5" “G-105, 25.6 L/P, XT-50 CON TOP-DRIVE, SUSPENDIO POR OBSERVAR GIRO DE LA LLAVE DE AGUANTE, PANDEO DE LINGADA Y JUNTA DOBLADA SOBRE ROTARIA. | 75.59 |  | 2018-12-10 14:03:50.000 | 255 | [5 empty] | 2019-01-19 11:00:00.000 | 2018-09-26 18:00:00.000 | 574.147 | 13484.2524 | 2019-01-14 06:00:00.000 | 45.2292 | 94.875 | 123.25 | 128.4583 | 35.2092 | 109.4057
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 132 | 19.6353 | -92.3574 | Ayatsil | Deviated | Direccional | 2018-01-27 12:00:00.000 | Primary Drilling | Pemex-9023 | ARMO BNA. 8 1/2" PDC C/SARTA ROT-NAVEG Y METE A 490 M DONDE PROBO HTA. DIRECC. + RECONOCIO FONDO P.I A 3849.5 C/ 5 TON +CIRCULO T.A.+ EFETUA DESP DE FLUIDOS AV: 5% | EFECTUAR DESPLAMIENTO DE LFUIDOS+ REBAJAR CMTO Y ACCS A 3879 M + CIRCULAR+PRUEBA DE LINER C/1000 PSI,+REBAJAR ZAP Y RECONCOER FNDO PERF A 3886 M | 32FC5334F69A4202A3E790522DCA86EA | METIO BNA 8 1/2" CON SARTA ROT. NAV. A 490 M. DONDE REALIZO PRUEBA DE HERRAMIENTAS DIRECCIONALES CON BBA#1, 51 EPM, Q:250 GPM, PBBEO:2170 PSI, Y BBA #2. 51 EPM, Q:250 GPM, PBBEO: 2200 PS | 70.46 |  | 2018-04-14 11:02:24.000 | [6 empty] | 2018-09-13 22:00:00.000 | 2018-02-03 19:00:00.000 | 0 | 13379.2655 | 2018-08-18 18:00:00.000 | 22.2708 | 88.8125 | 203.25 | 229.4167 | 9.7076 | 65.8266
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 151 | 19.6358 | -92.3575 | Ayatsil | Deviated | Direccional | 2019-08-18 12:00:00.000 | Primary Drilling | Pemex-9023 |  |  | 32FC5334F69A4202A3E790522DCA86EA | CON MOVIMIENTOS DE SARTA CIRCULO Y BAJO DENSIDAD DE LODO DE 1.63 A 1.61 GR/CC. EMBOLADAS TOTALES 15000 EMB, DENS. DE ENTRADA Y SALIDA 1.61 GR/CC, INCREMENTANDO Q= 500 A 700 GPM; P.BBEO=1350 – 2721 PSI; DEC= 1.634 G/CC. | 66.8 |  | 2019-10-31 19:13:35.000 | 218 | [5 empty] | 2019-10-01 00:00:00.000 | 2019-08-26 01:00:00.000 | 593.832 | 9186.352 | 2019-09-19 05:00:00.000 | 1.7708 | 16.0417 | 31.7083 | 43.5 | 4.0709 | 289.7141
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 292 | 19.6353 | -92.3574 | Ayatsil | Deviated | Direccional | 2019-02-20 12:00:00.000 | Primary Drilling | Pemex-9023 |  |  | 32FC5334F69A4202A3E790522DCA86EA | EN ACOPIO DE MATERIALES PARA INTERVENIR POZO AYATISIL-292 CONDUCTOR 7. **NOTA: DE 02:00 - 15:00 HORAS ATENDIO EMBARCACION DOÑA PAULA CON TUBERIA DE TRABAJO DE DOS BOCAS (172 TRAMOS TP 5 7/8”,41.06#,°S-135,XT-57; 158 TRAMOS TP 5”,25.60#,°G-105,XT-50, 100 TRAMOS DE TP 5" °X-95 25.6# XT50, 30 TP HW DE 5" XT50, 6 DC 9 1/2" Y 6 DC 8", UNA CANASTILLA CON COMBINACIONES); REALIZO MANIOBRAS CON GRUA DEL EQUIPO PARA SUBIR MANGUERA DE BARCO DOÑA PAULA Y RECIBIO 10,000 GLS DE DIESEL, REALIZO MANIOBRAS Y BAJO MANGUERA DE DIESEL A BARCO, A MISMA EMBARCACION BAJO 4 CANASTILLAS CON COMBINACIONES, CANASTILLA CON ESTROBOS Y LOTE DE ESTROBOS CON DESTINO A DOS BOCAS. *** 15:00 - 19:00 HRS REALIZO REACOMODO DE MATERIALES Y ACODERO EMBARCACION LINDA, RECIBIO CABINA Y HERRAMIENTAS DIRECCIONALES DE COMPAÑIA SCHLUMBERGER. ***CONTINUA ARMANDO 40 DE 211 LINGADAS DE TUBERIA DE PERFORACIÓN.(24 DE 59 LINGADAS DE TP 5 7/8”°G-105,26.03# XT-57; 16 DE 59 LINGADAS DE TP 5" °G-105 25.6# XT50). | 70.29 |  | 2019-05-01 06:55:09.000 | 248 | [5 empty] | 2019-08-16 00:00:00.000 | 2019-02-20 00:00:00.000 | 568.8977 | 13303.8062 | 2019-07-27 13:30:00.000 | 17.375 | 100.7083 | 157.0625 | 176.5 | 9.8442 | 84.7039
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | AYATSIL 107 | 19.6062 | -92.3359 | Ayatsil | Deviated | Direccional | 2017-10-10 12:00:00.000 | Primary Drilling | Pemex-9094 | Reconocio PI a 569 m, circulo pozo, probo integridad con 500psi, levanto a superficie, armo tubo diffusor con TP franca y metio a 504 m. | REALIZAR TxC, ABANDONO TEMPORAL AYATSIL 107. | 32FC5334F69A4202A3E790522DCA86EA | (N) CIRCULO LIMPIANDO POZO CON 150 EPM Q=859 GPM, P=1100 PSI, OBSERVANDO CIRCULACION NORMAL. | 65.25 |  | 2018-02-04 06:00:00.000 | [6 empty] | 2018-02-07 00:00:00.000 | 2017-12-01 23:30:00.000 | 574.147 | 3543.3072 | 2018-01-27 18:30:00.000 | 5.7708 | 19.875 | 109.2708 | 119.5 | 4.8291 | 32.4268
WH | MCA | Mexico | 32FC5334F69A4202A3E790522DCA86EA | 692 | 40262 | MCA Ayatsil Tekel AFE | IDS | MCA | AFE Assurance | YAXCHE 200 | 18.5128 | -93.2851 | Ayatsil | Deviated | Desvido | 2019-10-04 12:00:00.000 | Primary Drilling | Pemex-9095 | CON BNA PDC 17 1/2" A 2101 M. CON SARTA ROTATORIA NAVEGABLE, CIRCULA LIMPIANDO POZO, SIMULTANEAMENTE ARMO 48 TRAMOS DE TP 5 7/8" 135 XT-57 DE 26.3 LB/PIE, PERFORO A 2241 M | PERFORAR A 2700 MD+VIAJE CORTO+SACAR A SUPERFICIE+METER Y CEMENTAR TR 13 3/8" | 32FC5334F69A4202A3E790522DCA86EA | (N) CON BNA PDC 17 1/2” A 2101 M. CON SARTA NAVEGABLE ROTATORIA CON SECCION DE PODER, EQUIPADA CON LWD/MWD/APWD, BOMBEO 10 M3 DE BACHE VISCOSO DE 1.46 GR/CC X 150 SE/VISC CIRCULA LIMPIANDO POZO. CONJUNTAMENTE ARMA 30 TRAMOS DE TP 5 7/8” XT-57 S-135 DE 26.3 LB/PIE ESTIBANDO EN CHANGUERA, FALTANDO ARMAR 18 TRAMOS MAS DE TP 5 7/8”, CIRCULA CON 186 EPM. Q= 1100 GPM, PB=3795 PSI. | 123.16 |  | 2020-02-03 03:56:44.000 | [6 empty] | 2019-10-20 00:00:00.000 | 2019-10-03 23:30:00.000 | 216.5354 | 7352.3624 | 2019-10-20 00:00:00.000 | 0 | 10.5 | 15.5 | 15.5 | 0 | 474.346
MCA | MXM | Mexico | 8BF2A9B7B0EE4BE485231789F248BB43 |  |  | MCA Borr Drilling Opex Turnkey Gr2 | IDS | MCA | LSTK | Mulach 10 | 18.4879 | -93.3446 | Mulach | Deviated | Production | 2019-09-08 17:00:00.000 | Primary Drilling | Gersemi | PROBÓ CONJUNTO DE PREVENTORES 18-3/4" 15M CON 500 PSI EN BAJA Y 8,000 PSI EN ALTA (ANULAR 7,000 PSI) POR 5 Y 10 MINUTOS RESPECTIVAMENTE. ALOJÓ BUJE DE DESGASTE EN CABEZAL. ARMANDO BHA DIRECCIONAL, BAJO BHA DE 8 ½” DIRECCIONAL CON BARRENA DE 8 1/2” TRAMO X TRAMO DESDE 181 M HASTA 440 M. | BAJAR Y REBAJAR CEMENTO Y ACCESORIOS, DESPLAZAR FLUIDO DE E.I. DE 1.55 G/CC POR 1.65 G/CC Y REALIZAR PRUEBA LOT. PERFORAR TANGENTE HASTA PRIMER PUNTO DE NÚCLEO (3,373 MD POR DEFINIR). | 8BF2A9B7B0EE4BE485231789F248BB43 | ATENDIÓ EMBARCACIÓN LISA F DESEMBARCANDO PERSONAL. | 63.21 |  | 2019-11-10 05:02:24.000 | 200 | [5 empty] | 2019-10-21 22:30:00.000 | 2019-09-08 17:00:00.000 | 209.9738 | 10150.919 | 2019-10-21 19:00:00.000 | 6.0208 | 35.5417 | 43.0833 | 43.2292 | 13.9277 | 235.6113
MCA | MXM | Mexico | 8BF2A9B7B0EE4BE485231789F248BB43 |  |  | MCA Borr Drilling Opex Turnkey Gr2 | IDS | MCA | LSTK | Manik 4 | 19.4281 | 92.3333 | Manik | Deviated | Development | 2019-09-06 01:15:00.000 | Primary Drilling | Grid | INSTALA PREVENTOR 18 3/4" 15K, INSTALA CONEXIONES HIDRAULICAS Y LINEAS SUPERFICIALES. PROBO HERMETICIDAD DE CONEXIONES, CABEZAL Y TR 20 CON 2200 PSI X 30 MIN OK. INSTALO CAMPANA Y OVERSHOT, ARMO BHA 17 1/2", BAJO HASTA 450 M | BAJAR BHA 17 1/2" A TOC, REBAJAR CEMENTO, DESPLAZAR OBM, REBAJAR RESTO DE SHOE TRACK Y 5 M DE AGUJERO, REALIZAR LOT, PERFORAR ETAPA 17 1/2". | 8BF2A9B7B0EE4BE485231789F248BB43 | CON PERSONAL DE OPERACIONES Y SUPERVISION DE PERSONAL DE SLB D&M, ARMA SARTA NAVEGABLE CON BNA. 17 1/2" PDC BIT - SDSD0926 Y BAJO HASTA 277 M POWER DRIVE X6 1100 X 17 1/2" STABILIZED CC + RECEIVER FLOAT VALVE + LWD / APWD (ARC 9 ½") + MWD + ESTABILIZADOR 17 3/8" + LWD + ESTABILIZADOR 17 3/8" + 1 X DC 9 ½" + FILTRO / DHF 9 ½" + 3 X DC 9 ½" + X/O 7 5/8" REG (P) X 6 5/8" REG (B) + 3 X DC 8" + MARTILLO JAR 8" + 3 X DC 8" + X/O 6 5/8" REG (P) X GPDS55 (B) + 5 ½” HWDP (GPDS55) (15 JOINTS) | 120 |  | 2020-01-03 18:26:24.000 | 163 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-09-06 01:15:00.000 | 423.2284 | 8694.226 | 2019-10-03 00:00:00.000 | 13.9896 | 17.6458 | 26.9479 | 45.9479 | 30.4466 | 322.6307
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 1614 | 20.78 | -97.67 | Miquetla | S Shaped | Direccional | 2018-04-15 20:00:00.000 | Primary Drilling | CPL-647 | BAJO TR DE 7 5/8"A 1199.25 M, CEMENTO MISMA, INSTALO PACK OFF + BUJE DE DESGASTE, BAJO BNA 6 3/4" A 180 M, PROBO MWD, SIN EXITO, LEVANTO BNA A 21 M, PROBO MWD, BIEN, BAJO BNA 6 3/4" A 180 M. | BAJAR BNA PDC 6 3/4" + SARTA DIRECCIONAL A 1171 M CIMA DE COPLE, PROBAR TR 7 5/8" CON 1300 PSI, REBAJAR CEMENTO Y ACCESORIOS, PERFORAR A 2060 M. | 872A07F573CE455FA30047CE150243F2 | CON BNA PDC 6 3/4" A 21 M, PROBO HERRAMIENTA DIRECCIONAL CON 66 EPM, 180 GPM, PB=750 PSI, SATISFACTORIAMENTE. | 14 |  | 2018-04-29 00:00:00.000 | [6 empty] | 2018-04-28 17:00:00.000 | 2018-04-15 20:00:00.000 | 0 | 6814.3047 | 2018-04-26 10:00:00.000 | 0.95833 | 4.625 | 10.5833 | 12.875 | 7.4434 | 643.8713
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 1618 | 20.78 | -97.67 | Miquetla | S Shaped | Desarrollo | 2018-02-22 00:00:00.000 | Primary Drilling | CPL-647 | PERFORÓ CON BARRENA TRICONICA 14 3/4'' HASTA 101 M, SACO MISMA HASTA SUPERFICIE | BAJAR TR 10 3/4'' Y CEMENTAR MISMO. INSTALAR SECCION ''A'' DEL CABEZAL Y B.O.P. INICIAR ETAPA 9 1/2'' | 872A07F573CE455FA30047CE150243F2 | C/BNA TRIC 14 3/4" A 101 M BBEO BACHE VISCOSO DE 120 SEG Y CIRCULO POZO RECIPROCANDO SARTA CON UN GASTO DE 533 GPM, PRESION 354 PSI | 13.94 |  | 2018-04-08 22:35:24.000 | [6 empty] | 2018-04-12 17:00:00.000 | 2018-03-26 12:30:00.000 | 0 | 6883.2023 | 2018-04-09 14:00:00.000 | 2.6875 | 6.8333 | 46.5833 | 49.7083 | 5.4065 | 147.7611
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 1636 | 20.78 | -97.67 | Miquetla | S Shaped | Directional | 2018-04-30 16:00:00.000 | Primary Drilling | CPL-647 | METIO BNA 6 3/4" A 1189 M + PROBO T.R 7 5/8" + REBAJO CEMENTO Y ACCESORIOS + C/ BNA 6 3/4" PDC + SARTA DIRECCIONAL PERFORA A 1544 M. | CON BNA 6 3/4" PDC + SARTA DIRECCIONAL EQUIPADA CON MOTOR DE FONDO Y MWD PERFORAR A 2096 M. TOMAR REGISTROS ELECTRICOS + METER Y CEMENTAR T.R 5 1/2" 17# N-80 BCN. | 872A07F573CE455FA30047CE150243F2 | CONTINUO METIENDO BNA 6 3/4" PDC + SARTA DIRECCIONAL EQUIPADA CON MOTOR DE FONDO Y MWD POR LINGADAS CON TUBERIA DE TRABAJO T.P 4" DE 1050 M HASTA 1189 M, DONDE TOCO CIMA DE TAPON CON 5 TON. | 14 |  | 2018-05-14 00:00:00.000 | [6 empty] | 2018-05-13 11:30:00.000 | 2018-04-30 16:00:00.000 | 0 | 6929.1341 | 2018-05-09 23:30:00.000 | 0.16667 | 3.4375 | 9.3125 | 12.8125 | 1.3008 | 744.0681
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 1604 | 20.78 | -97.82 | Miquetla | S Shaped | Desarrollo | 2018-02-18 08:00:00.000 | Primary Drilling | DTM-638 | BAJO BNA. 6 3/4" A 1208 M, TOCO CIMA DE TAPON, CIRCULO, REALIZO PRUEBA DE HERMETICIDAD A TR, REBAJO CEMENTO Y ACCESORIOS A 1240 M, PERFORA A 1510 MTS. | PERFORAR CON BNA. PDC 6 3/4" A 2108 MTS. | 872A07F573CE455FA30047CE150243F2 | CONTINUO METIENDO BNA PDC 6 3/4" Y SARTA DIRECCIONAL CON MOTO DE FONDO A 1.15 A 1208 M., DONDE TOCO CIMA DE TAPON SOLIDO, LAS ULTIMOS 4 TRAMOS METE CON BOMBEO A Q= 210 GPM, PBBEO= 1180 PSI. | 14.04 |  | 2018-03-04 01:00:00.000 | [6 empty] | 2018-03-03 17:00:00.000 | 2018-02-18 08:00:00.000 | 0 | 6968.5042 | 2018-02-28 00:00:00.000 | 1.125 | 3.3333 | 9.6667 | 13.375 | 8.4112 | 720.8797
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 827 | 20.777 | -97.6685 | Miquetla | S Shaped | Desarrollo | 2018-03-05 18:30:00.000 | Primary Drilling | DTM-638 | PERFORO A 1521 M, SUSPENDE POR FALLA DEL MALACATE Y LEVANTO A 1230 M, CAMBIO MOTOR DEL MALACATE Y BAJO A 1521 M Y PERFORO A 1550 M | CON BNA 6 3/4" PDC + SARTA DIRECCIONAL EQUIPADA CON MOTOR DE FONDO Y MWD PERFORAR A 2130 M. | 872A07F573CE455FA30047CE150243F2 | LEVANTO BNA 6 3/4" PDC + SARTA DIRECCIONAL POR LINGADAS DE 1521 M HASTA 1230 M (ZAPATA 7 5/8), LIBRE LLENANDO POZO POR ESPACIO ANULAR CADA 5 LINGADAS VOLUMEN DE ACERO EXTRAIDO CON LODO DE E.I 1.20 GR/CC | 14.09 |  | 2018-03-19 02:06:00.000 |  |  | 20180313170259 |  |  |  | 2018-03-19 03:30:00.000 | 2018-03-05 18:30:00.000 | 0 | 7027.5593 | 2018-03-16 09:30:00.000 | 1.25 | 4.1042 | 10.625 | 13.375 | 9.3458 | 661.4173
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 849 | 20.7768 | -97.6683 | Miquetla | S Shaped | Desarrollo | 2018-02-02 11:00:00.000 | Primary Drilling | DTM-638 | BAJO BNA. PDC 6 3/4" CON SARTA DIRECCIONAL+HOMOGENIZO LODO+REBAJO CEMENTO Y ACCESORIOS+PERFORA A 1490 M. | PERFORAR CON BNA. PDC 6 3/4" A 2120 M., CIRCULAR, LEVANTAR BNA. A SUPERFICIE+TOMA DE REGISTROS+ METER TR 5 1/2" | 872A07F573CE455FA30047CE150243F2 | CIRCULO POZO CON 200 GPM Y PBA DE 1250 PSI, HOMOGENIZANDO COLUMNA A 1.20 GR/CC ENTRADA Y SALIDA | 14.04 |  | 2018-02-16 00:57:36.000 | [6 empty] | 2018-02-15 23:30:00.000 | 2018-02-02 11:00:00.000 | 0 | 6978.3467 | 2018-02-13 17:00:00.000 | 0.10417 | 3.2708 | 11.25 | 13.5208 | 0.77042 | 620.2975
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Miquetla 865 | 20.7693 | -97.6727 | Miquetla | S Shaped | Desarrollo | 2018-03-21 17:00:00.000 | Primary Drilling | DTM-638 | BAJO TR A 1232 MTS Y EFECTUO CEMENTACION DE LA MISMA, INSTALO ENSAMBLE DE SELLOS Y BUJE DESGASTE + ARMO BNA Y SARTA DIR Y BAJO 1202 MTS, PROBO TR Y PERFORO A 1271 MTS. | PERFORAR CON BNA DE 6 3/4" Y SARTA DIRECCIONAL HASTA 2145 MTS. | 872A07F573CE455FA30047CE150243F2 | CONTINUO BAJANDO BNA PDC DE 6 3/4" Y SARTA DIRECCIONAL DE 51 MTS A 1202 MTS EN DONDE RECONOCIO CIMA DEL COPLE FLOTADOR CON 10000 LBS DE PESO. | 13.83 |  | 2018-04-03 20:00:00.000 | [6 empty] | 2018-04-05 14:00:00.000 | 2018-03-21 17:00:00.000 | 0 | 7103.0186 | 2018-04-02 21:30:00.000 | 1.1042 | 3.8542 | 12.1875 | 14.875 | 7.423 | 582.8118
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Catedral 103RE | 17.4346 | -93.3399 | Catedral | Deviated | Reentrada desviado | 2019-02-02 20:00:00.000 | Primary Drilling | GC-402 | SACO CONJUNTO COLAGADOR SOLTADOR A SUP. + BAJO MOLINO 4 1/8" + SARTA LISA A 2,610 M, CIA. GSM CAMBIA GATO DEL TOP DRIVE AV:50% | METER MOLINO 4 1/8" + SARTA LISA A 2693.60 M CIMA DE COPLE DE RETENCIÓN + CON MOLINO DE 4 1/8" REBAJAR COPLE Y CEMENTO DE 2693 M HASTA 2707 M, PROBAR T.R CON 2000 PSI, EFECTUAR DESPLAZAMIENTO DE LODO DE 1.35 GR/CC A 0.95 GR/CC | 872A07F573CE455FA30047CE150243F2 | CON CIA SLB DESCARGO FLUIDO DE E.I . DE 0.95 GR/CC DE FRAC TANK A PRESAS DE TRABAJO | 10.07 |  | 2019-02-12 01:41:39.000 | 295 | [5 empty] | 2019-02-28 00:00:00.000 | 2019-02-02 20:00:00.000 | 6551.8375 | 9924.541 | 2019-02-18 17:30:00.000 | 2.0833 | 9.7917 | 15.8958 | 25.1667 | 8.2781 | 624.3486
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Catedral 13RE | 17.4397 | -93.352 | Catedral | Deviated | Desarrollo | 2018-11-27 14:00:00.000 | Primary Drilling | GC-402 | PERFORO ROTANDO Y DESLIZANDO CON BNA. 5 7/8" Y SARTA DIRECCIONAL DESDE 2,240 M. HASTA 2,400 M. | PERFORAR CON BNA. 5 7/8" Y SARTA DIRECCIONAL HASTA ALCANZAR LOS 30° A 2,490 M POR PROGRAMA + CIRCULAR + SACAR BNA. PARA CAMBIO DE MOTOR DE FONDO POR UN GT DE 5" | 872A07F573CE455FA30047CE150243F2 | SUSPENDE PERFORACION PARA REALIZAR VIAJE DENTRO DE LA TR DE 7" A 2,150 M. PARA BAJAR LA DENSIDAD DE LODO DE 1.07 GR/CC A 1.05 GR/CC., BOMBEO Y DESPLAZO 2 M3 DE BACHE VISCOSO DE 1.13 GR/CC POR 120 SEG, LECTURA MAXIMA DE GAS 15% AL TEMPO DE ATRASO, SIN CORTAR DENSIDAD. | 13.7 |  | 2018-12-21 16:48:00.000 | 196 | [5 empty] | 2018-12-28 00:00:00.000 | 2018-12-11 00:00:00.000 | 7874.016 | 8523.6223 | 2018-12-12 23:00:00.000 | 2.9583 | 0.64583 | 15.375 | 30.4167 | 9.726 | 554.3819
WH | MCA | Mexico | 872A07F573CE455FA30047CE150243F2 |  | 591259 | MCA Diavaz AFE | IDS | MCA | AFE Assurance | Catedral 43RE | 17.4346 | -93.3397 | Catedral | Deviated | Tipo J | 2019-04-01 00:00:00.000 | Primary Drilling | GC-402 | CON BNA. 4 1/8" A 3,042 M. REALIZO VIAJE CORTO A LA ZAPATA + REGRESO A FONDO + CIRCULO + SACO BNA. 4 1/8" HASTA 300 M. | TOMAR REGISTROS ELECTRICOS | 872A07F573CE455FA30047CE150243F2 | CON BNA, 4 1/8" Y SARTA NAVEGABLE A 3,042 M. CONTINUO CIRCULANDO CON UN GASTO DE 100 GPM, PB= 1,800 PSI HASTA OBSERVAR RETORNOS LIMPIOS Y COLUMNAS HOMOGENEAS A 0.97 GR/CC, SE CUANTIFICO NIVELES ESTABLES EN PRESAS, PARO BOMBEO Y OBSERVO POR 10 MIN. NIVEL DE LODO EN LINEA DE FLOTE, BAJO NIVEL +/- 30 CM, LLENO CON 230 LTS. | 19.47 |  | 2019-04-20 11:16:47.000 | 232 | [5 empty] | 2019-04-23 00:00:00.000 | 2019-04-17 00:00:00.000 | 9547.2444 | 9980.3153 | 2019-04-17 22:30:00.000 | 0.33333 | 0 | 16.9375 | 22 | 1.5152 | 589.2437
WH | MCA | Mexico | 75BF50690E474238AEF2EDD7B27C889B | 834 | 472097 | MCA Hokchi AFE | IDS | MCA | AFE Assurance | TOLTECA 1 | 18.285 | -94.325 | Bloque-2 | Vertical | Exploratorio | 2019-08-31 12:00:00.000 | Primary Drilling | Odin | PROBÓ BOP. ARMÓ LINGADAS DE 5" A LA TORRE. ARMÓ BHA DIRECCIONAL 8.1/2" CON VÁLVULA WELL COMMANDER. | BAJAR BHA DIRECCIONAL A +/- 500 MTS. PROBAR HERRAMIENTAS DIRECCIONALES A DIFERENTES CAUDALES. BAJAR BARRENA, CIRCULAR. PROBAR CASING-LINER. DRILL OUT SHOE TRACK + 3 MTS DE FORMACIÓN NUEVA. REALIZAR LOT. | 75BF50690E474238AEF2EDD7B27C889B | CON PERSONAL DE SLB DIRECCIONAL, LEVANTA FUENTE RADIOACTIVA, WELL COMMANDER Y CATCHER WELL COMMANDER AL RIG FLOOR | 34.46 |  | 2019-10-11 11:00:57.000 | 282 | [5 empty] | 2019-10-18 00:00:00.000 | 2019-09-07 00:00:00.000 | 187.0079 | 8503.9373 | 2019-10-11 23:45:00.000 | 7.5313 | 29.3021 | 41.4896 | 47.5 | 15.8553 | 204.9656
WH | MCA | Mexico | 75BF50690E474238AEF2EDD7B27C889B | 834 | 472097 | MCA Hokchi AFE | IDS | MCA | AFE Assurance | XAXAMANI-2EXP | 18.1822 | -94.3737 | Bloque-2 | Vertical | Exploratorio | 2019-07-03 12:00:00.000 | Primary Drilling | Odin | REPARÓ BOP. CEMENTÓ ESPACIO ANULAR 9.5/8" x 13.3/8" A TRAVÉS DE LOS DISPAROS EN TR 9.5/8". WOC. SACÓ STANDS DE DP 5.1/2" Y HWDP 5.1/2". ARMÓ BHA 36". REALIZÓ SIMULACRO DE ABANDONO. CORRIÓ REGISTRO CBL A TR 9.5/8". | BAJAR CON DP 3.1/2". REALIZAR 3° TxC. LEVANTAR SARTA, CIRCULAR. SACAR TOTAL. ARMAR CORTADOR PARA TR DE 9.5/8", BAJAR Y CORTAR TR. RECUPERAR TR CORTADA. | 75BF50690E474238AEF2EDD7B27C889B | CON OPERADOR DE BLACK HAWK VERIFICA CONDICIONES E INICIA MANIOBRAS PARA ASENTAR STINGER EN EL RETENEDOR. PESO DE LA SARTA 139 KLB. BAJA 1 MTS E INTRODUCE STINGER ASENTANDO 15 KLB WOB. ABRE WELL HEAD WINGS VALVES. ALINEA PRESA N°1 Y RETORNO A PRESA N°1. | 49.75 |  | 2019-09-11 18:01:26.000 | 210 |  | 20190918200701 |  |  |  | 2019-09-06 07:45:00.000 | 2019-07-24 16:15:00.000 | 190.2887 | 2995.4069 | 2019-08-05 00:30:00.000 | 4.9688 | 9.5729 | 32.5208 | 64.8229 | 7.6651 | 92.1073
WH | MCA | Mexico | 75BF50690E474238AEF2EDD7B27C889B | 834 | 472097 | MCA Hokchi AFE | IDS | MCA | AFE Assurance | YALUK 1 | 18.3058 | -94.3925 | Bloque-2 | Vertical | Exploratorio | 2019-05-09 00:01:00.000 | Primary Drilling | Odin | BAJÓ HERRAMIENTA DESDE 184 MTS HASTA 3495 MTS. CORRIÓ Y CORTÓ CABLE. REALIZÓ PRUEBA DE INTEGRIDAD DE CASING-LINER. REALIZÓ SIULACROS DE SURGENCIA | CIRCULAR PARA HOMOGENEIZAR LODO. REALIZAR LOT @ ZTO DE 9 5/8". PERFORAR SECCION DE HUECO DE 8 1/2" | 75BF50690E474238AEF2EDD7B27C889B | BAJA HERRAMIENTA DESDE 502 MTS HASTA 1419 MTS. BAJA HERRAMIENTA Y MONITOREA DESPLAZAMIENTO AL TANQUE DE VIAJE Y LLENANDO INTERIOR CADA 15 LINGADAS. | 87.7 |  | 2019-08-04 16:48:51.000 | 327 | 327 |  |  |  |  | 2019-06-29 07:00:00.000 | 2019-05-09 13:00:00.000 | 259.1864 | 13458.0057 | 2019-06-18 17:15:00.000 | 7.3542 | 34.7083 | 40.7181 | 51.291 | 14.3381 | 330.5169
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Madrefil-131 | 18.1728 | -93.3345 | MADREFIL | Build & Hold | J | 2018-03-13 00:00:00.000 | Primary Drilling | ICMA 879 | INSTALO EQUIPO MEX OIL 100 %, REALIZO CHECK LIST CON INPEDITIVA, CORRIGIO MISMA, PROBO SIFON, CONECTO BNA 36'' Y PERFORO A 15 M. | CONTINUAR PERFORANDO DE ACUERDO A PROGRAMA HASTA 50 M, BAJAR CONDUTOR DE 30'' Y CEMENTAR. | CA68BAB420A4491D91F6E79EC41AD153 | PERSONAL DE PPS, SERVICIO DE CONTRATO, ACTIVO BLOQUE SUR 03, PERSONAL DE SLB REALIZO CHECK LIST PRE ARRANQUE. ENCONTRANDO 1 IMPEDITIVA (EL SIFON PARA SACAR RECORTES Y FLUIDOS DEL CONTRAPOZO) | 167.53 |  | 2018-08-27 12:43:12.000 | [6 empty] | 2018-08-05 00:00:00.000 | 2018-03-13 00:00:00.000 | 0 | 19822.8353 | 2018-07-16 13:00:00.000 | 21.6458 | 76.1875 | 125.5417 | 145 | 14.9282 | 157.8985
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Ixachi 1001 | 18.5527 | -96.1399 |  | Deviated | Exploratory | 2018-06-17 00:00:00.000 | Primary Drilling | ICMA-880 | LEVANTO CORONA A 1,468 M. A VELOCIDAD CONTROLADA. SUSPENDIO POR FALLA DE LA LLAVE. MEXOIL REPARA LLAVE FH-100. CONTINUO SACANDO CORONA A SUPERFICIE. EXTRAJO MUESTRA, DESMANTELO BARRIL. EFECTUO ORDEN Y LIMPIEZA. RECUPERO BUJE. PROBO BOP'S 11" 15 M Y ENSAMBLE DE ESTRANGULACION. INSTALO BUJE. INSPECCIONO DADOS DE LA MORDAZA DEL T.D. | CAMBIAR SUSTITUTO DEL TOP DRIVE. ARMAR SARTA DIRECCIONAL ROTATORIA CON BNA PDC 8-1/2" Y METER A 6905 M. INSTALAR ELEMENTO SELLANTE. METER A 7017 M. CONTINUAR PERFORANDO ETAPA DE 8-1/2". | CA68BAB420A4491D91F6E79EC41AD153 | (N) CONTINUO LEVANTANDO CORONA 8-1/2" Y BARRIL MUESTRERO DE 6-1/4" A SUPERFICIE. VELOCIDAD RECOMENDADA POR ESPECIALISTA DE 2-3 MIN/LINGADA, ELIMINANDO; 21 TRAMOS TP H.W. 5" POR ESPACIO EN PEINES, 7 REDUCTORES DE FRICCIÓN (TOTAL 27 RECUPERADOS AL 100% DE ACUERDO A DISTRIBUCIÓN) Y ESTIBANDO 3 PARADAS D. COLLAR 6 1/2". CON ESPECIALISTA DE CIA. IPS, DESCONECTO CORONA DE 8-1/2", EXTRAJO FUNDA DE ALUMINIO CON MUESTRAS, BAJO A PATIO DE TUBERIAS Y ELIMINO BARRIL MUESTRERO. **NOTA: OBSERVANDO DESCONEXIÓN DE JUNTAS, NORMAL. **DESGASTE DE LA CORONA: 0-0-NO-A-X-I-NO-BHA. | 117.52 |  | 2018-10-12 12:28:48.000 | 164 | [5 empty] | 2018-12-24 13:00:00.000 | 2018-06-17 00:00:00.000 | 0 | 25862.8617 | 2018-11-29 19:00:00.000 | 20.9167 | 117.7083 | 165.7917 | 190.5417 | 10.9775 | 155.9962
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | YAXJUT-1EXP | 17 | -93 | Yaxjut | Vertical | Exploratorio | 2019-08-19 21:30:00.000 | Primary Drilling | ICMA-881 | ARMO BHA CON BNA PDC 17 1/2" + SARTA NAVEGABLE EQUIPADA CON MWD/LWD Y BAJA MISMA HASTA 500 MTS. REALIZO MANTENIMIENTO A TOP DRIVE Y REVISION DE PUNTOS CRITICOS, REALIZO CORTE Y DESLIZ DE CABLE DEL MALACATE PRINCIPAL, CONTINUO BAJANDO BNA PDC 17 1/2" HASTA 960 MTS | BAJAR A FONDO PERFORADO (1741 MTS)+ CIRCULAR A RETORNOS LIMPIOS + RETOMAR PERFORACIÓN | CA68BAB420A4491D91F6E79EC41AD153 | (N) METE BNA PDC 17 1/2" Y SARTA ROTATORIA CON LWD/PWD/MWD @ 960 MTS X LINGADAS DE TP 5 1/2" FH 21.9 #/PIE,LLENENDO INTERIOR CADA 500 MTS POR LLEVAR VCP. OBSERVANDO PERDIDA PARCIAL A FORMACION DE 1.5 M3. WS= 77 TON *FLUIDO PERDIDO A FORMACION EN EL DIA: 1.5m3 *FLUIDO PERDIDO A FORMACION ACUMULADO EN LA ETAPA: 34.5m3 | 42.9 |  | 2019-12-19 09:21:36.000 | 164 | [5 empty] | 2019-10-21 15:00:00.000 | 2019-08-19 21:30:00.000 | 42.6509 | 7706.6932 | 2019-10-01 06:00:00.000 | 24 | 21.7917 | 42.3542 | 62.7292 | 38.2597 | 181.9583
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Teotleco 204 | 17.942 | -93.28 | TEOTLECO | Build & Hold | Desarrollo | 2019-09-05 22:00:00.000 | Mobilization-Drill | ICMA-883 | PERFORA CON BARRENA PDC 12 1/4" Y SARTA NAVEGABLE EQUIPADA CON MWD A 3930 M | PERFORAR CON BNA 12 1/4" Y SARTA NAVEGABLE EQUIPADO CON MWD @ 4500 M KOP, CIRCULAR, SACAR A SUPERFICIE PARA CAMBIO DE SARTA POR SARTA ROTATORIA. | CA68BAB420A4491D91F6E79EC41AD153 | (N) PERFORA CON BARRENA PDC 12 1/4" Y SARTA NAVEGABLE EQUIPADA CON MWD A 3765 M. RECORD: 265 M EN 21:30 HRS, PROMEDIO 4.87 MIN/M, 3ULT: 6-4-5 ROP= 12.4 M/H. CONDICIONES DE OPERACIÓN: PSB 7-8 TON, 90 + 83 (MF) = 173 MF RPM, TORQUE 6000-7800 LBS-PIE, Q=520 GPM, PB= 3850 PSI, DENSIDAD DE ENTRADA Y SALIDA 1.91 GR/CC. NOTA: SE BOMBEAN BACHES DE REFORZAMIENTO (15 KG/M3 OPTISEAL III + 5 KG/M3 DE CARBONATO MEDIO + 30 KG/M3 DE GRAFITO) CADA 100 M PERFORADOS. | 105.84 |  | 2019-12-19 20:06:00.000 | 154 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-09-05 22:00:00.000 | 0 | 15196.8509 | 2019-10-22 00:00:00.000 | 5.25 | 25.8333 | 46.0833 | 46.0833 | 11.3924 | 329.7689
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Kenora 1A | 18.2661 | -92.942 | Kenora | Horizontal | Exploratory | 2018-12-08 00:00:00.000 | Primary Drilling | IPC-506 | CAMBIO MANGUERA DE STAND PIPE + METIO A 4452 M + REBAJA CEMENTO CON BNA PDC 8 1/2" A 4595 M + CIRCULO LIMPIANDO POZO + EFECTUO SEGUNDA PRUEBA DE HERMETICIDAD + REALIZA DESPLAZAMIENTO DE FLUIDOS AVANCE 45% | REALIZAR CAMBIO DE FLUIDO + INSTALAR ELEMENTO SELLANTE EN CABEZA ROTATORIA + REBAJAR CEMENTO Y ZAPATA HASTA 4608 M. + PERFORAR HASTA VIDA UTIL DE BNA 8 1/2" ( 5838 M. ) | CA68BAB420A4491D91F6E79EC41AD153 | (N) PERSONAL DE CIA. IPC. CON APOYO DE GRUA DE 60 TONS. DE LA CIA. SERIESA, INSTALA RAMAPA DE TUBERIAS NOTA: SIENDO LAS 17:30 HORAS SE DA POR INICIADA LA ETAPA DE PERFORACION DE 8 1/2" | 138.18 |  | 2019-04-25 04:19:12.000 | 164 | [5 empty] | 2019-04-29 18:00:00.000 | 2018-12-08 00:00:00.000 | 164.042 | 16374.6724 | 2019-04-01 19:30:00.000 | 39.5625 | 80.75 | 114.8125 | 142.75 | 27.7145 | 142.621
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Terra 101 | 18.15 | -92.93 | TERRA | Deviated | J | 2019-10-09 00:00:00.000 | Primary Drilling | IPC-506 | CIRCULO HOMOGENIZANDO PESO DE LODO + REALIZO PRUEBA DE INTEGRIDAD + REBAJO CEMENTO A 963 M + REALIZO SEGUNDA PRUEBA DE INTEGRIDAD + PERFORO A 980 M + CIRCULO + PRUEBA FIT + PERFORA A 1067 M | PERFORAR A 2970 M | CA68BAB420A4491D91F6E79EC41AD153 | (N) PERSONAL DE OPN. CON APOYO DE IZADORA DE CIA. MATYEP, ARMO Y ESTIBO EN CHANGUERO 4 LINGADAS (12 TRAMOS) DE TP 5", °S-135, 19.5 LB/FT, CALIBRANDO SU INTERIOR CON 2 9/16" NOTA: CON ESTA FECHA Y HORARIO SE DAN POR INICIADAS LAS ACTIVIDADES DE LA SECCION DE 13 3/8" | 8.53 |  | 2019-10-17 12:43:12.000 | 260 | [5 empty] | 2019-10-21 15:00:00.000 | 2019-10-09 19:00:00.000 | 154.1995 | 4570.2101 | 2019-10-21 15:00:00.000 | 0.5625 | 8.0208 | 12.625 | 12.625 | 4.4554 | 361.9968
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Teotleco 106 | 17.936 | -93.3275 | TEOTLECO | Deviated | J | 2019-03-13 22:00:00.000 | Primary Drilling | PEMEX-305 | REBAJO CEMENTO Y ACCESORIOS HASTA 5565 MTS, CIRCULO POZO HASTA RETORNOS LIMPIOS REALIZO PRUEBA DE HERMETICIDAD DEL LINER DE 7". BIEN. REALIZO DESPLAZAMIENTO DE FLUIDO DE CONTROL DE 1.63 GR/CC. X 0.95 GR/CC. SACO BNA TRIC HASTA 3850 M | FINALIZAR DE DESMANTELAR UAP. SACAR BNA TRIC. DE 6 1/2" HASTA SUPERFICIE. | CA68BAB420A4491D91F6E79EC41AD153 | (N)** PERSONAL DE WS/SLB DESMANTELA LINEAS SUPERFICIALES Y UNIDAD DE ALTA PRESION CON UN AVANCE DEL 100% | 163.17 |  | 2019-08-23 04:04:48.000 | 137 | [5 empty] | 2019-08-17 08:00:00.000 | 2019-03-13 22:00:00.000 | 29.5276 | 19389.7644 | 2019-08-09 21:00:00.000 | 22.7917 | 105.1875 | 148.9583 | 156.4167 | 14.5711 | 130.169
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Teotleco-205 | 17.9428 | -93.28 | TEOTLECO | Deviated | Directional | 2019-04-06 23:00:00.000 | Primary Drilling | PEMEX-331 | LEVANTO BNA 8 1/2" A SUPERFICIE, CAMERON RECUPERO BUJE DE DESGASTE, INSTALO MALACATES LEVANTO PREVENTORES, RETIRO CARRETE ESPACIADOR SENTÓ PREVENTORES. REALIZA PRUEBA DE EQUIPO DE SUPERFICIE (TOP DRIVE / MANIFOLD DE BOMBAS). | PROBAR BOP, INSTALAR CABEZA ROTATORIA Y EQUIPO DE N2. ARMAR SARTA NAVEGABLE. | CA68BAB420A4491D91F6E79EC41AD153 | (N) AFLOJO TORNILLERIA DE CARRETE ESPACIADOR 13 5/8" 10 M. | 112.18 |  | 2019-07-27 04:19:12.000 | 160 | [5 empty] | 2019-08-19 19:00:00.000 | 2019-04-06 23:00:00.000 | 39.3701 | 17847.7696 | 2019-08-07 08:00:00.000 | 33.1875 | 87.2917 | 122.375 | 134.8333 | 24.6137 | 145.8449
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Samaria-4121 | 17.9723 | -93.0803 | Samaria | Deviated | J | 2018-04-05 14:00:00.000 | Primary Drilling | Pemex-1389 | SACO BNA TRIC 8 1/2" A SUPERFICIE, QUEBRANDO TXT. DESPEJO PISO, MIDIO Y CALIBRO DC Y HWDP. ARMO Y BAJO SARTA LISA CON BNA PDC 6-1/2" A 1685 M. ARMANDO TP 3-1/2" TXT. CONTINUO METIENDO A 1914 M, POR LING DE TP 5". | METER BNA PDC 6-1/2" Y SARTA LISA HASTA RECONCER P.I. A +/- 4169 M. PROBAR TR CON UAP A 1,800 PSI. REBAJAR CEMENTO HASTA +/-4220 M. PROBAR TR CON 1,800 PSI. DESPLAZAR FLUIDO DE 1.62 x 0.95 GR/CC. | CA68BAB420A4491D91F6E79EC41AD153 | METIO BNA PDC 6 1/2" Y SARTA LISA A 1685.8 M, ARMANDO TXT TP 3-1/2" (21 LING TP 3-1/2", G-105, 13.3# + 1 LING TP 3-1/2", G-105, 15.5# + 29 LING TP 3-1/2", S-135, 15.5#), LLENANDO POR INTERIOR Y ROMPIENDO CIRCULACIÓN CADA 500 M (30 EPM, 125 GPM, 750 PSI), CALIBRANDO POR INTERIOR CON 1.5". | 74.53 |  | 2018-06-18 12:43:12.000 | [6 empty] | 2018-07-03 07:30:00.000 | 2018-04-05 04:00:00.000 | 164.042 | 14612.8614 | 2018-06-19 18:00:00.000 | 11.8958 | 53.6875 | 75.1667 | 88.7292 | 13.4069 | 194.4061
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Quesqui 1DEL | 18 | -93 | Quesqui | Deviated | Exploratorio | 2019-08-07 00:00:00.000 | Primary Drilling | Pemex-1503 | METIO BNA PDC 12-1/4" A 3474 M, DONDE OBSERVO RESISTENCIA DE 5 TONS. CIRCULO POZO HOMOGENIZANDO COLUMNAS A 1.62 GR/CC. EFECTUO 1ER PRUEBA DE HERMETICIDAD A LA TR DE 13-3/8" x 13-5/8". REBAJO CEMENTO Y ACCESORIOS DE 3474 M A 3568 M. BOMBEO BACHE VISCOSO Y CIRCULO POZO HASTA RETORNOS LIMPIOS. EFECTUO 2DA PRUEBA DE HERMETICIDAD A LA TR DE 13-3/8" x 13-5/8". REBAJA CEMENTO A 3571 M. | REBAJAR ZAPATA 13-5/8" + PERFORAR 10 M DE FORMACION NUEVA. CIRCULAR PARA RECUPERAR MUESTRA DE FONDO. EFECTUAR PRUEBA DE GOTEO. PERFORAR 30 M DE FORMACION A 3618 M. EFECTUAR PRUEBA DE INTEGRIDAD DE FORMACION. | CA68BAB420A4491D91F6E79EC41AD153 | (N) CON BNA PDC 12-1/4" Y SARTA ROTATORIA (POWER DRIVE + L/MWD) REBAJO CEMENTO A 3571 M. CONDICIONES DE OPERACION: PSB 4-5 TON, 60 RPM, TQ 4000/8000 FT.LBS, 102 EPM, 495 GPM, PBBA 2350 PSI. FLUIDO DE CONTROL 1.62 GR/CC, S/W 151 TON. * CON ESTE HORARIO 23:30 HRS DEL 26 DE SEPTIEMBRE DE 2019 SE DAN POR INICIADAS LAS ACTIVIDADES DE PERFORACION DE LA ETAPA DE 12-1/4" - LINER DE 11-3/4". | 120.78 |  | 2019-12-05 18:43:12.000 | 164 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-08-07 00:00:00.000 | 52.4934 | 12795.276 | 2019-10-08 03:00:00.000 | 24.5313 | 44.0625 | 62.125 | 76 | 32.278 | 205.9602
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Quesqui-1 | 17.9458 | -93.6355 | JUJO | Deviated | Exploratorio | 2018-07-23 00:00:00.000 | Primary Drilling | Pemex-1503 | REBAJO CEMENTO Y ACCESORIOS HASTA 6256 M. PERFORA A 6269 M. | PERFORAR ETAPA DE 5 7/8 O VIDA DE BARRENA | CA68BAB420A4491D91F6E79EC41AD153 | CON BNA PDC 5 7/8 SARTA ROTATORIA PERFORA A 6268 M RECORD: 10 M, 4:26 HRS, P: 26.6 MIN/M, ULTIMOS 3: 22-14-18, CONDICIONES DE OPERACIÓN : 6/8 TON/BNA, 120 RPM, TORQUE : 6000/8000 FT/LB, EPM: 54, Q: 263 GPM , PBBA 3900 PSI , PESO DE LA SARTA 172 TON, DL: 1.35 GR/CC.** OBSERVA SALIR PEDACERIA DE HULE Y ALUMINIO** | 93.17 |  | 2018-10-24 03:57:36.000 | 164 | [5 empty] | 2019-04-01 01:30:00.000 | 2018-07-23 00:00:00.000 | 52.4934 | 23120.0795 | 2019-02-15 09:00:00.000 | 83.1562 | 165.4896 | 207.375 | 252.0625 | 32.9903 | 111.4892
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Teotleco 103 | 17.56 | -93.19 | TEOTLECO | Deviated | J | 2019-01-25 00:00:00.000 | Primary Drilling | Pemex-1603 | LEVANTO BNA TRIC 6.5" Y SARTA LISA DE 4200 M A 232 M POR LINGADAS, CONTINUO LEVANTANDO BNA TRIC 6.5" DESCONECTANDO COMPONENTES DEL BHA HASTA SUPERFICIE, NIVELES ESTABLES. RECUPERO BUJE DE DESGASTE, INSTALO PROBADOR DE COPAS Y REALIZO PUREBA DE CONJUNTO DE BOP'S Y CSC. EN INTER PERSONAL DEL SINDICATO REALIZA LAVADO DE PRESAS Y PERS DE MPD REALIZA ALINEACION DEL COMPONENTES DEL EQUIPO. | DESMANTELAR CAMPANA Y CHAROLA ECOLOGICA E INSTALAR CABEZA ROTATORIA, PROBAR MISMA. | CA68BAB420A4491D91F6E79EC41AD153 | (N) CON UPH No: 301 DE CIA AP-SIGMA PROBÓ CABEZAL, PREVENTORES DE ARIETES 13 5/8" 10-K Y LSC EN BAJA C/300 PSI EN ALTA C/8000 PSI, PROBÓ PREVENTOR ESFÉFRICO 13 5/8" 10-K EN BAJA C/300 EN ALTA C/6000 PSI. PROBÓ ENSAMBLE DE BOMBAS Y STAND-PIPE EN BAJA C/300, EN ALTA C/4500 PSI, PROBÓ EMSAMBLE DE .ESTRANGULACION C/300 EN BAJA Y 4000/8000 EN ALTA, DURANTE 30 MIN CADA PRUEBA BIEN. EN INTER PERSONAL DE CIA SLB REALIZA LAVADO DE PRESAS DE TRABAJO AVANCE 85% PERSONAL DE CIA SLB INSTALA EQUIPO MPD AVANCE 10% | 165.04 |  | 2019-07-09 01:00:00.000 | 146 | [5 empty] | 2019-06-12 09:00:00.000 | 2019-01-25 00:00:00.000 | 49.2126 | 18536.746 | 2019-06-09 00:00:00.000 | 12.1875 | 88.1458 | 135 | 138.375 | 8.8076 | 137.3092
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Madrefil-64 | 18.162 | -93.3183 | CUNDUACAN | Deviated | Pozo de Desarrollo Terrestre Direcional | 2018-03-21 15:00:00.000 | Primary Drilling | Pemex-2005 | ARMO Y BAJO SONDA MEST-PPC-HNGT (IMAGEN RESISTIVA -GEOMETRA DE POZO-CALIPER DE 4 BRAZOS-ESPECTROSCOPIA DE GR) BAJANDO A 6450MD Y TOMANDO SECCION REPETIDA A 6350MD Y SECCION PRINDIPAL DE 6450MD A 6225MD. LEVANTA SONDA A SUPERFICIE Y ELIMINA MISMA ARMO SONDA AIT-RG (ARREGLO INDUCTIVO CON CALIPER DE 4 BRAZOS RAYOS GAMMA) A 6450 MTS FONDO PERFORADO LIBRE, TOMA REGISTRO EN SECCION REPETIDA DE 6450 A 6350 MTS. TOMO REGISTRO PRINCIPAL DE 6450M A 6220M Y LEVANTO LIBRE A SUPERFICIE ELIMINO SONDA AIT-RG Y ELIMINO ECP Y U.R.E. + PERSONAL PDM INSTAKLO BALERO Y CAMPANA DE VIAJES PERSONAL DE PPS REALIZA ORDEN Y LIMPIEZA ARMA NIPLE AGUJA+VCP+ESCAREADOR+TPHW+MARTILLO+TPHW A 149M |  | CA68BAB420A4491D91F6E79EC41AD153 | CON CARGO A CIA SCHLUMBERGER POR FALLA EN SONDA DE REGISTRO AIT (INDUCCION) 7 HORAS ACUMULADAS METIO CUARTA CORRIDA DE REGISTROS AIT-RG (ARREGLO INDUCTIVO CON CALIPER DE 4 BRAZOS RAYOS GAMMA) A 6450 MTS FONDO PERFORADO LIBRE, TOMA REGISTRO EN SECCION REPETIDA DE 6450 A 6350 MTS, BAJO A FONDO PERFORADO LIBRE Y LEVANTO REGISTRANDO SECCION PRINCIPAL DE 6450 A 6225 MTS VELOCIDAD 1300 PIES/HORA POSTERIOR CONTINUO LEVANTANDO A SUPERFICIE A UNA VELOCIDAD DE 14000 PIES/HORA CON UNA TENSION DE 3400 LBS | 215.5 |  | 2018-10-22 12:00:00.000 | 110.4 |  | 20181126214106 |  |  |  | 2018-11-16 00:00:00.000 | 2018-03-21 15:00:00.000 | 0 | 21161.418 | 2018-10-13 01:00:00.000 | 89.1875 | 160.4375 | 205.4167 | 239.375 | 37.2585 | 103.017
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Jolote 61 | 18.0089 | -93.2958 | JUJO | Build & Hold | J | 2018-07-08 18:00:00.000 | Primary Drilling | Pemex-206 | PERFORA CON BNA. PDC 5 7/8" Y SARTA ROTATORIA A 4942 M, BBEO 9 M3, DE BACHE VISCOSO, CIRCULO, DONDE SUSPENDIÓ POR FALLA DE GENERADOR, REPARO GENERADOR, CONTINUO CIRCULANDO, CONTINUA PERFORANDO A 4953 M. | PERFORAR CON BNA. PDC 5 7/8" Y SARTA ROTATORIA A 5480 M. | CA68BAB420A4491D91F6E79EC41AD153 | CON BNA PDC 5 7/8" T- MDSI713 No. SERIE JK5918 IADC M433, TOBERAS (1 (9/32"), 5 (8/32"), 1 (CIEGA)) TFA= 0.308 + SARTA ROTATORIA, EQUIPADA CON LWD/MWD CIA SLB, 4942 MTS OPERACIÓN SUSPENDIDA CON CARGO A MMTO, PPS CON 2 HRS ACUMULADAS POR FALLA DE GENERADOR 1-3 EN EL INTER PERSONAL DE MMTO CORRIGIÓ FALLA, SIMULTÁNEAMENTE, SE MANTUVO LA SARTA DURANTE 60 MINUTOS SIN CIRCULACIÓN, MANTENIENDO CON ROTACION DEL TOP DRIVE, 10 RPM TORQUE DE 1000 L/P, SE RESTABLECE UN GENERADOR Y CIRCULO CON BAJO GASTO 25 EPM 104 GPM 1700 PSI 10 RPM 1000 P/L TORQUE | 160.13 |  | 2018-12-15 03:07:12.000 | 164 |  | 20181222004113 |  |  |  | 2019-03-14 14:00:00.000 | 2018-07-08 00:00:00.000 | 164.042 | 18645.0137 | 2019-03-02 02:30:00.000 | 71.8958 | 181.1667 | 236.3542 | 248.8333 | 28.8932 | 78.8859
WH | MCA | Mexico | CA68BAB420A4491D91F6E79EC41AD153 | 879 | 200000000000000001252017 | MCA Integrados Mesozoico AFE | IDS | MCA | AFE Assurance | Terra-144 | 18.222 | -92.946 | TERRA | Build & Hold | Direccional tipo J | 2018-06-14 00:00:00.000 | Primary Drilling | Pemex-341 | REALIZO PRUEBA DE HERMETICIDAD DE LINER 7" SOBRE COPLE FLOTADOR. BIEN. REBAJO COPLE FLOTADOR Y CEMENTO HASTA 4564 M. CIRCULO HASTA RETORNOS LIMPIOS. PROBO HERMETICIDAD DE LINER 7". BIEN. RETIRO CAMPANA E INSTALO CHUPON. REALIZA TOMA DE PARAMETROS CON ROTACION, CIRCULACION. PESOS. FLUJO Y LLENA SEPARADOR. PERFORA A LA PROFUNDIDAD DE 4595 M. | PERFORAR AGUJERO 5 7/8" DE ACUERDO A PROGRAMA A 4730 M. | CA68BAB420A4491D91F6E79EC41AD153 | CON BNA PDC 5 7/8" Y SARTA ROTATORIA PERFORA A 4576 M RECORD: 4 M EN 00:57 MIN ULT: 14 , 12 , 15 , CONDICIONES DE OPERACIÓN S/BNA 4/6 TON 60 RPM TORQUE: 5000/9000 FT/LB EPM: 65 Q: 230 GPM P/BBA: 1800 PSI W/SARTA: 165 TON | 201.29 |  | 2019-01-01 06:57:36.000 | 150.88 | [5 empty] | 2018-11-24 15:30:00.000 | 2018-06-14 00:00:00.000 | 0 | 16643.7013 | 2018-09-04 01:30:00.000 | 21.1458 | 55.8333 | 82.0625 | 163.6458 | 12.9217 | 202.8174
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Cibix 1001 EXP | 18 | -93 | Cibix | Deviated | S | 2019-08-21 20:00:00.000 | Primary Drilling | ICMA-875 | PERFORA A 4181 M. SUSPENDE PERFORACION, CIRCULA PARA RECUPERAR MUESTRA, SE PROGRAMA CORTE DE NUCLEO | VIAJE CORTO A ZAPATA DE 9 5/8", SACAR A SUPERFICIE, METER CORONA Y BARRIL PARA CORTE DE NUCLEO. | 6D2105BD3737474B92E7290101E25255 | PERFORO CON BNA PDC DE 8 1/2" Y SISTEMA ROTATORIO EQUIPADO CON MWD Y LWD TUMBANDO ANGULO A PROF. 4147 M. RECORD; 447 M. EN 20:47 MIN. U/3.-2-3-3 MIN. C/U.; ROP 21.58 MTS/HRS. PROM=2.78 MIN/M. CONDICIONES: P/BNA=2-4 TON. ROT=150 RPM; TORQ=9000/11000 L/P; 160 EMB; Q= 515 GPM; PB= 4050 PSI. LODO DE 1.41 GR/CC X 76 SEG.; W/SARTA WE=120 , WS= 120 , WB= 115 TON. PRC @ 4134 M. BBA1 = 40 EPM - 550 PSI, PRC BBA2 = 40 EPM - 550 PSI. SUSPENDE PARA RECUPERAR MUESTRA DE FONDO. | 67.7 |  | 2019-10-27 16:48:00.000 | 164 | [5 empty] | 2019-10-21 15:00:00.000 | 2019-08-21 20:00:00.000 | 114.8294 | 15078.7406 | 2019-10-18 20:00:00.000 | 12.75 | 42.8333 | 58 | 60.7917 | 20.9733 | 259.9783
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Tokal 101 | 18 | -93 | TOKAL | S Shaped | Exploratorio | 2019-05-06 00:00:00.000 | Primary Drilling | ICMA-875 | REBAJO CEMENTO A 3415 MTS EFECTUO SEGUNDA PRUEBA DE PRESION A TR SATISFACTORIAMENTE LIMPIO CEMENTO HASTA 3425 MTS PERFORO A 3430 MTS. EFECTUO PRUEBA DE GOTEO A 2.24 GR/CC PERFORO A 3468 MTS | PERFORAR A 3600 MTS SACAR PARA CORTE DE NUCLEO | 6D2105BD3737474B92E7290101E25255 | CON BNA PDC DE 81/2 SARTA ROTATORIA EQ. CON MWD Y LWD A 3420 M. PNAL DE CIA SCHLUMBERGER Y OPERACIÓN INSTALO ELEMENTO SELLANTE EN CABEZA ROTATORIA 100% | 68.65 |  | 2019-08-30 21:35:31.000 | 198 | [5 empty] | 2019-07-06 14:00:00.000 | 2019-05-06 00:00:00.000 | 0 | 14845.801 | 2019-07-04 13:30:00.000 | 8.25 | 42.4375 | 59.5625 | 61.5833 | 13.3965 | 249.2474
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Castarrical 12T - 5in ST | 18.396 | -93.3132 | Castarrical | Build & Hold | Desarrollo | 2019-09-20 00:00:00.000 | Primary Drilling | Pemex-1381 | CON TR DE 7"- 29 #/PIE- L80- BCN CEMENTADA A 2942.75 M, Y CON POZO CERRADO, ABRIO POZO SIN OBSERVAR ESCURRIMIENTO, INSTALO ENSAMBRE DE SELLOS Y PROBO MISMOS, INSTALO GAFAS E=AL TOPDRIVE Y ELIMINO TXT HWDP 5" DEL PISO DE TRABAJO, ARMO TXT HERRAMIENTAS 4 3/4" Y HWDP 3 1/2" AL CHANGUERO | METER BNA 6" C/SARTA LISA A RECONOCER CIMA DE TAPONES DE DESPLAZAMIENTO+REBAJAR Y PROBAR HEMETICIDAD DE TR+REBAJAR CEMENTO HASTA 5 M ARRIBA DE LA ZAPATA+CIRCULAR A LIMPIAR POZO+SACAR BNA A SUPERFICIE ELIMINANDO TP T x T. | 6D2105BD3737474B92E7290101E25255 | CON TR DE 7"- 29 #/PIE- L80- BCN CEMENTADA A 2942.75 M, Y CON POZO CERRADO ALINEADO AL MULTIPLE DE ESTRANGULACION ESPERO FRAGUADO 12 DE 12 HRS PROGRAMADAS Y MONITOREA PRESIONES. PTP= 0.- PTR= 50 NOTA: DURANTE LA CEMENTACIÓN DE TR 7” SE OBSERVA CIRCULACIÓN PARCIAL OBSERVANDO UNA PÉRDIDA DE 11 M3 DE FLUIDO DE E.I. DE 1.30 GR/CC. SE DERIVAN 3 M3 DE FLUIDO CONTAMINADO CON BACHES DE CEMENTACIÓN. SE DEJAN ABANDONADOS 13.12 M3 DE FLUIDO DE EMULSIÓN INVERSA DE 1.30 GR/CC DE 3434 M A 3040 M. FLUIDO PERDIDO A FORMACIÓN EN EL DÍA = 11 M3 FLUIDO PERDIDO A FORMACIÓN ACUMULADO = 488.89 M3 CONSUMOS DE MATERIALES OBTURANTES: FORM A BLOCK ACUMULADO: 2471.5 KG (170 SACOS) CACO3 ACUMULADO 1550 KG (31 SACOS) OPTISEAL IV ACUMULADO 2450 KG (98 SACOS) MAGMA FIBER FINO ACUMULADO 965 KG (85 SCS). SAFE CARB 250 ACUMULADO 886 KG (39 SACOS) SAFE ACUMULADO 500 KG (22 SACOS) SAFE CARB 750 ACUMULADO 886 KG (39 SACOS) | 26.31 |  | 2019-10-25 07:26:24.000 | 624 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-09-29 15:30:00.000 | 9691.6014 | 11482.94 | 2019-10-15 05:00:00.000 | 8.75 | 12.6875 | 25.2083 | 32 | 27.3438 | 455.5216
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Castarrical-12T | 18.396 | -93.3132 | Castarrical | Build & Hold | Desarrollo | 2019-08-22 21:00:00.000 | Primary Drilling | Pemex-1381 | REALIZO INSTALACION DE ORING NUEVO PARA TUERCA UNION DE CUELLO DE GANSO. PROBO CON 3800 PSI, BIEN, BAJO BNA PDC 8 3/4" BAJO HASTA 2030 M LIBRE, PERSONAL D&M ENVIO COMANDOS A HTAS DIRECCIONAL, PERFORO CONSTRUYENDO Y MANTENIENDO RUMBO DE 2030 A 2269 M. | CON BNA PDC 8 3/4" Y SARTA ROTATORIA PERFORAR DE ACUERDO A PROGRAMA HASTA 3927 M. | 6D2105BD3737474B92E7290101E25255 | (TPEP/TPPS) CON BNA PDC 8 3/4" Y SARTA ROTATORIA EQUIPADA CON POWER DRIVE + LWD+MWD A 989 M,CON PERSONAL MECANICO DE PISO "CASTAÑO" INSTALO ORRING A UNION DEL CUELLO DE GANSO DEL TOP DRIVE, PROBO MISMO CON 3800 PSI BIEN. | 28.91 |  | 2019-09-19 21:50:24.000 | 711 |  | 20190919192648 |  |  |  | 2019-09-29 15:30:00.000 | 2019-08-22 21:00:00.000 | 164.042 | 11266.4046 | 2019-09-24 09:00:00.000 | 18.9792 | 24.8125 | 32.5 | 37.7708 | 50.2482 | 346.6586
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Rabasa-218 | 18.141 | -94.201 | Rabasa | Deviated | Desarrollo | 2017-11-27 00:00:00.000 | Primary Drilling | Pemex-1383 | PERFORO ZAPATA Y 10 M NUEVA FORMACION, CIRCULO, REALIZO PRUEBA INTEGRIDAD PARA UN EQUIVALENTE DE 1.65 GR/CC, PERFORO HASTA 1927 M. | PERFORAR CON BNA PDC 8 3/4" DE ACUERDO A PROGRAMA HASTA 3490 M EN MD | 6D2105BD3737474B92E7290101E25255 | CON BARRENA PDC 8 3/4" CON SARTA NAVEGABLE EQUIPADA CON MF, LWD, MWD PERFORO DE 1110 M A 1927 M, CON PSBNA=1-3 TONS, RPM=60-80, TORQUE=1500-4000 PIE/LB, EPM=108, GPM=450, PSI=2000-2580. RECORD DE BARRENA: 827 M CORTADOS EN 11 HR, 24 MIN, PROMEDIO 0.82 MIN/M. 04 M DESLIZADOS EN O HR 24 MIN, PROMEDIO 6 MIN/M, U6M=6-6-6 MIN. 823 M ROTADOS EN 11 HR 00 MIN, PROMEDIO 0.80 MIN/M, U3M=1-1-1 MIN. NOTA: BOMBEO 3 BACHES DE 4 M3 C/U CON 200 SEG DE VISCOSIDAD PARA REFORZAR LIMPIEZA DE HOYO + 7 BACHES DE 4 M3 C/U DE CONCENTRACION 40 KG/M3 DE CaCO3 (20 KG/M3 DE M-200+20 KG/M3 DE M-70) PARA REFORZAR AGUJERO. | 33.67 |  | 2018-01-06 16:10:41.000 | [6 empty] | 2018-01-09 19:00:00.000 | 2017-12-04 00:00:00.000 | 0 | 11450.1316 | 2017-12-23 00:30:00.000 | 7.125 | 12.7292 | 26.0208 | 43.7917 | 16.2702 | 440.0371
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | San Ramon 1626 | 18.245 | -93.899 | San Ramon | S Shaped | Desarrollo | 2018-04-12 00:00:00.000 | Primary Drilling | Pemex-1384 | ARMA LINGADAS DE TP 5" MIDIENDO, CALIBRANDO Y ESTIBANDO EN CHANGUERO. ARMA Y CONECTA BNA PDC 8 3/4" A POWER DRIVE Y REALIZA PRUEBA DE FUNCIONALIDAD DEL PD CON ÉXITO. CONTINUA ARMANDO SARTA DIRECCIONAL Y BAJA A 500 M, DONDE PROBO MWD Y LWD. BAJO BNA PDC 8 3/4" Y SARTA DIRECCIONAL A 950 M DONDE RECONOCIÓ TAPONES Y CIRCULO PARA HOMOGENEIZAR COLUMNAS. REALIZO PRUEBA DE INTEGRIDAD DE LA TR 9 5/8". REBAJO TAPONES Y CEMENTO. PERFORO A 1005 M. | PERFORAR CON BNA PDC 8 3/4" Y SARTA DIRECCIONAL A 1020 M. LEVANTAR Y CIRCULAR SARTA A 1000M. REALIZAR PRUEBA DE GOTEO. CONTINUAR CON LA PERFORACION A 2000 M. | 6D2105BD3737474B92E7290101E25255 | PNAL DE OPERACIÓN PPS BAJO SUPERVISIÓN DE CÍA. SLB CONTINUÓ ARMANDO LA SARTA A 500 M; BARRENA PDC DE 8 3/4" + POWER DRIVE 675 X6 DA DE 8 3/4" CON CAMISA LISA + RECEIVER ESTABILIZADO DE 8 5/8" CON VCP + LWD ARC675 (RES / GR) + MWD TELESCOPE 675 (DIRECCIÓN E INCLINACIÓN) + DC MONEL DE 6¾" + 15 TRAMOS DE HW DE 5" 50 LB/FT + MARTILLO HIDRÁULICO DE 6½" + 15 TRAMOS DE HW DE 5" 50 LB/FT + TP DE 5” °G-105 19.5 LB/FT. | 27 |  | 2018-05-26 23:54:14.000 | [6 empty] | 2018-05-27 22:00:00.000 | 2018-04-30 00:00:00.000 | 114.8294 | 10236.2208 | 2018-05-11 12:00:00.000 | 1.7292 | 7.1875 | 29.5 | 45.9167 | 3.7659 | 346.9905
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Cinco Presidentes 939 | 18.146 | -94.037 | Cinco Presidentes | Deviated | J | 2018-06-05 08:00:00.000 | Primary Drilling | Pemex-1481 | ARMO 38 LINGADAS DE 44 DE TP 4 XT-39. ESPERO POR ARRIBO DE CUADRILLA DEBIDO A CIERRE POR CONFLICTO CAMPESINO. ARMO COMPLEMENTO DE LINGADAS, ARMO SARTA DIRECCIONAL CON BNA 8 3/4 CON PD. BAJO SARTA A 197 M. | BAJAR BNA PDC 8 3/4 H +/- 1080 M, CIRCULAR, REALIZAR 1ER PRUEBA DE INTEGRIDAD A TR 9 5/8, REBAJAR TAPONES, COPLE Y 1/2 ST. CIRCULAR Y REALIZAR 2DA PRUEBA DE INTEGRIDAD A TR. | 6D2105BD3737474B92E7290101E25255 | CON TR 9 5/8" CEMENTADA A 1097 M, EN PRESENCIA DE PERSONAL DE LA CIA SLB, PERSONAL DE OPERACIÓN ARMO SARTA NAVEGABLE AGRAGANDO SISTEMA DE TRANSMISION CON VCP, SEGUIDO LWD DE 6 3/4", MAS MWD 6 3/4", MAS DC MONEL DE 6 3/4", MAS FILTRO DE FONDO DE 6 3/4" Y METIO A 30.68 M. | 29 |  | 2018-07-04 00:00:00.000 | [6 empty] | 2018-06-28 07:00:00.000 | 2018-06-05 17:00:00.000 | 157.4803 | 9517.7168 | 2018-06-18 10:00:00.000 | 1.3542 | 6.9583 | 13.0833 | 22.9583 | 5.8984 | 727.4688
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Cinco Presidentes 959 | 18.1466 | -94.0368 |  | S Shaped |  | 2018-09-11 00:00:00.000 | Primary Drilling | Pemex-1481 | REBAJO CEMENTO A 1293 M. CIRCULO. REALIZO SEGUNDA PRUEBA A TR. REBAJO CEMENTO Y ZAPATA HASTA 1300 M, PERFORO HASTA 1321 M, CIRCULO, INSTALO UAP Y LINEAS, REALIZO PRUEBA DE GOTEO, DESMANTELO EQUIPO. PERFORO CON BNA PDC 8 3/4" CON PD+MWD+LWD HASTA 1895 M | PERFORAR A 2300 MTS + CIRCULAR + VIAJE CORTO A 1300 MTS + PERFORAR A 3629 MTS. | 6D2105BD3737474B92E7290101E25255 | (N) INSTALO UNIDAD DE ALTA Y LINEAS DE WS-SLB PARA REALIZAR PRUEBA DE GOTEO. LEVANTO BNA A ZAPATA 9 5/8" (1300 M). PROBO LINEAS CON 1300 PSI. BIEN. | 28.11 |  | 2018-10-09 02:38:24.000 | [6 empty] | 2018-10-09 14:00:00.000 | 2018-09-11 00:00:00.000 | 154.1995 | 11906.1684 | 2018-10-08 08:00:00.000 | 1.5625 | 21.2083 | 27.3333 | 28.5833 | 5.4665 | 435.5915
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Brillante 202 | 18.1562 | -94.2718 | Brillante | Deviated | Development | 2019-07-01 00:00:00.000 | Primary Drilling | Pemex-324 | INSTALO UNIDADES DE CEMENTACION & LINEAS, BAJO SARTA COMBINADA DE 3-1/2" & 5" A 1980 MTS. + ROMPIO CIRCULACION + COLOCO BACHE DE SOPORTE DE 1980 A 1580 MTS. LEVANTO SARTA LISA A 1780 MTS Y DESCABEZO BACHE + CIRCULO HASTA COLUMNAS HOMOGENEAS A 1.60 GR/CC + EFECTUO COLOCACION DE TXC + LEVANTO SARTA A 1000 MTS Y ESPERA FRAGUADO. | CON EXTREMO DE TP 3 1/2" A 1000 M, ESPERAR 24 HRS PROGRAMADAS DE FRAGUADO DE TXC. + ARMAR Y BAJAR BARRENA 8 3/4" A 1580 M (CIMA DE TXC), PROBAR CON 2000 PSI + SACAR BNA 8 3/4" A SUPERFICIE + ARMAR Y BAJAR ESCARIADOR PARA TR 9 5/8" A 1100 M + TOMAR REGISTRO CBL-VDL | 6D2105BD3737474B92E7290101E25255 | (N) EFECTUO PLATICA DE SEGURIDAD Y OPERACIÓN A REALIZAR CON PERSONAL DE PEMEX Y SLB, + CONECTO LINEAS DE UAP A BOTELLA DE CIRCULACION, | 36.94 |  | 2019-09-20 13:31:12.000 | 440 | [5 empty] | 2019-08-23 16:00:00.000 | 2019-07-01 00:00:00.000 | 141.0761 | 12467.192 | 2019-08-10 04:00:00.000 | 9.9583 | 25.0417 | 40.1667 | 53.6667 | 18.5559 | 310.3865
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Puerto Ceiba 103B | 18.4383 | -93.2157 | Puerto Ceiba | Horizontal | Development | 2019-04-06 00:00:00.000 | Primary Drilling | Pemex-335 | CON BNA. PDC A 4698 M, CIRCULO, PERSONAL DE MEXOIL REALIZA MANTENIMIENTO A TOP DRIVE, LEVANTA A SUPERFICIE, CONECTO BNA. PDC 4 1/8", BAJA A 29 M. | ARMAR SARTA CON BNA. PDC 4 1/8" CON ESCARIAR TR 7" BAJAR HASTA 5309 M, LEVANTAR A SUPERFICIE. | 6D2105BD3737474B92E7290101E25255 | (N) CON BNA. PDC 5 7/8" Y SARTA LISA A 4698 M, PERSONAL DE CIA. MEXOIL REALIZA MANTENIMIENTO A TOP DRIVE. | 90.36 |  | 2019-07-05 08:38:24.000 | 217 | [5 empty] | 2019-07-05 22:00:00.000 | 2019-04-06 00:00:00.000 | 164.042 | 17844.4888 | 2019-06-23 11:30:00.000 | 23.4583 | 56.25 | 78.4792 | 90.9167 | 25.802 | 227.3787
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Puerto Ceiba 137B | 18.4378 | -93.2157 | PUERTO CEIBA | Horizontal | Development | 2019-03-16 20:00:00.000 | Primary Drilling | Pemex-336 | CON BNA PDC DE 5 7/8" + SARTA LISA REBAJO ACCESORIOS Y CEMENTO DESDE 4806 M A 4816 M, CIRCULO A RETORNOS LIMPIOS, REALIZO REUNIÓN DE SEGURIDAD Y PREOPERATIVA, REALIZO 2DA PRUEBA DE INTEGRIDAD DE LINER DE 7", BIEN. REBAJO CEMENTO Y ACCESORIOS DE 4816 M A 4821 M, PERFORO DE 4821 M A 4826 M, CIRCULO A RETORNOS LIMPIOS, SACA BNA PDC DE 5 7/8" A 1240 M. | SACAR BNA PDC 5 7/8" Y SARTA LISA A 500 M + CAMBIAR UNIFLEX DEL TOP DRIVE POR PROGRAMA + CONTINUAR SACANDO BNA Y SARTA LISA A SUPERFICIE + ARMAR Y BAJAR BNA PDC 5 7/8" Y SARTA ROTATORIA A F. PERF. 4826 M + PERFORAR A +/- 5430 M. | 6D2105BD3737474B92E7290101E25255 | CON BNA PDC 5 7/8" Y SARTA LISA PERFORO DE 4821 A 4826 M. COND. DE OPN: P.S.B, 4-6 TONS. 70 R.P.M. TORQ. 3000-4000 LB - FT. 38 EPM. Q= 160 GPM. PB. 2300 PSI. WS. 115 TONS. F.C. E.I. 1.95 GR/CC X 88 SEG, RECORD: 5 M. EN 01:16 HRS. PROM. 15.20 MIN/MTS. 3 ULT. 15-17-16. | 78.83 |  | 2019-06-02 19:55:12.000 | 271 | [5 empty] | 2019-06-24 05:30:00.000 | 2019-03-16 20:00:00.000 | 164.042 | 16912.7302 | 2019-06-03 09:00:00.000 | 20.8333 | 58.3333 | 78.5417 | 99.3958 | 20.96 | 215.3345
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Samaria 734 | 18.0028 | -93.0876 | Samaria | S Shaped | Desarrollo | 2018-10-29 00:00:00.000 | Primary Drilling | Pemex-9112 | CIRCULA POZO A HOMOGENIZAR COLUMNAS, A 501 M REALIZA PRUEBA DE HERMETICIDAD DE TR 9 5/8", BIEN, FINALIZA ETAPA 9 5/8" E INICIA ETAPA 7", REBAJA CEMENTO DE 501 M A 506 M, PERFORA CON BNA PDC 8 1/2" DE 506 M A 965M. | PERFORAR SEGUN PRGRAMA A 1580 MTS | 6D2105BD3737474B92E7290101E25255 | CON BNA PDC 8 1/2" + SARTA DIRECCIONAL EQUIPADA CON POWER DRIVE + LWD + MWD, REBAJA CEMENTO DE 501M A 506M Y ZAPATA GUIA PARA TR 9 5/8". CON Q: 540 GPM, PBBA: 2150 PSI, 80 RPM, TQ: 70-90 PSI, PSB: 2-4 TON RECORD: 30 MTS EN 02:19 HRS, U3M 1-1-7, 12.95 MTS/HR * OBSERVA SALIR CEMENTO POCO CONSISTENTE | 13.8 |  | 2018-11-11 19:12:00.000 | [6 empty] | 2018-11-26 00:00:00.000 | 2018-10-29 00:00:00.000 | 108.2677 | 5200.1314 | 2018-11-15 06:30:00.000 | 10.4375 | 13.3333 | 17.2708 | 28 | 37.2768 | 301.0933
WH | MCA | Mexico | 6D2105BD3737474B92E7290101E25255 | 922 | 475536 | MCA Integrados Terciario AFE | IDS | MCA | AFE Assurance | Samaria-733 | 17.59 | -93.05 | Samaria | Deviated | Desarrollo | 2018-08-06 12:30:00.000 | Primary Drilling | Pemex-9112 | CON BNA PDC 8 1/2" Y SARTA ROTATORIA ESTACIONADA A 488 M. PERSONAL DE MANTTO. DESMANTELO MOTOR C.I. #1 DEL MALACATE PRINCIPAL AL 100%. REALIZO REEMPLAZO DE MOTOR AL 100%. BAJO BNA Y SARTA A 892 M. PERFORO HASTA 902 M, SUSPENDE POR ROMPERSE BANDA EN MOTOR C.I. # 1 DEL MALACATE. CIRCULO Y LEVANTO A 488 M. REALIZO REEMPLAZO DE BANDA, PROBO MISMA SIN EXITO, POR OBSERVAR JUEGO EN FLECHA DE VENTILADOR. DESINSTALO VENTILADOR. | CAMBIAR BANDA DE MOTOR DE MALACATE Y PROBAR AL 100%.. BAJAR A F. PERFORADO 902 M. PERFORAR A 1589 M CON BNA PDC 8 1/2" Y SARTA ROTATORIA EQ. CON PD+ L/MWD DE ACUERDO A PROGRAMA. CIRCULAR LIMPIANDO POZO + VIAJE CORTO A 900 M. + METER A F. PERFORADO 1589 M. CIRCULAR. SACAR A SUPERFICIE. | 6D2105BD3737474B92E7290101E25255 | (TPPS) BAJO BNA PDC. 8 1/2" Y SARTA ROTATORIA EQUIPADA CON L/MWD A FONDO PERFORADO 892 M. LIBRE. OBSERVO DESPLAZAMIENTO NORMAL. HORAS ACUMULADAS POR EVENTO DE MOTOR DE MALACATE (INICIO A LAS 18.30 HRS DIA 13-AGOSTO-2018)=5.5 HRS DIA 13-AGOSTO-2018 + 18 HRS DIA 14-AGOSTO-2018= 23.5 HRS. | 10.17 |  | 2018-08-16 04:00:00.000 |  |  | 20180814063803 |  |  |  | 2018-08-22 02:00:00.000 | 2018-08-06 12:30:00.000 | 108.2677 | 5265.7482 | 2018-08-18 18:30:00.000 | 2.2917 | 8.8333 | 12.25 | 15.5625 | 14.7256 | 429.857
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Constituciones 1119 | 22.47 | -97.92 | Constituciones | Deviated |  | 2019-09-26 00:00:00.000 | Primary Drilling | Olimpia-884 | ARMO Y BAJO BNA PDC 6/4" Y BHA DIRECCIONAL EQUIPADO MOTOR DE FONDO A 1086 M (PI), PROBO TR 7 5/8" CON 1000 PSI DURANTE 15 MIN, REBAJO ACCESORIOS Y CEMENTO. PROBO TR 7 5/8" CON 1000 PSI DURANTE 15 MIN. REBAJO CEMENTO Y ZAPATA Y PERFORAR HASTA 1123 M. REALIZO FIT. PERFORA ROTANDO Y DESLIZANDO A 1394 M. | PERFORAR ETAPA DE 6 3/4" HASTA 1650 M, DE ACUERDO A PROGRAMA. | 5330C03904E04C80A9E81066BC68FD7A | REALIZO SIMULACRO DE CONTROL DE BROTE Y PRESENCIA DE H2S, CUADRILLA REALIZO PROCEDIMIENTO DE CIERRE DE POZO. | 14.92 |  | 2019-10-13 22:04:48.000 | 494 | [5 empty] | 2019-10-09 20:00:00.000 | 2019-09-29 08:30:00.000 | 26.2467 | 5403.5435 | 2019-10-07 16:30:00.000 | 2.9167 | 5.4375 | 11.6875 | 13.8333 | 21.0843 | 462.3353
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Constituciones 1175 | 22.47 | -97.92 | Constituciones | Deviated | Desarrollo | 2019-08-16 06:00:00.000 | Primary Drilling | Olimpia-884 | PERFORO ETAPA DE 6 3/4" HASTA 1632 M. CIRCULO HASTA OBTENER RETORNOS LIMPIOS. BOMBEO BACHE ANTIPERDIDA. SACO BNA A SUPERFICIE. TOMA REGISTRO AIT-BHC-LDL-CNL-GR. | TOMAR REGISTROS ELECTRICOS SEGUN PROGRAMA. BAJAR Y CEMENTAR TR DE 5 1/2", N-80, 17#, BCN A 1632 M. | 5330C03904E04C80A9E81066BC68FD7A | REALIZO ORDEN Y LIMPIEZA EN EL PISO DE TRABAJO. | 15.91 |  | 2019-09-14 21:50:24.000 | 489 | [5 empty] | 2019-09-09 10:00:00.000 | 2019-08-30 18:00:00.000 | 26.2467 | 5354.3309 | 2019-09-07 05:00:00.000 | 0.47917 | 3.9167 | 21.9583 | 24.1667 | 1.9828 | 243.8405
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Constituciones 1193 | 22.47 | -97.92 | Constituciones | Deviated | Desarrollo | 2019-09-15 12:30:00.000 | Primary Drilling | Olimpia-884 | PERFORO ETAPA DE 6 3/4", HASTA 1606 M. CIRCULO HASTA RETORNOS LIMPIOS, REALIZO VIAJE DE CALIBRACIÓN HASTA 1100 M, VERIFICO POZO ESTÁTICO | BAJAR A PROFUNDIDAD OBJETIVO, BOMBEAR Y DESPLAZAR TREN DE BACHES. CIRCULAR HASTA RETORNOS LIMPIOS. BOMBEAR BACHE OBTURANTE Y SACAR BNA PDC 6 3/4" + SARTA DIRECCIONAL A SUPERFICIE. REALIZAR REGISTROS ELÉCTRICOS. | 5330C03904E04C80A9E81066BC68FD7A | PERFORO ROTANDO Y DESLIZANDO CON BNA PDC 6 3/4" Y SARTA DIRECCIONAL EQUIPADA CON MOTOR DE FONDO Y MWD DE 1118 M A 1251 M. CON 250 - 260 GPM, 1800 - 1900 PSI, PRESION DIFERENCIAL: 500 - 550. PSB: 3 - 5 TON, TORQUE 2500 - 3500 FT/LBS RECORD DE BNA: 138 M EN 5.5 HRS, ROP: 25.9 M/HR. U3M: 1-1-1. ROTADOS: 109.35 M EN 2.37 HRS, ROP: 46.1 M/HRS. U3M: 1-1-1. DESLIZADOS: 28.65 M EN 1.28 HRS. ROP: 22.4 M/HRS, U3M: 2-3-3. ULTIMO SURVEY: PROF: 1215.73 M, INC: 20.93, AZIMUTH: 49.86, TVD: 1202.45 M | 14.92 |  | 2019-09-29 22:04:48.000 | 486 | [5 empty] | 2019-09-23 19:00:00.000 | 2019-09-15 12:30:00.000 | 26.2467 | 5269.029 | 2019-09-21 20:30:00.000 | 0.60417 | 3.9583 | 6.3333 | 8.2708 | 7.3048 | 831.952
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Constituciones 1263 | 22.48 | -97.93 | Constituciones | Deviated |  | 2019-10-10 00:00:00.000 | Primary Drilling | Olimpia-884 | ARMO BNA PDC 14 3/4" Y PERFORO A 108 M. CIRCULO A RETORNOS LIMPIOS. SACO BNA A SUPERFICIE. BAJO Y CEMENTO LA TR DE 10 3/4" A 108 M. CORTA Y BISELA TR 10 3/4", AVANCE: 50%. | CORTAR Y BISELAR LA TR DE 10 3/4". INSTALAR SECCION "A". INSTALAR Y PROBAR PREVENTORES 11 5M + CONEXIONES SUPERFICIALES DE CONTROL. ARMAR Y BAJAR BHA DIRECCIONAL. | 5330C03904E04C80A9E81066BC68FD7A | CONECTO ZAPATA 10 3/4" + 8 TRAMOS DE TR 10 3/4", H-40, 32.75#, 8HRR STC Y BAJO A 108 M, APLICANDO TORQUE OPTIMO DE 2050 LBS-PIE EN PRESENCIA DE PERSONAL DE TENARIS TAMSA. COLOCANDO 6 CENTRADORES DE 10 3/4" x 14 3/4". NOTA: A 27 M PROBO EQUIPO DE FLOTACION, BIEN. | 14.89 |  | 2019-11-01 21:21:36.000 | 602.68 | [5 empty] | 2019-10-22 00:00:00.000 | 2019-10-18 08:00:00.000 | 0 | 3330.0526 | 2019-10-21 14:00:00.000 | 0 | 2 | 11.5833 | 12 | 0 | 287.4866
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Constituciones 540D | 22.4464 | -97.9338 | Constituciones | Build & Hold | J | 2019-06-14 17:00:00.000 | Primary Drilling | Olimpia-884 | REPARO TOP DRIVE. BAJO A PROFUNDIDAD PERFORADA DE 1541 M. PERFORO ROTANDO Y DESLIZANDO HASTA 1568 M. | PERFORAR ETAPA DE 6 3/4 HASTA 1613 M. SACAR A SUPERFICIE, TOMAR REGISTROS ELECTRICOS | 5330C03904E04C80A9E81066BC68FD7A | PERFORO ROTANDO Y DESLIZANDO CON BNA 6 3/4" DESDE 1541 M HASTA 1568 M PSB 1-3 TON, RPM 55-65, 2500 PSI, 250 GPM, 3000 TQ ROP PROMEDIO 4.15 MPH (3 UTM 6-16-10) -TOTAL PARA LA BARRENA 548 MTS EN 28.58 HRS. CON PESO DEL LODO DE 1.18 GR/CC: ROTADOS: 434 M EN 18.7 HRS DESLIZADOS: 114 EN 10.18 HRS. -REPASA CADA LINGADA -ULTIMO SURVEY @ 1528.22 MD, 41.08º INCL, 331.15 AZIM, 1426.02 TVD, 0.54 DLS, 4.3 MTS. DE CT-CT CON RESPECTO AL PLAN | 15 |  | 2019-07-01 00:00:00.000 | 465 | [5 empty] | 2019-07-05 16:00:00.000 | 2019-06-16 00:00:00.000 | 26.2467 | 5291.9949 | 2019-07-03 10:00:00.000 | 6.9375 | 11.9792 | 18.7083 | 20.9583 | 33.1014 | 282.8683
WH | MCA | Mexico | 5330C03904E04C80A9E81066BC68FD7A |  | 584741 | MCA Integrales Terciario Norte LSTK | IDS | MCA | LSTK | Tamaulipas 917 | 22.4388 | -97.9409 | Constituciones | Deviated |  | 2019-07-28 05:00:00.000 | Primary Drilling | Olimpia-884 | REBAJO CEMENTO, PERFORO 5 M DE NUEVA FORMACIÓN, REALIZO FIT SATISFACTORIO Y PERFORO HASTA 1439 M | PERFORAR ETAPA DE 6 3/4", SEGUN PROGRAMA A 2000 M. | 5330C03904E04C80A9E81066BC68FD7A | PERFORO ROTANDO Y DESLIZANDO CON BNA PDC 6 3/4" Y BHA DIRECCIONAL EQUIPADO CON MOTOR DE FONDO Y MWD DE 1303 M A 1439 M. PARÁMETROS: 250 GPM, 2190 PSI, PRESIÓN DIFERENCIAL: 350. PSB: 2 - 3 TON, 70-80 RPM, TORQUE 3200 -4000 FT/LBS BNA: 440 M EN 17.24 HRS, ROP: 25.5 M/HR. U3M: 3-3-3. ROTADOS: 395.97 M EN 13.22 HRS, ROP: 30 M/HRS. U3M: 3-3-3. DESLIZADOS: 44.04 M EN 4.02 HRS. ROP: 11 M/HRS, U3M: 5-5-6. ULTIMO SURVEY: PROF: 1422.331 M, INC: 22.05, AZIMUTH: 333.66, TVD: 1381.39 M, CT-CT: 6.89 M. 2.42M POR DEBAJO DEL PLAN, 6.45 M A LA IZQUIERDA | 15 |  | 2019-08-17 00:00:00.000 | 572 | [5 empty] | 2019-08-15 01:30:00.000 | 2019-08-02 14:00:00.000 | 26.2467 | 6561.68 | 2019-08-12 18:00:00.000 | 0.67708 | 4.5 | 15.5417 | 17.8542 | 3.7923 | 422.1992
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 637 | 17.9891 | -93.1081 | Samaria | Deviated | Injection | 2019-03-04 00:00:00.000 | Primary Drilling | Simmons 836 | REALIZO PRUEBA DE INTEGRIDAD A 469 M CON 1000 PSI X 15 MIN. REBAJO CEMENTO Y ACCESORIOS HASTA 492 M Y REALIZO PRUEBA DE INTEGRIDAD A TR 9-5/8" CON 1000 PSI X 15 MIN. PERFORA SECCION 8-3/4" CON SARTA NAVEGABLE A 1007 M. | CONTINUAR PERFORANDO SECCION 8-3/4". CIRCULAR POZO Y REALIZAR VIAJE CORTO A 497 M Y BAJAR A FONDO PERFORADO. SACAR SARTA Y BARRENA PDC 8-3/4" A SUPERFICIE. TOMAR REGISTROS ELECTRICOS. | 92CE54401907490B93964F086E24D691 | PERFORO CON BNA PDC 8 3/4" CON SARTA NAVEGABLE EQUIPADA CON PD + MWD DE 975 M A 1007 M. CON LOS SIGUIENTES PARAMETROS DE PERFORACION: - 4-8 TON, 100-120 RPM, 7-9 KLB/FT, 475-500 GPM, 1950-2000 PSI. - REPASA 1 VEZ EL TRAMO PERFORADO. - LODO: 1.30 GR/CC **RECORD: 509.5 M, EN 18:30 HRS, ROP: 40 MPH, U3M: 2,1,3 MIN ULTIMO SURVEY: MD: 928.31 M INCL: 14.09 AZM: 56.95 TVD: 926.04 M CT-CT: 1.77 | 10.62 |  | 2019-03-14 14:52:48.000 | 400 | [5 empty] | 2019-03-12 00:30:00.000 | 2019-03-04 00:00:00.000 | 98.4252 | 3421.9161 | 2019-03-09 18:30:00.000 | 0.125 | 4.1042 | 5.7708 | 8.0208 | 1.5584 | 592.9674
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 644 | 17.994 | -93.0987 | Samaria | S Shaped | Injection | 2019-02-15 00:00:00.000 | Primary Drilling | Simmons 836 | SACA HASTA 493 M, BOMBEO BACHE Y CIRCULO TIEMPO DE ATRASO, BAJO LIBRE HASTA 1105 M, BOMBEO TREN DE BACHE, SACO LIBRE HASTA SUPERFICIE | INSTALAR EQUIPO DE WIRELINE | 92CE54401907490B93964F086E24D691 | OBSERVA POZO POR 15 MIN, POZO ESTATICO | 11.9 |  | 2019-02-26 21:36:00.000 | 400 | [5 empty] | 2019-02-24 22:30:00.000 | 2019-02-15 00:00:00.000 | 98.4252 | 3625.5051 | 2019-02-19 11:00:00.000 | 0.14583 | 2.8542 | 4.4583 | 9.9375 | 1.4675 | 813.1974
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 647 | 17.9887 | -93.1079 | Samaria | S Shaped | Injection | 2019-03-19 20:00:00.000 | Primary Drilling | Simmons 836 | ARMO Y BAJO BHA 8-3/4" A 473 M. REALIZO PRUEBA DE INTEGRIDAD CON 1000 PSI X 30 MIN. REBAJO TAPONES Y ACCESORIOS HASTA 495 M. REALIZO PRUEBA DE INTEGRIDAD DE LA TR 9 5/8". OK. PERFORA CON BNA PDC 8 3/4" A LA PROFUNDIDAD DE 1020 M. CIRCULO TREN DE BACHES A SUPERFICIE. | REALIZAR VIAJE CORTO A 500 M. SACAR BNA A SUPERFICIE. CORRER REGISTROS ELECTRICOS. | 92CE54401907490B93964F086E24D691 | BOMBEO TREN DE BACHE CON 360-370 GPM, 1100 PSI, DE LA SIGUIENTE MANERA: - 5 M3 BACHE DISPERSO - 7 M3 BACHE VISCOSO 250 SEG - 7 M3 CON 15 L/M3 DRILLZONE - 7 M3 BACHE VISCOSO 250 SEG | 10.51 |  | 2019-03-29 12:14:24.000 | 400 | [5 empty] | 2019-03-28 19:30:00.000 | 2019-03-19 20:00:00.000 | 98.4252 | 3438.3203 | 2019-03-26 18:30:00.000 | 0.95833 | 5.5625 | 6.9375 | 8.9792 | 10.6729 | 495.6137
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 649 | 17.996 | -93.104 | Samaria | S Shaped | Directional | 2019-08-07 17:00:00.000 | Primary Drilling | Simmons 836 | PERFORO CON BNA PDC 8 3/4'' + PD HASTA 727 M. DONDE SUSPENDIO PERFORACION PARA CAMBIO DE POWER DRIVE. BOMBEO BACHE VISCOSO Y CIRCULO H/OBSERVAR RETORNOS LIMPIOS. SACO A SUPERFICIE. OBSERVO PRIMER ESTABILIZADOR ANILLADO, SEGUNDO EN CALIBRE, PD LAVADO EN EL SELLO DEL TORQUE INFERIOR Y BARRENA CON 4 TOBERAS TAPADAS. ARMO BNA PDC 8 3/4'' MD616 + PD, PROBO HETAS DIRECCIONALES, BAJO BNA PDC 8 3/4'' + PD A 727 M FONDO PERFORADO. PERFORO CON BNA PDC 8 3/4'' + PD A 823 M. | SACAR BNA PDC 8 3/4'' + PD A SUPERFICIE, . ARMAR SARTA DIRECCIONAL CON MOTOR DE FONDO. BAJAR A FONDO PERFORADO A 823 M. PERFORAR CON BNA PDC 8 3/4'' + MF A +/- 1075 M. | 92CE54401907490B93964F086E24D691 | (TSLB) DESCONECTO HERRAMIENTAS DIRECCIONALES OBSERVANDO LO SIGUIENTE: * ESTABILIZADOR @ 28 MTS ANILLADO 1/2" DE ESPESOR POR 4" DE LONGITUD * ESTABILIZADOR @ 5.73 MTS EN CALIBRE * AL REALIZAR LA PRUEBA EN SUPERFICIE DEL POWER DRIVE OBSERVO LAVADO EN EL SELLO DEL TORQUE INFERIOR * BARRENA CON 4 TOBERAS TAPADAS | 20.31 |  | 2019-08-27 07:22:45.000 | 400 |  | 20190812134101 |  |  |  | 2019-08-26 03:00:00.000 | 2019-08-07 17:00:00.000 | 114.8294 | 3533.4647 | 2019-08-13 20:30:00.000 | 10.9792 | 4.3542 | 6.1458 | 18.4167 | 59.6154 | 574.9366
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 668 | 17.9942 | -93.0986 | Samaria | S Shaped | Steam Injection | 2019-04-18 10:00:00.000 | Primary Drilling | Simmons 836 | REALIZO CORTE Y BICELADO DE TR. INSTALO CABEZAL DE 11 X 9-5/8 3M. SOLDO CABEZAL Y PROBO MISMO, SATISFACTORIAMENTE. INSTALO CONJUNTO DE BOPs. PROBO MISMOS. INSTALO BUJE DE DESGASTE. INSTALO CAMPANA Y LINEA DE FLOTE. CONECTO BNA PDC 8 3/4" Y BAJO A 466 M.REALIZO PRUEBA DE HERMETICIDAD. REBAJO CEMENTO Y ACCESRIOS A 493 M. REALIZO 2DA PRUEBA DE HERMITICIDAD. REBAJO CEMENTO Y ACCESORIOS. PERFORO A 560 M. | PERFORAR ETAPA DE 8 3/4" A +/- 1040 M, CORRER REGISTROS ELECTRICOS. BAJAR Y CEMENTAR TR 7". | 92CE54401907490B93964F086E24D691 | PERFORO CON BNA PDC 8 3/4" Y SARTA NAVEGABLE EQUIPADA CON PD + MWD DE 498 M A 560 M. CON LOS SIGUIENTES PARAMETROS DE PERFORACION: - 4-7 TON, 100 RPM, 4-5 KLB/FT, 580 GPM, 2127 PSI. - REPASA 1 VEZ EL TRAMO PERFORADO. - BOMBEA BACHE VISCOSO DE LIMPIEZA CADA 100 M. - U3M: 1-1-2 - RECORD: 62 M, EN 1.15 HRS, ROP INST: 60-90 MPH. ULTIMO SURVEY: - MD:519.83 INCL, 26.13 AZIM. 0.42 DLS, 8.5 CT-CT | 9.3 |  | 2019-04-27 07:13:47.000 | [6 empty] | 2019-04-24 01:30:00.000 | 2019-04-18 10:00:00.000 | 108.2677 | 3405.5119 | 2019-04-21 13:00:00.000 | 0 | 1.75 | 3.125 | 5.6458 | 0 | 1089.7638
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 669 | 17.9893 | -93.1082 | Samaria | Deviated | Steam Injection | 2019-04-30 09:00:00.000 | Primary Drilling | Simmons 836 | TRABAJO SARTA. BOMBEO 4 M3 DE BACHE DESPEGADOR Y DEJO EN REPOSO. TRABAJO SARTA EN TENCION LIBERANDO MISMA CON EXITO. SACO BHA CON BNA PDC 8 3/4'' CON ROTACION Y CIRCULACION HASTA 486 M ZAPATA. CONTINUO SACANDO BNA PDC 8 3/4'' A SUPERFICIE Y DESCONECTO MISMA 100 %. | INSPECCIONAR BHA, DESLIZAR Y CORTAR CABLE DE PERFORACION, ARMAR BHA CON BNA PDC 8 3/4'' + BAJAR A 627 M FONDO PERFORADO PARA CONTINUAR PERFORANDO ETAPA DE 8 3/4" A +/- 900 M, CORRER REGISTROS ELECTRICOS. | 92CE54401907490B93964F086E24D691 | BAJO DENSIDAD A 1.15 GR/CC Y CONTINUO TRABAJANDO SARTA EN TENSION EN REPETIDAS OCASIONES OBSERVANDO LIBERACION CON EXITO, ESTABLECIO ROTACION Y CIRCULACION CON 557 GPM, TQ:1500-4000 LB/FT, 60-70 RPM, 1570 PSI. REPASO EN RPETIDAS OCASIONES OBSERVANDO SARTA 100 % LIBRE. | 9.1 |  | 2019-05-09 02:29:23.000 | 400 | 400 | 20190504191953 |  |  |  | 2019-05-07 03:00:00.000 | 2019-04-30 09:00:00.000 | 98.4252 | 2952.756 | 2019-05-04 14:30:00.000 | 1 | 2.9792 | 4.2292 | 6.75 | 14.8148 | 698.1886
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 670 | 17.9897 | -93.105 | Samaria | S Shaped | Steam Injection | 2019-05-26 12:00:00.000 | Primary Drilling | Simmons 836 | SOLDO CABEZAL Y PROBO MISMO. ESPERO ENFRIAMIENTO DE CABEZAL. INSTALO CONJUNTO DE PREVENTORES, PROBO PREVENTORES. ARMO SARTA DIRECCIONAL CON BNA 8-3/4''. BAJO A 416 M, RECONOCIO PI. EFECTUO PRUEBA DE HERMETICIDAD A TR 9 5/8" CON 1000 PSI, SATISFACTORIAMENTE. PERFORO CON BNA 8 ¾” A 531 M. SUSPENDIO POR FALLA EN BANCO DE VALVULAS DE HPU. LEVANTO BNA SARTA A 445 M. REPARO FALLA. BAJO SARTA A 531 M, PERFORO HASTA 615 M. | PERFORAR ETAPA DE 8 3/4" HASTA 1010 M DE ACUERDO A PROGRAMA. BOMBEAR TREN BACHES Y CIRCULAR HASTA RETORNOS LIMPIOS. REALIZAR VIAJE CORTO. REGRESAR A FONDO CIRCULAR Y SACAR A SUPERFICIE. | 92CE54401907490B93964F086E24D691 | (NPT SIMMONS) POR FALLA EN BANCO DE VÁLVULAS DE HPU REALIZÓ VIAJE A ZAPATA 9 5/8" DE 531 M A 445 M, OBSERVANDO LIBRE. REPARO FALLA. BAJO BARRENA PDC 8 3/4" CON SARTA DIRECCIONAL CON POWER DRIVE Y MWD A FONDO PERFORADO 531 M, BAJO ULTIMO TRAMO CON CIRCULACIÓN. | 9.01 |  | 2019-06-04 00:14:24.000 | 400 | 400 | 20190531222842 |  |  |  | 2019-06-01 14:30:00.000 | 2019-05-26 12:00:00.000 | 114.8294 | 3412.0736 | 2019-05-30 23:00:00.000 | 0.20833 | 3.0833 | 4.4583 | 6.1042 | 3.413 | 765.3249
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 676 | 17.9924 | -93.099 | Samaria | Deviated | Desarrollo | 2019-07-12 03:00:00.000 | Primary Drilling | Simmons 836 | INSTALO CONJUNTO DE PREVENTORES, PROBO MISMOS CON UNIDAD DE PRUEBAS BIEN. INSTALO CAMPANA Y LINEA DE FLOTE. ARMO BNA PDC 8 3/4'' + PD Y BAJO A 448 M PI, PROBO TR, REBAJO CEMENTO Y ACCESORIOS, PROBO TR 9 5/8" A 483 M. PERFORO CON BNA PDC 8 3/4'' + POWER DRIVE DE 488 M A 574 M. SUSPENDIO POR FALLA EN BOMBA DE LODOS. POSTERIORMENTE CONTINUO PERFORANDO HASTA 954 M. | PERFORAR CON BNA PDC 8 3/4'' + PD A 1072 M. BOMBEAR Y CIRCULAR TREN DE BACHES. REALIZAR VIAJE CORTO HASTA LA ZAPATA 9 5/8" A 488 M. REGRESAR A FONDO PERFORADO. CIRCULAR HASTA RETORNOS LIMPIOS. SACAR BHA A SUPERFICE. TOMAR REGISTROS ELECTRICOS, BAJAR Y CEMENTAR TR 7'' A 1070 M. | 92CE54401907490B93964F086E24D691 | (N) PERFORO CON BNA PDC 8 3/4" Y SARTA ROTATORIA EQUIPADA CON PD + MWD DESDE 488 M HASTA 574 M, DONDE SUSPENDE PERFORACION POR OBSERVAR FALLA EN BOMBA DE LODOS. *PARAMETROS DE PERFORACION: P/BNA 2-5 TON, 80-90 RPM, 2-6 KLB/FT, 580 GPM, 2100 PSI. * RECORD BNA: 72 M EN 1.5 HRS, ROP 48 M/HR. U3M: 1-1-1 *REPASO 1 VEZ EL TRAMO PERFORADO. *BOMBEO 7 M3 BACHE VISCOSO DE LIMPIEZA DE 250 SEG | 9.54 |  | 2019-07-21 12:56:59.000 | 400 | [5 empty] | 2019-07-19 17:00:00.000 | 2019-07-12 03:00:00.000 | 114.8294 | 3517.0605 | 2019-07-16 03:30:00.000 | 1.0625 | 2.7292 | 4.0208 | 7.5833 | 14.011 | 874.7093
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 677 | 17.9912 | -93.1084 | Samaria | Deviated | Direccional | 2019-08-31 20:00:00.000 | Primary Drilling | Simmons 836 | BAJO BNA PDC 8 3/4" + SARTA DIRECCIONAL HASTA 1055 M, LIBRE. BOMBEO Y CIRCULO BACHE VISCOSO HASTA RETORNOS LIMPIOS. LEVANTO BNA PDC 8 3/4" HASTA 482 M (ZAPATA 9 5/8"), LIBRE. COTINUO SACANDO A SUPERFICIE. ELIMINO HTAS DIRECCIONALES. BAJO 1ER SONDA HNGT-HRLT-DRCAL-GR Y REGISTRO DESDE 1055 M HASTA 482 M. ARMO Y CALIBRO 2DA SONDA DE REGISTRO DSI-LDL-CNL-GR, BAJO A 1055 M. REGISTRO DESDE 1055 M HASTA 482 M (ZAPATA 9 5/8"). SACO SONDA A SUPERFICIE. DESMANTELO URE. INSTALO EQUIPO INTEGRAL PARA INTRODUCCION DE TR. BAJA TR 7" L-80 26 LBS-FT VAM TOP HC @ 190 M. | BAJAR Y CEMENTAR TR 7" HASTA 1051 M. LEVANTAR CONJUNTO PREVENTORES, REALIZAR CORTE A TR 7'', RETIRAR CABEZAL TEMPORAL 11'', INSTALAR CABEZAL SOLDABLE 11'' x 9 5/8'', SOLDAR CABEZAL, INSTALAR CABEZAL DE PRODUCCION DE 7 1/16'' 5 M, SOLDAR Y PROBAR. | 92CE54401907490B93964F086E24D691 | (N) SACO BARRENA PDC 8 3/4" HASTA SUPERFICIE Y DESCONECTO SARTA DIRECCIONAL Y BNA AL 100 %. *LLEVO CONTROL DE LLENADO CON HOJA Y TANQUE DE VIAJES. *DESGASTE DE BNA: 1-1-CT-A-X-I-PN-LOG, OBSERVO SALIR CON 2 TOBERAS TAPADAS. | 9.39 |  | 2019-09-09 09:21:36.000 | 400 | [5 empty] | 2019-09-07 19:00:00.000 | 2019-08-31 20:00:00.000 | 98.4252 | 3461.2862 | 2019-09-04 17:00:00.000 | 0.083333 | 1.8125 | 3.875 | 6.9583 | 1.1976 | 893.2351
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 678 | 17.996 | -93.097 | Samaria | Deviated | J | 2019-07-25 00:00:00.000 | Primary Drilling | Simmons 836 | BOMBEO TREN DE BACHES Y CÍRCULO HASTA RETORNOS LIMPIOS, OBSERVÓ POZO SACO BNA PDC 8 3/4" DESDE 1057 M A 493, BAJA BNA PDC 8 3/4 A FONDO PERFORADO. LIBRE. SACO BNA A SUPERFICIE. ARMO Y CALIBRO SONDA DE REGISTRO. BAJO 1ER CORRIDA DE REGISTRO A FONDO. Y TOMO REGISTRO DE 1057 A 493 M, ARMO Y BAJO 2 DA CORRIDA DE REGISTRIOS A FONDO 1057 M, TOMA REGISTROS SIN TERMINAR. | TOMAR REGISTROS ELÉCTRICOS DE ACUERDO A PROGRAMA. REALIZAR PREPARATIVOS PARA INTRODUCCION DE TR 7”. CORRER TR 7” Y CEMENTAR MISMA A 1055 M. | 92CE54401907490B93964F086E24D691 | (N) BOMBEO TREN DE BACHES DE LIMPIEZA Y CIRCULA HASTA RETORNOS LIMPIOS EN SUPERFICIE, RECIPROCANDO SARTA. PARAMETROS: 520 GPM, 2700 PSI, 115 RPM, 3.5 LBS-FT. BACHES BOMBEADOS: -7 M3 BACHE DISPERSO -7 M3 BACHE VISCOSO 250 SEG -7 M3 SURFACTANTE CON 15 L/M3 DRILLZONE -7 M3 BACHE VISCOSO 250 SEG. | 9.46 |  | 2019-08-03 10:55:59.000 | 400 | [5 empty] | 2019-07-31 23:00:00.000 | 2019-07-25 14:00:00.000 | 114.8294 | 3467.8479 | 2019-07-29 00:00:00.000 | 0 | 1.9167 | 4 | 6.9583 | 0 | 866.962
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 680 | 17.9935 | -93.1038 | Samaria | Deviated | Steam Injection | 2019-05-13 00:00:00.000 | Primary Drilling | Simmons 836 | BAJO BNA A 884 M. PERFORO CON BNA PDC 8 3/4'' + MD A 1080 M. BOMBEO TREN DE BACHES Y CIRCULO HASTA RETORNOS LIMPIOS, REALIZO VIAJE CORTO, CIRCULO, Y SACO BNA A SUPERFICIE, ARMO UNIDAD DE REGISTROS, TOMA 1RA CORRIDA DE REGISTROS. | TOMAR REGISTROS ELECTRICOS, DESMANTELAR URE, ARMAR EQUIPO PARA INTRODUCCION DE TR 7'', BAJAR Y CEMENTAR TR A 1080 M. | 92CE54401907490B93964F086E24D691 | SACO BNA PDC 8 3/4" DESDE 1080 M HASTA 203 M, LIBRE, LLENANDO POR ESPACIO ANULAR CON TANQUE DE VIAJES MONITOREANDO LLENADO CON HOJA DE VIAJES. -REALIZO FLOW CHECK A LA PROF DE 465 M ZAPATA DE 9 5/8'' POZO ESTATICO | 9.05 |  | 2019-05-22 01:08:23.000 | 400 | [5 empty] | 2019-05-19 21:30:00.000 | 2019-05-13 00:00:00.000 | 98.4252 | 3543.3072 | 2019-05-17 08:00:00.000 | 0.6875 | 2.4583 | 4.3333 | 6.8958 | 9.9698 | 817.6863
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 681 | 18.002 | -93.0913 | Samaria | S Shaped | Steam Injection | 2019-04-05 12:00:00.000 | Primary Drilling | Simmons 836 | ARMO Y BAJO BHA 8-3/4" A 469 M. REALIZO PRUEBA DE INTEGRIDAD CON 1000 PSI X 30 MIN. REBAJO TAPONES Y ACCESORIOS HASTA 498 M. REALIZO PRUEBA DE INTEGRIDAD DE LA TR 9 5/8". OK. PERFORA CON BNA PDC 8 3/4" A LA PROFUNDIDAD DE 954 M. | PERFORAR SECCION 8-3/4" HASTA 1066 M. SACAR A SUPERFICIE, REGISTROS ELECTRICOS, VIAJE CORTO, | 92CE54401907490B93964F086E24D691 | CON BNA 8-3/4" CON SARTA NAVEGABLE EQUIPADA CON PD CEMENTO A 493 M HASTA 498 M 350 GPM, 70 RPM, 1220 PSI, 2-4 KLBFT. | 9.98 |  | 2019-04-14 23:29:59.000 | 400 | [5 empty] | 2019-04-12 05:30:00.000 | 2019-04-05 12:00:00.000 | 88.5827 | 3533.4647 | 2019-04-09 15:00:00.000 | 0.083333 | 2.8125 | 4.125 | 6.7292 | 1.2384 | 856.5975
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 698 | 17.9909 | -93.1041 | Samaria | S Shaped | Desarrollo | 2019-06-29 17:00:00.000 | Primary Drilling | Simmons 836 | PERFORO CON BNA PDC 8 3/4'' + PD A 1082 M. CIRCULO HASTA RETORNOS LIMPIOS, SACA BNA PDC 8 3/4'' A 178 M | SACAR BNA PDC 8 3/4'' A SUPERFICIE, INSTALAR UNIDAD DE REGISTROS, TOMAR REGISTROS ELECTRICOS, DESMANTELAR UNIDAD DE REGISTROS, BAJAR Y CEMENTAR TR 7'' A 1082 M. | 92CE54401907490B93964F086E24D691 | (N) PERFORO CON BNA PDC 8 3/4" Y SARTA ROTATORIA EQUIPADA CON PD + MWD HASTA 1072 M. *PARAMETROS DE PERFORACION: P/BNA 2-5 TON, 125-145 RPM, 2-4 KLB/FT, 580-600 GPM, 1930-2100 PSI. * RECORD BNA: 612 M EN 16.5 HRS, ROP 40.66 M/HR. U3M: 1-1-1 - REPASO 1 VEZ EL TRAMO PERFORADO. - TOMA SURVEY CADA DOS TRAMOS PERFORADOS 9 M ARRIBA DE FONDO - BOMBEO 7 M3 BACHE VISCOSO DE LIMPIEZA DE 250 SEG Y BACHE SURFACTANTE CON 15 L/M3 CADA 100 M. | 16.51 |  | 2019-07-15 12:14:23.000 | 400 | 400 |  |  |  |  | 2019-07-06 04:00:00.000 | 2019-06-29 15:00:00.000 | 0 | 3549.8689 | 2019-07-03 00:30:00.000 | 0 | 2.2083 | 3.3125 | 6.4583 | 0 | 1071.6585
WH | MCA | Mexico | 92CE54401907490B93964F086E24D691 | 138 | 602618 | MCA Integrales Terciario Sur LSTK | IDS | MCA | LSTK | Samaria 699 | 17.9969 | -93.0947 | Samaria | Deviated | Steam Injection | 2019-06-13 23:00:00.000 | Primary Drilling | Simmons 836 | PERFORO CON BNA PDC 8 3/4" HASTA 1021 M. CIRCULO HASTA RETORNOS LIMPIOS. REALIZO VIAJE CORTO A 401 M. CIRCULO BACHE DE LIMPIEZA. SACO BNA A SUPERFICIE, ARMO UNIDAD DE REGISTROS, REPARO FALLA EN UNIDAD DE REGISTROS, TOMA REGISTRO SIN TERMINAR. | TOMAR REGISTROS ELECTRICOS, BAJAR Y CEMENTAR TR 7'' A 1020 M. | 92CE54401907490B93964F086E24D691 | SACO BNA PDC 8 3/4" DESDE 1021 M HASTA 401 M (ZAPATA 9 5/8”). - LEVANTO LIBRE HASTA 800 M, DONDE OBSERVO ARRASTRE DE 5 TON, CONTINUO SACANDO ROTACION Y CIRCULACION REPASANDO PUNTOS APRETADOS HASTA OBSERVAR LIBRE. | 9.76 |  | 2019-06-22 18:14:24.000 | 400 | [5 empty] | 2019-06-23 21:30:00.000 | 2019-06-13 23:00:00.000 | 114.8294 | 3474.4096 | 2019-06-21 18:00:00.000 | 2.7292 | 6.3542 | 7.7917 | 9.9375 | 27.4633 | 445.9135
EH | NAL | United States | 043BBEE65E554D67B91E723718377E29 |  | 549403 | NAL-IWC-IDS PRB SAMSON LSTK 6 wells | IDS | MCA | LSTK | Allemand Federal 31-1918 39-74FH | 43.329 | -105.791 | Converse County, WY | Horizontal |  | 2018-09-08 16:30:00.000 | Primary Drilling | SST 63 | Installed MPD orbit valve and high pressure line, relocated trip tank, installed mouse hole and swap pipe elevators. Pressure tested BOP/MPD, P/U BHA #5 and RIH to 11,928'. Reamed f/11,928' t/12,115'. | RIH BHA#5 to tag top of cement, displace WBM with OBM, test casing and drill out shoe track. Perform FIT to 13ppg. Drill 6-1/8'' curve. | 043BBEE65E554D67B91E723718377E29 | Rig down and lowered trolleys, installed MPD orbit valves and flow-line (ongoing). | 35.82 |  | 2018-10-14 01:33:52.000 | 585 | [5 empty] | 2018-12-25 14:30:00.000 | 2018-09-08 11:00:00.000 | 110 | 22950.0007 | 2018-12-16 11:00:00.000 | 7.3958 | 17.4271 | 98.7708 | 107.9167 | 6.8533 | 232.3561
EH | NAL | United States | 043BBEE65E554D67B91E723718377E29 |  | 549403 | NAL-IWC-IDS PRB SAMSON LSTK 6 wells | IDS | MCA | LSTK | Allemand Federal 34-3031 39-74NH | 43.3292 | -105.791 | Converse County, WY | Horizontal |  | 2018-10-17 17:00:00.000 | Primary Drilling | SST 63 | Drilled from 20,665' to 20,698', circulated conditioning wellbore and POOH BHA #13 stripping to 11,540', spotted 70bbl of 18.1ppg mud cap and continued tripping to surface. L/D BHA #13 and R/U BOP testing unit. BOP pressure test ongoing. | Pressure test BOP, M/U and RIH BHA #14 to 11,550' to displace mud cap, continue RIH stripping to bottom and resume drilling 6-1/8'' lateral. | 043BBEE65E554D67B91E723718377E29 | POOH BHA #13 f/20,698' t/20,050' stripping with 720psi back-pressure MPD. | 28.92 |  | 2018-10-04 04:08:44.000 | 490 | [5 empty] | 2018-11-22 09:00:00.000 | 2018-09-05 11:00:00.000 | 80 | 22326.0007 | 2018-11-11 15:00:00.000 | 14.375 | 28.1042 | 24.9167 | 35.6667 | 40.3037 | 896.0268
EH | NAL | United States | 043BBEE65E554D67B91E723718377E29 |  | 549403 | NAL-IWC-IDS PRB SAMSON LSTK 6 wells | IDS | MCA | LSTK | Spearhead Federal 11-2635 40-75SH | 43.3869 | -105.832 | Converse County, WY | Horizontal |  | 2018-07-23 06:00:00.000 | Primary Drilling | SST 63 | Drilled lateral from 11435 ft to 12300 ft | Continue drilling the lateral | 043BBEE65E554D67B91E723718377E29 | Lubricate the TD | 29.32 |  | 2018-08-21 13:46:21.000 | 675 | [5 empty] | 2018-08-30 19:30:00.000 | 2018-07-23 06:00:00.000 | 0 | 21182.0007 | 2018-08-24 14:30:00.000 | 2.6875 | 13.0833 | 32.3542 | 38.5625 | 6.9692 | 654.6916
WH | NAL | United States | 848CF59C7A1448918363880FD06E786F |  |  | OneDrill Point Energy Partners Permian | SLR | NAM | LSTK | Jim Ed P-01H WC-A | 31.4334 | -103.2142 |  | Horizontal |  | 2019-07-11 21:30:00.000 | Primary Drilling | SLR-601 | Make up lateral BHA, RIH, Relog to bottom and drill ahead. Trouble shoot MWD noise issues. | Drill ahead 8.5" lateral section. M/U 5.5" Casing | 848CF59C7A1448918363880FD06E786F | TIH F/11054' T/11650' | 28.37 |  | 2019-08-30 08:30:00.000 | [6 empty] | 2019-09-03 01:00:00.000 | 2019-07-11 21:30:00.000 | 0 | 17567.0006 | 2019-08-23 06:00:00.000 | 12.3125 | 23.7604 | 42.3542 | 53.1458 | 23.1674 | 414.7644
WH | NAL | United States | 848CF59C7A1448918363880FD06E786F |  |  | OneDrill Point Energy Partners Permian | SLR | NAM | LSTK | Jim Ed P-02H WC-A | 31.4334 | -103.2142 |  | Horizontal | Development | 2019-05-25 08:00:00.000 | Primary Drilling | SLR-601 | POOH and L/D 8.75" curve assembly. M/U and TIH 8.5" lateral assembly. | Drill 8.5" lateral section | 848CF59C7A1448918363880FD06E786F | Continue TIH f: 7830' t: 8111' While troubleshooting DrillPilot; Bridge protection not differentiating from slack off or "in slips"; Attempting calibration of height set points without success. Stickup height out of calibration. Verified DW Calibration, error at High setpoint, deviation of setpoint alarm. All of this prevents Drillpilot operation. | 27.32 |  | 2019-06-21 13:47:14.000 | [6 empty] | 2019-07-09 00:00:00.000 | 2019-05-25 17:00:00.000 | 109 | 17498.0006 | 2019-07-03 18:00:00.000 | 5.3125 | 21.2604 | 39.4167 | 44.6667 | 11.8937 | 443.9239
WH | NAL | United States | 848CF59C7A1448918363880FD06E786F |  |  | OneDrill Point Energy Partners Permian | SLR | NAM | LSTK | Point Red White and Blue 1H | 31.4328 | -103.2351 |  | Horizontal | Horizontal Producer | 2019-09-26 10:00:00.000 | Primary Drilling | SLR-601 | Performed CIT to 750 psi surface pressure, drill out shoe track, and performed FIT to 13.3 EMW. Drill to depth. | Continue drilling to depth | 848CF59C7A1448918363880FD06E786F | Send downlink | 31.56 |  | 2019-11-09 23:38:39.000 | [6 empty] | 2019-10-21 06:00:00.000 | 2019-09-26 10:00:00.000 | 1245 | 10810.0003 | 2019-10-19 20:30:00.000 | 7.8542 | 12.0625 | 23.4375 | 24.8333 | 31.6275 | 461.2267
WH | LAN | Ecuador | E74D81B8D481466EBE5A81DBED29D09D | 728 | 159483 | Orion Energy ECG | IDS | MCA | LSTK | Eno-7 | -0.10858 | -76.86 | Eno | Build & Hold |  | 2017-02-27 12:00:00.000 | Primary Drilling | Nabors-609 | M/U and RIH directional BHA #6. Drill out half shoe track and test casing. Change drilling fluid. FIT. Drill 8-1/2" section to 10065'. | Drill 8-1/2" section according to directional plan. | E74D81B8D481466EBE5A81DBED29D09D | Conducted pre-job safety meeting before making up BHA# 6 for 8-1/2" Section. | 435.7 |  | 2018-05-08 22:48:00.000 | [6 empty] | 2017-03-30 18:30:00.000 | 2017-02-27 12:00:00.000 | 0 | 11500.0004 | 2017-03-23 02:30:00.000 | 2.2708 | 13.6458 | 23.6042 | 31.2708 | 7.2618 | 487.2021
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Bedel-14 | 17.82 | -95.4415 | Bedel | Deviated | Deviated | 2019-02-02 08:00:00.000 | Primary Drilling | Pemex-1004 | INSTALO EQUIPO 100%, REACOMODO Y REALIZO ORDEN Y LIMPIEZA EN COMPONENTES DEL EQUIPO , REALIZO CHECK LIST PRE ARRANQUE, BIEN, REALIZO DIMENCIONAMIENTO DE HTAS Y VERIFICO CERTIFICACIONES, EFECTUA LIBRANZA PARA INSTALACION DE PARAMETROSL EN TIEMPO REAL, AVANCE 50%. | INSTALAR PARAMETROS 100% Y CALIBRAR MISMO | 12825062400B4D229D629F322840398E | CON PERSONAL DE OPERACIÒN Y CIA SLB REALIZA DIMENSIONAMIENTO DE HERRAMIENTAS DE LA ETAPA, REVISÒ CERTIFICACIONES CORRESPONDIENTES. | 14.65 |  | 2019-02-15 15:36:00.000 | 629.76 | [5 empty] | 2019-03-09 02:00:00.000 | 2019-02-01 00:00:00.000 | 108.2677 | 9286.7457 | 2019-02-13 03:00:00.000 | 4.5208 | 6.7292 | 10.7917 | 34.75 | 13.0096 | 860.5479
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Bedel-34 | 17.8324 | -95.4572 | Bedel | S Shaped |  | 2019-06-08 03:00:00.000 | Primary Drilling | Pemex-1004 | CON BNA 8 1/2" Y SARTA DIRECCIONAL CON POWER DRIVE PERFORA HASTA 1835 MTS DONDE SUSPENDE POR FISURA EN MANGUERA DE 4" CAMBIA MANGUERA Y PERFORA HASTA 1929 M | PERFORAR ETAPA DIRECCIONAL HASTA 2516 M | 12825062400B4D229D629F322840398E | CON BARRENA DE 8 1/2" CIA. SCHLUMBERGER Y SARTA ROTATORIA DIRECCIONAL PERFORA DE 1598 m A 1769 m CON UN RECORD DE BARRENA DE: 817 m, EN 10:05 hrs, U3M(1-1-1), PERFORA CON LAS CONDICIONES DE 6 A 9 ton, 150 rpm EN ROTARIA, 134 epm, QB= 550 gpm, PB= 2790 psi, V.A.=297 ft/min, T.A.=21 min, ROP= 81:02 m/hr, PROM.=0.74 min/m, CON UN PESO DE SARTA DE ↑ 60 ton, → 56 ton, ↓ 54 ton. SE PERFORA CON LODO DE 1.15 gr/ccx 63 SEG, GENERANDO UNA D.E.C. 1.256 gr/cc. SE EFECTUARON 32 CONEXIONES EN UN TIEMPO DE CONEXIONES 04:04 hrs ; CON UN PROMEDIO DE 7.6 min/conexión (CUÑA A CUÑA: 4 MIN), TIEMPO DE SURVEYS 01:45 hrs, TIEMPO DE COMANDOS 01:03 hrs. NOTA: SE BOMBEAN 3.5 M3 DE BACHES VISCOSOS DE 1.15 GR/CC POR 180 SEG CADA 200 M. | 16.65 |  | 2019-06-24 15:37:26.000 | 840 | [5 empty] | 2019-06-29 05:00:00.000 | 2019-06-08 08:00:00.000 | 85.3018 | 8234.9084 | 2019-06-21 01:00:00.000 | 3.8333 | 8.1875 | 12.9167 | 21.0833 | 18.1818 | 637.5413
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Eltreinta-11 | 17.8325 | -95.4997 | El Treinta | Deviated | Desarrollo | 2018-02-18 09:00:00.000 | Primary Drilling | Pemex-1004 | CONTINUO BAJANDO BNA 8 1/2" CON SRD A 1918.5 M DONDE DETECTO PI, REALIZO PRIMERA PRUEBA DE TR SATISFACTORIAMENTE , REBAJA CEMENTO A 1945M PROBO TR, PERFORA A 2256 M CON BNA 8 1/2 Y SRD DE SLB. | PERFORAR ETAPA 8 1/2 A 2795 M SEGUN PROGRAMA | 12825062400B4D229D629F322840398E | CON BNA PDC 8 1/2" Y SRD DE CIA SLB PERFORA MANTENIENDO ANGULO Y RUMBO A LA PROF DE 2087 M, RECORD: 137 M EN 04:15 HORAS, U3M: 2-2-2 MIN/M, PROM: 1.86 MIN/M, CONDICIONES: PSB: 3-5 TON, 130 RPM, Q: 115 EPM, 550 GPM, P.BOM: 1980 PSI, VA: 285 FT/MIN, DEC: 1.273 GR/CC, TA: 25.5 MIN. TIEMPOS: CONEXION (15) 02:20 HORAS, PROM: 9.33 MIN/CONEXION, SURVEY: 00:32 HORAS, LIMPIO CEDAZO: 00:08 HORAS, CALIBRO PROFUNDIDAD: 00:05 MIN. PESO: 64-62-60 TON, ROP: 17.12 M/HORA | 28.82 |  | 2018-03-18 19:40:48.000 | [6 empty] | 2018-03-16 06:30:00.000 | 2018-02-18 09:00:00.000 | 137.7953 | 9163.3861 | 2018-03-06 05:00:00.000 | 4.4688 | 10.8125 | 15.8333 | 25.8958 | 17.2566 | 578.7402
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Eltreinta-13 | 17.8 | -95.3 | El Treinta | Deviated | Desarrollo | 2018-06-27 19:00:00.000 | Primary Drilling | Pemex-1004 | PROBO BOP 11" 5M. INSTALO BUJE DE DESGASTE. INSTALA CAMPANA, CHAROLA, LINEA DE FLOTE Y LLEANADERA. ARMO BHA DIRECCIONAL ROTATORIO A 50 M. PROBO HTTA. DIRECCIONAL BIEN. CAMBIO UNIFLEX/CORTO Y DESLIZO CABLE. BAJA BNA A 1102 M. | BAJAR A 500 MTS, DESLIZAR CABLE + BAJAR A CIMA DE TAPONES Y EFECTUAR 1ER PRUEBA A TR C/1500 PSI + REBAJAR ACCESORIOS Y CEMENTO HASTA 5 MTS ANTES DE LA ZAPATA + REALIZAR 2A PRUEBA A TR C/1500 PSI. | 12825062400B4D229D629F322840398E | PERSONAL DE OPERACIÓN EN PRESENCIA DE CIA SLB (DIRECCIONAL Y MWD) ARMA SARTA ROTATORIA DIRECCIONAL CON BNA PDC 8 1/2", MARCA SMITH, NO. SERIE: J9864, TIPO MDSi613, IADC: M333, CON 5 TOB DE 12/32" Y 1 DE 11/32", TFA= 0.645 PG2, 4 1/2" REG (LONG= 0.22 MTS) + POWER DRIVE X5 DE 6 3/4" x 2 1/4" CON CAMISA ESTABILIZADA A 8 3/8", NO. SERIE: CC79141 (LONG= 4.03 MTS) + MWD SLIM PULSE 6 3/4" x 3.880 PG, NO. SERIE: G3680 (LONG= 9.72 MTS) + DC MONEL DE 6 3/4" x 2 3/4", NOM. SERIE SD46022 (LONG= 8.10 MTS) Y BAJA A 23.3 MTS. | 27.2 |  | 2018-07-24 04:48:00.000 | [6 empty] | 2018-07-24 18:30:00.000 | 2018-06-27 19:00:00.000 | 59.0551 | 9429.1342 | 2018-07-16 22:00:00.000 | 1.8542 | 12.875 | 19.125 | 26.9792 | 6.8726 | 493.0266
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Gasifero-81 | 17.7871 | -95.3178 | Gasifero | Build & Hold | J | 2017-12-11 03:00:00.000 | Primary Drilling | Pemex-1004 | INSTALO CAMPANA, CHAROLA ECOLOGICA, LINEA DE FLOTE, LLENADERA, Y VOLANTES A PREVENTORES + CENTRO MISMOS CON ROTARIA + INSTALO BUJE DE DESGASTE + DESLIZO 13.1m DE CABLE AL T.P.M. + ELIMINO HTA. DE 8" + ARMO BNA DE 8 1/2" CON S.R.D. Y BAJA LLENANDO INTERIRO CADA 500m POR V.C.P. | BAJAR Y RENCONOCER P.I. @ 2317.29md + CIRCULAR T.A. + EFECTUAR PRUEBA DE TR CON 1500psi + REBAJAR CEMENTO Y ACCESORIOS A 2342m + CIRCULAR T.A. + EFECTUAR SEGUNDA PRUEBA DE TR CON 1500psi + PERFORAR TANGENCIALMENTE HASTA 3594m. | 12825062400B4D229D629F322840398E | PERSONAL DE CIA. SCHLUMBERGER ARMO BARRENA PDC DE 8 1/2" TIPO: MDSI616BPX CON 3tob DE 12/32" Y 3tob DE 11/32" M323 Y POWER DRIVE DE 6 3/4" CON ESTABILIZADOR DE 8 3/8" + 1 TRAMO DE TP DE 5" Y CONECTO FLECHA + EFECTUO PREPARTIVOS PARA PRUEBA DE HERRAMIENTA. | 36.77 |  | 2018-02-07 18:27:27.000 | [6 empty] | 2018-01-26 05:00:00.000 | 2017-12-11 05:00:00.000 | 57.4147 | 11791.339 | 2018-01-03 23:00:00.000 | 12 | 14.625 | 23.8333 | 46.0833 | 26.0398 | 494.7415
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Eltreinta-28 | 17.8357 | -95.4754 | El Treinta | Deviated | Desarrollo | 2018-03-01 12:30:00.000 | Primary Drilling | Pemex-317 | CON BNA PDC 8 1/2" Y SARTA DIRECCIONAL DE CIA SLB PERFORÓ MANTENIENDO ÁNGULO Y RUMBO A 3601M | BOMBEAR TREN DE BACHES DE LIMPIEZA, CIRCULAR A RETORNOS LIMPIOS, LANZAR REGISTRO GIROSCOPICO POR INTERIOR DE TP, RECUPERAR BNA 8 1/2" EN SUPERFICIE | 12825062400B4D229D629F322840398E | CON BNA PDC 8 1/2" Y SARTA DIRECCIONAL DE CIA SLB PERFORÓ MANTENIENDO ÁNGULO Y RUMBO A 3360 M RECORD: 810 M EN 31:06 HR PROM 2.30 MIN/M U3M 3-2-2, CONDICIONES DE OPERACIÓN: PSB 6-7 TON, 150 RPM, 470 AMP, 140 EMP, 585 GPM, 2650 PSI, DEN ENTRADA Y SALIDA 1.20 GR/CC, DEC 1.27 GR/CC, PESO SARTA 92/102/86 TON, VEL ANU 208 FT/MIN, T.A. 38 MIN. OBSERVA SALIR RECORTE NORMAL. SURVEY: 3271.49 MD, 59.73° INCL, 160.15° AZIM, 2618.57 TVD, 1298.83 VSEC, 0.17 °/30M. 7 CONEXIONES EN 01:02 HR PROM: 8.8 CONEX/MIN. PERFORANDO: 03:16 HR, BOMBEO DE BACHE: 00:10 HR, PRED: 00:08 HR, ENGRSA TUBO LAVADOR: 00:07 HR, AJUSTE DE PROFUNDIDAD: 00:04 HR. *NOTA: BOMBEÓ 7 M3 DE BACHE VISCOSO DE 1.20 GR/CC X 200 SEG. AL T.A. DEL BOMBEO DEL BACHE SE OBSERVÓ SALIR ABUNDANTE RECORTE. PRESIÓN REDUCIDA CON BBA No.1 45 EPM 188 GPM 600 PSI, CON BBA No.2 45 EPM 188 GPM 550 PSI | 34.19 |  | 2018-04-04 04:33:36.000 | [6 empty] | 2018-04-12 11:00:00.000 | 2018-03-01 12:30:00.000 | 0 | 11814.3048 | 2018-03-24 00:00:00.000 | 8.8542 | 14.1875 | 22.4792 | 41.9375 | 21.1128 | 525.5669
WH | MCA | Mexico | 12825062400B4D229D629F322840398E | 918 | 475603 | PEMEXMCAVeracruz | IDS | MCA | AFE Assurance | Gasifero-72 | 17.7918 | -95.3405 | Gasifero | Build & Hold | Tipo J | 2018-12-13 15:30:00.000 | Primary Drilling | Pemex-317 | PERFORA C/SRD Y BNA PDC 8 1/2" CIA SLB SEGÚN PROGRAMA A 2694 MTS + SUSPENDE POR FUGA EN STAND PIPE + LEVANTA BNA A 2323 MTS POR LINGADAS + REPARÓ FUGA DEL STAND PIPE + BAJÓ BNA A 2694 MTS (FONDO PERFORADO)+ PERFORA A 2770 MTS | PERFORAR CON SRD CIA SLB CONFORME A PROGRAMA A 3153 MTS.+ CIRCULAR HASTA RETORNOS LIMPIOS + REGISTRO GYROSCOPICO | 12825062400B4D229D629F322840398E | (F) PERSONAL DE OPERACIÓN REPARÓ FUGA EN STAND PIPE. CAMBIO EMPAQUE/HULE DAÑADO EN LA UNION DE GOLPE DE 4" DEL STAND PIPE AL TUBO VERTICAL, SATISFACTORIAMENTE. | 26.83 |  | 2019-01-08 19:55:12.000 | 587.12 |  | 20190102225048 |  |  |  | 2019-01-12 14:00:00.000 | 2018-12-13 15:30:00.000 | 95.1444 | 10344.4885 | 2019-01-04 15:00:00.000 | 2.8646 | 13.7083 | 21.9792 | 29.9375 | 9.5685 | 470.6497
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB024 |  |  | Y113-Y133 | Vertical |  | 2018-03-10 15:30:00.000 | Primary Drilling | SCP-50009 | BOP pressure test, preparation work before drilling 8-1/2" section, M/U BHA, drill out cement plug, casing pressure test, drill 8-1/2" hole to 546m, FIT, drill 8-1/2" hole | Drilling 8-1/2" section | 2D54099CD7834E349FE1061279261D62 | FIT: surface pressure 7.9MPa, held for 10min, 0.1MPa pressure drop, MWD 1.04SG, EMW 2.60SG, no leak. | 31 |  | 2018-04-10 00:00:00.000 | [6 empty] | 2018-04-10 00:00:00.000 | 2018-03-10 15:30:00.000 | 360.8924 | 11017.0607 | 2018-03-31 15:00:00.000 | 6.125 | 9.1146 | 20.9792 | 30.3542 | 20.1784 | 525.1429
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB024-D01 |  |  | Y113-Y133 | S Shaped |  | 2018-04-23 17:00:00.000 | Primary Drilling | SCP-50009 | Drilled from 2020m to 2084m, circulation hole clean, POOH to surface | M/U BHA, RIH, Drilling | 2D54099CD7834E349FE1061279261D62 | Drilled from 2084m to 2091m, ROP 3.5m/h. WOB 8-12t, flow rate 30L/s, SPP 10-12MPa | 0 |  | 2018-04-23 00:00:00.000 | [6 empty] | 2018-06-05 14:30:00.000 | 2018-04-23 16:00:00.000 | 381.8898 | 11666.667 | 2018-05-26 13:00:00.000 | 2.2083 | 18.7917 | 32.8333 | 42.8958 | 5.1481 | 355.33
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB024-H02 |  |  | Y113-Y133 | Horizontal |  | 2018-06-17 19:00:00.000 | Primary Drilling | SCP-50009 | RIH, Drill out cement plug, circulation, POOH to surface, preparation for 6" section drilling | 6" section drilling | 2D54099CD7834E349FE1061279261D62 | RIH to 3388m, touch the top of cement plug | 81.4 |  | 2018-09-06 09:36:00.000 | [6 empty] | 2018-12-29 13:00:00.000 | 2018-06-17 19:00:00.000 | 378.937 | 14957.3496 | 2018-12-20 06:30:00.000 | 98.8229 | 140.1667 | 185.4792 | 194.75 | 50.7435 | 80.6417
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB024-H03 |  |  | Y113-Y133 | Horizontal | development / gas | 2019-04-11 18:00:00.000 | Primary Drilling | SCP-50009 | 6‘’ hole section drilling | 6‘’ hole section drilling | 2D54099CD7834E349FE1061279261D62 | 6" hole section drilling from 3871 to 3881m Rotation drilling: ROP 1.55m/h, WOB 7-8t, FL 15l/s, SPP 19-20MPa, RPM 30r/min, Torque 15-17KN.m. | 90 |  | 2019-07-10 00:00:00.000 | [6 empty] | 2019-07-30 09:00:00.000 | 2019-04-11 18:00:00.000 | 246.063 | 15797.2446 | 2019-07-15 17:30:00.000 | 20.8438 | 46.4583 | 94.9792 | 109.625 | 19.0137 | 166.3233
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB006-D04 | 36 | 109 | Y113-Y133 | Build & Hold | Gas Well | 2018-08-22 16:30:00.000 | Primary Drilling | SCP-50010 | Cleaned conductor, drilled 12 1/4" hole from 65m to 119m, encountered mud loss. POOH to 65m and changed TDS saver sub. | Drill 12 1/4" hole as per plan. | 2D54099CD7834E349FE1061279261D62 | POOH from 119m to 65m. | 32 |  | 2018-09-23 00:00:00.000 | [6 empty] | 2018-10-05 15:30:00.000 | 2018-08-22 16:30:00.000 | 213.2546 | 11272.9662 | 2018-09-24 03:00:00.000 | 5.0521 | 14.625 | 32.4375 | 43.9583 | 11.4929 | 347.5288
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB006-D07 |  |  | Y113-Y133 |  |  |  | Primary Drilling | SCP-50010 | WOC, M/U BHA, RIH, drill out cement plug, drill ahead to 208m. | Drill ahead as per plan, POOH, running casing and cementing | 2D54099CD7834E349FE1061279261D62 | Wait for LCM function | 32.4 |  | 2018-12-07 09:36:00.000 | [6 empty] | 2018-12-18 13:00:00.000 | 2018-11-05 15:00:00.000 | 417.6509 | 12116.1421 | 2018-12-05 01:15:00.000 | 6.3229 | 9.8125
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB006-H01 |  |  | Y113-Y133 | Horizontal |  | 2019-09-22 01:00:00.000 | Primary Drilling | SCP-50010 | RIH, small bit drill to 405.5m for nudging up, change regular bit to redrill | Drill ahead, running casing and cementing | 2D54099CD7834E349FE1061279261D62 | Drill 17 1/2in section with 12.25in bit to nudge up, drill to 405.5m Rotating with ROP 28-36m/hr, WOB 4-6T, SRPM 45. FR 56L/S, SPP 10MPa, TQ 6-8KN.m Sliding with ROP 12-17m/hr, WOB 4-6T Enter YanChang Formation at 343m | 90 |  | 2019-12-21 00:00:00.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-09-22 01:00:00.000 | 488.8452 | 9035.4334 | 2019-10-17 18:30:00.000 | 1.2396 | 8.7396 | 25.7292 | 29.9583 | 4.1377 | 351.1747
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB006-H02 |  |  | Y113-Y133 | Horizontal | Development | 2019-03-20 00:00:00.000 | Primary Drilling | SCP-50010 | POOH, L/D BHA, Wiper trip run, rig maintenance | Running casing | 2D54099CD7834E349FE1061279261D62 | POOH, L/D BHA, bit grading 2-5-WT-A-X-1/16-NO-TD | 100 |  | 2019-06-28 00:00:00.000 | [6 empty] | 2019-09-07 10:00:00.000 | 2019-03-20 00:00:00.000 | 334.6457 | 16437.0084 | 2019-07-19 02:30:00.000 | 23.4896 | 69.1771 | 121.1042 | 171.4167 | 13.7032 | 135.7262
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB367-D04 |  |  | Y113-Y133 | S Shaped |  |  | Primary Drilling | SCP-50010 | Drilling | Drilling,circulation,POOH | 2D54099CD7834E349FE1061279261D62 | Drilled 12 1/4" hole from 32.64 m to 181 m. | 0 |  | 2018-06-11 00:00:00.000 | [6 empty] | 2018-06-11 12:00:00.000 | 2018-06-11 00:00:00.000 | 107.0866 | 626.6404 | 2018-06-11 12:00:00.000 | 0 | 0
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB013-D01 |  |  | Y113-Y133 | S Shaped |  | 2019-10-13 15:00:00.000 | Primary Drilling | SCP-50034 | Drill to section TD, casing | Cementing and drill ahead as per plan | 2D54099CD7834E349FE1061279261D62 | POOH to surface and L/D BHA, bit grading 0-1-WT-S-X-I-NO-TD | 29 |  | 2019-10-13 00:00:00.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-10-13 15:00:00.000 | 180.4462 | 4996.7193 | 2019-10-22 00:00:00.000 | 0.89583 | 3.8958 | 8.375 | 8.375 | 10.6965 | 596.6232
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB282-D04 | 29.32 | 38.59 | Y113-Y133 | S Shaped | Appraisal well | 2019-07-10 10:00:00.000 | Primary Drilling | SCP-50035 | Driling 12.25" borehole, wiper trip, run in 9 5/8" casing. |  | 2D54099CD7834E349FE1061279261D62 | Lay down BHA, bit, motor. | 0 |  | 2019-07-09 00:00:00.000 | [6 empty] | 2019-09-03 20:00:00.000 | 2019-07-09 21:00:00.000 | 278.8714 | 12483.5962 | 2019-08-27 08:00:00.000 | 20.9062 | 27.6979 | 47.9167 | 55.4167 | 37.7256 | 260.5272
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB282-H06 | 36.57 | 109.27 | Y113-Y133 | Horizontal | Horizontal well |  | Primary Drilling | SCP-50035 |  |  | 2D54099CD7834E349FE1061279261D62 | RIH to bottom,mud returns normally. | 0 |  | 2018-11-16 00:00:00.000 | [6 empty] | 2019-06-26 00:00:00.000 | 2018-11-16 09:00:00.000 | 0 | 14163.3863 | 2019-06-15 04:00:00.000 | 47.0938 | 95.1979
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB023-D06 |  |  | Y113-Y133 | S Shaped |  | 2019-04-01 16:00:00.000 | Primary Drilling | SCP-50036 | 8-1/2" hole drilling | 8-1/2" hole drilling | 2D54099CD7834E349FE1061279261D62 | Drill 8-1/2" hole from 1070m to 1129m, WOB 8T, RPM 65, FR 32L/s, pump pressure 8.5 Mpa, torque 8-9Kn.m | 31.5 |  | 2019-05-02 12:00:00.000 | [6 empty] | 2019-05-04 17:00:00.000 | 2019-04-01 16:00:00.000 | 500.3281 | 11843.8324 | 2019-04-29 08:30:00.000 | 0.72917 | 13.8958 | 27.6875 | 33.0417 | 2.2068 | 427.7682
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB023-D07 |  |  | Y113-Y133 | S Shaped | development | 2019-05-07 18:00:00.000 | Primary Drilling | SCP-50036 | drill 8.5in hole | drill 8.5in hole, circulate, POOH, MU BHA, RIH, drill 8.5in hole | 2D54099CD7834E349FE1061279261D62 | rotate drill 8.5in hole from 1079.20m to 1191m, WOB6-8t, RPM65, torque5-7KN.m, flow rate 32L/s, pump pressure 9-10Mpa | 33 |  | 2019-06-09 00:00:00.000 | [6 empty] | 2019-06-20 00:00:00.000 | 2019-05-07 18:00:00.000 | 139.2388 | 13172.5726 | 2019-06-11 10:00:00.000 | 4.3021 | 14.5833 | 34.6667 | 43.25 | 9.947 | 379.9781
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB023-D08 |  |  | Y113-Y133 |  |  | 2019-06-23 00:00:00.000 | Primary Drilling | SCP-50036 | make preparatipn for drilling, drill cement, dill 8.5in hole | drill 8.5in hole as plan | 2D54099CD7834E349FE1061279261D62 | drill 8.5in hole, ROP38.63m/h WOB:6-8t, RPM 65, TQ3-5Kn.m, FR32L/s, PP8-10Mpa | 35 |  | 2019-07-28 00:00:00.000 | [6 empty] | 2019-07-26 19:00:00.000 | 2019-06-23 00:00:00.000 | 356.3976 | 12860.8928 | 2019-07-16 08:00:00.000 | 4.4375 | 9.5521 | 23.3333 | 33.7917 | 13.1319 | 551.1811
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB461-D07 |  |  | Y113-Y133 | S Shaped | Development | 2018-09-18 13:30:00.000 | Primary Drilling | SCP-50036 | 8-1/2" hole drilling to 1656m | drill 8-1/2" hole. | 2D54099CD7834E349FE1061279261D62 | 8-1/2" hole section drilling from 1472 to 1546m. Rotation footage:69m, ROP 21.57m/h, WOB: 7-9t, RPM 65r/m, FL: 30L/s, SPP 8-9MPa, Torque: 11-16KN.m. Sliding footage:5m, ROP 6.67m/h, WOB: 8-12t, FL: 30L/s, SPP 8-9MPa | 29 |  | 2018-10-17 00:00:00.000 | [6 empty] | 2018-10-18 23:30:00.000 | 2018-09-18 13:30:00.000 | 101.706 | 11227.0345 | 2018-10-11 21:30:00.000 | 0.17708 | 10.9688 | 23.3333 | 30.4167 | 0.58219 | 481.1586
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB461-D08 |  |  | Y113-Y133 |  |  | 2018-10-23 12:30:00.000 | Primary Drilling | SCP-50036 | N/U BOP, pressure test, drill out cement plug, casing pressure test, FIT, 8-1/2" hole drilling | 8-1/2" hole drilling | 2D54099CD7834E349FE1061279261D62 | Drill out cement plug to 354m. WOB 1-2T，RPM 65r/min+LZ，FL 20L/s，SPP 4.5-5.5MPa，TORQUE2-5KN.m. | 29 |  | 2018-11-21 00:00:00.000 | [6 empty] | 2018-11-23 10:30:00.000 | 2018-10-23 12:30:00.000 | 104.9869 | 12099.7379 | 2018-11-13 01:00:00.000 | 1.125 | 5.1771 | 20.5208 | 30.9167 | 3.6388 | 589.6319
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB046 | 36.51 | 109.23 | Y113-Y133 | Vertical | development |  | Mobilization-Drill | SCP-50037 | Driled 12.25" borehole to 554.4m. circulated to hole clean, pump hi-vis pill sweep the hole prior to trip out to 87m. | Running casing, conducting cement job,WOC, rig up well head. | 2D54099CD7834E349FE1061279261D62 | Drilling 12.25" borehole from 432m to 554.4m. WOB:3-4T;footage:122.4m.torque:3-4kn.m; SPP:14Mpa; FR:50l/s;ROP:10.5m/h; | 0 |  | 2019-03-28 00:00:00.000 | [6 empty] | 2019-05-09 20:00:00.000 | 2019-04-05 00:00:00.000 | 167.3228 | 11026.9032 | 2019-04-27 12:30:00.000 | 0.9375 | 9.2812
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB046-H01 | 36.51 | 109.23 | Y113-Y133 | Horizontal | Development | 2019-05-16 14:00:00.000 | Primary Drilling | SCP-50037 | WOC for conductor cementing job. M/U BHA and RIH to bottom, drilling 17.5" bore hole section.correct flow line due to plug. | Drilling 17.5" bore hole section to TD. circulated clean the hole. run 13.375" casing. | 2D54099CD7834E349FE1061279261D62 | Drilling 17.5" borehole from 97m to 138m. WOB:3-4T; RPM:30;FR:30l/s; SPP:5-6Mpa; footage:41m; drilling hour:3h; ROP:11.5m/h; | 0 |  | 2019-05-16 00:00:00.000 | [6 empty] | 2019-09-02 18:00:00.000 | 2019-05-16 14:00:00.000 | 224.5407 | 14944.2262 | 2019-08-22 08:00:00.000 | 21.3958 | 55.6875 | 97.75 | 109.1667 | 19.5992 | 152.8821
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB053 |  |  | Y113-Y133 | Vertical |  | 2018-10-12 23:00:00.000 | Primary Drilling | SCP40004 | WOC, spud well | Drill 12 1/4in section | 2D54099CD7834E349FE1061279261D62 | WOC, prepare for spud | 30 |  | 2018-11-11 00:00:00.000 | [6 empty] | 2018-11-30 00:00:00.000 | 2018-10-12 00:00:00.000 | 328.084 | 10997.3757 | 2018-11-14 14:00:00.000 | 7.3958 | 22.9688 | 32.625 | 48.0417 | 15.3946 | 337.0843
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB015-D02 | 37.3 | 109.5 | Y113-Y133 | S Shaped | Development well | 2018-03-10 14:00:00.000 | Primary Drilling | SCP50002 | WOC, Prepare for 8.5 HS operation,M/U BHA, RIH and drilled out plug, Casing pressure test, D/A to MD 352m, performed LOT, D/A 8.5 HS to MD 544m. | D/A 8.5 HS per plan. | 2D54099CD7834E349FE1061279261D62 | Prepare for 8.5 HS operation | 0 |  | 2018-03-10 00:00:00.000 | [6 empty] | 2018-04-09 05:00:00.000 | 2018-03-10 14:00:00.000 | 175.689 | 11089.2392 | 2018-04-02 01:30:00.000 | 3.6771 | 6.9688 | 22.4792 | 29.625 | 12.4121 | 493.3118
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB015-H03 | 37.146 | 109.622 | Y113-Y133 | Horizontal | Development |  | Primary Drilling | SCP50002 | Drilled to 17.5" section TD 306.5m. Circulated hole clean. POOH. R/U Casing running tools. Found poor quality of 13 3/8" casing. Waited for service engineer from manufacture. Cont'd RIH 13 3/8" casing. Waited for cementing. | Conduct 13 3/8" cementing job. WOC. | 2D54099CD7834E349FE1061279261D62 | POOH to surface. | 80.02 |  | 2018-11-14 00:29:57.000 | [6 empty] | 2018-11-23 13:30:00.000 | 2018-08-26 00:00:00.000 | 144.357 | 14527.5595 | 2018-11-15 20:30:00.000 | 16.3958 | 39.8229
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB015-H04 | 37.146 | 119.622 | Y113-Y133 | Horizontal |  | 2018-04-22 17:00:00.000 | Primary Drilling | SCP50002 | POOH, M/U 6' HS BHA, SHT with 18l/s,SPPA 8.5-9Mpa, RIH, Liner pressure test,Drill out plug and DV, 6" HS D/A. | 6" HS D/A per geological instruction. | 2D54099CD7834E349FE1061279261D62 | 6" HS D/A. Rotated drill 15m, Sliding 4m. Drilling parameter: WOB 5-6t, SRPM 42rpm, Torque 17-18kn.m, FR 18l/s. | 80.02 |  | 2018-07-11 00:29:57.000 | [6 empty] | 2018-07-29 03:00:00.000 | 2018-04-22 17:00:00.000 | 150.853 | 14566.9296 | 2018-07-10 18:30:00.000 | 12.1042 | 38.5729 | 79.0625 | 97.4167 | 12.4251 | 184.2457
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB014-D02 |  |  | Y113-Y133 |  |  | 2019-10-12 18:00:00.000 | Primary Drilling | SCP50003 | Drill ahead POOH due to low ROP | POOH and change bit, RIH and resume drilling | 2D54099CD7834E349FE1061279261D62 | Circulate hole clean | 28 |  | 2019-11-09 00:00:00.000 | [6 empty] | 2019-10-22 00:00:00.000 | 2019-10-14 00:00:00.000 | 1830.7087 | 5905.512 | 2019-10-22 00:00:00.000 | 0 | 3.4583 | 9.25 | 9.25 | 0 | 638.4337
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB014-D05 |  |  | Y113-Y133 | S Shaped | Development | 2019-04-10 20:00:00.000 | Primary Drilling | SCP50003 | preparation to 8-1/2” drilling section, inspection of rig, 8-1/2” hole section drilling to 464m | 8-1/2” section drilling | 2D54099CD7834E349FE1061279261D62 | RIH to 395.5m and touch the top of cement. Cement height 28.58m | 30 |  | 2019-05-10 00:00:00.000 | [6 empty] | 2019-05-30 05:00:00.000 | 2019-04-10 20:00:00.000 | 0 | 10305.1184 | 2019-05-23 17:00:00.000 | 18.9583 | 27.5729 | 42.875 | 49.375 | 38.3966 | 240.3526
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB014-D08 |  |  | Y113-Y133 | S Shaped |  | 2019-08-24 12:00:00.000 | Primary Drilling | SCP50003 | drill as per plan, POOH to cure loss, cure loss | WOC, M/U BHA, RIH | 2D54099CD7834E349FE1061279261D62 | pump DiSaiEr LCM | 30 |  | 2019-09-23 00:00:00.000 | [6 empty] | 2019-10-01 04:00:00.000 | 2019-08-24 12:00:00.000 | 260.6955 | 10226.3783 | 2019-09-25 20:45:00.000 | 12.9271 | 18.4375 | 32.3646 | 37.6667 | 34.3197 | 315.9744
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB014-H03 |  |  | Y113-Y133 | Horizontal | Development |  | Primary Drilling | SCP50003 | wiper trip | completion job | 2D54099CD7834E349FE1061279261D62 | M/U BHA and run reamer BHA | 90 |  | 2019-09-01 00:00:00.000 | [6 empty] | 2019-08-17 22:00:00.000 | 2019-06-03 22:00:00.000 | 246.063 | 13750.0004 | 2019-08-10 01:00:00.000 | 5.6458 | 33.5104
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB509-D01 | 37.1405 | 109.5469 | Y113-Y133 | S Shaped | Gas well | 2018-03-30 22:00:00.000 | Primary Drilling | SCP50004 | Con't performing full BOP P/T. Rig site standardization. M/U 8 1/2" BHA and RIH, drill out shoetrack. | Con't drilling out shoetrack. Directional drilling 8 1/2" hole as per plan. | 2D54099CD7834E349FE1061279261D62 | P/U & M/U 8 1/2" motor BHA. Performed shallow test, OK. | 0 |  | 2018-04-06 00:00:00.000 | [6 empty] | 2018-06-03 20:00:00.000 | 2018-04-06 00:00:00.000 | 390.42 | 11404.1998 | 2018-05-25 04:00:00.000 | 7.6354 | 24.7708 | 55.25 | 64.9167 | 11.7619 | 206.4109
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB509-H01 | 37.8 | 109.32 | Y113-Y133 | Horizontal | Development | 2018-07-01 14:00:00.000 | Primary Drilling | SCP50004 | Drilled 6" borehole, inspected and repaired mud pump. POOH. | POOH, conducted CBL operation, M/U BHA, RIH. | 2D54099CD7834E349FE1061279261D62 | Drilled 6" borehole from 3767m to 3782m. WOB:5-6t; RPM:45-48r/m; torque:20-22KN.M; SPP:18-20.5Mpa; FR:18l/s;drilling time:4.5h; ROP:3.77m/h;footage:15m. | 0 |  | 2018-07-01 00:00:00.000 | [6 empty] | 2018-12-24 20:00:00.000 | 2018-07-01 14:00:00.000 | 488.8452 | 14425.8535 | 2018-12-11 09:00:00.000 | 52.5521 | 113.8021 | 162.7917 | 176.25 | 29.8168 | 88.6154
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB509-H02 | 37.8 | 109.32 | Y113-Y133 | Horizontal | Development | 2019-04-23 18:00:00.000 | Primary Drilling | SCP50004 | Drilling 17.5" borehole. | Drilling 17.5" borehole. | 2D54099CD7834E349FE1061279261D62 | M/U 17.5" BHA. -17.5" PDC bit -244mm* motor -Oriented sub -NMDC203.3mm*1joint -203mm DC*3joints -X/O sub -177.8mm DC*7joints -127mm HWDP | 0 |  | 2019-04-23 00:00:00.000 | [6 empty] | 2019-09-11 10:30:00.000 | 2019-04-23 00:00:00.000 | 426.5092 | 14612.8614 | 2019-08-30 04:30:00.000 | 40.7604 | 82.6562 | 128.4375 | 140.6875 | 28.9723 | 113.7741
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB002-D01 | 37.054 | 109.06 | Y113-Y133 | S Shaped |  | 2019-03-18 14:00:00.000 | Primary Drilling | SCP50031 | Performed and completed pre-spud check list. M/U 12 1/4" BHA. RIH. Tagged TOC at 69.5m. Drilled out of cement. Spud the well at 14:00. Drilled 12 1/4" hole to 264.42m. | Continue drilling 12 1/4" hole to section TD. Short trip and POOH. | 2D54099CD7834E349FE1061279261D62 | Drilled 12 1/4" hole to 264.42m. | 32 |  | 2019-04-19 00:00:00.000 | [6 empty] | 2019-04-29 12:00:00.000 | 2019-03-18 00:00:00.000 | 346.1286 | 11213.9111 | 2019-04-22 17:00:00.000 | 4.9375 | 16.5208 | 35.125 | 41.9167 | 11.7793 | 319.2573
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB002-H02 | 37.054 | 109.601 | Y113-Y133 | Horizontal |  |  | Primary Drilling | SCP50031 | Cont'd drilling 17.5" hole to section TD depth 496.5m. Circulated hole clean. POOH and run 13 3/8" casing to 174m. | Run 13 3/8" casing to bottom. Conduct cement job. | 2D54099CD7834E349FE1061279261D62 | POOH into 20" conductor. | 80.02 |  | 2018-11-18 00:29:57.000 | [6 empty] | 2018-12-04 00:00:00.000 | 2018-08-30 12:00:00.000 | 331.3648 | 14183.0713 | 2018-11-23 10:00:00.000 | 15.3438 | 42.7917
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB002-H06 T06 | 37.318 | 109.362 | Y113-Y133 | Horizontal | Gas Producer |  | Primary Drilling | SCP50031 | PJSM. P/U and M/U BHA. Drill 17 1/2" hole from 50 m to 69 m. Observed total loss at 59 m, 64 m and 69 m. Pumped LCM in hole to cure the loss. | Continue drilling 17 1/2" hole. | 2D54099CD7834E349FE1061279261D62 | Observed total loss at 59 m. Stopped drilling. Pumped LCM and monitored loss condition. Observed hole loss was secured at 14:00. | 0 |  | 2018-04-04 00:00:00.000 | [6 empty] | 2018-07-13 07:00:00.000 | 2018-04-04 00:00:00.000 | 164.042 | 15488.8456 | 2018-06-27 08:30:00.000 | 12.4896 | 40.2813
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB054 | 37 | 109 | Y113-Y133 |  | Vertical Well | 2018-10-03 00:00:00.000 | Primary Drilling | SCP50032 | RIH 17 1/2" BHA and drilled to 227 m. POOH due to low ROP. Changed BHA. RIH and cont'd drilling to 290 m. | Con't drilling 17 1/2" hole to section TD. POOH. Run surface casing and cement. | 2D54099CD7834E349FE1061279261D62 | POOH to surface. | 0 |  | 2018-10-03 00:00:00.000 | [6 empty] | 2018-11-09 10:00:00.000 | 2018-10-03 00:00:00.000 | 380.5774 | 10383.8586 | 2018-11-01 01:00:00.000 | 0 | 14.6458 | 29.0417 | 37.4167 | 0 | 357.5504
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB064-D05 |  |  | Y113-Y133 | S Shaped |  | 2019-09-02 15:00:00.000 | Primary Drilling | SCP50032 | drill as per plan, circulate, POOH | POOH, M/U BHA, RIH, drill as per plan | 2D54099CD7834E349FE1061279261D62 | rotate drilling with WOB 8-12t, RPM45, TQ4-6Kn.m, FR30L/s, PP10-12Mpa, ROP 11-14m/h sliding with WOB 8-12, FR30L/s, PP10-11Mpa, ROP5m/h | 29 |  | 2019-10-01 00:00:00.000 | [6 empty] | 2019-10-01 01:00:00.000 | 2019-09-02 15:00:00.000 | 100.0656 | 11049.8691 | 2019-09-24 07:00:00.000 | 1.1458 | 7.1146 | 21.6667 | 28.4167 | 4.0323 | 509.994
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB064-D06 |  |  | Y113-Y133 | S Shaped |  | 2019-07-21 12:00:00.000 | Primary Drilling | SCP50032 | CIT, Drill as per plan, FIT,drill as per plan | drill as per plan | 2D54099CD7834E349FE1061279261D62 | Drill with WOB 2-3t, RPM45, TQ 3-5Kn··m, FR30L/s, PP 7-8Mpa | 30 |  | 2019-08-20 00:00:00.000 | [6 empty] | 2019-08-21 00:00:00.000 | 2019-07-21 12:00:00.000 | 134.5144 | 11400.919 | 2019-08-15 07:30:00.000 | 1.3854 | 8.5313 | 24.8125 | 30.5 | 4.5423 | 459.4829
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB064-D08 | 36.94 | 109.42 | Y113-Y133 | S Shaped |  | 2019-06-12 00:00:00.000 | Primary Drilling | SCP50032 | RIH, drill cemnt and shoe track, CIT, drill 8.5in hole, FIT, drill 8.5in hole | drill 8.5in hole | 2D54099CD7834E349FE1061279261D62 | FIT, MW1.05SG, pump pressure4.2Mpa, EMD 2.15SG | 29.8 |  | 2019-07-11 19:12:00.000 | [6 empty] | 2019-07-12 00:00:00.000 | 2019-06-12 00:00:00.000 | 132.874 | 11227.0345 | 2019-07-05 09:00:00.000 | 5.4687 | 8.2083 | 23.375 | 30 | 18.2292 | 480.3009
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB163-H05 T02 | 37.4 | 109.33 | Y113-Y133 | Horizontal | Gas producer | 2018-04-29 18:00:00.000 | Primary Drilling | SCP50032 | Drilled 17.5 " bore hole from 79m to 148.77m. due to oriented reason, change 12.25" BHA, drilled 12.25" bore hole from 148.77m to189m. circulated and POOH to 28.5m. | POOH to surface ,change 17.5" bit ,run in and reaming to 189m, continue 17.5" bore hole drilling. | 2D54099CD7834E349FE1061279261D62 | Slide drilling 17.5 section from 125m to 148.77m, total footage: 23.77m , WOB:5-7T; FR:56L/S ; RPM:118 motor;ROP :3.65m/h; sliding time:6.51h; pumped 1.085sg, 70s ,hi-vis pill 20m³ to sweep the hole. No effective in inclination control. | 0 |  | 2018-04-29 00:00:00.000 | [6 empty] | 2018-09-03 21:00:00.000 | 2018-04-29 18:00:00.000 | 147.6378 | 13032.9072 | 2018-08-22 05:30:00.000 | 38.7812 | 69.1458 | 114.4792 | 127.125 | 30.5064 | 113.8452
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB361-D05 | 37.1 | 109.3 | Y113-Y133 | S Shaped | Development | 2018-03-08 06:30:00.000 | Mobilization-Drill | SCP50032 | Performed sealing operation, drilling 12.25" section to 569m, circulating until hole clean, POOH, run in casing to 230m. | Circulating, cementing, WOC. | 2D54099CD7834E349FE1061279261D62 | Circulating and cleaning the hole . | 0 |  | 2018-03-08 00:00:00.000 | [6 empty] | 2018-04-09 04:00:00.000 | 2018-03-08 06:30:00.000 | 321.5223 | 11131.8901 | 2018-04-01 04:30:00.000 | 2.6458 | 8.7188 | 23.9167 | 31.8958 | 8.2952 | 465.4449
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB004-D08 | 37132.85 | 1093641.54 | Y113-Y133 | S Shaped |  | 2018-06-06 21:30:00.000 | Primary Drilling | SCP50033 | Drilling 12-1/4" section from 68to 436.23m,POOH | POOH,run casing,cementing,WOC | 2D54099CD7834E349FE1061279261D62 | Slide drilling 12-1/4" section from 77.4m to 85.4m Drilling parameters: WOB:3-4t, FR:30-32L/s, SPP:3-4Mpa, | 0 |  | 2018-06-06 00:00:00.000 | [6 empty] | 2018-08-14 20:00:00.000 | 2018-06-06 21:30:00.000 | 139.1076 | 10787.4019 | 2018-08-05 05:45:00.000 | 21.0833 | 45.1146 | 59.3438 | 68.9375 | 30.5833 | 181.7782
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB004-H02 |  |  | Y113-Y133 | Horizontal |  | 2018-09-21 22:00:00.000 | Primary Drilling | SCP50033 | Drilled， circulation，short trip， wait on geologic order. | wait on geologic order. | 2D54099CD7834E349FE1061279261D62 | wait on geologic order. | 0 |  | 2018-09-21 00:00:00.000 | [6 empty] | 2018-12-13 12:00:00.000 | 2018-09-21 22:00:00.000 | 0 | 12467.192 | 2018-12-07 05:30:00.000 | 13.1875 | 46.8542 | 76.3125 | 82.5833 | 15.9687 | 163.3702
EH | FEA | China | 2D54099CD7834E349FE1061279261D62 | 499 | 200000000000000000262017 | SCP CHINA YC113 133 | SPM | Asia | Day Rate | YB011 T03 |  |  | Y113-Y133 | Vertical |  | 2018-09-03 04:00:00.000 | Primary Drilling | SCP50033 | killing mud loss, 8-1/2" hole section drilling, killing mud loss, 8-1/2" hole section drilling | Killing mud loss, 8-1/2" hole section drilling | 2D54099CD7834E349FE1061279261D62 | Killing mud loss operation: *06:00-10:00 mix 120m³ mud with LCM. *10:00-10:45 pumped 18m³ mud with LCM, displaced 20m³ mud, volume returned was as measured. | 29 |  | 2018-10-02 00:00:00.000 | [6 empty] | 2018-10-16 19:00:00.000 | 2018-09-03 04:00:00.000 | 98.4252 | 9891.7326 | 2018-10-04 06:00:00.000 | 2.625 | 15.8438 | 31.0833 | 43.625 | 6.0172 | 318.2327
EH | SEA | Bangladesh | D8BAD13B75D742D6ACE8202EB4CCF0A2 |  | 256554 | SEA_BD_BAPEX_IDS_4 Wells_2017-18 | IDS | Asia | Day Rate | Semutang S1 | 22.8142 | 91.7747 | Semutang Gas | Vertical | Exploration | 2018-07-29 16:35:00.000 | Primary Drilling | SOCAR AQS-1 | Conduct PJSM and JSA. R/U Schlumberger Wireline equipment and sheaves. P/U and M/U logging tools (USIT-CBL-VDL-GR). RIH USIT-CBL-VDL-GR tool string and log to 1998.5m and Log out to 190m. Re-log with changed parameters from 720 m to 190m. R/D wireline equipment and sheaves. P/U and M/U pendulum BHA with MT bit. RIH on singles of 5" DP to 768m. | Cont. RIH on 5" DP until 1980m. Wash down at tag cement/shoe at 2002m. Drill out shoe, clean rat hole and drill 3m new formation. Circulate and POOH to shoe. Perform FIT. RIH to bottom and time drilling 8 1/2" hole section. | D8BAD13B75D742D6ACE8202EB4CCF0A2 | Hold PJSM and JSA Rig up and M/U 8 1/2" MT bit and RIH with BHA to 113 m. | 86.34 |  | 2018-11-28 22:06:12.000 | 140 | [5 empty] | 2018-11-01 05:00:00.000 | 2018-07-28 00:00:00.000 | 0 | 9645.6696 | 2018-10-25 06:00:00.000 | 26.0417 | 75.4792 | 87.559 | 94.5174 | 27.5523 | 110.1619
EH | SEA | India | 10176026005C4AEBB0D7279BD4FB2CFC |  | 433475 | SEA_IN_Cairn_IDS_KG Offshore Exploration | IDS | Asia | LSTK | A3-2 | 15.4573 | 80.5284 | KG-OSN- 2009/3 | Vertical | Exploration | 2018-04-28 11:30:00.000 | Primary Drilling | West Telesto | Perform full BOP pressure test and test inner and outer SOV of wellhead. Install wear bushing. M/U and RIH 8-1/2" BHA. Wash down and tag TOC at 3085.7 m. Perform choke drill with 1st drill crew | Perform choke drill with 2nd drill crew. Drill out cement and shoe track. Circulate hole clean. Run 8 1/2" section LOT. Drill 8-1/2" hole section | 10176026005C4AEBB0D7279BD4FB2CFC | Make up TDS and fill up pipe completely. Perform shallow hole test MLWD tools @ 400gpm 500psi - Good test | 111.75 |  | 2018-08-17 18:00:00.000 | 210 | [5 empty] | 2018-09-12 11:00:00.000 | 2018-04-28 11:30:00.000 | 0 | 12939.633 | 2018-06-25 19:45:00.000 | 24.8854 | 37.2083 | 58.3438 | 136.9792 | 18.1673 | 221.7827
EH | SEA | India | 10176026005C4AEBB0D7279BD4FB2CFC |  | 433475 | SEA_IN_Cairn_IDS_KG Offshore Exploration | IDS | Asia | LSTK | H2 | 15.3609 | 80.583 | KG-OSN- 2009/3 | Deviated | Exploration | 2019-01-18 17:00:00.000 | Primary Drilling | West Telesto | Continued M/U 8-1/2" drilling BHA and RIH to tag TOC at 3168 m. Performed choke drill. Drilled out shoe track and 3 m of new formation. Performed LOT to 16.1 ppg EMW. Drilled 8-1/2" hole section to 3330 m. | Drill 8-1/2" hole section to well TD at +/- 4200 m | 10176026005C4AEBB0D7279BD4FB2CFC | Made up and RIH 8 x 6-3/4” DC, 4 x 5-1/2” HWDP, 6-1/2" jar, 6 x 5-1/2” HWDP to 221 m. | 112.55 |  | 2019-05-10 13:12:00.000 | 208.6964 | [5 empty] | 2019-03-26 13:00:00.000 | 2019-01-18 17:00:00.000 | 0 | 13248.0319 | 2019-02-25 02:00:00.000 | 3.5938 | 25.5729 | 37.375 | 66.8333 | 5.3772 | 354.4624
WH | NAL | United States | BDB7610DC2A8496DA08EB0E61CA8AED6 |  |  | SLR ROF Test | SLR | NAM | Other | ROF CT TEST WELL 1 | 30.903 | -97.023 | Watt Farm Pad 2 | Deviated | J Type | 2019-01-15 08:45:00.000 | Primary Drilling | SLR-601 | Performed Software updates/ Offline stand building. | working on COW Package #1/ Off line stand building | BDB7610DC2A8496DA08EB0E61CA8AED6 | TDA man basket training and TDA man basket practical | 10.13 |  | 2019-02-28 03:01:39.000 | [6 empty] | 2019-03-22 05:15:00.000 | 2019-02-18 00:00:00.000 | 5238.0002 | 5239.0002 | 2019-02-21 21:00:00.000 | 1.9271 | 3.7917 | 37.5104 | 65.8542 | 2.9263 | 139.6679
EH | EME | Oman | B598842C10FB4934A99BF2C48DD4BA59 |  |  | SLR-Oman | SLR | Gulf |  | SADAD 18 |  |  |  | Horizontal |  |  | Primary Drilling | SLR-207 |  |  | B598842C10FB4934A99BF2C48DD4BA59 |  | 56 |  | 2018-06-19 23:59:03.000 | [6 empty] | 2018-04-27 00:00:00.000 | 2018-04-25 00:00:00.000 | 0 | 1640.42 | 2018-04-26 22:00:00.000 | 0.375 | 0.75
EH | RCA | Georgia | D5E045596A03464286D35926ED73CD6D |  | 281702 | SPM IDS Rustaveli Project Georgia | IDS | RCA | Day Rate | PAT-E1 | 41.437 | 45.1058 |  | Vertical | Exploratory | 2018-05-31 12:00:00.000 | Mobilization-Drill | ZJ-50 DBS | R/U cementing head and lines. 1st stage cementing: Held PJSM. Pressure test lines to 3000psi. Pumping spacer 90 bbl (1.06 SG), pump batch mix slurry 200 bbls LiteCRETE (1.10 SG). Pump 100 bbls "G" TAIL slurry (1.92 SG). Drop top plug, displace it with 689 bbls water. Final displacement pressure is 50 psi, Bump plug with 750 psi (700 psi over), no water returns to surface. Inflate TAM packer with 1446psi - positive indicator for 26 psi - packer open, held 1420 psi open for 30 mins - increase pressure to 3000 psi to close port. Bled off 1000 psi to confirm packer fluid loss - 0.01 bbls - OK. Bled pressure to 0. N/D cementing head. Drop gravity bomb, confirmed plug set and stage tool open with 300 psi and 5 blls water. Circulate prior to stage #2 and while premix (Q=40 lps; P=34 atm). 2nd stage: Held PJSM. Lines pressure test to 7000 psi. Mix and pump 401 bbls "G" TAIL slurry (1.92 SG). Current operation: Cement displacement with water (total volume is 490bbls). Total Daily Loss – | WOC | D5E045596A03464286D35926ED73CD6D | Circulation through CRT, R/D TRS casing running tool | 144.8 |  | 2018-10-23 01:12:00.000 | [6 empty] | 2018-11-20 06:00:00.000 | 2018-05-31 12:00:00.000 | 0 | 16469.8168 | 2018-11-19 06:00:00.000 | 32.3854 | 131.6042 | 171.75 | 172.75 | 18.747 | 95.8941
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAC-172 RE | -0.7315 | -76.8796 | Auca | Deviated |  |  | Re-Entry | Hilong-15 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | ARMÓ TUBO A TUBO CALIBRANDO 6 JUNTAS DE HWDP 3 1/2" HT38 + 33 JUNTAS DE DP DE 3 1/2" HT 38. PROBÓ CADA 6 JTAS CON 3,000 PSI x 10 min, ok. ** QUEBRÓ 2 JUNTAS DE HWDP 3 1/2" HT38 AL OBSERVAR QUE NO HACE SELLO SACÓ TUBERÍA EN PARADAS A LA TORRE. QUEBRÓ VÁLVULA KELLY COCK, 1 JTA HWDP NC38 Y XO | 19.67 |  | 2018-12-26 22:04:48.000 | [6 empty] | 2018-12-22 23:00:00.000 | 2018-12-08 04:00:00.000 | 9386.0003 | 11500.0004 | 2018-12-20 11:00:00.000 | 0.020833 | 8.8125
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAD-098 RE | -0.72231 | -76.8779 | Auca | Deviated | RE-ENTRY |  | Re-Entry | Hilong-15 | INICIO OPERACIONES DE PERFORACION, CAMBIO RAMS SUPERIORES Y PROBO, INSTALO WEAR BUSHING, ARMO BHA #1 CON VALVULA MULTICICLOS Y PROBO, ARMO BHA #1 CON 8" WHIPSTOCK Y 8 1/2" TRI MILL FASTRACK Y REALIZA ORIENTACION. | BAJAR BHA #1 CON 8" WHIPSTOCK Y 8 1/2" TRI MILL FASTRACK A 7,384 PIES, ASENTAR WHIPSTOCK DE ACUERDO A CORRELACION, LIBERAR CONJUNTO TRIMILL Y REALIZAR OPERACIONES PARA ABRIR VENTANA EN CASING 9 5/8". | 79AB7DA4542A4070984C74DA09CB2C63 | RECUPERO TAPON DE PRUEBA Y QUEBRO PARADAS DE 5" HWDP Y 1 PARADA DE 5 1/2" DP. | 13.5 |  | 2018-08-31 18:00:00.000 | [6 empty] | 2018-09-04 23:00:00.000 | 2018-08-18 14:00:00.000 | 7354.0002 | 9533.0003 | 2018-08-26 19:30:00.000 | 5.9583 | 3.0625
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAK-120RE | -0.56833 | -76.901 | Auca | Deviated | Reentry |  | Re-Entry | Hilong-15 | BAJO LINER 7 HASTA FONDO @ 10,951 FT. CEMENTÓ LINER 7. SACÓ SETTING TOOL A SUPERFICIE. ARMÓ BHA TUBO A TUBO | BAJAR BHA ARMANDO TUBO A TUBO 30 JTAS DE DP 3 ½” + 6 JTAS DE DP 5”. CONTINUAR BAJANDO EN PARADAS DE 5 ½” HASTA 10,854 FT. MOLER TAPONES Y CEMENTO. REALIZAR PRUEBA DE CASING. PERFORAR 15 FT DE NUEVA FORMACIÓN REALIZAR FIT. PERFORAR SECCIÓN DE 6 1/8” | 79AB7DA4542A4070984C74DA09CB2C63 | ARMÓ BHA #4 DIRECCIONAL CON BROCA PDC MDi613 (3x13, TFA: 0.389), MOTOR A475M7838XP (BH 1.5) CON CAMISA DE 5 7/8", FLOAT SUB, PONY MONEL, STAB 5 7/8", PERISCOPE HD 475, DIGISCOPE, ADN-4, 3x4 3/4" DC, XO, 24x3 1/2" HWDP, MARTILLO, 9x3 1/2" HWDP, XO, 30 x 3 1/2" DP HT 38 (15.5 LBS/FT), XO, 6 x 5" DP (19.5 LBS/FT), XO, DP 5 1/2" | 19.47 |  | 2018-10-08 17:16:48.000 | [6 empty] | 2018-10-09 00:00:00.000 | 2018-09-19 16:00:00.000 | 9945.0003 | 11774.0004 | 2018-10-05 04:30:00.000 | 3.0625 | 12.25
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAR-128 | -0.72681 | -76.8504 | Auca | Deviated | J | 2018-10-16 22:30:00.000 | Primary Drilling | Hilong-15 | LAVO SECCIONES DEL CABEZAL E INSTALO PACK OFF, ARMO BHA #4 CON BROCA PDC 8 1/2", BAJO HASTA TOPE DE CEMENTO, MOLIO TAPONES, SHOE TRACK, ZAPATO Y FORMACION NUEVA A LA VEZ REALIZO CAMBIO DE FLUIDO, REALIZO FIT Y PERFORO SECCION 8 1/2" HASTA 10,750 FT. | PERFORAR SECCION 8 1/2" SEGUN PROGRAMA HASTA +/- 11,238 FT. | 79AB7DA4542A4070984C74DA09CB2C63 | CONECTO TDS Y REALIZO PRUEBA DE HERRAMIENTAS DIRECCIONALES CON 380 GPM / 850 PSI. OK. | 20.2 |  | 2018-11-05 10:48:00.000 | [6 empty] | 2018-11-06 00:30:00.000 | 2018-10-16 22:30:00.000 | 0 | 11200.0004 | 2018-11-03 14:30:00.000 | 0.47917 | 8.875 | 17.6667 | 20.0833 | 2.3859 | 633.9623
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAR-130 | -0.72678 | -76.85 | Auca | Deviated | J TYPE | 2018-11-07 21:00:00.000 | Primary Drilling | Hilong-15 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | BAJÓ BHA #5 DIRECCIONAL EN HUECO REVESTIDO DESDE 1,680 FT HASTA 11,440 FT (TOC) VELOCIDAD DE BAJADA: 1,500 FT/HR ** ROMPIÓ CIRCULACIÓN Y PROBÓ HERRAMIENTAS DIRECCIONALES CADA 1,500 FT. ** BAJÓ LAS ÚLTIMAS 3 PARADAS CON CIRCULACIÓN POR PRECAUCIÓN CON 350 GPM, 2,000-2,100 PSI. | 24.5 |  | 2018-12-01 18:00:00.000 | [6 empty] | 2018-11-30 23:00:00.000 | 2018-11-07 21:00:00.000 | 0 | 12350.0004 | 2018-11-27 22:00:00.000 | 0.20833 | 11.7917 | 20.0417 | 23.0833 | 0.90253 | 616.2162
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAE-005 WDW | -0.70167 | -76.8763 | Auca | Deviated | J | 2018-08-07 15:00:00.000 | Primary Drilling | SLR-401 | BAJÓ SARTA CON WASHING TOOL, LIMPIO SECCIÓN A Y B DE CABEZAL SOBRE COLGADOR 9 5/8". INSTALÓ PACK OFF. ARMÓ Y BAJO BHA # 4 HASTA 8,245' | TERMINAR DE BAJAR BHA # 4 @ 10, 250', MOLER TAPONES, CEMENTO, REALIZAR PRUEBA DE CASING CONTINUAR MOLIENDO CEMENTO ZAPATO Y 15' DE FORMACIÓN NUEVA, CAMBIAR FLUIDO, REALIZAR FIT, PERFORAR SECCION DE 8 1/2" DE ACUERDO A PROGRAMA | 79AB7DA4542A4070984C74DA09CB2C63 | BAJO SARTA HASTA 1100 PIES, CONECTO MARTILLO A 785 | 22.49 |  | 2018-08-29 17:45:36.000 | [6 empty] | 2018-09-10 12:00:00.000 | 2018-08-07 15:00:00.000 | 0 | 11178.0004 | 2018-09-05 16:00:00.000 | 3.5208 | 17.3958 | 29.0417 | 33.875 | 10.3936 | 384.8953
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACSD-022 | -76.8838 | -0.77083 | Auca Sur | Deviated | J |  | Re-Entry | SLR-401 | CONTINUÓ BAJANDO BHA # 8 DESDE 1,514' HASTA 8,003', CHEQUEO CIRCULACIÓN A TRAVÉS DE CHOKE MANIFOLD, POOR BOY, ZARANDA, VERIFICÓ CIERRE DE CHOKE. OK. PERFORÓ EQUIPO DE FLOTACIÓN LIMPIÓ CEMENTO Y ZAPATA A 9,738'. | CONTINUAR LIMPIANDO BOLSILLO DE 9,710 A 10,036'., BAJAR PROGRESIVAMENTE DENSIDAD DEL LODO DE 13.4 PPG Y EVALUAR COMPORTAMIENTO DEL POZO. | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINUÓ BAJANDO BHA # 8 DESDE 1,514' HASTA 8,003{ ( BAJO TUBO X TUBO HASTA 3078 PIES.) | 19 |  | 2018-11-19 06:00:00.000 | [6 empty] | 2018-12-11 18:00:00.000 | 2018-11-01 02:00:00.000 | 8587.0003 | 11020.0004 | 2018-12-01 14:00:00.000 | 12.6458 | 26.1875
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CHSA-014 | -0.9228 | -76.929 | Chonta Sur | Deviated | J HD | 2017-08-24 06:00:00.000 | Re-Entry | SLR-401 | CONTINUÓ BAJANDO 3.5¿ DP, ARMANDO TUBO A TUBO. PROBÓ CON 3000 PSI SIN ÉXITO. SACÓ QUEBRANDO. ARMÓ BHA # 5. OBSERVÓ FALLA EN COMUNICACIÓN ENTRE PERISCOPE Y DIGISCOPE. SACÓ BHA # 5. | REALIZAR EL CAMBIO DE PERISCOPE Y DIGISCOPE Y BAJAR BHA # 5. | 79AB7DA4542A4070984C74DA09CB2C63 | ARMÓ 1 PARADA DE 4 3/4" DC. | 20.9 |  | 2018-10-09 03:36:00.000 | [6 empty] | 2018-10-14 00:00:00.000 | 2018-09-18 22:30:00.000 | 8056.0003 | 12180.0004 | 2018-10-10 18:00:00.000 | 2.625 | 15.3333 | 412.5 | 415.75 | 0.63139 | 29.5273
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-040WDW | -0.46 | -76.89 | Culebra | Deviated | Tipo JHD | 2019-03-25 03:30:00.000 | Primary Drilling | SLR-401 | BAJÓ BHA #7 DESDE 1,500' HASTA 11,638' TOC, REALIZÓ DRILL OUT HASTA MEDIO SHOE TRACK., REALIZÓ PRUEBA DE CASING, DESPLAZÓ FLUIDO VIEJO KLA SHIELD POR FLUIDO NUEVO. REALIZÓ PRUEBA FIT. PERORANDO SECCIÓN DE 8.5'' @ 12,100'. | PERFORAR SECCIÓN DE 8.5'' SEGUN PROGRAMA HASTA +/- 12347'. | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINUÓ BAJANDO BHA # 7 DIRECCIONAL CON 5 1/2" DP DE 1,500' A 11,638' DONDE CONFIRMÓ TOPE DE TAPONES. VELOCIDAD E VIAJE 1,350 pies/hora BAJÓ CON CIRCULACIÓN LAS ÚLTIMAS DOS PARADAS POR PRECAUCIÓN CON 360 gpm, 2,000 psi, 40 rpm, TORQUE: 20 - 22 Klbs-pie. | 24.7 |  | 2019-04-17 22:48:00.000 | 563 | [5 empty] | 2019-04-23 23:00:00.000 | 2019-03-25 03:30:00.000 | 0 | 12360.0004 | 2019-04-21 11:30:00.000 | 4.125 | 19 | 27.3333 | 29.8125 | 13.8365 | 452.1951
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-041H | -0.4654 | -76.8982 | Culebra | Horizontal | Horizontal |  | Primary Drilling | SLR-401 | TERMINÓ CORRIDA DE LINER. REALIZÓ TRABAJO DE CEMENTACIÓN Y EXPANSIÓN DE COLGADOR. LIBERÓ SETTING TOOL Y SACÓ EN PARADAS. ARMÓ BHA # 6 Y BAJÓ JUNTA POR JUNTA EN TUBERÍA DE 3 ½ IN. BAJANDO BHA 6 A 2500 FT, EN PROCESO | BAJAR BHA # 6 PARA REALIZAR ACONDICIONAMIENTO Y DRILL OUT DE LINER DE 7 IN. | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZÓ REUNIÓN DE SEGURIDAD PREVIO AL ARMADO DE BHA # 6 PARA DRILL OUT DE SECCIÓN DE 6 1/8" | 36.19 |  | 2019-06-12 10:33:36.000 | 344 | [5 empty] | 2019-06-14 00:00:00.000 | 2019-05-08 00:00:00.000 | 0 | 11840.0004 | 2019-06-13 04:30:00.000 | 0.1875 | 27.5208
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-042H | -0.4655 | -76.898 | Culebra | Horizontal | HORIZONTAL |  | Primary Drilling | SLR-401 | BAJÓ, MOLIÓ TAPONES, LANDING COLLAR, CEMENTO, COLLAR FLOTADOR, CEMENTO Y ZAPATA DE 7'' DE 10,958' HASTA 11,050'. BAJÓ BHA # 11 HASTA 11,210', CIRCULÓ SACÓ BHA # 11 HASTA 10,222'. CAMBIO DE FLUIDO, BAJÓ BHA HASTA 11,216' Y SACÓ A 500'. | SACAR BHA # 11 CON BROCA DE 6.125'' A SUPERFICIE, DESARMAR BHA # 11, ARMAR BHA # 12 DIRECCIONAL, BAJAR BHA # 12, PERFORAR SECCIÓN DE 6 1/8'' SEGÚN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINUÓ BAJANDO BHA # 11 CON 5 1/2" DP DE 10,222' A 10,958' DONDE CONFIRMÓ TOPE DE TAPONES. BAJÓ CON CIRCULACIÓN LAS ÚLTIMAS DOS PARADAS POR PRECAUCIÓN CON 250 gpm, 1,950 psi, 30 rpm, TORQUE: 12 - 13 Klbs-pie. | 37.52 |  | 2019-09-25 18:28:48.000 | 350 | [5 empty] | 2019-10-05 00:00:00.000 | 2019-08-20 01:00:00.000 | 0 | 12325.0004 | 2019-10-04 02:30:00.000 | 13.75 | 31.4792
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-043H | -0.48331 | -76.8754 | Culebra | Horizontal | Horizontal | 2019-01-31 17:30:00.000 | Primary Drilling | SLR-401 | MIDIÓ, CALIBRÓ, INSPECCIONÓ TUBERÍA DE 3.5'' HWDP Y 3.5'' DP, ARMÓ BHA # 8 DIRECCIONAL CON BROCA DE 6 1/8'', BAJANDO ARMANDÓ BHA # 8 HASTA 2,031 FT. | CONTINUAR ARMANDO BHA # 8 DIRECCIONAL + BAJAR BHA HASTA 10,769' PERFORAR SECCIÓN DE 6 1/8'' SEGUN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | MIDIÓ, CALIBRÓ Y ARMÓ 10 PARADAS DE 3 1/2" DE HWDP CONEXIÓN NC-38, TORQUE APLICADO 17 Klb-Pie. | 39.26 |  | 2019-03-11 12:14:24.000 | 317 | [5 empty] | 2019-03-13 00:00:00.000 | 2019-01-31 17:30:00.000 | 0 | 12462.0004 | 2019-03-12 05:00:00.000 | 4.9583 | 27.2917 | 39.4792 | 40.2708 | 12.3125 | 315.6602
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-044H | -0.4655 | -76.8981 | Culebra | Horizontal | Horizontal | 2019-06-29 20:30:00.000 | Primary Drilling | SLR-401 | SACÓ SETTING TOOL A SUPERFICIE, CORTÓ CABLE DE PERFORACIÓN, ARMÓ BHA # 10 DE DRILL OUT , BAJO BHA # 10 A 10,352'. | BAJAR HASTA TOPE DE CEMENTO, MOLER MEDIO SHOE TRACK, BOMBEAR PILDORAS Y CIRCULAR, REALIZAR PRUEBA DE CASING, LIMPIAR CEMENTO HASTA ZAPATA, BOMBEAR PILDORAS Y CIRCULAR, SACAR BHA # 10 A SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | VISTIENDO EQUIPO + PREPARATIVOS PARA LEVANTAR TUBERIA 3 1/2". | 37.07 |  | 2019-08-05 07:40:48.000 | 365 | [5 empty] | 2019-08-07 20:30:00.000 | 2019-06-29 20:30:00.000 | 0 | 13277.0004 | 2019-08-07 03:00:00.000 | 5.125 | 26.7292 | 38.2708 | 39 | 13.141 | 346.9222
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBC-045 | -0.4655 | -76.8981 | Culebra | Deviated | J | 2019-01-04 20:00:00.000 | Primary Drilling | SLR-401 | INSTALÓ PACKOFF. ARMÓ BHA #5 BAJÓ BHA HASTA TOC. MOLIÓ SHOE TRACK. DESPLAZÓ FLUIDO. REALIZÓ FIT. INICIÓ PERFORACIÓN SECCIÓN 8 1/2" | PERFORAR SECCIÓN 8 1/2" HASTA TD DEL POZO. REALIZAR VIAJE DE CALIBRACIÓN. SACÓ BHA HASTA SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | BAJÓ BHA #5 EN HUECO REVESTIDO EN HWDP HASTA 1,046 FT. | 22.26 |  | 2019-01-26 12:14:24.000 | 607 | [5 empty] | 2019-01-27 19:00:00.000 | 2019-01-04 20:00:00.000 | 0 | 10750.0003 | 2019-01-24 22:00:00.000 | 0.1875 | 12.25 | 20.0833 | 22.9583 | 0.8167 | 535.2697
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CHSA-015 | -0.92286 | -76.9292 | Chonta Sur | Deviated | J | 2018-04-02 22:00:00.000 | Primary Drilling | Sinopec-119 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZA PRUEBA DE REVESTIDOR 9 5/8" CON 2100 POR 15 MINUTOS, OK | 19.51 |  | 2018-04-21 18:14:24.000 | [6 empty] | 2018-04-20 18:00:00.000 | 2018-04-02 22:00:00.000 | 0 | 11660.0004 | 2018-04-18 02:00:00.000 | 0.020833 | 7.8542 | 15.1667 | 17.8333 | 0.11682 | 768.7912
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | TTSA-001 | -0.85706 | -76.9493 | Tortuga | S Shaped | Directional | 2018-01-02 06:00:00.000 | Primary Drilling | Sinopec-119 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | CAMBIA SAVER SUB DE 4 1/2" IF x 5 1/2" XT54 + CAMBIA ELEVADORES DE 5" x 5 1/2" Y CONECTA 1 PARADA DE 5 1/2" DP. ** PRUEBA HTA DIRECCIONAL CON 380 GPM, 670 PSI. OK | 24.87 |  | 2018-02-05 02:52:48.000 | [6 empty] | 2018-02-21 14:00:00.000 | 2018-01-11 18:00:00.000 | 0 | 11055.0004 | 2018-02-17 08:00:00.000 | 15.8958 | 30.125 | 46.0833 | 50.3333 | 31.5811 | 239.8915
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | TTSA-002 | -0.85705 | -76.9492 | Tortuga | Deviated | J HD | 2018-05-04 15:00:00.000 | Primary Drilling | Sinopec-119 | FINALIZA PRUEBAS DE BOP, ARMA Y BAJA BHA No 5 DIRECCIONAL 8 ½ ". REALIZA DRILL OUT + CIT + CAMBIA DE FLUIDO + FIT + PERFORAR SECCION 8 1/2". | PERFORAR SECCION 8 1/2". REALIZAR VIAJE CORTO. SACAR BHA No 5 HASTA SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | ARMA BHA DIRECCIONAL No 5. COMO SIGUE: BROCA 8 1/2" PDC + MOTOR A675M W SLICK STAB; BH 1.5 + FLOAT SUB/FLOAT VALVE + STRING STAB 8 3/8" + PONY MONEL + TELESCOPE + MONEL + DOWNHOLE FILTER. | 24.4 |  | 2018-05-28 15:36:00.000 | [6 empty] | 2018-05-29 22:30:00.000 | 2018-05-04 15:00:00.000 | 0 | 11815.0004 | 2018-05-27 01:30:00.000 | 4.5417 | 15.5833 | 22.4375 | 25.3125 | 17.9424 | 526.5738
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | TTSA-004 | -0.85704 | -76.9492 | Tortuga | Deviated | J HD | 2018-06-09 18:00:00.000 | Primary Drilling | Sinopec-119 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | BOMBEA 80 BLS DE PILDORA VISCOSA PESADA DE 9.8 PPG. CIRCULA HASTA RETORNOS LIMPIOS EN ZARANDAS CON 380 GPM, 1600 PSI, 60 RPM, TQ 21 -24 KLBS-PIE. PESO DE LODO E/S 9.7 PPG ESPOTEA EN FONDO 70 BLS PILDORA ESTABILIZADORA CON MATERIAL DE SELLO + LUBRICANTE 3%. | 24.89 |  | 2018-07-04 03:21:36.000 | [6 empty] | 2018-07-03 06:00:00.000 | 2018-06-09 18:00:00.000 | 0 | 12800.0004 | 2018-06-30 08:30:00.000 | 0.20833 | 11.9167 | 20.6042 | 23.5 | 0.88652 | 621.2336
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBD-003WDW | -0.4768 | -76.8699 | Yulebra | Deviated | J | 2018-07-22 18:00:00.000 | Primary Drilling | Sinopec-119 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINUA BAJANDO BHA # 4 DESDE 1164 FT HASTA 3830 FT LLENA TUBERIA C/2000 PIES NOTA: . VELOCIDAD DE BAJADA EN HUECO ENTUBADO 1800 PPH | 22.8 |  | 2018-08-14 01:12:00.000 | [6 empty] | 2018-08-12 00:00:00.000 | 2018-07-22 18:00:00.000 | 0 | 11560.0004 | 2018-08-09 19:00:00.000 | 0.083333 | 10.1667 | 18.0417 | 20.25 | 0.41152 | 640.7391
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBD-023H | -0.4768 | -76.8699 | Yulebra | Horizontal | Horizontal | 2018-08-15 20:00:00.000 | Primary Drilling | Sinopec-119 | REALIZA PRUEBAS DE BOP, CHOKE MANIFOLD, ACUMULADOR, REALIZA RIG SERVICE ARMA Y BAJA BHA No 8 @ 9200 FT | BAJA BHA No 8 HASTA 11180 FT (LC) MOLER 1/2 SHOE TRACK, PERFORAR 5 FT DE NUEVA FORMACION, CAMBIAR FLUIDO SACAR BHA A SUPERFICIE | 79AB7DA4542A4070984C74DA09CB2C63 | CONECTA PRIMERA PARADA DE 5 1/2" DP Y CIRCULA CON 200 GPM, 800 PSI. OK. - RETORNOS LIMPIOS EN ZARANDAS. | 37.85 |  | 2018-09-22 02:24:00.000 | [6 empty] | 2018-09-20 08:30:00.000 | 2018-08-15 20:00:00.000 | 0 | 12782.0004 | 2018-09-19 00:00:00.000 | 1.875 | 19.6667 | 34.1667 | 35.5208 | 5.2786 | 374.1073
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBD-024H | -0.47677 | -76.8699 | Yulebra | Horizontal | Horizontal | 2018-11-06 18:00:00.000 | Primary Drilling | Sinopec-119 | BAJA BHA # 7 HASTA 10904 PIES (LC), MUEL 1/2 SHOE TRACK, CIT, MUELE RESTO DE SHOE TRACK, PERFORAR 5 PIES DE NUEVA FORMACION, CAMBIA FLUIDO, SACA BHA DESDE 10999 PIES HASTA 1000 PIES. | TERMINAR DE SACAR BHA A SUPERFICIE, QUEBRAR BHA #7, ARMAR Y BAJAR BHA #8, PERFORAR SECCION DE 6 1/8" SEGÚN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINÚA ROTANDO CEMENTO, PERFORA ZAPATA 10999 PIES. PARÁMETROS: Q: 250 GPM, P: 1700 PSI, WOB: 5/10 KLBS, ROT: 60/80 RPM, TQ: 8 KLBS-FT. | 39.25 |  | 2018-12-15 12:00:00.000 | [6 empty] | 2018-12-07 00:00:00.000 | 2018-11-06 18:00:00.000 | 0 | 12531.0004 | 2018-12-06 03:30:00.000 | 2.2917 | 17.9583 | 29.3958 | 30.25 | 7.5758 | 426.2849
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBD-025 | -0.47674 | -76.8699 | Yulebra | Deviated | J HD | 2018-09-30 21:00:00.000 | Primary Drilling | Sinopec-119 | CONT RIH BHA #5 H/11300 FT, PERF TAPONES, CF, H/11345 FT, CIT, LIMPIA CMNT, ZAPATA, + 15 FT H/11415 FT, CAMBIO DE FLUIDO, FIT, PERFORA SECCION 8 1/2" DESDE 11415 FT HASTA 11872 FT | PERFORAR SECCION DIRECCIONAL 8.5", CIRCULAR, VIAJE CORTO,VIAJE A SUPERFICIE | 79AB7DA4542A4070984C74DA09CB2C63 | CONTINUA BAJANDO BHA No 5 DESDE 3200 FT HASTA 11300 FT TOPA TAPONES. NOTA: BAJA LAS 2 ULTIMAS DOS PARADAS CON CIRCULACIÓN / ROTACIÓN LLENANDO TUBERÍA C/2000 FT. VELOCIDAD DE BAJADA: 1470 PPH | 23 |  | 2018-10-23 06:00:00.000 | [6 empty] | 2018-10-23 14:30:00.000 | 2018-09-30 21:00:00.000 | 0 | 12150.0004 | 2018-10-21 13:00:00.000 | 0.3125 | 10.9583 | 20.6667 | 22.7292 | 1.3749 | 587.9032
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBD-029 | -0.47671 | -76.8699 | Yulebra | Deviated | J HD | 2018-12-16 22:00:00.000 | Primary Drilling | Sinopec-119 | BAJÓ BHA #5 HASTA 11218'. MOLIÓ TAPONES COLLAR FLOTADOR y CEMENTO HASTA MEDIO SHOE TRACK A 11284'. PROBÓ CSG. CONTINUÓ MOLIENDO RESTO SHOE TRACK, ZAPATO Y 15' FM NUEVA HASTA 11333'. CAMBIÓ FLUIDO. REALIZÓ FIT. PERFORÓ HASTA 11540'. | CONTINUAR PERFORANDO HOYO 8 1/2" HASTA +/- 11318'. SEGÚN PROGNOSIS. CIRCULAR PÍLDORA. REALIZAR VIAJE CORTO. ESPOTEAR PÍLDORA. SACAR SARTA CON BHA #5 HASTA SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | EFECTUÓ PRUEBA DE REVESTIDOR DE 9 5/8" CON 2500 PSI x 15 MIN. SATISFACTORIO | 23.48 |  | 2019-01-08 17:31:12.000 | 573 | [5 empty] | 2019-01-06 02:00:00.000 | 2018-12-16 22:00:00.000 | 0 | 11917.0004 | 2019-01-03 19:30:00.000 | 0 | 9.0833 | 17.8958 | 20.1667 | 0 | 665.9092
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAC-167 | -0.731 | -76.878 | Auca | Deviated | J | 2018-07-08 22:00:00.000 | Primary Drilling | Sinopec-156 | PERFORO CON BHA # 4 HASTA 11.200' (PROF. FINAL), CIRCULO RETORNOS LIMPIOS. REALIZO VIAJE DE CALIBRE DESDE 11.200' @ 10.370', REGRESO A FONDO. ESPOTEO PILDORA LUBRICANTE. SACO BHA # 4 A SUPERFICIE, ARMANDO HERRAMIENTAS DE REGISTROS. | REALIZAR REGISTROS ELECTRICOS SEGUN PROGRAMA, DESARMAR EQUIPO, SUBIR EQUIPO DE TIW, BAJAR LINER DE 7''. | 79AB7DA4542A4070984C74DA09CB2C63 | PERFORÓ HOYO 8 1/2" CON BHA # 4 DIRECCIONAL. CON MOTOR DESDE 10,770' HASTA 11,200'. ** SON 430 PIES EN 7.5 HRS : 57 PPH PROMEDIO. PARÁMETROS ROTANDO: WOB 15 - 30, GPM 300 - 350 PRFF 1,500 PSI, PR DIF. 300 - 350 PSI. RPM 70 - 80 , TRQ 18 - 22 KLBFT. ** TOPE DE FORMACION "T" SUPERIOR @ 10,699' MD 9,827' TVD, / "T" INFERIOR @ 10,808' MD 9,931' TVD. ** BASE "T" INFERIOR @ 10,875' MD 9,995' TVD, / BASE LUTITA NAPO @ 10,908' MD 10,027' TVD. ** CALIZA "C" @ 10,960' MD 10,077' TVD, / HOLLIN SUPERIOR @ 10,976' MD 10,093' TVD. / HOLLIN INFERIOR @ 11,200' MD 10,311' TVD. ** KLA-SHIELD: DENSIDAD 9.3 LPG, 61 SEG, PV12 / 35YP, FILTRADO: 4.3 cc/30min, MBT: 2.5 LPB. ** ÚLTIMO SURVEY @ 11,135.46' : INC 12.73º, AZM 155.45º, TVD 10,248.46', V. SEC. 3,724.22', DL´s 0.73º, CT-CT 45.67', 44.84 PIES A LA DER + 8.86' POR DEBAJO. ** ÚLTIMA LITOLOGÍA: 11,200': 100 % ARENISCA. | 22 |  | 2018-07-30 06:00:00.000 | [6 empty] | 2018-07-26 06:00:00.000 | 2018-07-08 22:00:00.000 | 0 | 11200.0004 | 2018-07-23 13:30:00.000 | 0.10417 | 7.3542 | 14.6458 | 17.3333 | 0.60096 | 764.7226
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAD-152 | -0.72231 | -76.8781 | Auca | Deviated | J "HD" | 2018-03-22 01:30:00.000 | Primary Drilling | Sinopec-156 | ARMA 125 PARADAS DP 5 1/2" XT-54 Y 13 PARADAS 5" x 4 1/2" IF. EN TORRE + ARMA BHA #1 + PERFORA SECCION 26" DESDE 0 PIES HASTA 100 PIES. | CONTINUAR PERFORANDO SECCION DE 26" HASTA 252 PIES + BOMBEAR PILDORA VISCOSA + TOMAR GIRO + ESPOTEAR PILDORA + SACAR BHA #1 A SUPERFICIE Y QUEBRAR + ARMAR HRRTAS TIW Y CORRER CASING 20" + CEMENTAR CASING + CORTAR CASING + INSTALAR TUBO CONDUCTOR + ARMAR Y BAJAR BHA #2 DIRECCIONAL. | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZÓ PREPARATIVOS PARA ARMAR PARADAS: INSTALÓ BURROS DE TUBERÍA Y ALISTÓ HERRAMIENTAS EN LA MESA DE PERFORACIÓN. | 25.6 |  | 2018-04-15 20:24:00.000 | [6 empty] | 2018-04-11 00:00:00.000 | 2018-03-22 01:30:00.000 | 0 | 12680.0004 | 2018-04-09 07:00:00.000 | 0 | 9.75 | 18.2292 | 19.9375 | 0 | 695.5886
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAH-168H | -0.68066 | -76.8762 | Auca | Horizontal | HORIZONTAL | 2018-08-10 06:00:00.000 | Primary Drilling | Sinopec-156 |  |  | 79AB7DA4542A4070984C74DA09CB2C63 | 'BAJA BHA NO. 6 DE LIMPIEZA, LIBRE DESDE 2142 PIES HASTA 5000 PIES LLENANDO TUBERIA C/2000 PIES. | 36.01 |  | 2018-09-15 06:14:24.000 | [6 empty] | 2018-09-10 00:00:00.000 | 2018-08-10 06:00:00.000 | 0 | 12240.0004 | 2018-09-08 16:30:00.000 | 2.5417 | 18.8542 | 29.4375 | 30.75 | 8.2656 | 415.7962
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAI-219 | -0.63589 | -76.8774 | Auca | Deviated | J | 2017-12-14 22:00:00.000 | Primary Drilling | Sinopec-156 | PERFORÓ ETAPA DE 8 1/2" A 11,267', CIRCULÓ, REALIZÓ VIAJE DE CALIBRACIÓN A LA ZAPATA DE 9 5/8", RETORNÓ A FONDO, CIRCULÓ, ESPOTEÓ PÍLDORA LUBRICANTE, SACÓ BHA 8,730'. | SACAR BHA A SUPERFICIE, CORRER REGISTROS ELÉCTRICOS DE ACUERDO AL PROGRAMA, ARMAR Y BAJAR LINER DE 7". | 79AB7DA4542A4070984C74DA09CB2C63 | PERFORÓ SECCIÓN DE 8 1/2" CON BHA # 5 DIRECCIONAL ROTANDO Y DESLIZANDO DE 10,848' A 11,267'. ROP PROMEDIO: 25 pies/hr, PARÁMETROS 400 - 380 gpm ¦ 1,400 - 1,450 psi ¦ P. diferencial: 100 - 200 psi ¦ 100 rpm ¦ Torque: 17 - 21 Klbs-pie, ¦ WOB: 10- 15 Klbs.: PIES ROTADOS: 369' EN 7.5 hrs ROP: 49 pies/hr. ¦ PIES DESLIZADOS: 50' EN 9 hrs ROP: 6 pies/hr. ÚLTIMO SURVEY @ 11,190.02' MD ¦ 10,399.38' TVD ¦ 11.56º INCLINACIÓN ¦ 24.31º AZIMUTH ¦ CT-CT 63.98'¦ ABAJO 2.3' ¦ IZQUIERDA 63.94' ¦ TOPE DE "T" SUPERIOR 10,696' MD ¦ 9,919' TVD ¦¦ TOPE DE "T" INFERIOR 10,791' MD ¦ 10,010' TVD. BASE "T" INFERIOR 10,829' MD ¦ 10,047' TVD ¦¦ BASE DE LUTITA NAPO 10,916'MD ¦ 10,131' TVD. CALIZA "C" 10,990' MD ¦ 10,203' TVD ¦¦ HOLLÍN SUPERIOR 11,013' MD, ¦ 10,226' TVD. HOLLÍN INFERIOR 11,041' MD ¦ 10,253' TVD ¦¦ ÚLTIMA LITOLOGÍA 11,267': 100 % ARENISCA. | 20 |  | 2018-01-03 06:00:00.000 | [6 empty] | 2018-01-01 06:00:00.000 | 2017-12-14 22:00:00.000 | 0 | 11267.0004 | 2017-12-29 22:30:00.000 | 0.041667 | 6.4583 | 15.0208 | 17.3333 | 0.24038 | 750.0916
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAJ-196 | -0.6588 | -76.8818 | Auca | Deviated | J | 2018-02-15 22:00:00.000 | Primary Drilling | Sinopec-156 | BAJÓ CASING DE 9 5/8" A 10,008' Y CEMENTÓ. INSTALÓ Y PROBÓ PACK OFF, ARMÓ Y BAJÓ BHA # 4 DE 8 1/2" A TOPE DE TAPONES, MOLIÓ HASTA MEDIO SHOE TRACK, REALIZÓ CIT, MOLIÓ RESTO DE SHOE TRACK Y PERFORÓ HASTA 10,036', INICIÓ DESPLAZAMIENTO DE FLUIDO. | REALIZAR FIT, PERFORAR ETAPA DE 8 1/2" A 10,858'. | 79AB7DA4542A4070984C74DA09CB2C63 | 'SIGUIENDO "CHECK LIST" BAJÓ BHA # 4 DIRECCIONAL CON BROCA PDC DE 8 1/2" DE 109' A 9,925' DONDE CONFIRMÓ TOPE DE TAPONES. BAJÓ CON CIRCULACIÓN LAS ÚLTIMAS TRES PARADAS POR PRECAUCIÓN CON 380 gpm, 1,300 psi. VELOCIDAD DE VIAJE: 1,630 pies/hr. REALIZÓ PRUEBA DE FUNCIONAMIENTO DE HERRAMIENTA DIRECCIONAL A 1,131' CON 370-400 GPM, 700 - 730 PSI OK . | 21 |  | 2018-03-08 06:00:00.000 | [6 empty] | 2018-03-02 12:00:00.000 | 2018-02-16 14:00:00.000 | 48 | 10840.0003 | 2018-02-28 00:00:00.000 | 0 | 5.5208 | 12.0833 | 14.5833 | 0 | 897.1035
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ANCA-013 | -0.51252 | -76.8397 | Anaconda | S Shaped | S | 2018-05-03 06:00:00.000 | Primary Drilling | Sinopec-156 | TERMINÓ DE CEMENTAR CASING DE 9.675 PLG. LAVÓ CABEZAL. INSTALÓ Y PROBÓ PACK OFF. INSTALÓ WEAR BUSHING. ARMÓ, BAJÓ, MOLIÓ SHOE TRACK. PROBÓ CASING. PROBÓ FIT. PERFORÓ SECCIÓN . | PERFORAR SECCION DE 8.5 PLG. SEGÚN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | SIGUIENDO "CHECK LIST" BAJÓ BHA # 5 DIRECCIONAL CON BROCA PDC DE 8 1/2" DE 1,037' A 9,504' DONDE CONFIRMÓ TOPE DE TAPONES. BAJÓ CON CIRCULACIÓN LAS ÚLTIMAS TRES PARADAS POR PRECAUCIÓN CON 380 gpm, 1,380 psi. VELOCIDAD DE VIAJE: 1,310 pies/hr. | 20.74 |  | 2018-05-23 23:45:36.000 | [6 empty] | 2018-05-19 01:00:00.000 | 2018-05-04 00:00:00.000 | 0 | 10405.0003 | 2018-05-16 06:00:00.000 | 0 | 6 | 13 | 15.7917 | 0 | 800.3846
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBB-035 | -0.47875 | -76.9086 | Culebra | Deviated | J HD | 2018-06-02 16:00:00.000 | Primary Drilling | Sinopec-156 | BAJÓ CASING DE 9 5/8" A 11,526', CEMENTÓ SEGÚN PROGRAMA. INSTALÓ Y PROBÓ PACK OFF CON 2,400 psi, BIEN. INSTALÓ WEAR BUSHING. ARMÓ BHA # 5 CON BROCA DE 8 1/2" Y MOTOR DE FONDO. BAJÓ BHA # 5 A 3,800 psi. | BAJAR BHA # 5 A11,446', TOPE DE COLLAR FLOTADOR. ROTAR 1/2 SHOE TRACK, PROBAR CASING, CONTINUAR ROTANDO SHOE TRACK + 15' DE FORMACIÓN NUEVA Y CAMBIAR FLUÍDO. REALIZAR FIT. PERFORAR SECCIÓN DE 8 1/2" SEGÚN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | EFECTUÓ REUNIÓN DE SEGURIDAD PREVIO A ARMADO DE BHA # 5. | 23.75 |  | 2018-06-26 00:00:00.000 | [6 empty] | 2018-06-23 06:00:00.000 | 2018-06-02 16:00:00.000 | 0 | 11972.0004 | 2018-06-21 03:00:00.000 | 0 | 10.0417 | 18.4583 | 20.5833 | 0 | 648.596
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBA-026 WDW | -0.48331 | -76.8754 | Yulebra | Deviated | J HD | 2018-09-26 15:00:00.000 | Primary Drilling | Sinopec-156 | INSTALÓ Y PROBÓ PACK OFF, ARMÓ Y BAJÓ BHA # 6 DE 8 1/2" A TOPE DE TAPONES, MOLIÓ HASTA MEDIO SHOE TRACK, REALIZÓ CIT, MOLIÓ RESTO DE SHOE TRACK Y PERFORÓ HASTA 11,229', REALIZÓ DESPLAZAMIENTO DE FLUIDO, REALIZÓ PRUEBA FIT, PERFORANDO A 11,380'. | CONTINUAR PERFORANDO SECCIÓN DE 8.5'' HASTA +/- 12,032'. | 79AB7DA4542A4070984C74DA09CB2C63 | EFECTUÓ PRUEBA DE REVESTIDOR DE 9 5/8" CON 2,500 psi x 15 min. OK. | 31.62 |  | 2018-10-27 20:52:48.000 | [6 empty] | 2018-10-18 20:30:00.000 | 2018-09-26 15:00:00.000 | 0 | 12000.0004 | 2018-10-16 23:00:00.000 | 1.0625 | 10 | 20.3333 | 22.2292 | 4.7798 | 590.164
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBA-027H | -0.48331 | -76.8754 | Yulebra | Horizontal | HORIZONTAL | 2018-10-22 06:00:00.000 | Primary Drilling | Sinopec-156 | BAJÓ BHA # 9 HASTA TOPE DE CEMENTO. REALIZA DRILL OUT. PRUEBA REVESTIDOR. TERMINA DRILL OUT. REALIZA DESPLAZAMIENTO. PERFORA 5 PIES DE FORMACIÓN. TERMINA DESPLAZAMIENTO. SACA BHA # 9. | SACAR BHA # 9 A SUPERFICIE. REALIZAR CAMBIO DE BHA. | 79AB7DA4542A4070984C74DA09CB2C63 | 'TERMINÓ DE MOLER SHOE TRACK DESDE 11620' HASTA 11656' (ZAPATO DE 7"). RECONOCIÓ HOYO PERFORADO HASTA 11658'. | 40.26 |  | 2018-12-01 12:14:24.000 | [6 empty] | 2018-11-27 15:00:00.000 | 2018-10-22 06:00:00.000 | 0 | 13000.0004 | 2018-11-26 06:00:00.000 | 5.1042 | 21.0208 | 35 | 36.375 | 14.0321 | 371.4286
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBA-028 | -0.48331 | -76.8753 | Yulebra | Deviated | J | 2018-12-07 01:00:00.000 | Primary Drilling | Sinopec-156 | LAVÓ CABEZAL. INSTALÓ Y PROBÓ PACK OFF. INSTALÓ WEAR BUSHING. ARMÓ Y BAJÓ BHA 5 PARA SECCIÓN DE 8.5”. REALIZÓ DESPLAZAMIENTO Y CONTINUÓ PERFORANDO SECCIÓN. | CONTINUAR PERFORANDO SECCIÓN SEGÚN PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | SEGÚN "CHECK LIST" BAJÓ BHA 5 DIRECCIONAL DE 1,029' A 9,935' DONDE CONFIRMÓ TOPE DE TAPONES. VELOCIDAD DE VIAJE: 1,370 pies/hr. | 20.5 |  | 2018-12-26 18:00:00.000 | [6 empty] | 2018-12-22 22:00:00.000 | 2018-12-07 02:00:00.000 | 46 | 10600.0003 | 2018-12-20 15:30:00.000 | 0 | 7.125 | 13.6042 | 15.875 | 0 | 779.1731
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | YLBA-030 | -0.48331 | -76.8754 | Yulebra | Deviated | JHD | 2019-01-02 00:00:00.000 | Primary Drilling | Sinopec-156 | ARMÓ Y BAJÓ BHA #6 DIRECCIONAL Y BROCA PDC DE 8 1/2". MOLIÓ TAPONES, COLLAR FLOTADOR + MEDIO SHOE TRACK. REALIZÓ CIT. REALIZÓ DESPLAZAMIENTO. REALIZÓ FIT. PERFORÓ SECCIÓN DE 8 1/2" C/SARTA DIRECCIONAL Y BROCA PDC DE 8 1/2" DE 11,663' A 12,040' | CONTINUAR PERFORANDO SECCIÓN DE 8 1/2" @ 12,309' MD - 9,821' TVD. SACAR C/SARTA DIRECCIONAL Y BROCA PDC DE 8 1/2" A SUPERFICIE | 79AB7DA4542A4070984C74DA09CB2C63 | SIGUIENDO "CHECK LIST" BAJÓ BHA # 6 DIRECCIONAL CON BROCA PDC DE 8 1/2" DE 120' A 11,539' DONDE CONFIRMÓ TOPE DE CEMENTO. VELOCIDAD DE VIAJE: 1,350 pies/hr. BAJÓ ROMPIENDO CIRCULACIÓN Y PROBANDO HERRAMIENTA DIRECCIONAL CADA 2,000'. | 23.9 |  | 2019-01-25 03:36:00.000 | 558 | [5 empty] | 2019-01-23 08:00:00.000 | 2019-01-02 00:00:00.000 | 0 | 12280.0004 | 2019-01-21 10:30:00.000 | 0.29167 | 9.6042 | 19.4375 | 21.3333 | 1.3672 | 631.7685
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAI-004 WDW | -0.63592 | -76.8774 | Auca | Deviated | J | 2018-05-14 04:00:00.000 | Primary Drilling | Sinopec-168 | PERFORÓ CON BHA #5 CON MOTOR DE FONDO + LWD + MWD + PDC SECCION 8 1/2" DESDE 12302' HASTA 12350'. REALIZO VIAJE DE ACONDICIONAMIENTO. CIRCULO Y ESPOTEO PILDORAS. SACO SARTA A SUPERFICIE. REALIZANDO CORRIDA DE REGISTRO SIN TERMINAR | REALIZAR CORRIDA DE REGISTRO ELECTRICOS "XPT-GR-ECRD". SE TOMARAN PUNTOS DE PRESION DE FORMACION. BAJAR LINER DE 7" Y CEMENTAR. | 79AB7DA4542A4070984C74DA09CB2C63 | PERFORÓ SECCIÓN 8 1/2" CON BHA # 5 MOTOR FONDO + LWD + MWD + PDC DESDE 12302' HASTA 12350' SON 48' EN 1 HR = 48 PPH. ROP PROMEDIO. PARÁMETROS OPTIMOS: WOB 5 - 25 KLBS, GPM 390, PR 1400 - 1450 psi, PR Dif. 100 - 250 psi, RPM 90, TRQ 18 - 25 klb-pie. ÚLTIMO SURVEY @ 12259.52' MD, TVD 10360', VERT. SET 5804', INCLINACIÓN: 25.07°, AZM 68.24º, DL's 0.66, CT-CT 121.39'. ** ÚLTIMA LITOLOGÍA @ 12350': 100 % ARENISCA. ** PROFUNDIDAD FINAL DEL POZO DEFINIDA POR WELL SITE GEÓLOGO DE SHAYA EN SITIO. | 23.26 |  | 2018-06-05 12:14:24.000 | [6 empty] | 2018-06-07 22:00:00.000 | 2018-05-14 04:00:00.000 | 0 | 12350.0004 | 2018-06-05 06:30:00.000 | 4.1042 | 13.6458 | 22.1042 | 24.75 | 16.5825 | 558.7182
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACAL-204 | -0.58834 | -76.9128 | Auca | Deviated | Direccional JHD | 2018-11-01 05:00:00.000 | Primary Drilling | Sinopec-168 | BAJÓ BHA #5 HASTA 11869. MOLIÓ TAPONES COLLAR FLOTADOR y CEMENTO DE 11869' HASTA MEDIO SHOE TRACK A 11935'. PRUEBÓ CSG. CONTINUÓ MOLIENDO RESTO SHOE TRACK, ZAPATO, RAT HOLE y 15' FM NUEVA HASTA 11985'. CAMBIÓ FLUIDO. REALIZÓ FIT. PERFORÓ HASTA 12268'. | CONTINUAR PERFORANDO HOYO 8 1/2" HASTA +/- 12841'. SEGÚN PROGNOSIS. CIRCULAR PÍLDORA. REALIZAR VIAJE. ESPOTEAR PÍLDORA. SACAR SARTA CON BHA #5 HASTA SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | MOLIÓ TAPONES, COLLAR FLOTADOR y CEMENTO DE 11869' HASTA MEDIO SHOE TRACK A 11935'. PARÁMETROS 350 gpm, 1900 psi, 40 - 50 rpm, WOB: 10 - 15 Klbs TORQUE: 20 - 25 klbs-pie. | 24.25 |  | 2018-11-24 12:00:00.000 | [6 empty] | 2018-11-19 20:00:00.000 | 2018-11-01 05:00:00.000 | 0 | 12830.0004 | 2018-11-17 15:00:00.000 | 0.125 | 8.7917 | 16.4167 | 18.625 | 0.67114 | 781.5229
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | ACSC-032 | -0.80605 | -76.8844 | Auca Sur | Deviated | J | 2018-06-24 09:00:00.000 | Primary Drilling | Sinopec-168 | BOMBEO PILDORA EN FONDO, SACO Y QUEBRO BHA #4, BOMBEO PIDORAS DE LIMPIEZA, ARMO UNIDAD Y HERRAMIENTAS WL. REALIZO CORRIDA DE REGISTROS AIT-PEX-GR Y CMR - GR - ECRD | TERMINAR DE SACAR HERRAMIENTAS SOND A SUPERFICIE, RETIRAR UNIDAD WL. ARMAR HERRAMIENTAS TIW. BAJAR LINER 7" Y CEMENTARLO. | 79AB7DA4542A4070984C74DA09CB2C63 | CON PTA / BHA # 4 (BROCA PDC) @ 10395' CONECTA Y CIRCULA FONDO ARRIBA @ FULL PARAMETROS : GPM 400, PR 1500 PSI, RPM 80 SUBIENDO y 30 RPM BAJANDO RESIPROCANDO 90' DE TUBERIA. ** OBSERVA INCREMENTO EN ZARANDAS MENOR AL 5 %. OK. ** BOMBEO 50 BLS DE PILDORA PESADA DE 11.2 PPG ** LANZÓ CONEJO PARA CALIBRAR TUBERIA y SACÓ MIDIENDO POR PARADAS EN LA TORRE. OK | 20.61 |  | 2018-07-14 20:38:24.000 | [6 empty] | 2018-07-28 09:00:00.000 | 2018-06-24 09:00:00.000 | 0 | 11227.0004 | 2018-07-08 02:00:00.000 | 17.6875 | 6.6458 | 13.7083 | 34 | 52.0221 | 818.9909
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CHSA-016 | -0.92279 | -76.9293 | Chonta Sur | Deviated | J | 2018-03-07 16:00:00.000 | Primary Drilling | Sinopec-168 | INSTALA Y PRUEBA PACK OFF, INSTALA WEAR BUSHING, ARMAR BHA No. 6 (MOTOR A675M + BROCA PDC 8 ½”), BAJA BHA No. 6 HASTA 10540 FT, REALIZA DRILL OUT COLLAR FLOTADOR – CEMENTO, CIT C/2100 PSI, DRILL OUT SHOE, PERFORA 15' HASTA 10653'. REALIZA FIT. PERFORA SECCION 8.5" HASTA 10910 PIES | CONTINUAR PERFORANDO SECCION DE 8 1/2" HASTA +/- 11499 (TD). CIRCULAR PILDORA DE LIMPIEZA, REALIZAR VIAJE DE CALIBRACION, CIRCULAR Y ESPOTEO PILDORA Y SACA BHA A SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | BAJA BHA No. 6 EN 5in HWDP DESDE 107 PIES HASTA 1031 PIES. NOTA CAMBIA MARTILLO HIDRAULICO | 19.62 |  | 2018-03-26 20:52:48.000 | [6 empty] | 2018-03-27 00:00:00.000 | 2018-03-07 16:00:00.000 | 0 | 11455.0004 | 2018-03-24 17:00:00.000 | 1.0208 | 9.6875 | 17.0417 | 19.3333 | 5.2802 | 672.1761
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBA-036WDW | -0.48428 | -76.896 | Culebra | Deviated | Directional | 2018-08-13 14:00:00.000 | Primary Drilling | Sinopec-168 | BAJÓ BHA #6 HASTA 10007'. MOLIÓ TAPONES + C.F. + 1/2 SHOE TRACK. PROBO CSG. MOLIÓ RESTO SHOE TRACK + ZAPATO + 15' FM. NUEVA @ 10121'. REALIZÓ FIT. PERFORO HOYO 8 1/2" HASTA 10580'. | PERFORAR SECCION 8 1/2" HASTA +/- 10644' SEGÚN PROGRAMA-PROGNOSIS. REALIZAR VIAJE CORTO. BOMBEAR PILDORA. SACAR BHA #6 A SUPERFICIE. REALIZAR REGISTROS ELECTRICOS. | 79AB7DA4542A4070984C74DA09CB2C63 | SIGUIENDO "CHECK LIST" BAJÓ SARTA CON BHA # 6 DIRECCIONAL CON MOTOR + MWD + PDC 8 1/2" OD DESDE 109' HASTA 857''. VELOCIDAD DE BAJADA: 748 PPH. ** COLOCA 6 1/2" MARTILLO (60727H) | 22 |  | 2018-09-04 06:00:00.000 | [6 empty] | 2018-09-02 12:00:00.000 | 2018-08-13 14:00:00.000 | 0 | 10642.0003 | 2018-08-31 06:30:00.000 | 0.16667 | 8.7083 | 17.6875 | 19.9167 | 0.83682 | 601.6679
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBA-037 | -0.48421 | -76.896 | Culebra | Deviated | JHD | 2018-09-06 02:00:00.000 | Primary Drilling | Sinopec-168 | CEMENTÓ CASING 9 5/8". INSTALÓ Y PROBÓ PACK OFF, ARMÓ Y BAJÓ BHA #5, REBAJÓ TAPONES, MOLIÓ HASTA MEDIO SHOE TRACK, REALIZÓ CIT, MOLIÓ RESTO DE SHOE TRACK Y PERFORÓ HASTA 11,065', DESPLAZÓ FLUIDO. REALIZÓ FIT, PERFORÓ DESDE 11,065' HASTA 11,230'. | PERFORAR SECCIÓN 8 1/2" ACORDE A PROGRAMA HASTA +/- 11,654', CIRCULAR, SACAR BHA # 5 A SUPERFICIE, CORRER REGISTROS ELÉCTRICOS DE ACUERDO AL PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZÓ REUNIÓN DE SEGURIDAD. CORTÓ Y DESLIZÓ 110' DE CABLE DE PERFORACIÓN DE 1 1/2". | 22.5 |  | 2018-09-27 18:00:00.000 | [6 empty] | 2018-09-23 18:30:00.000 | 2018-09-06 02:00:00.000 | 0 | 11590.0004 | 2018-09-21 14:00:00.000 | 0.14583 | 7.9375 | 15.5 | 17.6875 | 0.8245 | 747.742
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | CLBA-038 | -0.48418 | -76.896 | Culebra | Deviated | TIPO J | 2018-10-01 23:00:00.000 | Primary Drilling | Sinopec-168 | BAJÓ CSG 9 5/8" DESDE 8017' HASTA 10399'. CEMENTÓ CSG 9 5/8". INSTALÓ PACK OFF EN SECCIÓN A Y B. ARMÓ Y BAJÓ BHA #5 HASTA 10311' | MOLER TAPONES, C.F., CEMENTO. REALIZAR PRUEBA DE CASING. CONTINUAR MOLIENDO CEMENTO, ZAPATO Y 15' FORMACIÓN NUEVA, CAMBIAR FLUIDO, REALIZAR FIT. PERFORAR SECCIÓN 8 1/2" DE ACUERDO A PROGRAMA. | 79AB7DA4542A4070984C74DA09CB2C63 | SIGUIENDO "CHECK LIST" BAJÓ SARTA CON BHA # 5 DIRECCIONAL CON MOTOR + MWD + PDC 8 1/2" OD DESDE 106.85' HASTA 10311'. VELOCIDAD DE BAJADA: 1570 PPH. ** COLOCÓ 6 1/2" MARTILLO (93100J). ** PROBÓ HERRAMIENTAS DIRECCIONALES CON GPM 380 Y PR 750 PSI @ 1037'. OK ** BAJÓ CON CIRCULACIÓN DESDE 10166’ HASTA 10311’ POR PRECAUCIÓN CON GPM 320, PR 1500 PSI. | 21.89 |  | 2018-10-23 03:21:36.000 | [6 empty] | 2018-10-17 20:00:00.000 | 2018-10-01 23:00:00.000 | 0 | 10920.0003 | 2018-10-15 23:00:00.000 | 0.083333 | 7.3333 | 14 | 15.875 | 0.52493 | 780
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | PTLA-002 | -0.5749 | -76.9565 | Pitalala | S Shaped | Directional | 2018-03-16 13:00:00.000 | Primary Drilling | Sinopec-168 | CEMENTÓ CASING 9 5/8". INSTALÓ Y PROBÓ PACK OFF, ARMÓ Y BAJÓ BHA #4, REBAJÓ TAPONES, MOLIÓ | REALIZAR FIT, PERFORAR ETAPA DE 8 1/2" A +/- 10,792' | 79AB7DA4542A4070984C74DA09CB2C63 | 'SIGUIENDO "CHECK LIST" BAJÓ BHA # 4 DIRECCIONAL CON BROCA DE 8 1/2" DESDE 109' A 2,859'. VELOCIDAD DE BAJADA: 1,000 pies/hr. NOTAS: PROBÓ HERRAMIENTAS DIRECCIONALES CON 350 gpm Y 550 psi @ 1,048'. CONEXIONES DE LA TUBERIA FH SE LAS REALIZA USANDO LA LLAVE DE POTENCIA PARA COMPLETAR TORQUE REQUIERIDO (56000 lbs/pie) | 18.74 |  | 2018-04-03 23:45:36.000 | [6 empty] | 2018-04-05 00:30:00.000 | 2018-03-16 13:00:00.000 | 0 | 10755.0003 | 2018-04-03 01:00:00.000 | 3.4167 | 11.125 | 17.5 | 19.4792 | 17.5401 | 614.5714
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | PTLA-003 | -0.57488 | -76.9565 | Pitalala | S Shaped | DIRECTIONAL | 2018-04-13 03:00:00.000 | Primary Drilling | Sinopec-168 | CEMENTÓ CASING 9 5/8". INSTALÓ Y PROBÓ PACK OFF, ARMÓ Y BAJÓ BHA # 4, REBAJÓ TAPONES, MOLIÓ HASTA MEDIO SHOE TRACK, REALIZÓ CIT, MOLIÓ RESTO DE SHOE TRACK Y PERFORÓ HASTA 10104', DESPLAZÓ DE FLUIDO, PERFORÓ ETAPA DE 8 1/2" HASTA @ 10120' | PERFORAR HASTA +/- 10830 CIRCULAR, REALIZAR VIAJE DE CALIBRACIÓN A LA ZAPATA DE 9 5/8", RETORNAR A FONDO, CIRCULAR, ESPOTEAR PÍLDORA LUBRICANTE, SACAR BHA # 4 A SUPERFICIE | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZÓ REUNIÓN DE SEGURIDAD CON TODO EL PERSONAL INVOLUCRADO PREVIO A CORTAR CABLE DE PERFORACIÓN. CORTÓ Y DESLIZÓ 120' DE CABLE DE PERFORACIÓN DE 1 1/2" | 17.25 |  | 2018-04-29 12:00:00.000 | [6 empty] | 2018-04-28 06:00:00.000 | 2018-04-13 03:00:00.000 | 0 | 10782.0003 | 2018-04-26 00:00:00.000 | 0 | 6.3542 | 12.875 | 15.125 | 0 | 837.4369
WH | LAN | Ecuador | 79AB7DA4542A4070984C74DA09CB2C63 | 755 | 162454 | Shaya | IDS | MCA | LSTK | PTLA-004 | -0.57494 | -76.9564 | Pitalala | Deviated | JHD | 2018-11-28 15:00:00.000 | Primary Drilling | Sinopec-168 | PERFORÓ SECCION 8 1/2" HASTA 12,380'(PTO. LINER). REALIZÓ VIAJE CORTO. ESPOTEÓ PILDORA. SACÓ BHA #5 SUPERFICIE Y DESARMÓ. ARMÓ HRTAS TIW. BAJÓ LINER HASTA 220'. | TERMINAR DE BAJAR LINER DE 7" HASTA 12378', CIRCULAR , CEMENTAR , EXPANDIR COLGADOR, LIBERAR SETTING TOOL, CAMBIAR FLUIDO POR AGUA, SACAR SETTING TOOL A SUPERFICIE. | 79AB7DA4542A4070984C74DA09CB2C63 | REALIZÓ CHEQUEO DE FLUJO ESTÁTICO OK. SACÓ BHA # 5 DIRECCIONAL LIBRE DE 12,380' A 11,670' (DENTRO DE ZAPATA DE TR 9 5/8" ). NOTA: REALIZÓ CHECK LIST PREVIO A SACAR TUBERÍA. | 23.89 |  | 2018-12-22 03:21:36.000 | [6 empty] | 2018-12-16 07:00:00.000 | 2018-11-28 15:00:00.000 | 0 | 12380.0004 | 2018-12-14 13:30:00.000 | 0.20833 | 8.2708 | 15.9375 | 17.6667 | 1.1792 | 776.7843
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | 9/11a-AMPB | 59.5906 | 1.0568 | Mariner | Horizontal |  | 2019-03-29 00:30:00.000 | Primary Drilling | Noble Lloyd Noble | RIH with 24x34" motor BHA from 146m to 208m. Spudded well from 209,8m to TD at 313,3m, pumped 40m3 hi-vis pill at TD. The DP hit a cable tray below the XMT deck after start pumping after connection (04:00 at 234m MD), no damage to cables etc, continued drilling .Performed 2 check trip from 308 to 312m to check for fill. Displaced to 1,20 sg mud. POOH and L/D BHA. Inspected topdrive for loose parts. Rigged up caisng running equipment. RIH with 28" conductor to 238m. | Cement 28" Conductor pipe. | 1664C0880B794793B13A395857CB9462 | Displaced the well with 3200 lpm, 53 bar, 0 rpm. Pulled back slowly whilst pumping from 312m to 301m. Flowrate limited because of excessive vibration with bit off bottom. | 20.44 |  | 2019-04-17 10:39:56.000 | [6 empty] | 2019-03-31 05:00:00.000 | 2019-03-28 21:30:00.000 | 688.3202 | 1027.231 | 2019-03-29 09:30:00.000 | 0 | 0.125 | 0.375 | 2.1875 | 0 | 2739.2827
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | 9/11a-AMPF | 59.5892 | 1.057 | Mariner | Horizontal |  | 2019-02-26 17:00:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Stopped circulating the first batch of PST fluid over the cubes. Lined up to circulate conventionally. Staged up pumps incrementally to 2000 l/min, 153 bar. At 2000 l/min observed losses of 10 m3/hr. Reduced flow rate to 1536 l/min, 98 bar. Transferred fresh unsheared flothru WBM into the active system from the reserve pit, whilst transfering 35m3 of sheared WBM to the WBM Primary Storage 2 pit for the second batch of PST fluid. | 30.99 |  | 2019-04-03 08:45:00.000 | [6 empty] | 2019-09-20 02:15:00.000 | 2019-02-26 17:00:00.000 | 1026.9029 | 13139.7642 | 2019-09-14 11:15:00.000 | 12.9375 | 37.6042 | 199.7604 | 205.3854 | 6.2991 | 65.7776
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMIC | 59.589 | 1.057 | Mariner | Horizontal | INJECTION | 2019-04-03 00:00:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Drilled ahead 24" hole from 502m to 598m with 4550lpm, 97bar, 60rpm, 5 - 22kNm, 1 - 5 t WOB. Instantaneous ROP: 8 - 40m/hr. Top drive stalled out on occasion with torque limit (22kNm) and limited instantaneous ROP. Dumped sand traps and diluted mud system by 70 - 80m3 roughly once per hour. Sand content 0.5 - 1.4%, mud wt in: 1.04 - 1.05sg, mud wt out: 1.04 - 1.06sg. ECD: 1.12 - 1 .15 sg EMW. Downlinked to Archer tool as required, used NOV MMC automated system for connections (NOV fine tuning system and driller intervening when necessary). Typical connection time with MMC: 16 - 18 mins. Gyro surveys taken each single down after connections (gyro tool times-out and goes into "sleep" mode if no flow for more than 15 mins). Offline: Cameron installed starter wellhead on slot 14 (AMPJ). | 29.77 |  | 2019-05-01 18:22:44.000 | [6 empty] | 2019-04-29 00:00:00.000 | 2019-04-02 22:00:00.000 | 675.853 | 2362.2048 | 2019-04-25 12:00:00.000 | 1.3854 | 3.4792 | 22.5 | 26 | 5.3285 | 104.9869
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMPA | 59.589 | 1.057 | Mariner | Horizontal |  | 2019-04-05 17:00:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Carried out check trip with pumps off from 311m to 316m to check for fill - 1m of fill observed. Circulated hole between 316 m to 311m with 4000 lpm, 112 bar, 0 rpm. Displaced the well from seawater to 1,20 sg mud, pumped 1,5 x OH volume and pulled string up to 298m. | 20.44 |  | 2019-04-25 10:39:56.000 | [6 empty] | 2019-04-07 11:15:00.000 | 2019-04-05 17:00:00.000 | 685.6956 | 1036.7454 | 2019-04-06 01:15:00.000 | 0 | 0 | 0.34375 | 1.7604 | 0 | 3015.9867
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMPG | 59.589 | 1.057 | Mariner | Horizontal |  | 2019-04-10 17:15:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | P/U side entry sub, removed X/O and removed 3m pup for space out. Installed dart above cement head TIW. M/U X/O and L/O side entry sub. Installed 2 x foam wiper balls in DP pup jt. | 20.44 |  | 2019-04-30 10:39:56.000 | [6 empty] | 2019-04-12 00:00:00.000 | 2019-04-10 17:15:00.000 | 685.6956 | 1030.1838 | 2019-04-11 00:15:00.000 | 0 | 0 | 0.29167 | 1.2812 | 0 | 3532.0586
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMPI | 66.0742 | 3.9029 | Mariner | Horizontal | Directional | 2019-03-17 02:15:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Held TOFS for safe use of rig tongs to make up string stabilizer, training new roughnecks on correct use of manual tongs. | 4.79 |  | 2019-03-21 19:01:20.000 | [6 empty] | 2019-04-22 04:00:00.000 | 2019-03-17 01:45:00.000 | 685.3675 | 2378.609 | 2019-04-18 16:30:00.000 | 2.1354 | 8.9583 | 32.5938 | 36.0729 | 5.9197 | 72.9775
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMPJ | 66.0741 | 3.902 | Mariner | Horizontal | Directional | 2019-03-25 08:30:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Drilled ahead 24” hole from 315m to 355m with 3800 lpm, 48bar, 40 rpm, 2-7kNm. Dumped sand traps by 43m3 twice per stand drilled. Mud wt in - 1.05+sg, ECD - 1.12sg EMW. San d content 0.25% | 4.99 |  | 2019-03-29 23:45:36.000 | [6 empty] | 2019-05-05 00:00:00.000 | 2019-03-25 00:00:00.000 | 688.3202 | 2368.7665 | 2019-05-02 20:00:00.000 | 0.39583 | 3.8229 | 38.4792 | 40.6458 | 0.97386 | 61.5597
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-AMPU | 66.074 | 3.902 | Mariner | Deviated |  | 2019-03-28 02:15:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Circulated hole between 319m to 314m with 4000 lpm, 102 bar, 0 rpm. Pumped and displaced 40m3 hi-vis pill. Took TD survey: 0.23 deg inc. | 20.44 |  | 2019-05-02 10:39:56.000 | [6 empty] | 2019-04-14 00:00:00.000 | 2019-04-12 14:15:00.000 | 685.696 | 1048.2284 | 2019-04-12 22:00:00.000 | 0 | 0 | 15.8229 | 16.9062 | 0 | 66.2475
EH | EUR | United Kingdom | 1664C0880B794793B13A395857CB9462 | 642 | 469032 | Statoil UK Mariner | IDS | Europe | AFE Assurance | GB 9/11a-ASA | 66.0742 | 3.902 | Mariner | Deviated |  | 2019-04-08 14:15:00.000 | Primary Drilling | Noble Lloyd Noble |  |  | 1664C0880B794793B13A395857CB9462 | Tagged seabed at 14:45 hrs at 208.9m, no WOB observed. Staged up to drilling parameters and drilled ahead 34" hole from 209m to section TD at 317m. Varied drilling parameters occasionally to reduce string vibrations but generally drilled ahead with 3700 - 4000 lpm, 80 - 97bar, 0 surface rpm, 2-7t WOB, 12-30m/hr instantaneous ROP. | 4.78 |  | 2019-04-12 18:43:12.000 | [6 empty] | 2019-04-10 07:00:00.000 | 2019-04-08 14:45:00.000 | 685.6956 | 1040.0263 | 2019-04-08 22:15:00.000 | 0 | 0 | 0.33333 | 1.6979 | 0 | 3120.0788
WH | NAL | United States | 34F5D2E9B03C46478550120F87661A41 |  |  | Wold Powder River | IDS | NAM | LSTK | Pacific Power 3675-27-34-3-1FH | 43.0576 | -105.8456 | Converse County, WY | Horizontal | Development | 2018-02-05 14:30:00.000 | Primary Drilling | Nabors-X21 | Performed casing test. Drilled out shoe track. Performed FIT. Drilled ahead t/ 12,573'. Circulated B/U and POOH t/ 7900' | POOH BHA to surface. Inspect BHA. RIH t/ 12,573'. | 34F5D2E9B03C46478550120F87661A41 | Drilled F/ 12478 T/ 12573'. WOB 10-14 klbs, 35 RPM, Torque 4-11 ft.klbs, 250 GPM, PP 2700-3000 psi Rotated for 1.0 hours Slid for 5.75 hours | 40.33 |  | 2018-03-17 13:51:13.000 | [6 empty] | 2018-03-16 00:00:00.000 | 2018-02-05 10:00:00.000 | 172 | 20970.0007 | 2018-03-12 00:00:00.000 | 4.0417 | 18.3021 | 34.3958 | 38.3958 | 10.5263 | 609.6669
WH | NAL | United States | 34F5D2E9B03C46478550120F87661A41 |  |  | Wold Powder River | IDS | NAM | LSTK | Sand Springs Unit 3-34FH | 43.1283 | -105.9673 | Converse County, WY | Horizontal |  | 2017-12-26 00:00:00.000 | Primary Drilling | Nabors-X21 | FINISH RU SLB WL TOOLS. STARTED LOGGING. TOOLS BEGAN TO MALFUNCTION AND THEY COULD NOT RECEIVE WAVES BACK FROM TOOL. POOH TOOL AND TROUBLESHOOT. FIXED TOOL AND RIH TO LOG. FOUND CEMENT @ 5500'. RD WL. PU/MU 6 3/4" CURVE BHA AND RIH WHILE MU DP. | FINISH RIH AND PU DP TO TAG CEMENT. CIRCULATE WHILE SLIP AND CUT DRILL LINE. DRILL OUT 1/2 SHOE TRACK AND PRESSURE TEST CASING. DRILL OUT REST OF SHOE TRACK + 10' NO NEW FORMATION. PERFORM FIT TEST @ 9.5 PPG EMW. DRILL AHEAD. | 34F5D2E9B03C46478550120F87661A41 | PICK UP DRILL PIPE F/BHA - T/2086' | 40.42 |  | 2018-02-04 16:06:12.000 | [6 empty] | 2018-01-29 18:00:00.000 | 2017-12-27 00:30:00.000 | 115 | 20600.0007 | 2018-01-25 01:00:00.000 | 3.1979 | 14.6562 | 30.0417 | 34.75 | 9.2026 | 685.7143
WH | NAL | United States | 34F5D2E9B03C46478550120F87661A41 |  |  | Wold Powder River | IDS | NAM | LSTK | Tuesday Draw 3874-26-23-14-3FH | 43.2438 | -105.7075 | Converse County, WY | Horizontal |  | 2018-03-21 03:00:00.000 | Primary Drilling | Nabors-X21 | Finish MPD and BOP pressure testing. Install wear bushing. R/U WL and run USIT log. P/U and M/U 6 3/4" BHA. RIH to 8000'. | Continue RIH and tag cement. Drill out 1/2 shoe track and perform casing pressure testing. Drill rest of shoe track + 10' of new formation and perform FIT. Drill ahead to land curve. | 34F5D2E9B03C46478550120F87661A41 | P/U drill pipe and RIH F/BHA T/1470' | 41.44 |  | 2018-04-30 16:29:37.000 | [6 empty] | 2018-04-29 01:00:00.000 | 2018-03-21 03:00:00.000 | 0 | 22610.0007 | 2018-04-23 20:00:00.000 | 2.9792 | 17.4375 | 33.7083 | 38.9167 | 7.6552 | 670.754
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ579 | 24.8984 | 53.7255 | Zakum | Horizontal | Single Oil producer | 2017-11-08 15:30:00.000 | Primary Drilling | ND131 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Change Saver Sub | 85 |  | 2018-01-31 23:58:22.000 | 390.7 | [5 empty] | 2018-01-07 08:00:00.000 | 2017-11-08 15:30:00.000 | 280 | 27385.0009 | 2017-12-28 15:30:00.000 | 3.9375 | 28.125 | 50 | 59.6875 | 6.5969 | 547.7
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ589 | 24.9006 | 53.7257 | Zakum | Horizontal | Single Oil Producer | 2018-01-26 18:00:00.000 | Primary Drilling | ND131 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | RIH SLB 8-1/2" RSS BHA 1,555 ft to 8,205 ft on 5" DP stds, while fill up DP increase GPM to test BHA, Ecoscope tool readings out of tolerance. - Using WFD bucking unit to make stands | 61.22 |  | 2018-03-28 05:16:48.000 | 473.8 | [5 empty] | 2018-03-07 03:00:00.000 | 2018-01-26 00:00:00.000 | 280 | 24330.0008 | 2018-02-28 05:30:00.000 | 2.4375 | 17.4167 | 32.4792 | 39.375 | 6.1905 | 749.0956
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ590 | 24.9013 | 53.7265 | Zakum | Horizontal | ERD Water Injector | 2018-02-23 21:00:00.000 | Primary Drilling | ND131 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Drilled 12-1/4" hole section from 6274' to 8320'. WOB = 15-45 kips, RPM = 120-160 GPM = 1100, SPP = 2750-3000 Torque = 12-22 k.ft-lbs MW = 11.7 / 11.7 in/out ECD = 11.8- 11.96 ppg. ROP = 100-150 fph. Last Survey: 8208.20' MD, 7095.31' TVD, 64.60 deg inclination, 214.30 deg azimuth. Compared to Plan: 5.26' above & 9.30' left. * Observed very trace amount of splintery cavings on shakers while drilling N. Umr. Size ranged from 1-2" x 0.5-0.75". * Ann. press. between 20" X 13 3/8" CSG = 10 PSI. * Safety Talk (AM): Hald safety stand-down dicussion regarding recent fatality & the need to never take short cuts. Discussed importance of safety triangle. * Safety Talk (PM): High level HSEO. Review area manager autjorities. Update JSA and PTW system. | 49.05 |  | 2018-04-13 01:12:00.000 | 545 | [5 empty] | 2018-04-07 00:00:00.000 | 2018-02-23 21:00:00.000 | 288 | 19300.0006 | 2018-03-27 01:00:00.000 | 5.3125 | 16.5833 | 31.1667 | 42.125 | 12.6113 | 619.2514
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ602 | 24.9005 | 53.7256 | Zakum | Horizontal | ERD | 2018-06-18 08:00:00.000 | Primary Drilling | ND131 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | RIH SLB 8-1/2" RSS BHA f/ 443 ft to 1,476 ft on 5" DP stds. | 44.39 |  | 2018-08-01 09:21:36.000 | 645.2 | [5 empty] | 2018-08-27 09:30:00.000 | 2018-06-18 00:00:00.000 | 275 | 23028.0007 | 2018-08-18 11:30:00.000 | 24.5833 | 40.2917 | 61.1458 | 70.0625 | 35.0877 | 376.6078
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ614 | 24.9003 | 53.7253 | Zakum | Horizontal | ERD - Producer | 2018-09-11 12:30:00.000 | Primary Drilling | ND131 | RIH SLB 8-1/2" RSS BHA f/ 9,061 ft and tag TOC at 10,961 ft. Conduct 9-5/8" casing test. Drill out shoe track & rathole f/ 10,961 ft to 11,120 ft. Drill 8-1/2" Production hole f/ 11,120 ft to 12,860 ft. | Drill 8-1/2" Production hole to 32,950 ft. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Wash down f/ 10,849 ft with 300 gpm & 750 psi, tagged top of cmt at 10,961 ft w/ 20 kips. Space out for csg test. | 59.75 |  | 2018-11-09 18:01:28.000 | 667.6 | [5 empty] | 2018-11-04 00:00:00.000 | 2018-09-11 12:30:00.000 | 0 | 32871.0011 | 2018-10-23 02:30:00.000 | 11.6042 | 26.25 | 41.5833 | 53.4792 | 21.6985 | 790.485
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ620 | 24.9005 | 53.7177 | Zakum | Horizontal | Water Injector | 2018-11-19 03:00:00.000 | Primary Drilling | ND131 | RIH lower & upper packoff seal assy. Conduct BOP test for 5-1/2" & 4-1/2" DP. Install 9" short wear bushing. P/U SLB 8-1/2" Orbit RSS BHA & RIH f/ surface to 1,202 ft. | RIH. Slip & cut. Tag TOC. 9-5/8" casing test. Power choke drill. Drill out shoe track. Drill 8-1/2" Production hole f/ 10,052 ft to ~30,012 ft (TD). | 8DF85281E77C4297AE8F2EBBCB6E91D3 | M/U BOP test assy - 1x std 5-7/8" HWDP & test plug. | 51.33 |  | 2019-01-09 07:48:46.000 | 704.43 | [5 empty] | 2018-12-23 00:00:00.000 | 2018-11-19 00:00:00.000 | 282 | 30125.001 | 2018-12-13 04:00:00.000 | 3.1042 | 12.6667 | 24.0417 | 33.875 | 9.1636 | 1253.033
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ633 | 24.9002 | 53.7252 | Zakum | Deviated | WATER INJECTOR | 2019-02-20 04:00:00.000 | Primary Drilling | ND131 | 24 Hrs Summary: Cont. BOP test for 5-1/2" & 4-1/2" DP. Install 9" short wear bushing. RIH SLB 8-1/2" Orbit RSS BHA f/ surface to 13,285 ft. Conduct Power choke/Stripping drills. Wash down f/ 13,285 ft to 13,385 ft. | Tag top of cmt. Circulate 1x BU. 9-5/8" casing test. Drill out shoe track. Drill 8-1/2" Production hole to ~25,108 ft (TD). | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Wash down f/ 13,285 ft to 13,385 ft with 150 gpm & 350 psi. | 43.1 |  | 2019-04-04 02:18:25.000 | 712.66 | [5 empty] | 2019-04-03 06:00:00.000 | 2019-02-20 00:00:00.000 | 290 | 23000.0007 | 2019-03-22 04:30:00.000 | 4.5417 | 17.6667 | 30.0208 | 42.0833 | 10.7921 | 766.1347
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ636 | 24.9004 | 53.7254 | Zakum | Horizontal | Water Injector | 2019-04-06 15:00:00.000 | Primary Drilling | ND131 | Test packoff seals. Conduct BOP test for 5-1/2" & 4-1/2". M/U 8-1/2" BHA f/ surface to 417 ft. RIH to 3,560 ft on 5-1/2" DP. | RIH 8-1/2" BHA to ~14,100 ft. Power choke/Stripping drill. Csg test. Drill ahead to ~30,150 ft. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Break for Iftar. | 66.87 |  | 2019-06-11 20:51:53.000 | 532.5 | [5 empty] | 2019-06-07 13:30:00.000 | 2019-04-06 21:00:00.000 | 273 | 30105.001 | 2019-05-30 16:00:00.000 | 7.3333 | 31.1458 | 54.0417 | 61.9375 | 11.8399 | 557.0702
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ576 | 24.7943 | 53.7311 | Zakum | Horizontal | Single oil Producer | 2017-11-01 06:00:00.000 | Primary Drilling | ND32 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | MU 5" DP test pipe, screw into test plug & press test as follows: - Annular BOP to to 300 / 5000 psi at 10 min each, OK - Top VBR & NRV on kill line to 300 / 5000 psi at 10 min each, OK - Bottom VBR to 300 / 5000 psi at 10 min each, OK - Pressure test choke manifold valves to 300 / 5000 psi at 10 min each offline. OK. - POOH 5'' test assembly and test plug and LD same. | 74.96 |  | 2018-01-14 23:08:22.000 | 485 | [5 empty] | 2017-12-31 09:30:00.000 | 2017-11-01 06:00:00.000 | 268 | 27313.0009 | 2017-12-14 09:00:00.000 | 0.041667 | 12.9167 | 43.125 | 60.1458 | 0.069276 | 633.3449
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ634 | 24.8396 | 53.6561 | Zakum | Horizontal | Water Injector | 2019-03-24 10:30:00.000 | Primary Drilling | ND33 | RIH with 8-1/2" while P/U singles of 5-1/2'' DP to 10,549'. Performed BOP, Power choke drills & stimulate stripping drill. | RIH with 8-1/2", Drill Shoe track & Cement, Drill 8-1/2" Hole. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | PJSM with crew for picking up 5-1/2" DP singles. - Discussed importance of checklist/HSEO. | 39.05 |  | 2019-05-02 01:16:12.000 | 682.77 | [5 empty] | 2019-05-06 07:45:00.000 | 2019-03-24 10:30:00.000 | 280 | 22200.0007 | 2019-04-28 06:30:00.000 | 2.2292 | 17.3438 | 34.8333 | 42.8854 | 5.198 | 637.3206
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ586 | 24.7957 | 53.7319 | Zakum | Horizontal | Single Oil Producer | 2018-01-20 04:00:00.000 | Primary Drilling | ND66 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | -Rig service. | 75.43 |  | 2018-04-05 10:19:12.000 | 551.8 | [5 empty] | 2018-04-08 00:00:00.000 | 2018-01-20 00:00:00.000 | 0 | 28869.0009 | 2018-03-19 20:00:00.000 | 16.9375 | 35.1042 | 58.6667 | 77.8333 | 21.7612 | 492.0852
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ598 | 24.7961 | 53.7323 | Zakum | Horizontal |  | 2018-04-22 18:00:00.000 | Primary Drilling | ND66 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | - Rig Service. | 70.17 |  | 2018-06-30 04:06:23.000 | 583.1 | [5 empty] | 2018-06-21 00:00:00.000 | 2018-04-21 00:00:00.000 | 280 | 29810.001 | 2018-05-23 12:30:00.000 | 2.1458 | 16 | 30.7708 | 59.25 | 3.6217 | 968.7746
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ605 | 24.796 | 53.7322 | Zakum | Horizontal | ERD | 2018-06-27 00:00:00.000 | Primary Drilling | ND66 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Continue RSS Drill 8 1/2" hole section from 17,030 ft to 17,187 ft section TD. 24 hrs Drilling Summary: GPM: 450-500, Press: 1880 psi - 2450 psi MW in/out: 10.10-10.15ppg / 10.1-10.2 ppg, ECD: 11.54-11.80 ppg Losses : 2-3 bph downhole. WOB 05 - 10 klbs, RPM: 170-200 On btm tq: 17 – 29.5 kft-lbs, Off btm tq: 9-13 kft-lbs. Last P/U: 288 klbs, S/O: 235 klbs T&D: PU FF: 0.09, SO FF: 0.05, TQ FF 0.16 Avg. On btm ROP: 108 ftph Last Survey: 17094.2' MD, 90.171INC, 270.66 AZ, 7704.32 TVD Current to plan: 5.26' below, 6.57' left ** Record SCR at 17,180': 30 40 50 Mud pump #1 430 550 700 Mud pump #2 420 540 700 Mud pump #3 420 540 700 ** Cuttings skips received last 24 hrs 8 skips (99 bbls), Total received 39 skips (490 bbls). ** Soft Torq on. ** Prior connection: Drill stand, ream up & down 10 ft. ** MWD survey every stand after connection. ** Porosity logs not working in Ecoscope tool from 14,460 ft. | 37.58 |  | 2018-07-30 13:55:12.000 | 588.4 | [5 empty] | 2018-08-05 00:00:00.000 | 2018-06-23 00:00:00.000 | 267 | 17187.0005 | 2018-07-29 19:30:00.000 | 2.0417 | 23.0833 | 32.8125 | 39 | 5.235 | 523.7943
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ613 | 24.7953 | 53.7322 | Zakum | Horizontal | Water Injector | 2018-08-31 05:30:00.000 | Primary Drilling | ND66 | Jet well head, Set pack-off assy & test the same, perform full BOP test, install WB, P/U 8 1/2" RSS BHA. | Cont. RIH w/ 8 ¼" RSS BHA to TOC, Press test 9-5/8" csg, Drilled out shoe track. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | - PJSM. - P/U, M/U & RIH w/ 8 1/2" RSS BHA as below: 8.5" PDC Bit (MR616M) + Xceed 675 (RSS) + EcoScope (LWD) + TeleScope 675 NF + 6.75" X/O + 6.75" Flex NMDC + 6.75" Anti SnS Tech + 6.75" Flex NMDC + Float Sub (Non Ported Valve) + 6-3/4" DAV Catcher Sub + 6-3/4" DAV Valve Sub + 9 x 5" HWDP (3 stds) + X/O + 5 1/2" DP to surface. | 55.4 |  | 2018-10-25 09:35:51.000 | 666.3 | [5 empty] | 2018-10-15 00:00:00.000 | 2018-08-31 05:30:00.000 | 279 | 28400.0009 | 2018-10-05 13:30:00.000 | 0.29167 | 19 | 35.3333 | 44.7708 | 0.65147 | 803.7736
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ623 | 24.7957 | 53.7327 | Zakum | Deviated | OIL PRODUCER | 2018-12-07 13:30:00.000 | Primary Drilling | ND66 | Drill 8 1/2" hole section from 10,730' to 11,968', Circulated with 475gpm, troubleshoot Drwks | Drill ahead 8 1/2" hole w/ SLB RSS assy to 25,654' section TD. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Flow check well static | 43.86 |  | 2019-01-19 20:43:26.000 | 722.3 | [5 empty] | 2019-01-18 00:00:00.000 | 2018-12-07 13:30:00.000 | 280 | 24692.0008 | 2019-01-09 16:30:00.000 | 7.5417 | 21.625 | 33.125 | 41.4375 | 18.2001 | 745.4189
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ630 | 24.7955 | 53.7325 | Zakum | Horizontal | Water Injector | 2019-02-20 04:00:00.000 | Primary Drilling | ND66 | RIH w/ 8 1/2" RSS BHA to 12,154', Wash down from 12,154' to the TOC @ 12,354', Circulate B/U, Pressure test 9 5/8" CSG to 4500 psi, drill out cement, cement plugs, float collar and float shoe, Con't drilling to 12,592'. | Drill ahead 8 1/2" hole w/ SLB RSS assy to 27,524' section TD. | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Cont. drill 8 1/2" hole section to 12,592' with 450-480 gpm, 1600-1900 psi spp, 60 rpm, 14-20 klb.ft trq & 1-10 klbwob. ** LP of UZ630-01H is at 12592 ft MD and TD will be 27592 ft MD in III J0B 15000 ft Horizontal. Record SCR at 12,585' 30 40 50 Mud pump #1 350 580 890 Mud pump #2 340 570 880 | 49.4 |  | 2019-03-28 09:40:14.000 | 722.8 | [5 empty] | 2019-03-26 05:00:00.000 | 2019-02-07 22:30:00.000 | 282 | 27592.0009 | 2019-03-12 02:30:00.000 | 4.125 | 18.2917 | 19.9375 | 34.0417 | 12.1175 | 1383.9248
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ635 | 24.7954 | 53.7323 | Zakum | Horizontal | Appraisal Well | 2019-04-05 05:00:00.000 | Completion | ND66 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Cont. RSS Drill 6" hole from 11313' to 12646' . with 275 gpm, 3280-3490 psi spp, 160-180 rpm, 9-12 klb.ft trq &5-17 klbs wob. MW in/out: 10.6 ppg / 10.6 ppg, ECD: 11.44 - 11.75 ppg. ** TOFS- Refresher topic - OFF-THE-JOB INCIDENT AVOIDANCE | 51.54 |  | 2019-05-26 13:02:42.000 | 440.8 | [5 empty] | 2019-06-09 05:30:00.000 | 2019-04-05 11:00:00.000 | 280 | 20747.0007 | 2019-05-30 21:30:00.000 | 17.8958 | 41.3333 | 55.6875 | 65.0208 | 27.5232 | 372.5612
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ575 | 24.8994 | 53.7272 | Zakum | Horizontal | ERD Water Injector | 2017-10-27 15:30:00.000 | Primary Drilling | ND67 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Circulated hole w/ 500 gpm, 2100 psi, while rotating at 40 rpm and reciprocating string. * Observed cement on shakers. | 70.85 |  | 2018-01-05 20:28:54.000 | 444.6 | [5 empty] | 2017-12-11 00:00:00.000 | 2017-10-27 00:00:00.000 | 0 | 27669.0009 | 2017-12-01 05:00:00.000 | 0.79167 | 9.5 | 34.5625 | 44.3542 | 1.7849 | 800.5498
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ583 | 24.9011 | 53.7268 | Zakum | Horizontal | Water Injector | 2017-12-28 00:00:00.000 | Primary Drilling | ND67 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Continued RIH with 8-1/2" RSS BHA to 3614' picking up 5" DP in doubles during trip. | 45.68 |  | 2018-02-11 16:19:12.000 | 507.1 | [5 empty] | 2018-02-01 00:00:00.000 | 2017-12-28 00:00:00.000 | 291 | 19078.0006 | 2018-01-22 12:00:00.000 | 1.4583 | 14 | 25.5 | 35 | 4.1667 | 748.1569
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ596 | 24.9014 | 53.7266 | Zakum | Horizontal | ERD | 2018-04-17 22:00:00.000 | Primary Drilling | ND67 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Held pre-job saftey meeting. P/U & M/U 8-1/2" RSS BHA while P/U 5" DP to 1080 ft. - P/U 5" DP by crane in single. * Safety Talk (PM): Proper way to store DPs and CSG. Use tag line. Banksman duties. Review Safety flash | 63.73 |  | 2018-06-19 17:31:12.000 | 475.9 | [5 empty] | 2018-06-12 00:00:00.000 | 2018-04-17 00:00:00.000 | 285 | 26041.0008 | 2018-05-24 18:30:00.000 | 6.1458 | 21.7396 | 36.8542 | 55.0833 | 11.1573 | 706.5958
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ603 | 24.9019 | 53.7271 | Zakum | Horizontal |  | 2018-06-22 03:00:00.000 | Primary Drilling | ND67 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | RIH with 8.5" drilling assy from 393' to 5133' * Perform shallow test MWD at 1,500' with 475 gpm, 1,250 psi - OK. | 50.51 |  | 2018-08-11 12:13:08.000 | 654.4 | [5 empty] | 2018-08-05 00:00:00.000 | 2018-06-22 00:00:00.000 | 288 | 26914.0009 | 2018-07-22 14:30:00.000 | 3.2708 | 16.25 | 30.4792 | 43.875 | 7.4549 | 883.0294
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ618 | 24.9016 | 53.7268 | Zakum | Horizontal | Water Injection | 2018-11-01 05:00:00.000 | Primary Drilling | ND67 |  |  | 8DF85281E77C4297AE8F2EBBCB6E91D3 | RIH w/ 8 1/2" RSS string to 1,540' while P/U 5" DPS. ( Fill string every 15 STDS). | 74.07 |  | 2019-01-14 01:44:41.000 | 478.1 | [5 empty] | 2019-01-14 06:30:00.000 | 2018-11-01 00:00:00.000 | 286 | 30102.001 | 2019-01-05 00:30:00.000 | 16.3542 | 45.3542 | 64.8125 | 74.0625 | 22.0816 | 464.4475
EH | EME | United Arab Emirates | 8DF85281E77C4297AE8F2EBBCB6E91D3 | 749 | 372245 | Zadco Islands IDS | IDS | Gulf | AFE Assurance | UZ629 | 24.9017 | 53.7269 | Zakum | Deviated | Water Injector | 2019-01-24 21:30:00.000 | Primary Drilling | ND67 | RIH with 8½" SLB RSS BHA to 12,488', Slip and Cut, Perform chocke Drill & stripping drill. POOH to 12,394'. | POOH to 11,400', RIH & tag TOC, Drill shoe track, Drill 8½" Hole to TD (~ 27,648 ft). | 8DF85281E77C4297AE8F2EBBCB6E91D3 | Rig service. | 89.7 |  | 2019-04-23 16:48:13.000 | 463.87 | [5 empty] | 2019-04-03 17:30:00.000 | 2019-01-24 20:30:00.000 | 280 | 27653.0009 | 2019-03-23 17:30:00.000 | 13.4792 | 38.4167 | 57.8333 | 68.8333 | 19.5823 | 478.1499